## Full summary
List of Project / Facility Changes Submitted to NYISO and Determined to Be (1) Non-Material Under the NYISO Interconnection Procedures or (2) Not Subject to an OATT 3.7 System Impact Study (Updated as of 01/3/24)
Queue Pos. | Project/Facility Name | Owner/Developer | Date SRIS Approved by OC | Description of Change(s) | Date NYISO Received Request/Notification | Date of TPAS Review
N/A | Indian Pt. 3 Nuclear Unit | Entergy | N/A | Increase size to 1,042 MW. | 2002-09-12 | 2002-10-17
N/A | East 74th St. GTs | Con Edison | N/A | Change interconnection of existing units. | 2003-02-14 | 2003-03-04
N/A | Indian Pt. 2 Nuclear Unit | Entergy | N/A | Increase size to 1,042 MW. | 2003-04-02 | 2003-04-30
N/A | Fitzpatrick Nuclear Unit | Entergy | N/A | Increase plant size from 883 MW to 896 MW. | 2004-08-10 | 2004-09-14
N/A | Black River Plant | Black River Generation | N/A | Increase plant size by about 7 MW. | 2006-02-06 | 2006-02-22
N/A | Seymour Gas Turbines | NYPA | N/A | Change interconnection of existing GTs from Gowanus- Greenwood line to Greenwood bus. | 2006-03-13 | 2006-04-10
N/A | Jamaica Upgrades | Con Edison | N/A | Two new breakers, 30 MVAR Cap, relocate connection of KIAC generator. | 2007-08-21 | 2007-10-03
N/A | Niagara Gen Facility | Niagara Generation | N/A | Change in fuel and related equipment (no change to generator) | 2008-02-26 | 2008-04-08
N/A | Fort Drum Gen Facility | ReEnergy Black River LLC | N/A | Change of fuel type. | 2012-06-07 | 2012-07-12
N/A | Black River Gen Facility | ReEnergy Black River LLC | N/A | Change of interconnection configuration of the Black River Gen Facility to directly serve the Fort Drum Load. | 2013-10-10 | 2013-12-03
N/A | Lewiston Pump Generating Plant | NYPA | N/A | Life extension and modernization project to refurbish or replace several plant components. | 2013-04-10 | 2014-01-07
N/A | Durkirk Units 2, 3 and 4 | NRG Energy, Inc. | N/A | Addition of natural gas as fuel for Units 2, 3 and 4 with an expected completion date of 9/1/2015. | 2014-01-15 | 2014-04-01
N/A | Black River Gen Facility | ReEnergy Black River LLC | N/A | Additional changes to the planned interconnection of the Black River Gen Facility to the Fort Drum Load. | 2014-05-15 | 2014-06-02
N/A | High Sheldon Wind Farm | Sheldon Energy LLC | N/A | Application of GE WindBoost on 47 of 75 turbines to increase capacity from 1.5 MW to 1.62 MW per turbine, a total increase in ERIS of 5.64 MW. | 2014-03-07 | 2014-10-02
N/A | East River Units 10 & 20 | Con Edison | N/A | Installation of GE controls to improve efficiency and increase maximum output. Upgrades determined to be non-material subject to increase in capacity not to exceed 10 MW above base ERIS level for each unit. | 2014-10-10 | 2014-12-03
N/A | Sithe Independence Station | Dynegy Marketing and Trade, LLC | N/A | Upgrade of combustion turbine components to improve efficiency. May increase maximum summer capability by up to 43 MW, but not above the base ERIS level. | 2015-04-08 | 2015-06-01
N/A | Stony Creek Wind Farm | Stony Creek Energy LLC | N/A | Application of GE WindBoost on 58 turbines to increase capacity by 0.09 MW per turbine, cancel plans to install a 59th turbine, for a net total increase in ERIS of 3.62 MW. | 2014-06-24 | 2015-07-06
N/A | Lasher Rd 115kV | NGrid | N/A | Addition of the Lasher Rd 115kV switch yard does not require an SIS. | 2015-11-25 | 2016-01-04
N/A | East River Units 6 & 7 | Con Edison | N/A | Increase ERIS for Units 6 and 7 for 10 and 2 MW, respectively, due to better operational optimization of the units. | 2016-09-16 | 2016-11-01
N/A | Lines 141 and 142 Reconductoring | NGrid | N/A | Reconductoring of the northern 20.5 miles of the Gardenville-Dunkirk 141 and 142 115 kV lines does not require an SIS. | 2016-12-13 | 2017-01-03
N/A | New Buchanan 345kV | Con Edison | N/A | Installing a new breaker#12 at Buchanan North 345 kV substation does not require an SIS. | 2017-01-04 | 2017-02-17
N/A | 2nd East Garden-Valley | LIPA | N/A | Addition of the 2nd EGC-Valley Stream 138kV line does not require an SIS. | 2017-05-04 | 2017-08-01
N/A | PV-20 Submarine Cable Replacement | NYPA | N/A | Replacing a portion of PV-20 that runs underground and underneath Lake Champlain for approximately 1.7 miles between Cumberland Head, NY and Grand Isle, VT does not require an SIS. | 2017-04-10 | 2017-10-02
N/A | Canandaigua | Canandaigua LLC | N/A | Replace Clipper C-96 machines with either GE or Vestas machines. | 2017-05-23 | 2017-11-03
N/A | Avangrid NYSEG/RG&E BES Projects | NYSEG/RG&E | N/A | Addition of Geneva, Ithaca, Oneonta North and Rochester transmission projects does not require an SIS. | 2017-07-24 | 2018-01-05
N/A | Nine Mile Point 2 | Nine Mile Point Nuclear Station LLC | N/A | Replace the GE Mark I Analog Turbine Control System with a Westinghouse Digital Turbine Control and Protection System | 2017-09-19 | 2018-01-05
N/A | Fenner | Canastota LLC | N/A | Replace 19 out of 20 GE turbines from a 1.5 MW GE wind turbine with a 70.5 m rotor with a 1.5 MW SLE GE win turbine with an 82.5 m rotor. | 2017-10-16 | 2018-01-05
N/A | Leeds-Hurley Series Compensation | Central Hudson | N/A | Replace the conventional series compensation with SmartWire SmartValve technology. | 2017-12-15 | 2018-05-01
N/A | Hempstead Railroad | Covanta | N/A | Replace the normally out-of-service generator step-up (GSU) transformer Bank 1 from a 15/20/25 MVA, 13.2kV-69kV, with an impedance of 6.66% on 15 MVA to a 57.8/76.9/96 MVA, 13.2kV-69kV, with an impedance of 8.8% with ± 7.5% tolerance on 57.8 MVA base. | 2018-11-12 | 2019-01-09
N/A | 2nd Riverhead-Canal 138kV | LIPA | N/A | Build a 2nd 138kV line from Riverhead to Canal | 2019-01-15 | 2019-03-06
N/A | Burns-West Nyack 138kV | O&R | N/A | Build a new138kV line from Burns to West Nyack (Line 705) | 2019-03-14 | 2019-05-03
N/A | Oak Street 138kV Substation | O&R | N/A | Build a new Oak Street 138kV substation between the O&R Burns to Corporate Drive 138 kV line (Line 702) | 2019-05-01 | 2019-06-10
N/A | Ramapo Bank 2300 Replacement | O&R | N/A | Replace the existing three single-phase Ramapo 345/138 kV transformer (Bank 2300) with a new single three- phase transformer | 2019-05-17 | 2019-06-10
N/A | NYSEG and RG&E Multiple LTP Projects | NYSEG/RG&E | N/A | · Frog Valley Capacitor | 2019-05-03 | 2019-07-08
· Big Tree Expansion
· Erie St Expansion
· Stolle Rd Rebuild
· Robinson Rd Rebuild/Expansion
· Line 947 Uprate
· Station 418 to Station 48 New 115kV Line
· Station 56 Reconfiguration
· Hook Rd Capacitor
· Coddington Series Bus-Tie Breaker
· Etna Series Bus-Tie Breaker
· Line 981 Uprate (Etna-East Ithaca)
· Fuller Hollow Expansion
· Langdon Rd Expansion
· Oakdale Expansion and Westover 115kV Removal
· Coopers Corners Rebuild
· Colliers Rebuild
· East Norwich Rebuild
· Jennison Rebuild
· Fraser Expansion and Delhi 115kV Removal
· New Morris Station
· Klinekill Reverse Power Relay
· Churchtown Capacitor
· Ten Mile River Expansion
N/A | Erie/Steel Wind Facilities | Erie Wind, LLC/ Niagara Wind Power, LLC | N/A | Replace the wind turbines of the existing Erie/Steel Wind facility (PTIDs 323596 and 323693) from Clipper 2.5 MW wind turbines for a total of 35 MW to GE 2.5 MW wind turbines for the same total of 35 MW. | 2019-03-20 | 2019-12-04
N/A | Greenidge | Emera Energy U.S. Sub. No. 1, Inc. | N/A | Add a 30 MW load at Greenidge generation bus including a reverse relay tripping to prevent the load facility from drawing power from the grid. | 2019-09-23 | 2019-12-04
N/A | Ramapo Bank 1300 Replacement | O&R | N/A | Replace the existing three single-phase Ramapo 345/138 kV transformer (Bank 1300) with a new single three-phase transformer. | 2019-10-25 | 2019-12-04
N/A | Astoria 3 | Astoria Generating Company L.P. | N/A | Replace the equipment, e.g., generator step up transformers, generator leads, and other equipment at site, associated with Astoria 3 with the equipment associated with the retired Astoria 4 that also results in changing Astoria 3’s breaker positions. | 2020-01-24 | 2020-03-05
N/A | Greenidge | Emera Energy U.S. Sub. No. 1, Inc. | N/A | Increase the behind-the-meter (BTM) load at Greenidge generation bus from the current 32 MW to 64 MW and continue to maintain the reverse relay tripping to prevent the BTM load facility from drawing power from the grid. | 2020-08-06 | 2020-10-05
N/A | ConEd LTP Projects | ConEd | N/A | Add (1) 2nd 345/138 kV PAR controlled Rainey – Corona feeder, (2) 3rd 345/138 kV PAR controlled Gowanus – Greenwood feeder, and (3)345/138 kV PAR controlled Goethals – Fox Hills feeder with Fox Hills rebuild as a ring bus. | 2020-11-12 | 2020-12-08
N/A | NGrid LTP Project | NGrid | N/A | Rebuild a major portion of Lockport – Batavia 115kV circuit (aka circuit #112). | 2020-11-12 | 2021-02-02
N/A | PSEG-LIPA LTP Project | PSEG-LIPA | N/A | Convert the Wildwood-Riverhead 69 kV line to the Wildwood-Riverhead 138 kV line. | 2021-02-09 | 2021-03-01
N/A | NYPA Niagara Exciter and Governor Upgrade | NYPA | N/A | Replace the exciters and governors of Niagara units. | 2021-02-03 | 2021-04-07
N/A | NYPA St. Lawrence AVR Upgrade | NYPA | N/A | Replace the automatic voltage regulator (AVR) of St. Lawrence units | 2021-03-12 | 2021-05-03
N/A | PSEG-LIPA SDU Project | NYPA | N/A | Modify the PSEG-LIPA CY17 SDU to build a new underground Terryville-Flowerfield 69 kV line rather than reconductoring the Port Jefferson-Stony Brook 69 kV line. | 2021-03-11 | 2021-05-03
N/A | RG&E LTP Project | RG&E | N/A | Rebuild RG&E transmission lines: Lines 917 (Station 7 - Station 69), 945 (Station 69 - Station 71), 946 (Station 70 - Station 71) and 947 (Station 418 – Station 113 – Spencerport – Station 70). | 2021-07-27 | 2021-10-01
N/A | Flats Rd Substation | CHG&E | N/A | Change the design kV level of the Flats Rd 69kV substation from a 69kV substation to a 115kV substation, but continue to operate it as a 69kV substation. | 2021-11-03 | 2022-01-04
N/A | Nine Mile Point 2 | Nine Mile Point Nuclear Station LLC | N/A | Replace the generator step-up transformers | 8/11/2021 | 2022-03-01
N/A | NYSEG Wave Trap | NYSEG | N/A | Change the design of the wave trap of the East Towanda-Hillside 230 kV line (Line#70) from 3000A to 2000A. | 2022-05-18 | 2022-06-02
N/A | Far Rockaway GT1 | PSEG-LIPA | N/A | Install the evaporative cooling and wet compression system resulted in increasing the Summer ERIS baseline from 53.5 MW to 61.5 MW. | 2022-07-31 | 2022-09-01
N/A | NGrid LTP Project | NGrid | N/A | Rebuild Mortimer-Pannell 24/25 115kV circuits to increase the line ratings from 150 MVA to 250 MVA. | 2022-07-05 | 2022-11-01
N/A | Nine Mile Point 2 | Nine Mile Point Nuclear Station LLC | N/A | Install a 2MW electrolyzer, resulting in a 2MW increase to the facility’s auxiliary load | 2022-08-29 | 2022-11-01
N/A | Jericho Rise Wind Farm | Jericho Rise Wind Farm LLC | N/A | Increase existing generating capability from 77.7 MW to 80.3 MW via software improvement | 2022-10-21 | 2022-12-02
N/A | Ball Hill Wind Farm | Ball Hill Wind Energy LLC | N/A | Increase existing generating capability from 100 MW to 103 MW without any change to equipment | 2023-01-03 | 2023-01-19
N/A | KIAC JFK | Calpine Energy Service LP | N/A | Increase in the KIAC generating facility’s auxiliary load by 10 MVA; operation of the KIAC generating facility as a Behind-the-Meter Net Generation Resource to feed the KIA Central Substation#2 in the event of an outage of the distribution 27kV/13.kV switchgear of the KIA Central Substation#2. | 2022-10-27 | 2023-01-19
N/A | Nine Mile Point 1 | Nine Mile Point Nuclear Station LLC | N/A | Replace 40 and 55 relays with a new digital SEL-700G relay | 2023-02-24 | 2023-04-03
N/A | ConEd Brooklyn Clean Energy Hub | Con Edison | N/A | Build a new 345kV substation between Rainey-Farragut transmission circuits | 2023-05-22 | 2023-06-05
N/A | Clinton Wind Power | AES | N/A | Repower the project by replacing turbine blades and drivetrains on each of the individual WTGs at the site. To limit the maximum output at the POI to the current nameplate capacity, developer will use a GE WindCONTROL software platform at the project substation | 2023-08-18 | 2023-06-29
N/A | Bliss Wind Power | AES | N/A | Repower the project by replacing turbine blades and drivetrains on each of the individual WTGs at the site. To limit the maximum output at the POI to the current nameplate capacity, developer will use a GE WindCONTROL software platform at the project substation | 2023-08-18 | 2023-06-29
N/A | Altona Wind Power | AES | N/A | Repower the project by replacing turbine blades and drivetrains on each of the individual WTGs at the site. To limit the maximum output at the POI to the current nameplate capacity, developer will use a GE WindCONTROL software platform at the project substation | 2023-08-18 | 2023-06-29
N/A | Ellenburg Wind Power | AES | N/A | Repower the project by replacing turbine blades and drivetrains on each of the individual WTGs at the site. To limit the maximum output at the POI to the current nameplate capacity, developer will use a GE WindCONTROL software platform at the project substation | 2023-08-18 | 2023-06-29
N/A | Wethersfield Wind Power | AES | N/A | Repower the project by replacing turbine blades and drivetrains on each of the individual WTGs at the site. To limit the maximum output at the POI to the current nameplate capacity, developer will use a GE WindCONTROL software platform at the project substation | 2023-08-18 | 2023-06-29
N/A | Chateaugay Wind Power | AES | N/A | Repower the project by replacing turbine blades and drivetrains on each of the individual WTGs at the site. To limit the maximum output at the POI to the current nameplate capacity, developer will use a GE WindCONTROL software platform at the project substation | 2023-08-18 | 2023-06-29
N/A | Southhampton to Deerfield Transmission | LIPA | N/A | Construction of a new 138kV circuit from Southhampton to Deerfield Substation the project will be initially operated at 69kV with the flexibility of converting to 138kV as needed | 2023-08-04 | 2023-09-06
N/A | 115 kV Line 982 Full Rebuild | Avangrid | N/A | (1) Rebuild the existing 21-mile 115 kV line with 1192 Bunting ACSR conductor on the existing centerline with light duty steel monopole structures | 2023-10-10 | 2023-12-01
N/A | Clarks Corners 345/115 Substation Upgrades | Avangrid | N/A | (1) 2 Bay 115 kV Expansion to the north. (2) Two (2) new power transformer positions. | 2023-10-10 | 2023-12-01
N/A | Jennison 115/46 kV Substation Upgrades | Avangrid | N/A | (1) Rebuild Jennison Substation “off-site” as a 4 bay BAAH 0.75 miles away. (2) Bring line 919 in and out. | 2023-10-10 | 2023-12-01
N/A | 115 kV Line 946 Full Rebuild | Avangrid | N/A | (1) Rebuild the existing 20-mile 115 kV line with 1192 Bunting ACSR on an offset and with light duty steel monopoles. | 2023-10-10 | 2023-12-01
N/A | 115 kV Line 949 Full Rebuild | Avangrid | N/A | (1) Rebuild the existing 25-mile 115 kV line with 1192 Bunting ACSR conductor on an offset and with light duty steel monopoles | 2023-10-10 | 2023-12-01
N/A | 115 kV Line 962 Full Rebuild | Avangrid | N/A | (1) Rebuild the existing 35-mile 115 kV line with 1192 Bunting ACSR conductor on an offset with light duty steel monopole structures. (2) Modify terminal bay at South Owego. (3) Modify terminal bay at Hillside | 2023-10-10 | 2023-12-01
N/A | Lounsberry 115/12.5 kV Substation Full Rebuild | Avangrid | N/A | (1) New 115 kV four position Ring bus. (2) Install new 22.4 MVA 115/12.5 kV transformer with LTC. (3) Install new 12.5 kV MV GIS and Control Building. | 2023-10-10 | 2023-12-01
N/A | 115 kV Line 961 Full Rebuild | Avangrid | N/A | (1) Rebuild the existing 18-mile 115 kV line with 1192 Bunting ACSR conductor on an offset with light duty steel monopole structures. (2) Modify terminal bay at South Owego. | 2023-10-10 | 2023-12-01
N/A | NYSEG 230 kV Line 68 Full Rebuild | Avangrid | N/A | Rebuild the existing 24-mile 230 kV line with bundled 1192 Bunting ACSR conductor on an offset with steel H-Frame structures. | 2023-10-10 | 2023-12-01
N/A | NYSEG 230 kV Line 69 Full Rebuild | Avangrid | N/A | Rebuild the existing 1-mile 230 kV line with 2156 Bluebird ACSR conductor on an offset with steel monopole structures. | 2023-10-10 | 2023-12-01
N/A | NYSEG 230 kV Line 72 Full Rebuild | Avangrid | N/A | Rebuild the existing 27-mile 230 kV line with 2156 Bluebird ACSR conductor on an offset with steel H-Frame structures. | 2023-10-10 | 2023-12-01
N/A | Bath 115/34.5 kV Substation Rebuild | Avangrid | N/A | Full rebuild of substation as 115 kV three-bay breaker-and-a-half (BAAH) air insulated substation (AIS) with two (2) new 115/34.5 kV 50 MVA transformers, a +150/-150 MVAR dynamic VAR compensation unit (STATCOM or SVC) | 2023-10-10 | 2023-12-01
N/A | Bennett 115/34.5 kV Substation Expansion and Upgrades | Avangrid | N/A | Partial rebuild of the substation with a 115kV bus expansion (extra position for interconnecting a new generator), a 0.05pu Power Flow Control Device, and terminal work on L725. | 2023-10-10 | 2023-12-01
N/A | NYSEG 115 kV Line 932 Power Flow Control Device & Structure Replacements | Avangrid | N/A | Install a Power Flow Control Device at Bennett Substation and perform in-kind structure replacements where required to address all asset condition issues. | 2023-10-10 | 2023-12-01
N/A | NYSEG 115 kV Line 723 Full Rebuild | Avangrid | N/A | Rebuild the existing 15-mile 115 kV line with bundled 795 Drake ACSR conductor on an offset with light duty steel monopole structures. | 2023-10-10 | 2023-12-01
N/A | NYSEG 115 kV Line 953 Full Rebuild | Avangrid | N/A | Rebuild the existing 5-mile 115 kV line with 2156 Bluebird ACSR conductor on an offset with light duty steel monopole structures. | 2023-10-10 | 2023-12-01
N/A | NYSEG 115 kV Line 965 Full Rebuild | Avangrid | N/A | Rebuild the existing 22-mile 115 kV line with bundled 795 Drake ACSR conductor on an offset with light duty steel monopole structures. | 2023-10-10 | 2023-12-01
N/A | NYSEG 115 kV Line 711 Full Rebuild | Avangrid | N/A | Rebuild the existing 3-mile 115 kV line with 2156 Bluebird ACSR conductor on an offset with light duty steel monopole structures. | 2023-10-10 | 2023-12-01
N/A | NYSEG 115 kV Line 712 Full Rebuild | Avangrid | N/A | Rebuild the existing 6-mile 115 kV line with 2156 Bluebird ACSR conductor on an offset with light duty steel monopole structures. | 2023-10-10 | 2023-12-01
N/A | NYSEG 115 kV Line 935 Full Rebuild | Avangrid | N/A | Rebuild the existing 9-mile 115 kV line with 2156 Bluebird ACSR conductor on an offset with light duty steel monopole structures. | 2023-10-10 | 2023-12-01
N/A | Stoney Ridge Transformer Replacement | Avangrid | N/A | Replace transformer Bank 1 with one (1) new 448 MVA transformer. | 2023-10-10 | 2023-12-01
N/A | Hickling 115/34.5 kV Substation Rebuild | Avangrid | N/A | Full rebuild of the substation as a 115 kV four-bay breaker-and-a-half (BAAH) air insulated substation (AIS) design, two (2) new 115/34.5 kV 50 MVA transformers, a new 34.5 kV GIS straight bus with a tie breaker as well as a 12.5 kV GIS straight bus. | 2023-10-10 | 2023-12-01
N/A | Eelpot 115 kV Substation Expansion | Avangrid | N/A | Addition of a new 115 kV circuit breaker, a +100/-100 MVAR new dynamic VAR compensation unit (STATCOM or SVC), and 115 kV line terminal work. | 2023-10-10 | 2023-12-01
N/A | Greenidge 115 kV Substation Upgrades | Avangrid | N/A | One (1) new 115 kV circuit breaker for Line 968, Line 968 terminal work, and a new 30 MVAR capacitor bank (with 115 kV circuit breaker). | 2023-10-10 | 2023-12-01
N/A | NYSEG 115 kV Line 722 Full Rebuild | Avangrid | N/A | Rebuild the existing 23-mile 115 kV line with 1590 Falcon ACSR conductor on an offset with light duty steel monopole structures. | 2023-10-10 | 2023-12-01
N/A | NYSEG 115 kV Line 724 Full Rebuild | Avangrid | N/A | Rebuild the existing 15-mile 115 kV line with 1590 Falcon ACSR conductor on an offset with light duty steel monopole structures. | 2023-10-10 | 2023-12-01
N/A | NYSEG 115 kV Line 968 Full Rebuild | Avangrid | N/A | Rebuild the existing 5-mile 115 kV line with 1590 Falcon ACSR conductor on an offset with light duty steel monopole structures. | 2023-10-10 | 2023-12-01
N/A | Watercure 345/230/115 kV Substation Expansion | Avangrid | N/A | Expand the 345 kV two-bay breaker-and-a-half (BAAH) with an extra bay that has one (1) empty bay position, adding a three-bay BAAH for a 115 kV addition, rerouting the Hillside 115 kV lines to Watercure Road’s new 115 kV BAAH, and adding one (1) new 345/115 kV three winding 448 MVA transformer. The transformer will connect with the new 115 kV BAAH and the 345 kV BAAH expansion. | 2023-10-10 | 2023-12-01
N/A | Hillside 230/115/34.5 kV Substation Upgrades | Avangrid | N/A | Decommissioning the substation’s 115 kV bus work, decommissioning the two (2) 115/34.5 kV transformers (Banks 1 and 2), re-routing the 115 kV lines to a new 115 kV at Watercure Road substation (at least 1.3 miles), replacing two 230 kV breakers, separating the 34.5 kV breaker position of Bank 3 and 4 (new 34.5 kV breaker and position for Bank 3), grounding the 115 kV side at the 230 kV transformers. | 2023-10-10 | 2023-12-01
N/A | Montour Falls 115/34.5 kV Substation Rebuild | Avangrid | N/A | Full rebuild of the substation as a four-bay breaker-and-a-half (BAAH) air insulated substation (AIS) design, two (2) new 115/34.5 kV 50 MVA transformers, two (2) new 115 kV 30 MVAR capacitor banks, a new 34.5 kV GIS straight bus, well as a 12.5 kV GIS straight bus (converted from 8.3 kV). | 2023-10-10 | 2023-12-01
N/A | NYSEG 115 kV Line 978 Full Rebuild | Avangrid | N/A | 115 kV Line 978 is double circuit with 115 kV Line 963 from Montour Falls to Ridge Road to Hillside. Rebuild the existing 16-mile double circuit line with 1192 Bunting ACSR from Montour Falls to Ridge Road and 1192 Bunting ACSR from Ridge Road to Hillside. The new double circuit line would be rebuilt on an offset with custom steel structures. | 2023-10-10 | 2023-12-01
N/A | NYSEG 115 kV Line 963 Partial Rebuild | Avangrid | N/A | 115 kV Line 963 is double circuit with 115 kV Line 978 from Montour Falls to Ridge Road to Hillside. Rebuild the existing 16-mile double circuit line with 1590 Falcon ACSR from Montour Falls to Ridge Road and 1590 Falcon ACSR from Ridge Road to Hillside. The new double circuit line would be rebuilt on an offset with custom steel structures. | 2023-10-10 | 2023-12-01
N/A | NYSEG 230 kV Line 67 Full Rebuild | Avangrid | N/A | Rebuild the existing 11-mile 230 kV line with bundled 1192 Bunting ACSR conductor on an offset with steel monopole structures. | 2023-10-10 | 2023-12-01
N/A | RGE 115 kV Line 906 Full Rebuild | Avangrid | N/A | Rebuild the existing 30-mile 115 kV line with 1590 Falcon ACSR conductor on an offset with light duty steel monopole structures. | 2023-10-10 | 2023-12-01
N/A | NYSEG 115 kV Line 934 Full Rebuild | Avangrid | N/A | Rebuild the existing 19-mile 115 kV line with 795 Drake ACSR conductor on an offset with light duty steel monopole structures. | 2023-10-10 | 2023-12-01
N/A | NYSEG 34.5 kV Line 539 Partial Rebuild | Avangrid | N/A | Rebuild 2 miles from Marshall to Marsh Hill of the existing 13-mile 34.5 kV line with 477 Pelican ACSR conductor on an offset with light duty steel monopole structures. | 2023-10-10 | 2023-12-01
N/A | NYSEG 34.5 kV Line 542 Full Rebuild | Avangrid | N/A | Rebuild the existing 6-mile 34.5 kV line with 477 Pelican ACSR conductor on an offset with light duty steel monopole structures. | 2023-10-10 | 2023-12-01
N/A | NYSEG 34.5 kV Line 546 Partial Rebuild | Avangrid | N/A | Rebuild 8 miles of 34.5 kV line from Troupsburg to Marsh Hill with 477 Pelican ACSR conductor on an offset with light duty steel monopole structures. Rebuild 3 miles of the existing 8-mile 34.5 kV line from Troupsburg to Woodhull with 477 Pelican conductor on an offset with light duty steel monopole structures. | 2023-10-10 | 2023-12-01
N/A | NYSEG 34.5 kV Line 565 Full Rebuild | Avangrid | N/A | Rebuild the existing 8-mile 34.5 kV line with 477 Pelican ACSR conductor on an offset with light duty steel monopole structures. | 2023-10-10 | 2023-12-01
N/A | Minor Substation Upgrades | Avangrid | N/A | Terminal Equipment at the following stations will be replaced. Moraine Rd Flat St Spencer Hill Yawger Rd Caton Ave West Erie Ave Sta 128 Sullivan Park | 2023-10-10 | 2023-12-01
N/A | Con Edison’s Jamaica to KIAC-JFK Feeder Replacement | Calpine | N/A | Replace the existing 138kV cable between Con Edison’s Jamaica substation and KIAC-JFK’s high voltage switchyard with like in kind. | 2023-09-09 | 2023-11-02
69 | Empire State Newsprint | Besicorp-Empire Power | 2001-11-14 | Small changes to interconnection plans. | 2003-12-22 | 2004-01-08
93 | In-City I (Cross Hudson) | PSEG Power | 2001-12-12 | Reduce size from 1200 MW to 550 MW. | 2002-08-19 | 2002-09-13
107 | Caithness Bellport | Caithness Long Island | 2005-06-30 | Increase size from 290 MW to 309.6 MW. | 2004-10-13 | 2004-11-09
113 | Prattsburgh Wind Park | Windfarm Prattsburgh | 2004-02-19 | Reduce size from 75 MW to 55.5 MW. | 2006-11-10 | 2007-05-03
115 | E. Fishkill Transformer | Central Hudson | N/A | Request to install for standby operation. | 2006-06-14 | 2006-06-19
119 | Prattsburgh Wind Farm | Ecogen LLC | 2004-04-29 | Potential change of turbines. | 9/10/07-9/13/07 | 2007-10-03
119 | Prattsburgh Wind Farm | Ecogen LLC | “ | Change of proposed I/S date to 09/2010. | 2009-02-24 | 2009-12-22
119 | Prattsburgh Wind Farm | ECOGEN, LLC | “ | Change of proposed I/S date to 05/2012. | 2010-08-23 | 2010-09-30
125 | Linden VFT | East Coast Power | 2006-03-09 | Remove NY-side capacitor banks. | 2009-03-30 | 2009-05-29
125 | Linden VFT | Linden VFT LLC | 2006-03-09 | Alternative configuration for Goethals ring bus. | 2011-01-21 | 2011-02-17
127A | Munnsville | Airtricity | 2006-06-15 | Change I/S date for the last 6 MW of the project to 12/31/2012. | 2008-04-22 | 2009-12-22
135&199 | Canandaigua I & II | UPC Wind Management | 2007-02-27 | Change in Developer Attachment Facilities. | 2006-03-07 | 2007-05-03
135&199 | Canandaigua I & II | UPC Wind Management | “ | Change machines. | 2006-07-13 | 2007-05-03
135&199 | Canandaigua I & II | UPC Wind Management | “ | Increase size of projects by 0.5 MW each. | 2006-08-30 | 2007-05-03
141 | Flat Rock Wind Power | Flat Rock Wind Power | 2004-01-22 | Change machines. | 2004-03-03 | 2004-03-09
141 | Flat Rock Wind Power | Flat Rock Wind Power | “ | Increase size from 300 MW to 321 MW. | 2006-03-30 | 2006-04-10
142 | Steuben Wind (formerly Hartsville) | EC&R Northeast, LLC | 2006-06-15 | Change COD to 11/2010. | 2008-05-27 | 2009-12-22
144 | High Sheldon Windfarm | Sheldon Energy | 2006-06-15 | Potential changes: Reduce size from 129 MW to 112.5 MW, elimination of 20 MVAr fixed capacitor due to increased machine VAr cap. | 2/15/08-5/28/08 | 2008-06-12
144 | High Sheldon Windfarm | Sheldon Energy | “ | Notice of decision to implement changes. | 2008-06-16 | N/A
147 | West Hill Windfarm | NY Windpower | 2006-06-27 | Change machines and reduce size to 37.5 MW. | 2007-01-19 | 2007-05-03
147 | West Hill Windfarm | NY Windpower | “ | Reduce size from 37.5 MW to 31.5 MW, change transformer. (Potential impact of changes on design of SUFs to be evaluated in engineering design studies conducted under the Interconnection Agreement.) | 2009-03-03 | 2009-12-22
147 | West Hill Windfarm | West Hill Windpower, LLC | 2006-06-27 | Change of proposed I/S date to 09/2012. | 2010-08-31 | 2010-09-30
152 | Moresville Energy Ctr | Moresville Energy | 2006-06-15 | Potential changes: change turbines to Vestas V90, reduce size from 129 MW to 99 MW. | 3/26/08-5/29/08 | 2009-12-22
156 | Fairfield Wind Project | PPM Energy/Atlantic Wind | 2006-06-15 | 1) Change proposed COD to 01/2011; | 2009-09-23 | 2010-04-29
2) Reduce size from 120 MW to 74 MW;
3) Change of turbines to Gamesa 2.0 MW units;
4) Reduce 34.5 kV collection system and 34.5/115 kV step-up transformer to match reduced project size;
5) Move POI 1.6 miles west, but on same line.
157 | NY I Project | BP Wind Energy NA, Inc. | 2008-12-18 | Change of proposed I/S date to 12/15/2013. | 2010-07-17 | 2010-07-29
160 | Jericho Rise Wind Farm | Jericho Rise Wind Farm | 2007-02-27 | Change machines, reduce size from 101.2 MW to 79.2 MW, and change POI to Willis 115 kV Substation. | 10/22/07-11/14/07 | 2007-12-20
161&171 | Marble River & Clinton | Marble River, LLC | 2006-06-15 | Increase in combined size of projects from 208 MW to 218 MW. | 2006-08-10 | 2006-08-21
County Wind Farms
161&171 | Marble River | Marble River, LLC | “ | Change turbines, change size to 216.3 MW. | 5/1/08-10/8/08 | 2008-10-14
161&171 | Marble River | Marble River, LLC | “ | Change of COD to 10/31/2011. | 12/11/08-11/6/09 | 2009-12-22
161&171 | Marble River | Marble River, LLC | “ | Change of COD to 10/31/2012. | 2011-01-27 | 2011-02-17
161&171 | Marble River | Marble River, LLC | “ | Change of turbines to Vestas V112, resultant reduction in size from 216.3 MW to 215.3 MW, and elimination of capacitor banks. | 2011-08-17 | 2012-01-23
166 | St. Lawrence Wind Farm | Acciona Windpower | 2007-02-27 | Change machines. | 2008-03-05 | 2008-06-12
166 | St. Lawrence Wind Farm | Acciona Windpower | “ | Potential size reduction from 130 to 79.5 MW. | 2008-06-09 | 2008-06-12
166 | St. Lawrence Wind Farm | Acciona Windpower | “ | Notice of size reduction to 79.5 MW. | 2009-08-06 | N/A
166 | St. Lawrence Wind Farm | Acciona Windpower | “ | Potential extension of COD to 12/2011. | 2008-08-11 | 2009-12-22
166 | St. Lawrence Wind Farm | Acciona Wind Energy | “ | Potential change of COD to 9/2012. | 2010-01-19 | 2010-02-19
166 | St. Lawrence Wind Farm | St. Lawrence Windpower | “ | Change of in-service date to 09/2013 and change of COD to 12/2013. | 2011-05-04 | 2011-07-05
166 | St. Lawrence Wind Farm | Cape Vincent Wind Power | “ | Change of ownership and combined with Q#207 Cape Vincent Project. (See related entry for Q#207 below.) | 2012-03-22 | 2012-08-07
168 | Dairy Hills Wind Farm | Dairy Hills Wind Farm | 2006-06-15 | Reduce size from 132 MW to 120 MW. | 2007-06-11 | 2007-06-26
169 | Alabama Ledge Wind Farm | Alabama Ledge Wind Farm | 2007-02-27 | Change of POI, change turbines, change in size. | 7/11/08-10/3/08 | 2008-10-14
169 | Alabama Ledge Wind Farm | Alabama Ledge Wind Farm | “ | Change of turbines to Suzlon S88, increase size from 79.2 MW to 79.8 MW. | 2009-02-02 | 2009-12-22
169 | Alabama Ledge Wind Farm | Alabama Ledge Wind Farm | “ | Extension of the COD to October 2013. | 2011-06-16 | 2012-02-16
172 | Clinton Windfield | Noble Envir. Power | 2006-06-15 | Potential size reduction from 80.0 to 79.5 MW. | 2007-12-05 | 2007-12-20
175 | Ellenburg Windfield | Noble Envir. Power | 2006-06-15 | Potential size increase from 79.5 to 81.0 MW. | 2007-12-05 | 2007-12-20
177 | Wethersfield Windfield | Noble Envir. Power | 2007-02-27 | Potential size reduction from 127.5 to 126.0 MW. | 2007-12-11 | 2007-12-20
178 | Allegany Windpark | Noble Envir. Power | 2007-02-27 | Potential increase in size from 99 MW to 100.5 MW. | 2008-06-23 | 2008-09-08
178 | Allegany Windpark | Noble Envir. Power | “ | Notice of change in size. | 2008-09-19 | N/A
178 | Allegany Windpark | Noble Envir. Power | “ | Change of POI. | 2008-09-30 | 2009-12-22
182 | Howard Wind | Everpower Global | 2007-02-27 | Change machines and reduce size to 62.5 MW. | 2007-06-11 | 2007-06-26
182 | Howard Wind | Howard Wind, LLC | “ | Change machines and reduce size to 57.4 MW. | 2011-03-03 | 2011-08-02
182 | Howard Wind | Howard Wind, LLC | “ | Change of COD to December 2011. | 2011-03-03 | 2011-12-05
186 | Jordanville Wind | Community Energy | 2006-06-15 | Reduce size from 150 MW to 136 MW. | 2007-09-18 | 2007-10-03
186 | Jordanville Wind Project | Iberdrola | “ | Reduce size from 136 MW to 80 MW, replace 230 kV line with 34.5 kV feeders. | 2008-04-11 | 2008-06-12
186 | Jordanville Wind Project | Iberdrola | “ | Potential change of proposed in-service date to 12/2011. | 2008-12-23 | 2009-12-22
197 | Roaring Brook Wind | PPM Roaring Brook, LLC | 2008-02-28 | Change of I/S Date to 10/2015 and COD to 12/2015. | 2012-10-11 | 2013-02-19
198 | New Grange Wind Farm | New Grange | 2008-02-28 | Change turbines, reduce size from 79.8 MW to 79.2 MW. | 4/10/08-8/11/08 | 2008-09-08
198 | Arkwright Summit Wind (formerly New Grange) | New Grange | “ | Change of turbines to Suzlon S88, increase size from 79.2 to 79.8 MW, change proposed I/S date to 2010. (Developer proposal to change from 6-breaker ring to 3- breaker ring yet to be evaluated by NYISO and TO.) | 1/20/09-6/23/09 | 2009-12-22
198 | Arkwright Summit Wind | New Grange | “ | Developer proposal to change from 6-breaker ring to 3- breaker ring interconnection. | 1/20/09-1/26/10 | 2010-04-29
198 | Arkwright Summit Wind | New Grange | “ | Extension of the COD to 9/30/2013. | 2011-12-20 | 2012-01-23
201 | Berrians GT | NRG Energy | 2009-02-27 | Change machines (no change in size), change in-service date to 2010/06 | 2007-10-25 | 2007-12-20
201 | Berrians GT | NRG Energy | “ | Potential change of machine to GE 7FA CC. | 2009-11-11 | 2009-12-22
201 | Berrians GT | NRG Energy | “ | Notice of change of machine. | 2009-12-31 | N/A
201 | Berrians GT | NRG Energy | “ | Change of in-service date to June 2014. | 2011-04-27 | 2011-07-05
201 | Berrians GT | NRG Energy | “ | Change in specifications for the generator lead cable for the Berrians GT & GT II project (Q#201/224) . | 2014-06-16 | 2014-08-01
206 | Hudson Transmission | Hudson Trans. Partners | 2008-02-28 | Change of COD to 5/31/2013. | 2011-03-17 | 2011-04-04
207 | Cape Vincent | BP Alternative Energy | 2008-02-28 | Change turbines and transformers. | 2008-07-23 | 2008-09-08
207 | Cape Vincent | Cape Vincent Wind Power | “ | Change of in-service date to 09/2013 and change of COD to 12/2013. | 2011-05-23 | 2011-07-05
207 | Cape Vincent | Cape Vincent Wind Power | “ | Q#166 St. Lawrence Wind Farm Project combine with Q#207 Cape Vincent Project. Modifications: Configuration: Both projects connecting into the Rockledge Substation through a single 115 kV line. | 2012-03-22 | 2012-08-07
Change of COD to 12/31/2014.
Change of turbines: Change to Siemens 2.3 turbines for both projects. Resultant reduction in size -
Q#166: Change from 79.5 MW to 75.9 MW
Q#207: Change from 210 MW to 209.3 MW Overall: Change from 289.5 MW to 285.2 MW
210 | Fortran | Canadian Niagara Power | 2009-02-27 | Change of proposed I/S date to Q4 2012. | 2010-01-13 | 2010-02-19
212 | Bliss II Windfield | Noble Envir. Power | 2007-02-27 | Potential size reduction from 30.0 to 28.5 MW. | 2007-12-05 | 2007-12-20
213 | Ellenburg II Windpark | Noble | 2007-02-27 | Change of COD to 10/10/2011. | 2010-05-12 | 2010-05-26
214 | Chateaugay Windpark | Noble Envir. Power | 2007-02-27 | Increase size from 100 MW to 106.5 MW. | 2007-05-30 | 2007-06-26
216 | Nine Mile Point 2 Uprate | Nine Mile Point Nuclear | 2008-02-28 | Change of proposed I/S date to Q2/2012. | 2009-01-15 | 2009-12-22
216 | Nine Mile Point 2 Uprate | Nine Mile Point Nuclear | “ | Change of COD for full capacity uprate to June 2014. Partial capacity uprate (115 MW) expected by June 2012. | 2011-03-28 | 2011-05-04
219 | Huntley | NRG Energy | N/A | Change machines and increase size from 630 to 661 MW | 2007-08-27 | 2007-10-03
222 | Ball Hill Windpark | Noble Envir. Power | 2008-06-19 | Potential reduction in size from 99 MW to 93 MW. | 2008-06-24 | 2008-09-08
222 | Ball Hill Windpark | Noble Envir. Power | “ | Reduce size to 90 MW. | 2008-09-29 | 2008-10-14
224 | Berrians GT II | NRG Energy | N/A | Change machines, reduce size from 322.5 MW to 256/280 MW summer/winter. | 2007-10-25 | 2007-12-20
224 | Berrians GT II | NRG Energy | N/A | Potential changes: reduce size from 256/280 MW to 50/90 MW summer/winter, use excess capacity of Q201 rather than new units. | 2009-11-11 | 2009-12-22
224 | Berrians GT II | NRG Energy | N/A | Notice of size reduction to 50/90 MW summer/winter. | 2009-12-31 | N/A
224 | Berrians GT II | NRG Energy | 2011-02-28 | Change of in-service date to June 2014. | 2011-04-27 | 2011-07-05
224 | Berrians GT II | NRG Energy | “ | Change in specifications for the generator lead cable for the Berrians GT & GT II project (Q#201/224) | 2014-06-16 | 2014-08-01
231 | Seneca | Seneca Energy II, LLC | 2008-02-28 | Change of in-service date to 10/1/2012. | 2011-11-30 | 2012-01-23
232 | Bayonne Energy Center | Bayonne Energy Center | 2008-10-23 | Change machines (no change in size). | 2007-11-21 | 2007-11-28
232 & 510 | Bayonne Energy Center I & II | Bayonne Energy Center | N/A | Amend the BEC I’s IA to include 110 MVAr shunt reactor, a second 1.75 MW diesel engine, and associated equipment, instead of including such equipment in BEC II. | 2016-06-06 | 2016-07-01
234 | Steel Winds II | Steel Winds | 2008-02-28 | Reduce size from 60 MW to 45 MW, change in-service date to 9/30/09 | 2008-03-13 | 2008-04-08
234 | Steel Winds II | Steel Winds, LLC | “ | Reduce size from 45 MW to 15 MW. | 2010-01-27 | 2010-02-19
237 | Allegany Wind | Allegany Wind, LLC | 2010-02-26 | Change of COD to 12/2/2013. | 2012-09-19 | 2012-10-09
251 | CPV Valley Energy Center | CPV Valley, LLC | 2009-02-27 | Potential change of in-service date to May 2016. | 8/8/11-11/11/11 | 2011-11-16
251 | CPV Valley Energy Center | CPV Valley, LLC | “ | Confirmation of above change of in-service date. | 2011-12-06 | N/A
251 | CPV Valley Energy Center | CPV Valley, LLC | “ | Increase in maximum output for ERIS from 656 MW Summer/753 MW Winter to 678 MW Summer/784 MW Winter. | 2012-01-13 | 2012-02-16
251 | CPV Valley Energy Center | CPV Valley, LLC | N/A | Change of COD to 2/15/18. | 2016-07-28 | 2016-09-02
254 | Ripley-Westfield Wind | Ripley-Westfield Wind, LLC | 2009-02-27 | Change to Siemens 2.3 MW turbines. Reduced size from 124.8 MW to 124.2 MW. | 2010-03-29 | 2010-05-26
260 | Stephentown Flywheel | Beacon Power | N/A | Potential change in transformer size. | 2010-04-12 | N/A
261 | South Pier Improvement | Astoria Generating Co. | 2010-02-26 | Change of in-service date to January 2015. | 2011-10-17 | 2011-11-16
263 | Stony Creek Wind Farm | Stony Creek Wind Farm | 2010-02-26 | Potential reduction in size from 142.5 MW to 88.5 MW. | 2010-04-21 | 2010-04-29
263 | Stony Creek Wind Farm | Stony Creek Wind Farm | “ | Notice of size reduction from 142.5 MW to 88.5 MW. | 2010-04-29 | N/A
263 | Stony Creek Wind Farm | Stony Creek Wind Farm | “ | Increase in maximum output for ERIS from 88.5 MW to 94.4 MW. | 2012-01-30 | 2012-02-16
263 | Stony Creek Wind Farm | Stony Creek Wind Farm | “ | Change of COD to September 2013. | 2012-06-07 | 2012-07-12
263 | Stony Creek Wind Farm | Stony Creek Wind Farm | “ | Reduction of number of turbines from 59 to 58 and reduction in overall size from 94.4 MW to 92.8 MW. | 2013-08-28 | 2013-09-05
266 | Berrians GT III | NRG Energy | 2009-02-27 | Change of machines to GE 7FA CC. | 2009-11-11 | 2009-12-22
266 | Berrians GT III | NRG Energy | “ | Reduction in size from 744 MW Summer/789 MW Winter to 250 MW Summer/290 MW Winter, and change of in-service date to June 2014. | 2011-09-12 | 2011-11-16
266 | Berrians GT III | NRG Energy | “ | Change of in-service date to June 2016. | 2012-02-24 | 2012-03-07
267 | Winergy NYV Wind Farm | Winergy Power | N/A | Change of turbines to Siemens SWT-6.0-154 and extension of COD to Jan 2019 for Stage 1 and Jan 2020 for Stage 2. | 2012-01-12 | 2012-02-16
270 | Hounsfield Wind | Wind Development Contract Company | 2009-02-27 | Change of COD to 12/2015. | 2011-12-22 | 2012-01-23
276 | Homer Solar Energy Center | EDF Renewable | N/A | Change the proposed facility from a 90 MW wind farm facility to a 90 MW solar farm facility. | 2019-05-21 | 2019-09-05
276 | Homer Solar Energy Center | EDF Renewable | N/A | Move POI approximately 728 feet south/southwest along the Cortland-Fenner 115kV line | 2022-08-22 | 2022-11-01
291 | LI Cable – Phase 1 | Long island Cable | N/A | Change of turbines to Siemens SWT-6.0-154 and extension of COD to Jan 2019 for Stage 1 and Jan 2020 for Stage 2. | 2012-01-12 | 2012-02-16
292 | LI Cable – Phase 2a | Long island Cable | N/A | Change of turbines to Siemens SWT-6.0-154 and extension of COD to Jan 2019 for Stage 1 and Jan 2020 for Stage 2. | 2012-01-12 | 2012-02-16
310 | Cricket Valley Energy Center | Cricket Valley Energy Center | 2011-02-28 | Increase in maximum output for ERIS from 1,002 MW Summer/1,115 MW Winter to 1,019.9 MW Summer/ 1,136 MW Winter. | 2012-01-27 | 2012-02-16
330 | Upton Solar Farms | BP Solar | 2010-02-26 | Change of inverter vendor to SMA Sunny Central with small reduction in size from 32.0 MW to 31.5 MW. | 2010-04-13 | 2010-05-26
349 | Taylor Biomass | Taylor Biomass Energy- Montgomery, LLC | N/A | Change of COD to 04/2021. | 2017-12-08 | 2018-01-05
363 | Poseidon Offshore | Anbaric Development Partners, LLC | N/A | Change the project type from a Class Year Transmission project to a Large Generating Facility project. | 2018-06-28 | 2019-04-01
386 | Grand Isle Inter-Tie Project | NGrid | N/A | Redesigned the new proposed 230 kV to add an additional breaker to a bay and reconfigure the connections in the station to add the 3rd 230/115 kV transformer to the new 230 kV substation. | 2016-11-07 | 2017-03-02
387 | Cassadaga | Everpower | N/A | Relocate the Cassadaga POI station location to a nearby parcel. | 2018-04-02 | 2018-09-06
387 | Cassadaga | Innogy | N/A | Change (1) the composition of the wind turbines from 42 Vestas 3.0 MW V112s with a total output of 126.0 MW to 10 Gamesa 2.625 MW G114s and 27 Nordex 3.675 MW N117s with a total output of 126.5 MW and (2) the main transformer from a three-winding 115/34.5/13.8kV 84/112/140 MVA transformer with 8% impedance to a two-winding 115/34.5kV 112/140 MVA transformers with 11% impedance. | 2019-01-18 | 2019-08-01
387 | Cassadaga | Innogy | N/A | Change proposed In-Service Date from 1/2021 to 12/2020, change the proposed Initial Synchronized Date from 12/2020 to 3/2021 and change Commercial Operation Date from 4/2021 to 6/2021. | 2021-02-19 | 2021-04-07
393 | Berrians East Repower | NRG | N/A | Change of two 1-on-1 combined cycle plant to 3 simple cycle plant (aka replacing two HRSG steam units that are part of the two 1-on-1 combine cycle plant with a GT unit, and there is no change to the original two GT units that are part of the two 1-on-1 combine cycle plant.) | 2017-02-27 | 2017-04-03
393 | Berrians East Repower | NRG | N/A | Change the turbine composition from three simple cycle 7F turbines to a single simple cycle 7H turbine, which could reduce the net total output of the project from 508 MW in summer and 584 MW in winter to 431 MW in summer and 438 MW in winter. | 2019-08-15 | 2020-02-04
393 | Berrians East Repower | NRG | N/A | Modification to the proposed generator to retire the existing 38.5 MVAR cap bank and replace the existing 547 MVA H65 generator with a new H84 generator with a rating of 600 MVA in order to meet Con Edison’s power factor requirements. | 2020-07-12 | 2020-11-02
393 | Berrians East Repower | NRG | N/A | Change proposed In-Service Date, Initial Synchronized Date, and Commercial Operation Date from 01/2022, 01/2023, and 06/2023 to 05/2022, 08/2023, and 12/2023, respectively. | 2021-07-21 | 2021-08-02
393 | Berrians East Repower | NRG | N/A | Change proposed In-Service, Initial Synchronization, and Commercial Operation Dates from 5/2022, 8/2023, and 12/2023 to 5/2023, 8/2024 and 12/2024, respectively. | 2022-06-15 | 2022-07-01
396 | Baron | Innogy | N/A | Change (1) the composition of the wind turbines from 100 Vestas 3.0 MW V112s with a total output of 300.0 MW to 11 Gamesa 2.625 MW G114s and 56 Nordex 3.675 MW N117s with a total output of 238.4 MW and (2) the entrance into the Canandaigua substation from the Northwest corner to the Southeast corner resulted in an additional 600 ft of 230kV underground cable. | 2019-01-18 | 2019-08-01
396 | Baron | Innogy | N/A | Change (i) the turbine composition from eleven (11) Gamesa G114 2.625 MW and fifty-six (56) Nordex N117 3.675 MW to eight (8) Gamesa G114 2.625MW and fifty-one (51) Vestas V150 4.2MW (no change in the MW size of the project), (ii) the main transformer from one (1) 34.5/230 kV, 150/200/250 MVA transformer to two (2) 34.5/230 kV, 84/112/135 MVA transformers, and (iii) the Commercial Operation Date from December 2020 to two operational phases with a proposed Commercial Operation Date for phase 1 (126MW) of September 1, 2022, and a proposed Commercial Operation Date for phase 2 (109MW) of July 9, 2023. | 2020-05-26 | 2020-08-31
396 | Baron | Innogy | N/A | Change proposed In-Service Date from 5/2020 to 5/2022, change proposed Initial Synchronized Date from 5/2020 to 6/2022 and change proposed Commercial Operation Date from 7/2020 to 9/2022. | 2021-02-19 | 2021-04-07
396 | Baron | Innogy | N/A | Change the COD of Phase 1 of the project to 12/15/22 and clarify the MW sizes of Phases 1 and 2 of the project as 121.8 MW and 113.2 MW, respective. | 2021-06-15 | 2021-07-01
396 | Baron | Innogy | N/A | Change Phase 2 COD of the project from 7/9/23 to 12/31/23. | 2021-10-22 | 2022-01-04
396 | Baron | Innogy | N/A | Change wind turbines of the Phase 2 of the project from 27 Vestas V150 4.2 MW to 26 Vestas V150 4.5 MW including their associated electrical equipment resulted in increasing the Phase 2 MW output from 113.2 MW to 117.0 MW and change the Phase 2 COD from December 31, 2023 to December 2024. | 2022-07-01 | 2023-03-02
401 | Caithness II | Caithness | N/A | Change a 2x1 F-Class dual fuel combined cycle plant that has a maximum generating capacity of 764 MW in summer (at 85°F, 20 MW station load) and 808 MW in winter (at 10°F, 22 MW station load) to a 1x1 H-class dual-fuel combined-cycle plant that has a maximum potential generating capacity of 599 MW in summer (at 85°F, 16.5 MW station load) and 632 MW in winter (at 10°F, 14.5 MW station load); change the project request for both ERIS and CRIS from 744 MW to 533 MW; and reconfigure both the modified Sills Rd ring bus and the proposed new Sills Rd ring bus as detailed in the attached one-line diagram. | 2017-02-13 | 2017-05-09
422 | Eight Point Wind | NextEra | N/A | Change project name, reduce size from 103.4 MW to 101.2 MW, change wind turbines from thirty-two 3.32 MW GE to twenty-seven 3.43 MW GE and five 1.715 MW GE, and other electrical characteristic changes. | 2017-02-24 | 2017-04-03
422 | Eight Point Wind | NextEra | N/A | Change wind turbines from thirty-two (32) GE 3.23‐130 series for a total of 101.2 MW to twenty-seven (27) GE 3.43‐130 and four (4) GE 2.3‐130 series wind turbines for a total of 101.8 MW resulted in increasing the project’s Energy Resource Interconnection Service (ERIS) value from 101.2 MW to 101.8 MW, which is a 0.6 MW increase in proposed ERIS value. | 2019-01-15 | 2019-03-06
422 | Eight Point Wind | NextEra | N/A | Change the composition of wind turbines from twenty-seven (27) GE 3.43-130 series and four (4) GE 2.3-130 series wind turbines to eight-teen (18) GE 5.5MW/6.44MW and six (6) GE 2.03MW/2.78 MVA wind turbines and also increase its ERIS to 111.2 MW from its ERIS baseline of 101.2 MW. | 2022-05-17 | 2022-07-01
422 | Eight Point Wind | NextEra | N/A | Change the composition of wind turbines from eighteen (18) GE 5.5MW/6.44MW and six (6) GE 2.03MW/2.78 MVA wind turbines to (8) GE 5.449 MW/6.44 MVA, (10) GE 5.5 MW/6.44 MVA and (7) GE 2.086 MW/2.78 MVA including the electrical characteristics of their corresponding padmount transformers without changing its ERIS values of 111.2 MW | 2022-10-21 | 2022-12-02
430 | Cedar Rapids Transmission | H.Q. Energy Services U.S. Inc. | N/A | Change the route of the #12 Line (National Grid 115 kV Alcoa – Dennison #12 line) that is required to be reconductored as part of the project resulted in shortening the existing line from ~3 miles to ~1.7 miles. | 2019-11-26 | 2020-03-05
430 | Cedar Rapids Transmission | H.Q. Energy Services U.S. Inc. | N/A | Change the composition of the circuit from NYPA MAL4 through the NGrid line from 100% of 1590 MCM AAC conductor to a combination of 636 MCM ACSS conductor and 1590 MCM AAC conductor. | 2019-11-26 | 2020-12-08
458 | CH Interconnection | TDI USA Holding | N/A | Change the project from a three-terminal project (two points of withdrawal at Hertel and New Scotland and one point of injection at Astoria) to a two-terminal project (one at Hertel and one at Astoria). | 2016-12-06 | 2017-04-03
458 | CH Interconnection | TDI USA Holding | N/A | Change the operating voltage of the HVdc cable of Q458 CH Interconnection from 320 kV to 400 kV. | 2019-06-11 | 2019-08-01
467 | Tallgrass Solar | Invenergy | N/A | Change of inverter from a single GE module of 4MVA to a new GE 4x1MVA due to product discontinued. | 2016-06-15 | 2016-08-01
467 | Tallgrass Solar | Invenergy | N/A | Rescinded the 6/15/16 change request. Keep the inverter as a single GE module of 4MVA. | 2016-11-07 | 2016-12-01
495 | Mohawk Solar | Mohawk Solar LLC | N/A | Change (1) the inverter type from 45 SMA SC2200-US central station inverters to 710 SMA Sunny Highpower PEAK3 150 kVA string inverters, (2) inverter step-up transformers from 45, 2.2 MVA pad mounted transformers to eight (8) 1 MVA, fifteen (15) 2 MVA, and nineteen (19) 3 MVA units, (3) three 34.5 kV collector circuits from the solar array areas to the collector substation to four 34.5 kV collector circuits, and (4) the 115/34.5 kV main step-up transformer from 60/80/100 MVA, 8% impedance to 66/88/110 MVA, 9.5% impedance. | 2019-04-05 | 2019-05-03
495 | Mohawk Solar | Mohawk Solar LLC | N/A | Change proposed Commercial Operation Date from December 2022 to November 2024 | 2022-01-26 | 2022-03-01
505 | Ball Hill Wind | Ball Hill Wind Energy, LLC | N/A | Change COD to 12/2021. | 2016-10-06 | 2020-02-04
505 | Ball Hill Wind | Ball Hill Wind Energy, LLC | N/A | Change the turbine composition from twenty-nine (29) 3.45 MW Vestas V126 turbines to twenty-two (22) 4.3MW Vestas V150 and three (3) 4.2 MW Vestas V136 turbines without changing the project’s size of 100 MW. | 2021-04-02 | 2021-06-01
505 | Ball Hill Wind | Ball Hill Wind Energy, LLC | N/A | Changing Project model from 4 generators to a 1 generator equivalent model | 2023-09-29 | 2023-11-02
510 | Bayonne Energy Center II | Bayonne Energy Center | N/A | Redesign of using one breaker to provide the fault protection for both shunt reactor and capacitor devices, but also retain a circuit switcher for the shunt reactor device. | 2016-10-06 | 2016-11-01
519 | Canisteo Wind | Canisteo Wind Energy LLC | N/A | Change the generation composition from ninety (90) GE 3.23-130 series wind turbines for a total maximum output of 290.7 MW to sixty-nine (69) Vestas V150-4.2 series wind turbines for a total maximum output of 289.8 MW. | 2021-08-06 | 2022-04-01
522 | NYC Energy | NYC Energy LLC | N/A | Change the proposed facility from a 79.9 MW gas turbine facility to a 79.9 MW energy storage facility. | 2019-02-28 | 2019-09-05
525 | Western NY Energy Link | NYPA | N/A | Remove the new bus-tie breaker at Niagara 115 kV from the proposed project. | 2017-04-04 | 2017-05-09
531 | Number 3 Wind | Invenergy | N/A | Change the composition of the project’s wind turbines from forty-six (46) GE2.3‐116 turbines to twenty-six (26) GE3.6‐137 turbines and five (5) GE 2.3‐116 turbines for the same total output of 105.8MW. | 2019-01-22 | 2019-03-06
531 | Number 3 Wind | Invenergy | N/A | Add a 10.5 MVAr capacitor bank at 34.5 kV side and change the rating of the main transformer at the collector station to 78/104/130 MVA. | 2019-03-06 | 2019-04-01
531 | Number 3 Wind | Invenergy | N/A | Change the composition of the project from a configuration of five (5) GE 2.3-116 series wind turbines and twenty-six (26) GE 3.6-137 series wind turbines for a total maximum output of 105.8MW and a 10.5MVAR cap bank to a configuration of five (5) GE 2.3-116 series wind turbines and twenty-two (22) Vestas V150-4.2 series wind turbines for a total maximum output of 103.9MW and a 7.2MVAR cap bank. | 2021-01-20 | 2021-04-07
543 | NY Transco Segment B | Transco | N/A | Change in the physical location of the two shunt capacitor banks connecting at the Pleasant Valley 345 kV substation of Q543 from the Pleasant Valley 345 site to the Van Wagner site, which is 0.81 miles away. | 2019-07-08 | 2019-08-01
543 | NY Transco Segment B | Transco | N/A | Change a portion of the project from (1) removing the existing 138 kV line from Shoemaker (O&R) to Sugarloaf (O&R) 138 kV substations and installing two new 138 kV lines on a double circuit structure between the two stations to (2) keeping the existing 138 kV line from Shoemaker-Sugarloaf 138 kV line as is, repurposing the parallel path Rock Tavern-Sugarloaf 115 kV and adding a Sugarloaf 115/138 kV transformer. | 2020-05-15 | 2020-08-07
543 | NY Transco Segment B | Transco | N/A | Expand the configuration of the Van Wagner substation to a two-bay breaker-and-a-half substation to loop Athens-Pleasant Valley and Leeds Pleasant Valley 345 kV lines (Line 91 and 92, respectively) into the Van Wagner substation resulting in the creation of four new line segments: an Athens-Van Wagner line, a Leeds-Van Wagner line, and two Van Wagner-Pleasant Valley lines with reconductoring of the two new Van Wagner- Pleasant Valley lines. This modification retracts the initial proposal of the radial connection of the Van Wagner cap banks to Pleasant Valley substation. | 2020-06-18 | 2020-10-05
543 | NY Transco Segment B | Transco | N/A | Change the single 50% series compensation system to a two-step series compensation system (16.67% and 33.33%). Also change the proposed line ratings of transmission lines 34, 42, 44 and 305. | 2020-12-28 | 2021-03-01
543 | NY Transco Segment B | Transco | N/A | Classify the Dover phase angle regulators (PARs) as a transmission facility and part of the project and install a by-pass breaker in lieu of a by-pass disconnect for the Dover PARs. | 2022-04-22 | 2022-06-02
545A | Empire State Line | NextEra | N/A | Reconfigure the two double circuit entrances to the new Dysinger 345 kV substation to two single circuit entrance and one double circuit entrance. | 2020-09-28 | 2020-12-01
546 | Roaring Brook Wind | Atlantic Wind LLC | N/A | Change (1) the composition of the project from 39 Gamesa 2.0 MW wind turbine generators to a combination of 12 Siemens Gamesa 4.5 MW, 3 Siemens Gamesa 4.2 MW and 5 Gamesa 2.625 MW wind turbine generators, resulting in a change of Project output from 78 MW to 79.725 MW; (2) the individual wind turbine step-up transformers from thirty-nine 2.35 MVA pad mounted transformers to twelve 5.5 MVA, three 5.0 MVA, and five 2.85 MVA units to match the wind turbine generators; (3) the 34.5 kV collector system to account for connection of 20 wind turbines instead of the original 39 wind turbines; and (4) the 115/34.5 kV main step up transformer from 60/80/100 MVA, 9% impedance to a main step-up transformer with 51/68/85 MVA, 9.5% impedance. | 2019-09-10 | 2019-11-01
546 | Roaring Brook Wind | Atlantic Wind LLC | N/A | Change proposed In-Service Date, Initial Synchronized Date, and Commercial Operation Date from 03/2021, 04/2021, and 04/2021 to 09/2021, 10/2021, and 12/2021, respectively. | 2021-07-15 | 2021-08-02
546 | Roaring Brook Wind | Atlantic Wind LLC | N/A | Change proposed Commercial Operation Date from December 2021 to April 2022. | 2022-01-12 | 2022-03-01
579 | Blue Stone Wind | Calpine | N/A | Change wind turbines from 36 Vestas 126 3.45 MW turbines to 31 Vestas 136 4.0 MW turbines. | 2018-12-13 | 2019-01-09
579 | Blue Stone Wind | Calpine | N/A | Change (1) the turbine composition of the project from 36 Vestas 3.45 MW turbines with a total generating capacity of 124.2 MW to 27 Siemens Gamesa SG4.X- 145 turbines with an operating configuration of 4.6 MW per turbine to maintain the total generating capacity of 124.2 MW and (2) the plant GSU transformer from an 86 MVA transformer to a 133 MVA transformer. | 2019-04-04 | 2019-07-08
579 | Blue Stone Wind | Northland Power | N/A | Change wind turbines from thirty-six (36) 3.45MW Vestas turbines to twenty-six (26) 4.3MW Vestas turbines resulted in decreasing the project’s total MW output from 124.2 MW to 111.8 MW | 2021-03-11 | 2021-05-03
580 | WNY STAMP | Genesee County Economic Development | N/A | Reconfigure the new Q580 STAMP load 345 kV substation design from a breaker-and-half substation to a | 2021-09-30 | 2021-12-01
normally non-bus tie, two-ring bus substation and reduce the proposed load project from 500 MW to 300 MW.
581 | Hills Solar | SunEast Hills Solar LLC | N/A | Changing inverter from TEMIC 4200/3360 to SunGrow SG3600UD | 2023-06-07 | 2023-09-06
586 | Watkins Rd Solar | SunEast Watkins Road Solar LLC | N/A | Changing inverter from TEMIC 4200/3360 to SunGrow SG3600UD | 2023-03-20 | 2023-09-06
596 | Alle Catt II Wind | Invenergy | N/A | Reduce the project’s size comprised of 118 GE 3.23 MW turbines for a total of 381.1 MW to 105 GE 3.23 MW | 2018-11-27 | 2019-01-09
turbines for a total of 339.1 MW (10.78% reduction in size).
596 | Alle Catt II Wind | Invenergy | N/A | Move the Point of Interconnection (POI) of the project | 2019-01-28 | 2019-03-06
approximately 300’ south of the original POI along the same line.
596 | Alle Catt II Wind | Invenergy | N/A | Change (1) the composition of wind turbines of Q596 project from one hundred five GE 3.23-130 turbines for a total of 339.1 MW to eighty-six GE 3.6-137 and twelve GE 2.3-116 turbines for a total of 339.78 MW resulted in an increase of 0.68 MW of the project’s Energy Resource Interconnection Service (ERIS) value and (2) the length | 2019-05-07 | 2019-07-08
of the generator lead line from 8 to 10.68 miles.
596 | Alle Catt II Wind | Invenergy | N/A | Change the generation composition from twelve (12) GE 2.3-116 series and eighty-six (86) 3.6-137 series wind turbines for a total maximum output of 339.7 MW to eighty-one (81) Vestas V150-4.2 series wind turbines for a total maximum output of 340.2 MW. | 2021-10-08 | 2022-08-01
612/695 | South Fork I & II Wind Farm | Deepwater Wind South Fork, LLC | N/A | Change wind turbines from seventeen (17) 8 MW Siemens turbines for a 136 MW total output to twelve (12) 11.5 MW Gamesa turbines for a 138 MW total output. | 2020-10-09 | 2021-05-03
612/695 | South Fork I & II Wind Farm | Deepwater Wind South Fork, LLC | N/A | Modify In-Service Date, Initial Synchronization Date, and Commercial Operation Date from January 2023, July 2023 and August 2023 to May 2023, August 2023 and November 2023, respectively. | 2023-03-14 | 2023-04-03
612 & 695 | South Fork Wind Farm & South Fork Wind Farm II | South Fork Wind, LLC | N/A | Adding a +/-75 MVAr STATCOM unit and a 30.5 MVAr harmonic filter to the 69 kV bus | 2023-08-09 | 2023-10-02
618 | High River Solar | High River Energy Center LLC | N/A | Change the inverters from (49) 2.0 MVA GE LV5-1511-30-UL-SLR to (30) 3.43 MVA/3.09 MW @35°C Power Electronics FS3430M inverters including the electrical characteristics of their corresponding padmount transformers and feeders. | 2022-06-09 | 2022-10-03
619 | East Point Solar | East Point Energy Center LLC | N/A | Change the inverters from (27) 2.0 MVA inverters GE LV5-1511-30-UL-SLR to (15) 4.2 MVA Sunny Central 4200 UP-US Solar Inverters feeders. | 2022-06-09 | 2022-10-03
620 | North Side Solar | North Park Energy, LLC | N/A | Move the POI of the project approximately 0.72 mile to the east of its original location. | 2021-02-25 | 2021-05-03
631 | NS Power Express | Champlain Hudson Power Express, Inc. | N/A | Change the project from a three-terminal HVdc project to a two-terminal HVdc project, eliminating the New Scotland converter station and the proposed 320 kV DC transmission line from New Scotland to the Astoria converter station connecting to the Astoria Annex 345 kV station. | 2021-02-10 | 2021-03-01
631 & 887 | NS Power Express & CH Uprate | CHPE LLC | N/A | Reconfigure the Astoria 345kV ring bus from an 8-breaker ring bus to a 6-breaker ring bus | 2023-03-29 | 2023-06-05
637 | Flint Mine Solar | Flint Mine Solar LLC | N/A | Change proposed Commercial Operation Date from September 2023 to October 2024 | 2022-08-26 | 2022-11-01
637 | Flint Mine Solar | Flint Mine Solar LLC | N/A | Changing projects’ In-Service Date, Initial Synchronization Date, and Commercial Operation Date from September 2023, September 2023 and September 2023 to December 2025, December 2025 and May 2026, respectively | 2023-07-11 | 2023-11-02
678 | Calverton Solar Energy Center | LI Solar Generation, LLC | N/A | Change the POI within the PSEG-LIPA Edwards 138 kV substation from between breaker#1320 and bank#2 to between bank#2 and breaker#1360 resulted in also moving the new breaker from between breaker#1320 and bank#2 to between bank#2 and breaker#1360. | 2019-08-14 | 2019-09-05
678 | Calverton Solar Energy Center | LI Solar Generation, LLC | N/A | Change (1) the composition of inverters from 22 x 1.155 MVA GE inverters to 8 x 3.43 MVA Power Electronics FS3430M inverters, (2) the composition of padmount transformers from 11 x 2.31 MVA transformers with 8 x 3.51 MVS transformers, (3) the main transformer from a two-winding 138/34.5kV 25.4 MVA transformer to a three-winding 138/34.5/13.8kV 30 MVA transformer, and (4) the generating collection system design, but maintain the project’s total maximum output at 22.9 MW. | 2022-05-27 | 2022-07-01
686 | Bull Run Solar | Invenergy Solar Development North America LLC | N/A | Move the Point of Interconnection along the Patnode-Duley 230kV line to directly interconnect to the new 230kV substation created by Q521 Bull Run II Wind and reduce the Project’s size from 170 MW to 125 MW | 2023-03-09 | 2023-04-03
698 | Energy Storage II | Helix Ravenswood, LLC | N/A | Change the POI from Vernon-Rainey 138kV to Rainey- Farragut 345kV. | 2019-07-17 | 2019-09-05
706 | High Bridge Wind | Northland Power | N/A | Change the turbine rating from Vestas V150 4.2 MW to Vestas V150 4.3 MW without changing the project’s size of 100.8 MW total MW output. | 2021-03-11 | 2021-05-03
710 | Horseshoe Solar | Invenergy Solar Development North America LLC | N/A | Change the inverters from 63x 3.2MVA inverters to 48x 4.2MVA, replace the transformer from one 121 MVA 3- winding transformer (115/34.5/13.8kV) to two 66 MVA 3-winding transformers (115/34.5/13.8kV) and shorten the generator lead from 0.75 miles to 0.1 miles. | 2021-02-15 | 2021-04-07
717 | Morris Ridge Solar Energy Center | EDF Renewables Development, Inc. | N/A | Change inverters from Power Electronics (PE) FS3430M to SMA SUNNY CENTRAL 4200 UP-US including its plant step-up transformer impedance and rating | 2023-01-16 | 2023-04-03
720 | Trelina Solar | Trelina Solar Energy Center LLC | N/A | Reduce the generation output from 80MW to 79.8MW | 2022-02-08 | 2022-04-01
737 | El Sunset Park | Empire Offshore Wind LLC | N/A | Change of turbine composition from sixty-eight 12 MW turbines to fifty-four 15 MW turbines with no change in MW output. | 2022-02-04 | 2023-01-19
740 | Oakdale Battery Storage | Bay State Wind | N/A | Change inverters of the project from forty-eight (48) SMA 2750-EV-US inverters to forty-seven (47) SMA SC-3600 US-UP inverters with no change to the total MW charging or discharging of the project. | 2020-09-30 | 2020-12-01
746 | North Street Energy Storage | Peconic River Energy Storage LLC d/b/a North Street Energy Storage | N/A | Change proposed Commercial Operation Date from March 31, 2024 to February 7, 2025. | 2023-01-12 | 2023-05-05
764 | NY Wind Shoreham (aka Canal) | Bay State Wind | N/A | Change an alternative POI, e.g., Canal 138 kV, to a primary POI and reduce the size of the project from 880 MW to 440 MW | 2019-01-22 | 2019-03-06
766 | NY Wind Holbrook | Bay State Wind | N/A | Change the generator lead technology from HVdc to AC | 2019-01-23 | 2019-03-06
766 | NY Wind Holbrook | Bay State Wind | N/A | Replace (a) two AC generator leads of the generating facility directly connected to the Holbrook 138kV substation to (b) a combination of a monopole HVdc and two AC leads connected to the Holbrook 138kV substation. | 2020-10-19 | 2021-02-02
777 | White Creek Solar | Community Energy Solar, LLC | N/A | Change the composition of the project inverters from fifty-four (54) 2.7 MVA TMEIC units to thirty-one (31) 6 x 0.795 MVA TMEIC inverter units. | 2021-03-03 | 2021-04-07
783 | South Ripley Solar | ConnectGen Chautauqua County LLC | N/A | Change the project’s inverter nameplate rating from 273.8 MW to 278.1 MW without changing the 270 MW total output of the project. | 2021-04-05 | 2021-05-03
783/1014 | South Ripley Solar | ConnectGen Chautauqua County LLC | N/A | Merge the queue positions of two co-located projects – Q783 South Ripley 270 MW solar project and Q1014 South Ripley 20 MW energy storage project | 2021-04-28 | 2021-06-01
783 | South Ripley Solar | ConnectGen Chautauqua County LLC | N/A | Modify the Point of Interconnection to interconnect the Project directly to the South Ripley 230kV substation | 2023-01-11 | 2023-03-02
785 | Erie Wyoming County Solar | ConnectGen Erie-Wyoming LLC | N/A | Addition of 175 MW energy storage to proposed 175 MW solar Generator behind the same Point of Interconnection with no change in proposed ERIS. | 2022-12-07 | 2023-01-19
800 | Rich Road Solar | EDF Renewables Development, Inc. | N/A | Change its 240 MW Large Facility project comprised of 240 MW solar Generator to a 240 MW Large Facility project comprised of 240 MW solar Generator and 20 MW battery Generator behind a single Point of Injection. | 2022-08-15 | 2022-12-02
811 | Cider Solar | Hecate Energy Cider Solar LLC | N/A | Move the proposed Point of Interconnection (POI) approximately 3 miles from the original proposed POI along the same transmission line. | 2020-10-14 | 2021-03-01
825 | Setauket Energy Storage | Setauket Energy Storage, LLC | N/A | Reduce the size of the project from 76.8 MW to 65.3 MW. | 2020-12-15 | 2021-04-07
857 | Columbia Solar | EDF Renewables Development, Inc. | N/A | Change its 350 MW Large Facility project comprised of 350 MW solar Generator to a 350 MW Large Facility project comprised of 350 MW solar Generator and 20 MW battery Generator behind a single Point of Injection. | 2022-08-15 | 2022-12-02
857 | Columbia Solar | EDF Renewables Development, Inc. | N/A | Move the Point of Interconnection along the Edic-Fraser 345kV line | 2023-03-07 | 2023-04-03
858 | Genesee Road Solar | EDF Renewables Development, Inc. | N/A | Change its 350 MW Large Facility project comprised of 350 MW solar Generator to a 350 MW Large Facility project comprised of 350 MW solar Generator and 20 MW battery Generator behind a single Point of Injection. | 2022-08-15 | 2022-12-02
858 | Genesee Road Solar | EDF Renewables Development, Inc. | N/A | Reduce project size from 350 MW to 250 MW | 2022-11-11 | 2023-01-19
860 | Rosalen Solar | EDF Renewables Development, Inc. | N/A | Reduce project size from 350 MW to 200 MW | 2022-11-11 | 2023-01-19
881 | New Bremen Solar | New Bremen Solar LLC | N/A | Modify the project configuration at the Point of Interconnection (POI) from five (5) breaker ring bus to three (3) breaker ring bus including moving the POI along the Bremen-Lowville 115kV (Line#6). | 2023-02-01 | 2023-03-02
883 | Garnet Energy Center | Garnet Energy Center LLC | N/A | Clarify the Point of Interconnection as interconnecting on the Pannell-Clay 345kV circuit#2 (PC2) rather than the Pannell-Clay 345kV circuit#1 (PC1) | 2023-02-14 | 2023-04-03
907 | Harlem River Yard | 174 Power Global | N/A | Change the inverter manufacturer from SMA to Tesla. | 2021-02-02 | 2021-03-01
907 | Harlem River Yard |  | N/A | Proposing to reduce the project's capacity from 100 MW to 79.9 MW for both ERIS and CRIS due to site considerations. The decrease will be made through the plant controller to limit the project output to 79.9 MW. | 2023-06-07 | 2023-12-01
912 | Intrepid Storage 69 | Hecate Grid Intrepid LLC | N/A | Move the Point of Interconnection of the project from Barrett 69kV substation to a new 34.5kV substation that is interconnected via a loop-in/loop-out of the two existing Barrett – Oil City and Barrett – Ocean 4T2 34.5 kV lines. | 2022-05-27 | 2022-07-01
918 | Intrepid Storage 138 | Hecate Grid Intrepid LLC | N/A | Move the Point of Interconnection of the project from Barrett 138kV substation to a new 138kV substation that is interconnected via a loop-in/loop-out of the two existing Barrett – Valley Stream 138 kV lines. | 2022-05-27 | 2022-07-01
931 | Astoria Energy Storage | Hanwha Energy USA Holdings d/d/a/ 174 Power Global | N/A | Change the inverter manufacturer from SMA to Tesla. | 2021-02-02 | 2021-03-01
950 | Orlean Solar | Orleans Solar LLC | N/A | Change the number of circuits looping into the new proposed substation from three Lockport-Mortimer lines (Lines#111, 113 and 114) to two Lockport-Mortimer lines (Lines#111 and 113). | 2021-02-05 | 2021-04-07
971 | East Setauket Energy Storage | Savion, LLC | N/A | Reduce the size of the project from 293.5 MW to 125 MW. | 2020-12-15 | 2021-04-07
956 | Holbrook Energy Storage | Holbrook Energy Storage | N/A | Reduce the project size from 296.4 MW to 110 MW. | 2020-12-23 | 2021-03-01
957 | Holtsville Energy Storage | Holtsville Energy Storage | N/A | Move the Point of Interconnection of Q#957 along the Holtsville-Patchogue 69kV | 2023-02-24 | 2023-04-03
958/959 | EI Oceanside 1 & 2 | Empire Offshore Wind LLC | N/A | Reduce Q959 from 1500 MW to 1260 MW and Q958 from 1000 MW to 96 MW and clarifying Q958 as a 96 MW uprate or a 1356 MW alternative project of Q959. | 2021-03-26 | 2021-05-03
958/959 | EI Oceanside 1 & 2 | Empire Offshore Wind LLC | N/A | Move the Point of Interconnection (POI) of Q959/958 from the Barrett 138 kV substation to a new Barrett 138kV expansion substation, which is also known as the Liotta 138kV substation that is interconnected via a loop-in/loop-out of the two existing Barrett-Valley Stream 138kV lines. | 2022-03-04 | 2022-04-01
959 | EI Oceanside 2 | Empire Offshore Wind LLC | N/A | Modify the project configuration at the Liotta 138kV Point of Interconnection from a four-bay 138kV bus to a three-bay 138kV bus, and redesign the generating facility equipment (e.g., modify transformers at Liotta substation from 138/230kV transformers to 138/345kV transformers) | 2023-01-17 | 2023-04-03
959 | El Oceanside 2 | Empire Offshore Wind LLC | N/A | Change wind turbines from GE turbines to Vesta turbines, including the Developer Attachment Facilities. | 2023-02-25 | 2023-05-05
971 | East Setauket Energy Storage | Savion LLC | N/A | Move the Point of Interconnection along the Holbrook-Miller Place 138kV line | 2023-03-02 | 2023-04-03
974 | KCE NY 19 | KCE NY 19 LLC | N/A | Reduce the project size from 80 MW to 79 MW and modify facility equipment | 2023-02-16 | 2023-04-03
987/1045 | NY Wind Holbrook 2 | Bay State Wind | N/A | Change the classification of Q987 and Q1045 as uprated projects of Q766, e.g., (1) Q987 is a 44 MW uprate of Q766 and (2) Q1045 is (i) a 126 MW uprate of Q987 or (ii) a 170 MW uprate of Q766. | 2021-02-09 | 2021-04-07
1007 | NYC Energy LLC Phase 2 | NYC Energy LLC | N/A | Relocate the POI within the same Hudson Avenue substation. | 2022-07-19 | 2022-09-01
1016 | El Steinway 1 | Beacon Wind LLC | N/A | Move the Point of Interconnection of the project from Astoria West 138kV substation to a new 345kV substation that is interconnected via a loop-in/loop-out of the two existing Mott Haven-Rainey 345kV circuits | 2023-03-17 | 2023-05-05
1017 | El Steinway 2 | Beacon Wind LLC | N/A | Move the Point of Interconnection of the project from Astoria East 138kV substation to a new 345kV substation that is interconnected via a loop-in/loop-out of the two existing Mott Haven-Rainey 345kV circuits | 2023-03-02 | 2023-05-05
1031 | Mill Point Solar | ConnectGen Montgomery County LLC | N/A | Add 174 MW energy storage to proposed 250 MW solar Generator behind the same Point of Interconnection with no change in proposed ERIS | 2022-10-13 | 2023-01-19
1036 | Mainesburg ESS | Juno Power Management LLC | N/A | Reduce the project size from 300 MW to 130 MW | 2023-02-10 | 2023-03-02
1040 | Riverline Energy Center | Riverline Energy Center LLC | N/A | Change the project fuel type from a 200MW solar project to a 200 MW battery project. | 2022-06-30 | 2022-12-02
1041 | Silverline Energy Center | Silverline Energy Center, LLC | N/A | Reduce the project size from 200 MW to 150 MW and modify the project to a Co-located Storage Resource project consisting of 150 MW solar Generator and 20 MW energy storage Generator | 2023-02-15 | 2023-06-05
1068 | Buchanan Point BESS | Juno Power Management LLC | N/A | Reduce the project size from 500 MW to 300 MW | 2023-02-10 | 2023-03-02
1079 | Somerset Solar | Somerset Solar LLC | N/A | Reduce the project size from 200 MW to 125 MW | 2023-01-25 | 2023-03-02
1081 | KCE NY 28 |  | N/A | Changing Inverter, PSU impedance change, Collection impedance change, aux power load | 2023-10-13 | 2023-12-01
1088 | Harvest Hills Solar | ConnectGen Cayuga County LLC | N/A | Change its 200 MW Large Facility project comprised of 200 MW solar Generator to a 200 MW Large Facility project comprised of 200 MW solar Generator and 150 MW battery Generator behind a single Point of Injection. | 2022-06-23 | 2022-12-02
1089/1115 | Flat Creek Solar 1 & 2 | SED NY Holdings LLC | N/A | Modify the project configuration to utilize a single/common gen-tie facility for both projects | 2022-12-13 | 2023-03-02
1096 | Allegany 2 Solar | Northland Power U.S. Projects | N/A | Add 40 MW energy storage to proposed 100 MW solar Generator behind the same Point of Interconnection with no change in proposed ERIS | 2022-10-26 | 2023-01-19
1125 | NYPA Northern NY Priority Transmission Project | NYPA | N/A | Change the breaker arrangement of the new Haverstock 345 kV substation from a breaker-and-a-half scheme to a double-breaker double-bus double-bus-tie-breaker scheme, move the termination of the Adirondack-Marcy line to a separate bay within Marcy 345 kV substation and relocate the new Wills 230 kV site from north of the existing Willis 230kV site to east of the existing Willis 230kV site. | 2022-02-17 | 2022-05-05
1125 | NYPA Northern NY Priority Transmission Project | NYPA | N/A | Modify (1) the new bay at Edic 345kV of the project to include a hybrid breaker, e.g., two breakers in series in a single breaker position, and (2) the design from retiring the entire Porter 230 kV substation to partial retiring the Porter 230kV substation, e.g., keeping Edic 345/230K transformer, Edic-Porter 230kV circuit (Line#17), and two Porter 230/115kV transformers | 2022-11-28 | 2023-03-02
1136 | Honey Ridge Solar | Honey Ridge Solar 1, LLC | N/A | Change Capacitive Resource Interconnection Service (CRIS) request of the Co-located Storage Resource project from 30 MW energy storage Generator and 95 MW solar Generator to 60 MW energy storage Generator and 65 MW solar Generator without changing the Project’s total CRIS request. | 2023-02-02 | 2023-03-02
1137 | Salt Rush Wind | Invenergy Wind Development North America LLC | N/A | Increase the nameplate to 81MW to achieve the requested 75MW ERIS | 2023-08-08 | 2023-10-02
1138 | Wintergreen Solar | Invenergy Solar Project Development LLC | N/A | Increase the nameplate to 79.8MW to achieve the requested 75MW ERIS and the addition of a 13MVAR shunt capacitor to meet powerfactor requirement | 2023-08-08 | 2023-10-02
1142 | Minerva BESS I | Minerva Power Connection LLC | N/A | Change the MW size of the project from 600 MW to 300 MW | 2021-10-07 | 2022-01-04
1177 | Souther Tier Energy Center | Southern Tier Energy Center, LLC | N/A | Changing from Solar to 4hr Standalone battery storage | 2023-09-29 | 2023-11-02
1180 | BPUS Generation Development LLC | BPUS Generation Development LLC | N/A | Operate the power factor (PF) of the facility within +/- 0.95 while its PF capability is a leading 0.95 PF to a lagging 0.83 PF | 2022-08-29 | 2022-12-02
1180 | Union Energy Center | Union Energy Center, LLC | N/A | Reduce the project size from 150 MW to 116 MW. | 2023-03-21 | 2023-05-05
1188 | North Seneca Solar Project | North Seneca Solar Project, LLC | N/A | Change the generator step-up transformer from a 2-winding transformer to a 3-winding transformer | 11/1022 | 2023-01-19
1190 | OW Ocean Winds East 4 | Bluepoint Wind, LLC. | N/A | Change in POI from Farragut 345kV substation to the Brooklyn Clean Energy Hub 345kV substation | 2023-09-18 | 2023-11-02
1197 | Cold Creek Solar | Northland Power U.S. Projects | N/A | Move the Point of Interconnection of the project to a different point along the same transmission line, Station 162- Station 180 115kV line (Line#907) | 2023-03-12 | 2023-05-05
1199 | El Steinway 1.1 | Beacon Wind LLC | N/A | Reduce the project size from 300 MW to 200 MWand move the Point of Interconnection of the project from Astoria West 138kV substation to a new 345kV substation that is interconnected via a loop-in/loop-out of the two existing Mott Haven-Rainey 345kV circuits | 2023-03-17 | 2023-05-05
1203 | Suffragette Solar | EDF Renewables Development, Inc. | N/A | Change the transformer model | 2022-12-15 | 2023-02-02
1206 | NY Interconnection 2 | NY Interconnection LLC | N/A | Change the project type from a Class Year Transmission project to a Large Generating Facility project. | 2022-09-13 | 2022-10-03
1207 | NY Interconnection 1 | NY Interconnection LLC | N/A | Change the project type from a Class Year Transmission project to a Large Generating Facility project. | 2022-09-13 | 2022-10-03
1223 | Moffitt ESC | Fresh Air Energy II | N/A | Change the generator step-up transformer from a 2-winding transformer to a 3-winding transformer with wye grounded high side | 2022-12-15 | 2023-02-02
1223 | Moffitt ESC | Fresh Air Energy II | N/A | Increasing nameplate rating from 100MW to 103.9MW and from 100MVA to 140.4MVA to account for losses and meet powerfactor criteria | 2023-07-14 | 2023-08-01
1230 | Erie-Wyoming County Solar II | ConnectGen Erie-Wyoming LLC | N/A | Change from Solar to CSR Solar plus storage ERIS/CRIS Solar 50MW BESS 0MW | 2023-08-02 | 2023-10-02
1231 | Mill Point Solar II | ConnectGen Montgomery County LLC | N/A | 100MW Solar facility changing fuel source from Solar to CSR (ES+Solar) 100MW solar with 0MW storage. This is an uprate project to 1031 which is CSR. | 2023-05-30 | 2023-07-17
1255 | Holtsville Brookhaven Battery Storage | Holtsville Brookhaven Battery Storage LLC | N/A | Reduce the project from 80 MW to 79.9 MW | 2023-01-27 | 2023-03-02
1265 | Monticello Hills Wind | Liberty Renewables Inc. | N/A | Addition of 1 turbine to increase the nameplate rating, and increase the PSU size from 20/27/30MVA to 22/29/36MVA | 2023-08-03 | 2023-11-02
1292 | Hemlock Hollow Wind | Liberty Renewables Inc. | N/A | Decrease ERIS and CRIS from 90MW to 87.9MW to account for losses | 2023-09-13 | 2023-10-02
1307 | Riverhead Energy, LLC | Riverhead Energy | N/A | Change inverter from Power Electronics FP3350k to FP4200M inverter | 2023-09-26 | 2023-11-02
1352 | Buchanan Energy Storage - North | Peekskill BESS LLC | N/A | Increase maximum withdrawal from the system from 500MW to 505MW | 2023-11-07 | 2023-11-16
1353 | Eastview Energy Storage Project | Central Westchester Power LLC | N/A | Increase maximum withdrawal from the system from 400MW to 404MW | 2023-11-07 | 2023-11-16
1360 | Buchanan Energy Storage-South | Peekskill BESS LLC | N/A | Increase maximum withdrawal from the system from 500MW to 505MW | 2023-11-07 | 2023-11-16
1374 | Community OSW East Garden City 1 | Community Offshore Wind, LLC | N/A | Change in turbine from Vestas V236-15M to GE Haliade- X 17MW | 2023-03-22 | 2023-09-06
1493 | Queensboro Renewable Express Circuit A | Queensboro Development, LLC | N/A | Designate the 2 feeders to Vernon 138kV, a 345kV PAR, and 138kV transformer as an elective SUF | 2023-10-13 | 2023-11-02
1502 | Oswego Solar | Oswego Clean Energy LLC | N/A | Change from (9) 3.15MVA Sungrow SG3150UD-MV inverters to (8) 3.425MVA Sungrow SG3425UD-MV inverters | 2023-11-02 | 2023-11-16