## Interconnection Queue
Queue Pos. | Owner/Developer | Project Name | Date of IR | SP (MW) | WP (MW) | Type/ Fuel | County | State | Z | Interconnection Point | Utility | S | Last Update | Availability of Studies | FS Complete/ SGIA Tender | Proposed In-Service | Proposed Initial-Sync | Proposed COD
0276 | EDF Renewables Development, Inc. | Homer Solar Energy Center | 2008-01-30 | 90 | 90 | S | Cortland | NY | C | Cortland - Fenner 115kV | NM-NG | 10 | 2021-02-28 | FES, SRIS, FS | 2021-02-09 | 08/2023 | 09/2023 | 09/2023
0386 | Vermont Green Line Devco, LLC | Grand Isle Intertie | 2012-06-28 | 400 | 400 | DC | Clinton | NY | D | Plattsburgh 230kV-New Haven, VT 345kV | NYPA | 6 | 2018-11-30 | FES, SIS |  | 12/2023 | N/A | N/A
0387 | Cassadaga Wind, LLC | Cassadaga Wind | 2012-07-19 | 126.5 | 126.5 | W | Chautauqua | NY | A | Dunkirk - Moon Station 115 kV | NM-NG | 14 | 2021-06-30 | FES, SRIS, FS | 2019-07-09 | I/S | I/S | I/S
0393 | NRG Berrians East Development, LLC | Berrians East Replacement | 2012-10-16 | 94.2 | 57 | D | Queens | NY | J | Astoria East 138kV | ConEd | 11 | 2021-11-30 | FES, SRIS, FS | 2019-07-09 | 05/2022 | 08/2023 | 12/2023
0396 | Baron Winds, LLC | Baron Winds | 2012-11-30 | 238.4 | 238.4 | W | Steuben | NY | C | Hillside - Meyer 230kV | NYSEG | 11 | 2021-11-30 | FES, SRIS, FS | 2019-07-09 | 05/2022 | 06/2022 | 12/2023
0396A | New York State Electric & Gas | Wood Street Transformer | 2012-12-14 | N/A | N/A | AC | Putnam | NY | G | Wood St. 345/115kV | NYSEG | 12 | 2021-04-30 | SIS | N/A | 12/2022 | N/A | N/A
0422 | NextEra Energy Resources, LLC | Eight Point Wind Energy Center | 2013-11-07 | 101.8 | 101.8 | W | Steuben-Allegany | NY | C | Bennett 115kV | NYSEG | 11 | 2021-03-31 | FES, SRIS, FS | 2019-07-09 | 09/2022 | 09/2022 | 09/2022
0429 | Orange & Rockland | North Rockland Station | 2014-02-12 | N/A | N/A | AC | Steuben | NY | G | Line Y88 345kV | ConEd | 6 | 2021-12-31 | SIS | N/A | 06/2023 | N/A | N/A
0430 | H.Q. Energy Services U.S. Inc. | Cedar Rapids Transmission | 2014-03-05 | N/A | N/A | AC | St. Lawrence | NY | D | Dennison - Alcoa 115kV | NM-NG | 12 | 2020-04-30 | SIS, FS | 2018-10-02 | 10/2021 | N/A | N/A
0487 | LI Energy Storage System, LLC | Far Rockaway Battery Storage | 2015-03-09 | 20 | 20 | ES | Nassau | NY | K | Far Rockaway 69kV | LIPA | 10 | 2022-01-31 | FES, SRIS, FS | 2020-11-05 | 10/2024 | 10/2024 | 11/2024
0495 | Mohawk Solar LLC | Mohawk Solar | 2015-04-02 | 90.5 | 90.5 | S | Montgomery | NY | F | St. Johnsville - Marshville 115kV | NM-NG | 11 | 2022-01-31 | FES, SRIS, FS | 2021-02-09 | 09/2024 | 09/2024 | 11/2024
0497 | Invenergy Wind Development LLC | Bull Run Wind | 2015-04-24 | 303.6 | 303.6 | W | Clinton | NY | D | Patnode 230kV | NYPA | 7 | 2018-09-30 | FES, SRIS |  |  |  | 12/2022
0505 | Ball Hill Wind Energy, LLC | Ball Hill Wind | 2015-06-02 | 100 | 100 | W | Chautauqua | NY | A | Dunkirk - Gardenville 230kV | NM-NG | 12 | 2021-10-31 | FES, SRIS, FS | 2019-07-09 | 10/2022 | 10/2022 | 11/2022
0506 | Empire State Connector Corp. | Empire State Connector | 2015-06-10 | 1000 | 1000 | DC | Onondaga-New York | NY | E, J | Marcy - Gowanus 345kV | NYPA/ConEd | 7 | 2019-08-31 | FES, SRIS |  | 10/2025 | 01/2026 | 03/2026
0513 | Orangeville Energy Storage LLC | Orangeville | 2015-09-21 | 20 | 20 | ES | Wyoming | NY | C | Stony Creek 230kV | NYSEG | 13 | 2022-01-31 | SIS, FS | 2018-01-29 | 2/2022 | 2/2022 | 2/2022
0519 | Canisteo Wind Energy LLC | Canisteo Wind | 2015-11-02 | 290.7 | 290.7 | W | Steuben | NY | C | Bennett 115kV | NYSEG | 10 | 2021-02-28 | FES, SRIS, FS | 2021-02-09 | 09/2022 | 12/2022 | 12/2022
0520 | EDP Renewables North America | Rolling Upland Wind | 2015-12-03 | 72.6 | 72.6 | W | Madison | NY | E | County Line - Brothertown 115kV | NYSEG | 7 | 2020-06-30 | FES, SRIS |  | 09/2023 | 09/2023 | 11/2023
0521 | Invenergy NY, LLC | Bull Run II Wind | 2015-12-15 | 145.4 | 145.4 | W | Clinton | NY | D | Patnode-Duley, Ryan-Platts 230kV | NYPA | 9 | 2021-06-30 | FES, SRIS |  | 12/2021 |  | 12/2022
0522 | NYC Energy LLC | NYC Energy | 2015-12-16 | 79.9 | 79.9 | ES | Kings | NY | J | Hudson Avenue East 138kV | ConEd | 9 | 2021-06-30 | FES, SRIS |  | 12/2023 | 12/2023 | 12/2023
0526 | Atlantic Wind, LLC | North Ridge Wind | 2015-12-23 | 100 | 100 | W | St. Lawrence | NY | D | Malone - Colton 115kV | NM-NG | 7 | 2021-02-28 | FES, SRIS |  | 09/2025 | 11/2025 | 12/2025
0531 | Number Three Wind LLC | Number 3 Wind Energy | 2016-01-11 | 103.9 | 103.9 | W | Lewis | NY | E | Taylorville - Boonville 115kV | NM-NG | 11 | 2021-05-31 | FES, SRIS, FS | 2021-02-09 | 05/2022 | 08/2022 | 10/2022
0535 | Riverhead Solar 2 LLC | Riverhead Expansion | 2016-02-23 | 36 | 36 | S | Suffolk | NY | K | Edwards 138kV | LIPA | 10 | 2022-01-31 | FES, SRIS, FS | 2021-02-09 | 10/2022 | 12/2022 | 12/2022
0540 | AVANGRID | Connect NY Edic - PV | 2016-04-28 | 1000 | 1000 | DC | Oneida-Dutchess | NY | E, G | Edic - PV 345kV | NM-NG/ ConEd | 6 | 2020-05-31 | SIS |  | 12/2020 | N/A | N/A
0541 | AVANGRID | Connect NY Edic - Ramapo | 2016-04-28 | 1000 | 1000 | DC | Oneida-Dutchess | NY | E, G | Edic - Ramapo 345kV | NM-NG/ ConEd | 6 | 2020-05-31 | SIS |  | 12/2020 | N/A | N/A
0543 | National Grid | Segment B Knickerbocker-PV | 2016-05-04 | N/A | N/A | AC | Albany-Dutchess | NY | F, G | Greenbush - PV 345kV | NM-NG/NYSEG/ CHGE/ConEd | 9 | 2021-12-31 | SIS | N/A | 12/2023 | N/A | N/A
0545 | Sky High Solar LLC | Sky High Solar | 2016-05-10 | 20 | 20 | S | Onondaga | NY | C | Tilden -Tully Center 115kV | NM-NG | 11 | 2022-01-31 | FES, SIS, FS | 2019-10-01 | 06/2023 | 06/2023 | 06/2023
0545A | NextEra Energy Transmission New York, Inc. | Empire State Line Alt | 2016-05-17 | N/A | N/A | AC | Niagara-Erie | NY | A | Dysinger - Stolle 345kV | NYPA/NYSEG | 12 | 2021-03-31 | SIS, FS | N/A | 06/2022 | N/A | N/A
0546 | PPM Roaring Brook, LLC | Roaring Brook Wind | 2016-05-19 | 78 | 78 | W | Lewis | NY | E | Chases Lake 230kV | NM-NG | 13 | 2022-01-31 | FES, SRIS, FS | 2021-02-09 | 04/2022 | 04/2022 | 04/2022
0556 | LS Power Grid New York, LLC | Segment A Double Circuit | 2016-07-06 | N/A | N/A | AC | Oneida-Albany | NY | E, F | Edic - New Scotland 345kV | NM-NG | 11 | 2021-12-31 | SIS, FS | N/A | 06/2022 | N/A | N/A
0560 | Atlantic Wind, LLC | Deer River Wind | 2016-07-08 | 100 | 100 | W | Lewis | NY | E | Lighthouse Hill - Black River 115kV | NM-NG | 8 | 2021-10-31 | FES, SRIS |  | 09/2025 | 10/2025 | 12/2025
0564 | Rock District Solar, LLC | Rock District Solar | 2016-07-25 | 20 | 20 | S | Schoharie | NY | F | Sharon - Cobleskill 69kV | NM-NG | 11 | 2021-08-31 | SIS, FS | 2020-07-10 | 10/2022 | 11/2022 | 12/2022
0565 | Tayandenega Solar, LLC | Tayandenega Solar | 2016-07-25 | 20 | 20 | S | Montgomery | NY | F | St. Johnsville - Inghams 115kV | NM-NG | 11 | 2021-08-31 | SIS, FS | 2020-07-01 | 08/2022 | 09/2022 | 10/2022
0566 | New York Power Authority | MA 1 & 2 Rebuild | 2016-08-04 | N/A | N/A | AC | St. Lawrence-Lewis | NY | D, E | Moses - Adirondack 230kV | NYPA | 12 | 2021-04-30 | SIS | N/A | 12/2022 | N/A | N/A
0570 | Hecate Energy Albany 1 LLC | Albany County 1 | 2016-08-17 | 20 | 20 | S | Albany | NY | F | Long Lane - Lafarge 115kV | NM-NG | 11 | 2022-01-31 | SIS, FS | 2020-03-04 | 11/2022 | 11/2022 | 12/2022
0571 | Heritage Renewables, LLC | Heritage Wind | 2016-09-01 | 200.1 | 200.1 | W | Genesee | NY | B | Lockport - Mortimer 115kV | NM-NG | 9 | 2021-08-31 | FES, SRIS |  | 06/2023 | 07/2023 | 10/2023
0572 | Hecate Energy Greene 1 LLC | Greene County 1 | 2016-09-06 | 20 | 20 | S | Greene | NY | G | Coxsackie - North Catskill 69kV | CHGE | 11 | 2022-01-31 | SIS, FS | 2020-02-18 | 03/2023 | 02/2023 | 01/2023
0573 | Hecate Energy Greene 2 LLC | Greene County 2 | 2016-09-06 | 10 | 10 | S | Greene | NY | G | Coxsackie 13.8kV | CHGE | 11 | 2022-01-31 | SIS, FS | 2020-02-18 | 02/2023 | 01/2023 | 03/2023
0574 | Atlantic Wind, LLC | Mad River Wind | 2016-09-16 | 450 | 450 | W | Jefferson-Oswego | NY | E | Volney - Marcy 345kV | NM-NG | 7 | 2021-02-28 | FES, SRIS |  | 09/2025 | 10/2025 | 12/2025
0575 | Little Pond Solar, LLC | Little Pond Solar | 2016-09-16 | 20 | 20 | S | Orange | NY | G | Mongaup - Shoemaker 69kV | O&R | 10 | 2022-01-31 | FES, SIS, FS | 2021-01-29 | 07/2023 | 06/2023 | 07/2023
0577 | Greene County Energy Properties, LLC | Greene County Energy | 2016-09-20 | 20 | 20 | S | Greene | NY | G | New Baltimore - Coxsackie 69 kV | CHGE | 9 | 2020-07-31 | SIS |  | 07/2021 | 10/2021 | 01/2022
0579 | Bluestone Wind, LLC | Bluestone Wind | 2016-09-21 | 111.8 | 111.8 | W | Broome | NY | E | Afton - Stilesville 115kV | NYSEG | 11 | 2021-12-31 | FES, SRIS, FS | 2021-02-09 | 06/2022 | 08/2022 | 10/2022
0580 | Genesee County Economic Devel. | WNY STAMP | 2016-09-27 | 300 | 300 | L | Genesee | NY | B | Kintigh/Niagara - Rochester 345kV | NYPA | 9 | 2021-12-31 | SIS |  | 06/2022 | N/A | NA
0581 | SunEast Hills Solar LLC | Hills Solar | 2016-10-06 | 20 | 20 | S | Herkimer | NY | E | Fairfield - Inghams 115kV | NM-NG | 11 | 2021-11-30 | FES, SIS, FS | 2020-04-07 | 07/2023 | 07/2023 | 08/2023
0584 | SunEast Dog Corners Solar LLC | Dog Corners Solar | 2016-11-02 | 20 | 20 | S | Cayuga | NY | C | Aurora 34.5kV | NYSEG | 11 | 2021-03-31 | SIS, FS | 2018-09-24 | 02/2022 | 02/2022 | 05/2022
0586 | SunEast Watkins Road Solar LLC | Watkins Rd Solar | 2016-11-08 | 20 | 20 | S | Herkimer | NY | E | Watkins Rd - Ilion 115kV | NM-NG | 11 | 2022-01-31 | SIS, FS | 2020-02-18 | 01/2023 | 01/2023 | 06/2023
0589 | Duke Energy Renewables Solar, LLC | North Country Solar | 2016-12-02 | 15 | 15 | S | Lewis | NY | E | Boonville 46kV | NM-NG | 11 | 2022-01-31 | FES, SIS, FS | 2020-03-16 | 10/2023 | 09/2023 | 10/2023
0590 | Duke Energy Renewables Solar, LLC | Scipio Solar | 2016-12-02 | 18 | 18 | S | Cayuga | NY | C | Scipio 34.5kV | NYSEG | 11 | 2021-10-31 | SIS, FS | 2019-05-22 | 05/2023 | 05/2023 | 05/2023
0591 | SunEast Highview Solar LLC | Highview Solar | 2016-12-02 | 20 | 20 | S | Wyoming | NY | C | South Perry 34.5kV | NYSEG | 10 | 2022-01-31 | SIS, FS | 2021-02-09 | 11/2023 | 09/2023 | 12/2023
0592 | Duke Energy Renewables Solar, LLC | Niagara Solar | 2016-12-02 | 20 | 20 | S | Wyoming | NY | B | Bennington 34.5kV | NYSEG | 11 | 2021-10-31 | SIS, FS | 2019-05-22 | 05/2023 | 05/2023 | 05/2023
0594 | North Park Energy, LLC | NW Energy | 2016-12-29 | 60 | 60 | ES | Wyoming | NY | C | Wethersfield 230kV | NYSEG | 8 | 2021-10-31 | SRIS |  | 10/2023 | 11/2023 | 12/2023
0596 | Invenergy Wind Development LLC | Alle Catt II Wind | 2017-01-04 | 339.1 | 339.1 | W | Cattaraugus | NY | A | Stolle Rd - Five Mile Rd 345kV | NM-NG | 10 | 2021-02-28 | SRIS, FS | 2021-02-09 | 02/2023 | 05/2023 | 05/2023
0597 | Hecate Energy Greene County 3 LLC | Greene County 3 | 2017-01-10 | 20 | 20 | S | Greene | NY | G | North Catskill - Coxsackie 69kV | CHGE | 9 | 2021-11-30 | SIS |  | 02/2023 | 03/2022 | 04/2023
0598 | Hecate Energy Albany 2 LLC | Albany County 2 | 2017-01-10 | 20 | 20 | S | Albany | NY | F | Long Lane - Lafarge 115kV | NM-NG | 11 | 2022-01-31 | SIS, FS | 2020-03-04 | 11/2022 | 10/2022 | 12/2022
0612 | South Fork Wind, LLC | South Fork Wind Farm | 2017-02-14 | 96 | 96 | W | Suffolk | NY | K | East Hampton 69kV | LIPA | 10 | 2022-01-31 | SRIS, FS | 2021-02-09 | 01/2022 | 08/2022 | 12/2022
0617 | Watkins Glen Energy Center, LLC | Watkins Glen Solar | 2017-03-27 | 50 | 50 | S | Schuyler | NY | C | Bath - Montour Falls 115kV | NYSEG | 10 | 2022-01-31 | SRIS, FS | 2021-02-09 | 09/2023 | 10/2023 | 11/2023
0618 | High River Energy Center, LLC | High River Solar | 2017-03-27 | 90 | 90 | S | Schenectady | NY | F | Inghams - Rotterdam 115kV | NM-NG | 10 | 2021-04-30 | SRIS, FS | 2021-02-09 | 02/2022 | 03/2022 | 11/2022
0619 | East Point Energy Center, LLC | East Point Solar | 2017-03-27 | 50 | 50 | S | Schoharie | NY | F | Cobleskill - Marshville 69kV | NM-NG | 10 | 2021-04-30 | SRIS, FS | 2021-02-09 | 10/2022 | 10/2022 | 11/2022
0620 | North Side Energy Center, LLC | North Side Solar | 2017-03-27 | 180 | 180 | S | St. Lawrence | NY | D | Massena - Moses 230kV | NYPA | 10 | 2021-04-30 | FES, SRIS, FS | 2021-02-09 | 10/2023 | 10/2023 | 11/2023
0624 | Franklin Solar, LLC | Franklin Solar | 2017-04-11 | 150 | 150 | S | Franklin | NY | D | Malone 115kV | NM-NG | 7 | 2021-02-28 | SRIS |  | 09/2023 | 10/2023 | 12/2023
0629 | Silver Lake Solar, LLC | Silver Lake Solar | 2017-04-27 | 24.9 | 24.9 | S | Wyoming | NY | C | South Perry 34.5kV | NYSEG | 9 | 2020-12-31 | FES, SRIS |  | 10/2022 | 12/2022 | 12/2022
0631 | CHPE LLC | NS Power Express | 2017-05-02 | 1000 | 1000 | DC | Quebec - NY | NY | J | Astoria Annex 345kV | NYPA | 9 | 2021-09-30 | SRIS |  | 10/2026 | 10/2026 | 12/2026
0632 | GridAmerica Holdings Inc. | Alps - Berkshire | 2017-05-04 | N/A | N/A | AC | Rensselaer | NY | F | Alps - Berkshire 345kV | NM-NG | 6 | 2019-02-28 | SIS |  | 09/2021 | N/A | N/A
0637 | Flint Mine Solar LLC | Flint Mine Solar | 2017-06-29 | 100 | 100 | S | Greene | NY | G | LaFarge - Pleasant Valley 115kV, Feura Bush - North Catskill 115kV | NM-NG | 10 | 2022-01-31 | FES, SRIS, FS | 2021-02-09 | 10/2022 | 11/2022 | 09/2023
0638 | Pattersonville Solar Facility, LLC | Pattersonville | 2017-07-11 | 20 | 20 | S | Montgomery | NY | F | Rotterdam - Meco 115kV | NM-NG | 11 | 2022-01-31 | FES, SIS, FS | 2020-02-18 | 04/2022 | 03/2022 | 12/2022
0644 | Hecate Energy Columbia County 1, LLC | Columbia County 1 | 2017-07-26 | 60 | 60 | S | Columbia | NY | F | Craryville 115kV | NYSEG | 10 | 2021-02-28 | FES, SRIS, FS | 2021-02-09 | 10/2023 | 12/2023 | 12/2023
0654 | Renovo Energy Center LLC | Renovo Energy Center | 2017-08-11 | N/A | N/A | AC | Clinton | PA | C | Homer City - Mainsburg 345kV | NYSEG | 10 | 2022-01-31 | SIS, FS | N/A | 12/2024 | N/A | N/A
0666 | Martin Rd Solar LLC | Martin Rd Solar | 2017-09-14 | 20 | 20 | S | Machias | NY | A | Arcade - Five Mile 115kV | NM-NG | 11 | 2020-11-30 | SIS, FS | 2020-03-24 | 09/2022 | 10/2022 | 10/2022
0667 | Bakerstand Solar LLC | Bakerstand Solar | 2017-09-14 | 20 | 20 | S | Cattaraugus | NY | A | Machias - Maplehurst 34.5kV | NM-NG | 11 | 2020-11-30 | SIS, FS | 2020-03-04 | 09/2022 | 09/2022 | 10/2022
0668 | North Bergen Liberty Generating, LLC | Liberty Generating Alternative | 2017-09-15 | 1171 | 1172 | CC | New York | NY | J | West 49th St 345kV | ConEd | 8 | 2021-05-31 | SRIS |  | 04/2023 | 04/2023 | 02/2024
0670 | SunEast Skyline Solar LLC | Skyline Solar | 2017-09-21 | 20 | 20 | S | Westmoreland | NY | E | Campus Rd - Clinton 46kV | NM-NG | 11 | 2022-01-31 | FES, SIS, FS | 2020-08-13 | 03/2022 | 03/2022 | 04/2022
0678 | LI Solar Generation, LLC | Calverton Solar Energy Center | 2017-10-26 | 22.9 | 22.9 | S | Suffolk | NY | K | Edwards Substation 138kV | LIPA | 10 | 2022-01-31 | SRIS, FS | 2021-02-09 | 04/2022 | 04/2022 | 06/2022
0679 | Anbaric Development Partners, LLC | New York City Offshore Wind | 2017-11-07 | 1200 | 1200 | W | Kings | NY | J | Gowanus 345kV | ConEd | 6 | 2021-05-31 | FES, SRIS |  | 07/2026 | 11/2026 | 12/2026
0680 | Anbaric Development Partners, LLC | Long Island Offshore Wind | 2017-11-07 | 1200 | 1200 | W | Suffolk | NY | K | Ruland Rd. 138kV | LIPA | 6 | 2021-06-30 | FES, SRIS |  | 07/2025 | 11/2025 | 12/2025
0682 | Grissom Solar, LLC | Grissom Solar | 2019-10-18 | 20 | 20 | S | Montgomery | NY | F | Ephratah - Florida 115kV | NM-NG | 11 | 2022-01-31 | FES, SIS, FS | 2020-08-05 | 05/2022 | 04/2022 | 06/2022
0683 | KCE NY 2, LLC | KCE NY 2 | 2018-01-18 | 200 | 200 | ES | Montgomery | NY | G | Coldenham 115kV | CHGE | 10 | 2021-02-28 | SRIS, FS | 2021-02-09 | 11/2022 | 12/2022 | 12/2022
0684 | ITC Lake Erie Connector, LLC | Lake Erie Connector | 2018-01-18 | N/A | N/A | AC | Chautauqua | NY | A | S. Ripley 230kV | NM-NG | 10 | 2019-09-30 | SIS, FS | 2019-04-22 | 03/2024 | N/A | N/A
0686 | Invenergy Solar Development North America LLC | Bull Run Solar Energy Center | 2018-01-26 | 170 | 170 | S | Clinton | NY | D | Patnode - Duley 230kV | NYPA | 7 | 2021-02-28 | SRIS |  | 10/2024 | 10/2024 | 12/2024
0693 | Renovo Energy Center, LLC | Renovo Energy Center Uprate | 2018-02-13 | 515 | 548 | CC | Clinton | PA | C | Homer City - Mainesburg 345kV | NYSEG | 7 | 2021-08-31 | SRIS |  | 12/2024 | 12/2024 | 06/2025
0694 | Sunset Hill Solar, LLC | Sunset Hill Solar | 2018-02-16 | 20 | 20 | S | Albany | NY | G | New Baltimore - Westerlo NW 69 kV | CHGE | 9 | 2021-06-30 | FES, SIS |  | 11/2022 | 11/2022 | 11/2022
0695 | South Fork Wind, LLC | South Fork Wind Farm II | 2018-02-16 | 42 | 42 | W | Suffolk | NY | K | East Hampton 69kV | LIPA | 10 | 2022-01-31 | SRIS, FS | 2021-02-09 | 01/2022 | 08/2022 | 12/2022
0697 | Helix Ravenswood, LLC | Ravenswood Energy Storage 1 | 2018-03-09 | 129 | 129 | ES | Queens | NY | J | Rainey - Farragut 345kV | ConEd | 8 | 2021-05-31 | SRIS |  | 03/2022 | 12/2021 | 05/2022
0698 | Helix Ravenswood, LLC | Ravenswood Energy Storage 2 | 2018-03-09 | 129 | 129 | ES | Queens | NY | J | Rainey - Farragut 345kV | ConEd | 8 | 2021-08-31 | SRIS |  | 03/2022 | 12/2021 | 05/2022
0700 | Able Grid Energy Solutions, LLC | Robinson Grid | 2018-03-13 | 300 | 300 | ES | Kings | NY | J | Gowanus 345kV | ConEd | 9 | 2021-06-30 | FES, SRIS |  | 05/2025 | 06/2025 | 07/2025
0704 | Bear Ridge Solar, LLC | Bear Ridge Solar | 2018-03-20 | 100 | 100 | S | Niagara | NY | A | Mountain- Lockport 115kV | NM-NG | 10 | 2021-02-28 | SRIS, FS | 2021-02-09 | 09/2022 | 10/2022 | 12/2022
0706 | High Bridge Wind, LLC | High Bridge Wind | 2018-04-25 | 100.8 | 100.8 | W | Chenango | NY | E | E. Norwich - Jennison 115kV | NYSEG | 10 | 2021-02-28 | SRIS, FS | 2021-02-09 | 07/2022 | 10/2022 | 12/2022
0709 | Alder Creek Solar, LLC | Alder Creek Solar | 2018-05-18 | 165 | 165 | S | Oneida | NY | E | Chases Lake - Porter 230kV | NM-NG | 9 | 2021-06-30 | FES, SRIS |  | 04/2023 | 04/2023 | 12/2023
0710 | Invenergy Solar Development North America LLC | Horseshoe Solar | 2018-05-29 | 180 | 180 | S | Livingston | NY | B | Golah 115kV | NM-NG | 9 | 2021-11-30 | FES, SRIS |  | 05/2023 | 05/2023 | 10/2023
0716 | EDF Renewables Development, Inc. | Moraine Solar Energy Center | 2018-06-04 | 87.4 | 93.5 | S | Allegany | NY | C | Moraine 115kV | NYSEG | 9 | 2021-08-31 | FES, SRIS |  | 06/2023 | 07/2023 | 10/2023
0717 | EDF Renewables Development, Inc. | Morris Ridge Solar Energy Center | 2018-06-04 | 177 | 177 | S | Steuben | NY | C | South Perry - Meyer 230kV | NYSEG | 9 | 2021-06-30 | FES, SRIS |  | 08/2023 | 08/2023 | 10/2023
0718 | Cortland Energy Center, LLC | Cortland Energy Center | 2018-06-07 | 50 | 50 | S | Cortland | NY | C | Cortland - SUNY 115 kV | NM-NG | 8 | 2021-02-28 | SRIS |  | 08/2022 | 09/2022 | 11/2022
0719 | East Light Energy Center, LLC | East Light Energy Center | 2018-06-07 | 40 | 40 | S | Montgomery | NY | F | Meco - Rotterdam 115 kV | NM-NG | 8 | 2019-10-31 | SRIS |  | 08/2022 | 09/2022 | 11/2022
0720 | Trelina Solar Energy Center, LLC | Trelina Solar Energy Center | 2018-06-07 | 80 | 80 | S | Seneca | NY | C | Border City - Station 168 115 KV | NYSEG | 10 | 2022-01-31 | SRIS, FS | 2021-02-09 | 08/2023 | 08/2023 | 11/2023
0721 | Excelsior Energy Center, LLC | Excelsior Energy Center | 2018-06-07 | 280 | 280 | S | Genesee | NY | B | N. Rochester - Niagara 345 kV | NYPA | 10 | 2021-08-31 | SRIS, FS | 2021-02-09 | 06/2022 | 08/2022 | 11/2022
0730 | Darby Solar, LLC | Darby Solar | 2018-06-11 | 20 | 20 | S | Washington | NY | F | Mohican - Schaghticoke 115kV | NM-NG | 11 | 2022-01-31 | FES, SIS, FS | 2020-04-29 | 03/2022 | 02/2022 | 12/2022
0731 | Branscomb Solar, LLC | Branscomb Solar | 2018-06-11 | 20 | 20 | S | Washington | NY | F | Battenkill - Eastover 115kV | NM-NG | 14 | 2021-12-31 | FES, SIS, FS | 2020-04-29 | I/S | I/S | I/S
0734 | ELP Ticonderoga Solar LLC | Ticonderoga Solar | 2018-06-12 | 20 | 20 | S | Essex | NY | F | Ticonderoga - Republic 115kV | NM-NG | 10 | 2021-08-31 | FES, SIS, FS | 2021-03-18 | 07/2022 | 08/2022 | 08/2022
0735 | ELP Stillwater Solar LLC | ELP Stillwater Solar | 2018-06-12 | 20 | 20 | S | Saratoga | NY | F | Luther Forest - Mohican 115kV | NM-NG | 11 | 2022-01-31 | FES, SIS, FS | 2020-04-29 | 10/2021 | 10/2021 | 09/2022
0737 | Empire Offshore Wind LLC | EI Sunset Park | 2018-06-12 | 816 | 816 | W | Kings | NY | J | Gowanus 345kV | ConEd | 10 | 2022-01-31 | SRIS, FS | 2021-06-14 | 06/2025 | 11/2025 | 12/2026
0738 | Empire Offshore Wind LLC | EI Melville | 2018-06-12 | 816 | 816 | W | Suffolk | NY | K | Ruland Rd. 138kV | LIPA | 8 | 2021-05-31 | SRIS |  | 06/2023 | 02/2024 | 12/2024
0740 | Oakdale Battery Storage LLC | Oakdale Battery Storage | 2018-06-18 | 120 | 120 | ES | Broome | NY | C | Oakdale 115kV | NYSEG | 9 | 2021-06-30 | SRIS |  | 03/2023 | 03/2023 | 06/2023
0744 | Granada Solar, LLC | Magruder BESS | 2018-07-18 | 20 | 20 | ES | Ulster | NY | G | East Walden - Modena 115kV | CHGE | 10 | 2021-04-30 | SIS,FS | 2021-04-06 | 10/2022 | 11/2022 | 12/2022
0745 | Energy Storage Resources, LLC | Huckleberry Ridge Energy | 2018-07-25 | 100 | 100 | ES | Orange | NY | G | Shoemaker-Westtown 69kV | O&R | 7 | 2020-04-30 | SRIS |  | 03/2022 | 03/2022 | 04/2022
0746 | Peconic River Energy Storage, LLC | Peconic River Energy Storage | 2018-07-30 | 150 | 150 | ES | Suffolk | NY | K | Brookhaven - Sills 138kV | LIPA | 10 | 2022-01-31 | SRIS, FS | 2021-04-26 | 03/2022 | 03/2022 | 06/2022
0748 | Regan Solar, LLC | Regan Solar | 2018-08-09 | 20 | 20 | S | Montgomery | NY | F | Market Hill - Johnstown 69kV | NM-NG | 11 | 2022-01-31 | FES, SIS, FS | 2020-08-05 | 05/2022 | 04/2022 | 06/2022
0758 | Sithe/Independence Power Partners, LP | Sithe Independence | 2018-09-06 | 9 | 27 | CC | Oswego | NY | C | Sithe 345kV | NM-NG | 9 | 2020-04-30 | SRIS |  | I/S | I/S | I/S
0759 | KCE NY 6, LLC | KCE NY 6 | 2018-09-06 | 20 | 20 | ES | Erie | NY | A | Gardenville - Bethlehem Steel Wind 115kV | NM-NG | 10 | 2022-01-31 | SIS, FS | 2020-10-15 | 04/2022 | 04/2022 | 04/2022
0766 | Sunrise Wind LLC | NY Wind Holbrook | 2018-09-28 | 880 | 880 | W | Suffolk | NY | K | Holbrook 138kV | LIPA | 9 | 2021-06-30 | SRIS |  | 03/2024 | 04/2024 | 05/2024
0768 | Janis Solar, LLC | Janis Solar | 2018-10-01 | 20 | 20 | S | Cortland | NY | C | Willet 34.5kV | NYSEG | 11 | 2021-10-31 | SIS, FS | 2020-03-04 | 12/2021 | 02/2022 | 04/2022
0769 | New York Power Authority | North County Energy Storage | 2018-10-05 | 20 | 20 | ES | Franklin | NY | D | Willis 115kV | NYPA | 11 | 2021-11-30 | SIS | 2021-01-07 | 03/2022 | 03/2022 | 03/2022
0770 | KCE NY8 LLC | KCE NY 8a | 2018-10-09 | 20 | 20 | ES | Greene | NY | G | South Cairo 13.2kV | CHGE | 7 | 2021-02-28 | SIS |  | 09/2024 | 09/2024 | 10/2024
0774 | EDF Renewables Development, Inc. | Tracy Solar Energy Centre | 2018-10-18 | 119 | 119 | S | Jefferson | NY | E | Thousand Island - Lyme 115kV | NM-NG | 9 | 2021-06-30 | SRIS |  | 12/2022 | 12/2022 | 01/2023
0775 | Puckett Solar, LLC | Puckett Solar | 2018-10-22 | 20 | 20 | S | Chenango | NY | C | Chenango Forks 34.5kV | NYSEG | 11 | 2021-10-31 | SIS, FS | 2020-06-29 | 12/2021 | 02/2022 | 04/2022
0776 | Greenidge Generation LLC | Greenidge Load | 2018-10-22 | 60 | 60 | L | Yates | NY | C | Greenidge 115kV | NYSEG | 6 | 2021-08-31 | SIS |  | 12/2022 | N/A | N/A
0777 | Community Energy Solar, LLC | White Creek Solar | 2018-11-01 | 135 | 135 | S | Livingston | NY | B | Sta 82 - Sta 128 115kV | RG&E | 9 | 2021-06-30 | SRIS |  | 07/2023 | 10/2023 | 12/2023
0778 | Astoria Generating Company LP | Gowanus Gas Turbine Facility Repowering | 2018-11-08 | 549 | 588 | CT | Kings | NY | J | Gowanus 345kV | ConEd | 8 | 2021-02-28 | SRIS |  | 11/2021 | 02/2022 | 05/2022
0779 | Hecate Energy Gedney Hill LLC | Gedney Hill Solar | 2018-11-09 | 20 | 20 | S | Albany | NY | G | New Baltimore - Westerlo 69kV | CHGE | 9 | 2021-08-31 | SIS |  | 02/2023 | 03/2023 | 04/2023
0780 | Hecate Energy Johnstown LLC | Johnstown Solar | 2018-11-09 | 20 | 20 | S | Schenectady | NY | F | Stoner - Rotterdam 115kV | NM-NG | 9 | 2022-01-31 | SIS |  | 02/2023 | 03/2023 | 04/2023
0783 | ConnectGen Chautauqua County LLC | South Ripley Solar | 2018-12-07 | 270 | 270 | CR | Chautauqua | NY | A | South Ripley 230kV | NM-NG | 9 | 2021-08-31 | FES, SRIS |  | 09/2023 | 09/2023 | 11/2023
0784 | High Bridge Wind, LLC | High Bridge Battery | 2018-12-11 | 5 | 5 | ES | Chenango | NY | E | E. Norwich - Jennison 115kV | NYSEG | 10 | 2021-02-28 | SIS, FS | 2021-02-05 | 06/2022 | 07/2022 | 09/2022
0785 | ConnectGen Erie-Wyoming LLC | Erie-Wyoming County Solar | 2018-12-12 | 175 | 175 | S | Wyoming | NY | C | Stolle Road - High Sheldon 230kV | NYSEG | 5 | 7/31/21 | FES |  | 09/2022 | 09/2022 | 11/2022
0787 | Levy Grid, LLC | Levy Grid, LLC | 2018-12-20 | 150 | 150 | ES | Erie | NY | A | Gardenville 115kV | NM-NG | 9 | 2021-06-30 | SRIS |  | 08/2023 | 08/2023 | 09/2023
0789 | Atlantic Shores Offshore Wind Project 3, LLC (EDF) | Atlantic Shores Offshore Wind 8 | 2019-01-14 | 880 | 880 | W | Kings | NY | J | Gowanus 345kV | ConEd | 5 | 2019-09-30 |  |  | 06/2025 | 08/2025 | 12/2025
0790 | Atlantic Shores Offshore Wind Project 2, LLC (EDF) | Atlantic Shores Offshore Wind 9 | 2019-01-14 | 880 | 880 | W | Richmond | NY | J | Fresh Kills 345kV | ConEd | 5 | 2019-09-30 |  |  | 06/2025 | 08/2025 | 12/2025
0791 | Danskammer Energy LLC | Danskammer Energy Center | 2019-01-14 | 84.4 | 88.9 | CC | Orange | NY | G | Danskammer 115kV | CHGE | 10 | 2021-02-28 | SRIS, FS | 2021-02-09 | 08/2023 | 09/2023 | 10/2023
0792 | Anbaric Development Partners, LLC | Long Island Offshore Wind Connection | 2019-01-29 | 800 | 800 | W | Suffolk | NY | K | Ruland Road 138kV | LIPA | 6 | 2021-06-30 | SRIS |  | 07/2025 | 11/2025 | 12/2025
0800 | EDF Renewables Development, Inc. | Rich Road Solar Energy Center | 2019-02-20 | 240 | 240 | S | St. Lawrence | NY | E | Moses - Adirondack 230kV | NYPA | 6 | 2021-01-31 | FES, SRIS |  | 11/2024 | 12/2024 | 12/2024
0801 | Prattsburgh Wind, LLC | Prattsburgh Wind Farm | 2019-02-21 | 147 | 147 | W | Steuben | NY | C | Stoney Ridge - Canadaigua 230kV | NYSEG | 9 | 2021-06-30 | SRIS |  | 10/2022 | 11/2022 | 12/2022
0803 | Yonkers Grid, LLC | Yonkers Grid, LLC | 2019-03-11 | 100 | 100 | ES | Westchester | NY | I | Dunwoodie North 138kV | ConEd | 5 | 2021-02-28 | FES |  | 04/2022 | 04/2022 | 05/2022
0804 | KCE NY 10, LLC | KCE NY 10 | 2019-03-22 | 20 | 20 | ES | Erie | NY | A | Erie 34.5kV | NYSEG | 9 | 2021-08-31 | FES, SIS |  | 10/2022 | 10/2022 | 10/2022
0805 | Oxbow Hill Solar, LLC | Oxbow Hill Solar | 2019-03-22 | 140 | 140 | S | Madison | NY | C | Fenner 115kV | NM-NG | 9 | 2021-06-30 | SRIS |  | 08/2023 | 09/2023 | 09/2023
0806 | SED NY Holdings LLC | Limestone Solar | 2019-03-25 | 20 | 20 | S | Fulton | NY | F | Stoner - Rotterdam 115kV | NM-NG | 5 | 11/30/21 | FES |  | 11/2023 | 11/2023 | 12/2023
0807 | SunEast Hilltop Solar LLC | Hilltop Solar | 2019-03-28 | 20 | 20 | S | Rensselaer | NY | F | Eastover - Schaghticoke 115kV | NM-NG | 11 | 2022-01-31 | SIS,FS | 2021-04-07 | 07/2023 | 07/2023 | 07/2023
0811 | Hecate Energy Cider Solar LLC | Cider Solar | 2019-04-03 | 500 | 500 | S | Genesee | NY | B | Dysinger - New Rochester 345kV | NYPA | 9 | 2021-07-31 | SRIS |  | 08/2023 | 10/2023 | 12/2023
0815 | Bayonne Energy Center | Bayonne Energy Center III | 2019-04-05 | 49.8 | 49.8 | ES | Kings | NY | J | Gowanus 345kV | ConEd | 9 | 2021-06-30 | SRIS |  | 05/2023 | 05/2023 | 06/2023
0822 | Astoria Generating Company LP | Whale Square Energy Storage 1 | 2019-04-15 | 58.2 | 58.2 | ES | Kings | NY | J | Narrows Barge Feeder 23162 | ConEd | 9 | 2021-06-30 | SRIS |  | 02/2024 | 03/2024 | 05/2024
0825 | Setauket Energy Storage, LLC | Setauket Energy Storage | 2019-04-15 | 65.3 | 65.3 | ES | Suffolk | NY | K | Port Jefferson - Terryville 69kV | LIPA | 8 | 2021-07-31 | FES, SRIS |  | 10/2023 | 11/2023 | 12/2023
0826 | NRG Astoria Storage LLC | Astoria Energy Storage 1 | 2019-04-18 | 66 | 66 | ES | Queens | NY | J | North Queens 27kV | ConEd | 4 | 2021-09-30 |  |  | 07/2025 | 10/2025 | 12/2025
0827 | NRG Arthur Kill Storage LLC | Arthur Kill Energy Storage 1 | 2019-04-22 | 15 | 15 | ES | Richmond | NY | J | Fresh Kills 13.8kV | ConEd | 9 | 2021-08-31 | SIS |  | 01/2024 | 04/2024 | 06/2024
0828 | SunEast Valley Solar LLC | Valley Solar | 2019-04-24 | 20 | 20 | S | Tioga | NY | C | Owego 34.5kV | NYSEG | 10 | 2022-01-31 | SIS, FS | 2021-01-22 | 06/2022 | 06/2022 | 07/2022
0830 | NRG Astoria Storage LLC | Astoria Energy Storage 2 | 2019-04-26 | 79.9 | 79.9 | ES | Queens | NY | J | Astoria West 138kV | ConEd | 9 | 2021-06-30 | SRIS |  | 01/2024 | 04/2024 | 06/2024
0832 | Granada Solar, LLC | CS Hawthorn Solar | 2019-05-06 | 20 | 20 | S | Rensselaer | NY | F | North Troy - Hoosick 115kV | NM-NG | 9 | 2021-06-30 | FES, SIS |  | 10/2022 | 11/2022 | 12/2022
0833 | Dolan Solar, LLC | Dolan Solar | 2019-05-06 | 20 | 20 | S | Washington | NY | F | Battenkill - Mohican 115kV | NM-NG | 10 | 2022-01-31 | SIS,FS | 2021-04-13 | 06/2023 | 07/2023 | 09/2023
0834 | Astoria Generating Company, LP | Luyster Creek Energy Storage 2 | 2019-05-07 | 79 | 79 | ES | Queens | NY | J | Astoria West 138kV | ConEd | 9 | 2021-06-30 | SRIS |  | 02/2024 | 03/2024 | 05/2024
0835 | Astoria Generating Company, LP | Luyster Creek Energy Storage 1 | 2019-05-07 | 56.3 | 57.3 | ES | Queens | NY | J | Astoria West 138kV | ConEd | 9 | 2021-06-30 | SRIS |  | 02/2024 | 03/2024 | 05/2024
0838 | NRG Astoria Storage LLC | Astoria Energy Storage 3 | 2019-05-09 | 20 | 20 | ES | Queens | NY | J | North Queens 27kV | ConEd | 4 | 2021-06-30 |  |  | 05/2022 | 08/2022 | 10/2022
0840 | Hecate Grid Swiftsure LLC | Swiftsure Energy Storage | 2019-05-09 | 650 | 650 | ES | Richmond | NY | J | Fresh Kills 345kV | ConEd | 9 | 2021-06-30 | SRIS |  | 05/2022 | 06/2022 | 06/2022
0843 | Sandy Creek Solar LLC | NY37 Solar | 2019-05-17 | 20 | 20 | S | Jefferson | NY | E | Coffeen St - West Adams 115kV | NM-NG | 9 | 2021-10-31 | SIS |  | 10/2023 | 10/2023 | 11/2023
0848 | SED NY Holdings LLC | Fairway Solar | 2019-05-20 | 20 | 20 | S | St. Lawrence | NY | E | McIntyre - Colton 115kV | NM-NG | 11 | 2021-11-30 | SIS, FS | 2021-04-13 | 08/2022 | 08/2022 | 03/2022
0849 | Somerset Operating Company, LLC | Somerset Load | 2019-05-21 | 250 | 250 | L | Niagara | NY | A | Kintigh 345kV | NYSEG | 6 | 2021-03-31 | SIS |  | 11/2021 | N/A | N/A
0850 | Cayuga Operating Company, LLC | Cayuga Load | 2019-05-21 | 50 | 50 | L | Cayuga | NY | C | Milliken 115kV | NYSEG | 6 | 2021-08-31 | SIS |  | 11/2021 | N/A | N/A
0852 | Niagara Dolomite Solar, LLC | Niagara Dolomite Solar | 2019-05-24 | 180 | 180 | S | Niagara | NY | A | Robinson Rd - Stolle Rd 230kV | NYSEG | 5 | 2021-06-30 | FES |  | 09/2022 | 09/2022 | 10/2022
0855 | Bald Mountain Solar LLC | NY13 Solar | 2019-05-24 | 20 | 20 | S | Washington | NY | F | Mohican - Schaghticoke 115kV | NM-NG | 10 | 2021-10-31 | SIS, FS | 2021-10-07 | 09/2023 | 10/2023 | 11/2023
0857 | EDF Renewables Development, Inc. | Columbia Solar Energy Center | 2019-05-28 | 350 | 350 | S | Herkimer | NY | E | Edic - Fraser 345kV | NYPA | 6 | 2021-05-31 | FES, SRIS |  | 09/2024 | 10/2024 | 10/2024
0858 | EDF Renewables Development, Inc. | Genesee Road Solar Energy Center | 2019-05-28 | 350 | 350 | S | Erie | NY | A | Stolle Rd - Five Mile Rd 345kV | NYSEG | 6 | 2021-05-31 | SRIS |  | 09/2024 | 10/2024 | 10/2024
0859 | EDF Renewables Development, Inc. | Ridge View Solar Energy Center | 2019-05-28 | 350 | 350 | S | Niagara | NY | A | Kintigh - Dysinger 345kV | NYSEG | 6 | 2021-08-31 | SRIS |  | 09/2024 | 10/2024 | 10/2024
0860 | EDF Renewables Development, Inc. | Rosalen Solar Energy Center | 2019-05-28 | 350 | 350 | S | Steuben | NY | B | Pannell - Clay 345kV | NYPA | 6 | 2022-01-31 | SRIS |  | 09/2024 | 10/2024 | 10/2024
0863 | Mitsubishi Hitachi Power Systems Americas, Inc. | Coverdale Solar | 2019-05-29 | 20 | 20 | S | Livingston | NY | B | Highbanks 34.5kV | RG&E | 9 | 2021-10-31 | SIS |  | 06/2023 | 08/2023 | 10/2023
0864 | Greens Corners Solar LLC | NY38 Solar | 2019-05-29 | 120 | 120 | S | Jefferson | NY | E | Coffeen St - East Watertown 115kV | NM-NG | 9 | 2021-10-31 | SRIS |  | 01/2024 | 02/2024 | 03/2024
0865 | SED NY Holdings LLC | Flat Hill Solar | 2019-05-31 | 20 | 20 | S | Herkimer | NY | E | Inghams - Little Falls Hydro Plant | NM-NG | 9 | 2021-05-31 | SIS |  | 01/2023 | 01/2023 | 02/2023
0866 | RES Americas Developments, Inc. | North Country Wind | 2019-06-03 | 298.2 | 298.2 | W | Franklin | NY | D | Willis 230kV | NYPA | 5 | 2021-02-28 | FES |  | 09/2023 | 09/2023 | 12/2023
0869 | SunEast Tabletop Solar LLC | Tabletop Solar | 2019-06-04 | 80 | 80 | S | Montgomery | NY | F | Clinton 115kV | NM-NG | 5 | 1/31/22 | FES |  | 09/2024 | 10/2024 | 12/2024
0871 | Invenergy Solar Project Development LLC | Verona Solar Energy Center I | 2019-06-05 | 250 | 250 | S | Oneida | NY | C | Clay - Edic 345kV | NYPA | 5 | 2021-01-31 | FES |  | 10/2023 | 10/2023 | 12/2023
0873 | Invenergy Solar Project Development LLC | Verona Solar Energy Center II | 2019-06-05 | 250 | 250 | S | Oneida | NY | C | Clay - Edic 345kV | NYPA | 5 | 2021-01-31 | FES |  | 10/2023 | 10/2023 | 10/2023
0878 | Energy Storage Resources, LLC | Pirates Island | 2019-06-10 | 100 | 100 | ES | Erie | NY | A | Huntley - Gardenville 115kV | NM-NG | 9 | 2021-06-30 | SRIS |  | 09/2023 | 10/2023 | 01/2024
0879 | Empire Community Solar LLC | Holley Road Solar | 2019-06-10 | 19.9 | 19.9 | S | Orleans | NY | B | Lockport - Mortimer 115kV | NM-NG | 5 | 7/31/21 | FES |  | 01/2023 | 03/2023 | 03/2023
0880 | Brookside Solar, LLC | Brookside Solar | 2019-06-10 | 100 | 100 | S | Franklin | NY | D | Chateaugay - Willis 115kV | NYSEG | 9 | 2021-06-30 | SRIS |  | 07/2023 | 09/2023 | 11/2023
0881 | New Bremen Solar, LLC | New Bremen Solar | 2019-06-10 | 100 | 100 | S | Lewis | NY | E | Bremen - Lowville 115kV | NM-NG | 9 | 2021-06-30 | SRIS |  | 07/2023 | 09/2023 | 11/2023
0882 | Riverside Solar, LLC | Riverside Solar | 2019-06-10 | 100 | 100 | S | Jefferson | NY | E | Lyme 115kV | NM-NG | 9 | 2021-06-30 | SRIS |  | 07/2023 | 09/2023 | 11/2023
0883 | North Park Energy, LLC | Garnet Energy Center | 2019-06-11 | 200 | 200 | S | Cayuga | NY | B | Pannell - Clay 345kV | NYPA | 9 | 2021-06-30 | SRIS |  | 08/2023 | 09/2023 | 11/2023
0885 | SED NY Holdings LLC | Grassy Knoll Solar | 2019-06-12 | 20 | 20 | S | Herkimer | NY | E | Watkins Rd - Inghams 115kV | NM-NG | 9 | 2021-05-31 | SIS |  | 01/2023 | 01/2023 | 02/2023
0887 | CHPE LLC | CH Uprate | 2019-06-12 | 250 | 250 | DC | Quebec-NY | NY | J | Astoria Annex 345kV | NYPA | 9 | 2021-09-30 | SRIS |  | 10/2026 | 10/2026 | 12/2026
0899 | Sithe/Independence Power Partners, LP | Scriba-Volney Series Reactor | 2019-08-02 | N/A | N/A | AC | Oswego | NY | C | Volney - Scriba 345 kV | NM-NG | 9 | 2022-01-31 | SIS |  | 03/2024 | N/A | N/A
0907 | 174 Power Global | Harlem River Yard | 2019-09-04 | 100 | 100 | ES | Queens | NY | J | Hell Gate 138kV | NYPA | 9 | 2021-08-31 | SRIS |  | 10/2023 | 10/2023 | 12/2023
0911 | Dimension NY 1 LLC | Southold BESS | 2019-10-01 | 20 | 20 | ES | Suffolk | NY | K | Peconic - Southold 69kV | LIPA | 6 | 2021-04-30 | SIS |  | 05/2022 | 05/2022 | 05/2022
0912 | Hecate Grid Intrepid 1 LLC | Intrepid Storage 69 | 2019-10-02 | 50 | 50 | ES | Nassau | NY | K | EF Barrett 69kV | LIPA | 5 | 2021-09-30 |  |  | 12/2023 | 12/2023 | 12/2023
0913 | SED NY Holdings LLC | SunEast Manchester Solar LLC | 2019-10-04 | 20 | 20 | S | Wayne | NY | C | Hooks Rd - Elbridge 115kV | NM-NG | 5 | 2021-08-31 |  |  | 11/2023 | 11/2023 | 12/2023
0918 | Hecate Grid Intrepid 1 LLC | Intrepid Storage 138 | 2019-10-09 | 250 | 250 | ES | Nassau | NY | K | Barrett 138kV | LIPA | 5 | 2021-09-30 |  |  | 12/2023 | 12/2023 | 12/2023
0925 | Hecate Grid Clermont 1 LLC | Clermont 1 | 2019-10-17 | 100 | 100 | ES | Suffolk | NY | K | West Babylon 69kV | LIPA | 9 | 2021-06-30 | SRIS |  | 12/2022 | 12/2022 | 12/2022
0929 | EDF Renewables Development, Inc. | Morris Ridge Battery Storage | 2019-10-22 | 83 | 83 | ES | Livingston | NY | C | South Perry - Meyer 230 kV | NYSEG | 9 | 2021-06-30 | SRIS |  | 11/2023 | 11/2023 | 12/2023
0930 | Astoria Generating Co., LP | Astoria BES to 27kV North Queens | 2019-10-25 | 15 | 15 | ES | Queens | NY | J | North Queens 27kV | ConEd | 5 | 2020-09-30 |  |  | 09/2021 | 11/2021 | 12/2021
0931 | Hanwha Energy USA Holdings d/d/a/ 174 Power Global | Astoria Energy Storage | 2019-10-28 | 100 | 100 | ES | Queens | NY | J | Astoria West 138kV | ConEd | 9 | 2021-08-31 | SRIS |  | 10/2022 | 10/2022 | 12/2022
0932 | Oriden LLC | Hatchery Solar | 2020-01-02 | 20 | 20 | S | Livingston | NY | B | Caledonia - Golah 34.5 kV | NM-NG | 5 | 2021-09-30 |  |  | 09/2023 | 09/2023 | 09/2023
0935 | SED NY Holdings LLC | SunEast Oriskany Solar LLC | 2019-11-01 | 20 | 20 | S | Oneida | NY | E | Brothertown-Oriskany Falls 46kV | NYSEG | 5 | 7/31/20 |  |  | 09/2021 | 10/2021 | 12/2021
0939 | National Grid Generation LLC | Far Rockaway Power Station Battery Energy Storage System (BESS) | 2019-11-05 | 30 | 30 | ES | Queens | NY | K | Far Rockaway 69kV | LIPA | 6 | 2021-03-31 | SRIS |  | 10/2022 | 10/2022 | 12/2022
0940 | National Grid Generation LLC | Glenwood Power Station Battery Energy Storage System | 2019-11-08 | 50 | 50 | ES | Nassau | NY | K | Glenwood 138kV | LIPA | 3 | 8/31/20 |  |  | 10/2022 | 10/2022 | 12/2022
0941 | National Grid Generation LLC | Southampton Power Station Battery Energy Storage System (BESS) | 2019-11-08 | 30 | 30 | ES | Suffolk | NY | K | Southampton 69kV | LIPA | 5 | 2021-01-31 | FES |  | 10/2022 | 10/2022 | 12/2022
0942 | KCE NY 21, LLC | KCE NY 21 | 2019-11-08 | 60 | 60 | ES | Suffolk | NY | K | Pulaski 69kV | LIPA | 9 | 2021-06-30 | SRIS |  | 11/2024 | 11/2024 | 12/2024
0945 | Niagara Grid I, LLC | Niagara Grid I | 2019-11-13 | 20 | 20 | ES | Erie | NY | A | Huntley - Praxair 115kV | NM-NG | 5 | 2022-01-31 |  |  | 07/2022 | 07/2022 | 09/2022
0947 | Dimension NY 1 LLC | Livonia BESS | 2019-11-16 | 11.3 | 11.3 | ES | Livingston | NY | B | North Lakeville 34.5kV | NM-NG | 6 | 2021-04-30 | SIS |  | 10/2022 | 10/2022 | 10/2022
0949 | National Grid Generation LLC | Port Jefferson Power Station Battery Energy Storage System (BESS) | 2019-11-19 | 100 | 100 | ES | Suffolk | NY | K | Port Jefferson 138kV | LIPA | 4 | 2021-03-31 | FES |  | 10/2022 | 10/2022 | 12/2022
0950 | Orleans Solar LLC | Orleans Solar | 2019-11-21 | 200 | 200 | S | Orleans | NY | B | Lockport - Mortimer 115kV | NM-NG | 9 | 2021-08-31 | SRIS |  | 12/2022 | 11/2022 | 12/2022
0951 | Cayuga Grid, LLC | Cayuga Grid, LLC | 2019-12-04 | 100 | 100 | ES | Erie | NY | A | Gardenville 115kV | NYSEG | 5 | 2021-08-31 |  |  | 09/2022 | 09/2022 | 09/2022
0952 | Catskill Grid, LLC | Catskill Grid, LLC | 2019-12-04 | 100 | 100 | ES | Greene | NY | G | North Catskill - Milan 115kV | CHGE | 5 | 2020-07-31 |  |  | 09/2022 | 09/2022 | 09/2022
0953 | Sugar Maple Solar, LLC | Sugar Maple Solar | 2019-12-05 | 125 | 125 | S | Lewis | NY | E | Coffeen St - Taylorville 115kV | NM-NG | 9 | 2021-06-30 | SRIS |  | 08/2023 | 10/2023 | 12/2023
0954 | Empire Solar, LLC | Empire Solar | 2019-12-05 | 157.9 | 150 | S | Westfield | NY | A | South Ripley - Dunkirk 230 kV | NM-NG | 9 | 2021-06-30 | SRIS |  | 08/2023 | 10/2023 | 12/2023
0956 | Holtsville Energy Storage, LLC | Holtsville 138kV Energy Storage | 2019-12-10 | 294.9 | 296.4 | ES | Suffolk | NY | K | West Bus 138 kV | LIPA | 9 | 2021-10-31 | SRIS |  | 03/2023 | 04/2023 | 05/2023
0957 | Holtsville Energy Storage | Holtsville Energy Storage | 2019-12-10 | 76.8 | 76.8 | ES | Suffolk | NY | K | Holtsville Patchogue 69kV | LIPA | 6 | 2021-03-31 | SRIS |  | 03/2023 | 04/2023 | 05/2023
0958 | Empire Offshore Wind LLC | EI Oceanside | 2019-12-10 | 96 | 96 | W | Nassau | NY | K | Barrett 138 kV | LIPA | 9 | 2021-06-30 | SRIS |  | 06/2024 | 08/2024 | 12/2025
0959 | Empire Offshore Wind LLC | EI Oceanside 2 | 2019-12-11 | 1260 | 1260 | W | Nassau | NY | K | Barrett 138 kV | LIPA | 9 | 2021-06-30 | SRIS |  | 06/2024 | 08/2024 | 12/2025
0960 | SWEB Development USA, LLC | Cobleskill Solar Project | 2019-12-12 | 20 | 20 | S | Schoharie | NY | F | Cobleskill - Schoharie 69kV | NM-NG | 5 | 2021-11-30 | FES |  | 11/2023 | 11/2023 | 12/2023
0961 | Calpine Mid Atlantic Development, LLC | Bethpage Battery Energy Storage System | 2019-12-18 | 20 | 20 | ES | Nassau | NY | K | Grumman Substation 69 kV | LIPA | 3 | 2021-03-31 |  |  | 01/2022 | 03/2022 | 06/2022
0962 | Brookfield Power US Asset Management LLC | Beardslee Solar | 2019-12-19 | 20 | 20 | S | Herkimer | NY | E | St. Johnsville - Inghams 115kV | NM-NG | 5 | 8/31/20 |  |  | 10/2022 | 11/2022 | 12/2022
0965 | Yaphank Energy Storage, LLC | Yaphank Energy Storage | 2019-12-21 | 76.8 | 77.6 | ES | Suffolk | NY | K | William Floyd - Brookhaven 69kV | LIPA | 9 | 2021-06-30 | SRIS |  | 03/2023 | 04/2023 | 05/2023
0966 | Suffolk County Energy Storage, LLC | Suffolk County Storage | 2019-12-21 | 40.3 | 40.3 | ES | Suffolk | NY | K | West Babylon - Lindenhurst 69kV | LIPA | 8 | 2021-07-31 | SRIS |  | 03/2023 | 04/2023 | 05/2023
0967 | KCE NY 5 LLC | KCE NY 5 | 2019-12-27 | 94 | 94 | ES | Ulster | NY | G | Ohioville 115kV | CHGE | 9 | 2022-01-31 | SRIS |  | 10/2022 | 10/2022 | 10/2022
0971 | Savion, LLC | East Setauket Energy Storage | 2020-01-10 | 125 | 125 | ES | Suffolk | NY | K | Holbrook-Miller Place 138kV | LIPA | 8 | 2021-07-31 | SRIS |  | 03/2024 | 04/2024 | 05/2024
0972 | SWEB Development USA, LLC | Warner Hill Solar Project | 2020-01-10 | 19.8 | 19.8 | S | Schoharie | NY | F | Middleburg Tap - Middleburg 69kV | NM-NG | 5 | 2021-11-30 | FES |  | 10/2023 | 09/2023 | 11/2023
0974 | KCE NY 19 LLC | KCE NY 19 | 2020-01-14 | 80 | 80 | ES | Orange | NY | G | Sugarloaf - Wisner 69kV | O&R | 6 | 2021-03-31 | SRIS |  | 05/2022 | 05/2022 | 06/2022
0979 | North Country Data Center | Load Increase at North Country Data Center (Former Reynolds Substation) to 435MW | 2020-01-22 | 185 | 185 | L | St. Lawrence | NY | E | Reynolds 115kV | NYPA | 4 | 2021-10-31 |  |  | 10/2020 | N/A | N/A
0982 | National Grid Generation LLC | West Babylon Power Station Battery Energy Storage System | 2020-01-22 | 50 | 50 | ES | Suffolk | NY | K | West Babylon 69kV | LIPA | 5 | 2021-09-30 |  |  | 10/2022 | 10/2022 | 12/2022
0987 | Sunrise Wind LLC | NY Wind Holbrook 2 | 2020-01-29 | 924 | 924 | W | Suffolk | NY | K | Holbrook 138kV | LIPA | 9 | 2021-06-30 | SRIS |  | 01/2023 | 04/2024 | 05/2024
0993 | VESI 30 LLC | Empire Energy Storage | 2020-01-31 | 10 | 10 | ES | Monroe | NY | B | Station 55 - Station 73 34.5kV | RG&E | 5 | 2021-06-30 |  |  | 10/2022 | 11/2022 | 12/2022
0994 | KCE NY 22, LLC | KCE NY 22 | 2020-02-12 | 90 | 90 | ES | Suffolk | NY | K | Holbrook-Sills Road 138kV | LIPA | 9 | 2021-06-30 | SRIS |  | 11/2024 | 11/2024 | 12/2024
0995 | Alabama Solar Park LLC | Alabama Solar Park LLC | 2020-02-27 | 130 | 130 | S | Genesee | NY | B | Lockport - Batavia 115kV | NM-NG | 9 | 2021-06-30 | SRIS |  | 08/2023 | 09/2023 | 10/2023
1000 | SED NY Holdings LLC | SunEast Flat Stone Solar LLC | 2020-03-18 | 20 | 20 | S | Oneida | NY | E | Oneida - Rome 115kV | NM-NG | 5 | 8/31/20 |  |  | 10/2022 | 11/2022 | 11/2022
1001 | Empire State Connector LLC | Empire State Connector II | 2020-03-20 | 1250 | 1250 | DC | Onondaga-New York | NY | E, J | Marcy - Rainey 345 kV | NYPA/ConEd | 3 | 2020-09-30 |  |  | 10/2025 | 01/2026 | 03/2026
1003 | Oriden LLC | Clear View Solar | 2020-04-06 | 20 | 20 | S | Steuben | NY | C | Eelpot Road 34.5kV | NYSEG | 5 | 8/31/21 |  |  | 10/2022 | 10/2022 | 11/2022
1004 | Renewable Energy Aggregators, Inc. | Mifflin | 2020-04-13 | 300 | 300 |  | Sullivan | NY | E | Coopers Corner 345kV | NYSEG | 5 | 2021-03-31 |  |  | 01/2024 | 01/2024 | 01/2024
1007 | NYC Energy | NYC Energy LLC - Phase 2 | 2020-04-22 | 220.1 | 220.1 | ES | Kings | NY | J | Hudson Ave East 138kV | ConEd | 5 | 2021-08-31 |  |  | 06/2024 | 07/2024 | 09/2024
1008 | KCE NY 26, LLC | KCE NY 26 | 2020-04-28 | 60 | 60 | ES | Suffolk | NY | K | Jamesport - Peconic 69kV | LIPA | 4 | 7/31/21 |  |  | 10/2023 | 11/2023 | 12/2023
1009 | Granada Solar, LLC | Yellow Barn Solar | 2020-04-30 | 160 | 160 | S | Tompkins | NY | C | Cayuga - Etna 115kV | NYSEG | 5 | 10/31/20 |  |  | 05/2022 | 06/2022 | 07/2022
1010 | OCS-A 0522, LLC | Vineyard Wind I | 2020-04-30 | 1403 | 1403 | W | Nassau | NY | K | East Garden City 345kV | NYPA | 5 | 1/31/22 |  |  | 07/2026 | 11/2026 | 12/2026
1011 | OCS-A 0522, LLC | Vineyard Wind II | 2020-04-30 | 1403 | 1403 | W | Suffolk | NY | K | Ruland Road 138kV | LIPA | 4 | 2022-01-31 | FES |  | 07/2026 | 11/2026 | 12/2026
1012 | Suffolk County Energy Storage II | Suffolk County Storage II | 2020-05-04 | 76.86 | 76.86 | ES | Suffolk | NY | K | Southold 69 kV | LIPA | 5 | 7/31/21 | FES |  | 01/2024 | 03/2024 | 05/2024
1013 | Barrett Ridge Energy, LLC | Barrett Ridge Energy - PARs | 2020-05-05 | 168 | 168 | AC | Orange | NY | G | Sugarloaf 138 kV | O&R | 5 | 8/31/21 |  |  | 04/2024 | 05/2024 | 06/2024
1015 | Granada Solar, LLC | Somers Solar, LLC | 2020-05-05 | 20 | 20 | S | Washington | NY | F | Mohican - Battenkill 115kV | NM-NG | 5 | 10/31/20 |  |  | 10/2022 | 12/2022 | 12/2022
1016 | Beacon Wind LLC | EI Steinway 1 | 2020-05-19 | 1300 | 1300 | W | Queens | NY | J | Astoria West 138 kV | ConEd | 5 | 2021-12-31 |  |  | 12/2026 | 03/2027 | 11/2027
1017 | Beacon Wind LLC | EI Steinway 2 | 2020-05-19 | 1300 | 1300 | W | Queens | NY | J | Astoria East 138 kV | ConEd | 5 | 2021-12-31 |  |  | 12/2027 | 03/2028 | 11/2028
1018 | Naturgy Candela DevCo LLC | Stone Mill Solar | 2020-05-21 | 20 | 20 | S | Columbia | NY | F | Churchtown 115kV | NYSEG | 5 | 2021-10-31 |  |  | 06/2023 | 05/2023 | 07/2023
1019 | Naturgy Candela DevCo LLC | Marshville Solar | 2020-05-21 | 20 | 20 | S | Montgomery | NY | F | Marshville 69kV | NM-NG | 5 | 2021-10-31 |  |  | 06/2023 | 05/2023 | 07/2023
1020 | Beacon Wind LLC | EI Fort Salonga | 2020-05-21 | 1300 | 1300 | W | Suffolk | NY | K | Northport 138 kV | LIPA | 5 | 2021-12-31 |  |  | 12/2026 | 03/2027 | 11/2027
1021 | Beacon Wind LLC | EI East Shoreham | 2020-05-27 | 1300 | 1300 | W | Suffolk | NY | K | Shoreham 138 kV | LIPA | 5 | 2021-06-30 |  |  | 12/2026 | 03/2027 | 11/2027
1022 | Equinor Wind US LLC | EI Glenwood Landing | 2020-05-27 | 1300 | 1300 | W | Nassau | NY | K | Shore Road 345 kV | LIPA | 4 | 2020-08-31 |  |  | 12/2026 | 03/2027 | 11/2027
1023 | KCE NY 27, LLC | KCE NY 27 | 2020-06-02 | 50 | 50 | ES | Suffolk | NY | K | Tiana - Quogue 69kV | LIPA | 4 | 7/31/21 | FES |  | 09/2022 | 10/2022 | 10/2022
1027 | Naturgy Candela DevCo LLC | Knickerbocker Solar | 2020-06-08 | 20 | 20 | S | Rensselaer | NY | F | Valkin - Greenbush 115kV | NM-NG | 5 | 2021-10-31 |  |  | 05/2023 | 06/2023 | 07/2023
1028 | Excelsior Reserve Energy | Raquette Lake Energy Storage | 2020-06-09 | 20 | 20 | ES | Hamilton | NY | E | Old Forge - Raquette Lake 46kV | NM-NG | 5 | 2022-01-31 |  |  | 08/2022 | 09/2022 | 10/2022
1029 | Naturgy Candela DevCo LLC | Half Moon Solar | 2020-06-11 | 20 | 20 | S | Rensselaer | NY | F | Valkin - Greenbush 115kV | NM-NG | 5 | 2021-08-31 |  |  | 05/2023 | 06/2023 | 07/2023
1030 | Boralex US Development | NY109 Solar | 2020-06-15 | 20 | 20 | S | Fulton | NY | F | Stoner - Rotterdam 115kV | NM-NG | 5 | 7/31/21 |  |  | 11/2023 | 11/2023 | 12/2023
1031 | ConnectGen Montgomery County LLC | Mill Point Solar | 2020-06-18 | 250 | 250 | S | Montgomery | NY | E | Marcy - New Scotland 345kV | NM-NG | 5 | 2020-12-31 |  |  | 10/2023 | 10/2023 | 12/2023
1035 | Boralex US Development | NY08 Solar | 2020-06-22 | 20 | 20 | S | Washington | NY | F | Battenkill 34.5kV | NM-NG | 5 | 2021-06-30 |  |  | 11/2023 | 11/2023 | 12/2023
1036 | Juno Power Management LLC | Mainesburg ESS | 2020-06-22 | 300 | 300 | ES | Tioga | PA | C | Mainesburg - Watercure 345kV | NYSEG | 5 | 2021-06-30 | FES |  | 02/2022 | 04/2022 | 06/2022
1037 | Juno Power Management LLC | East Sayre ESS | 2020-06-22 | 75.92 | 83.52 | ES | Bradford | PA | C | East Sayre-North Waverly 115kV | NYSEG | 3 | 7/31/21 |  |  | 02/2022 | 04/2022 | 06/2022
1038 | ELP Rotterdam Solar LLC | ELP Rotterdam Solar | 2020-06-23 | 20 | 20 | S | Schenectady | NY | F | Rotterdam - Meco 115kV | NM-NG | 5 | 2021-02-28 |  |  | 10/2022 | 11/2022 | 12/2022
1039 | SED NY Holdings LLC | Morris Solar Project | 2020-06-23 | 20 | 20 | S | St. Lawrence | NY | E | Battle Hill - Balmat 115kV | NM-NG | 5 | 2021-02-28 |  |  | 10/2022 | 11/2022 | 11/2022
1040 | Riverline Energy Center, LLC | Riverline Energy Center | 2020-06-24 | 200 | 200 | S | St. Lawrence | NY | E | Moses - Adirondack 230 kV | NYPA | 5 | 4/30/21 |  |  | 04/2023 | 05/2023 | 11/2023
1041 | Silverline Energy Center, LLC | Silverline Energy Center | 2020-06-25 | 200 | 200 | S | Tompkins | NY | C | Miliken - Etna 115 kV | NYSEG | 5 | 2021-01-31 |  |  | 04/2023 | 05/2023 | 11/2023
1042 | Boralex US Development LLC | Fort Edward Solar Farm (NY53) | 2020-06-26 | 100 | 100 | S | Washington | NY | F | Mohican - Battenkill 115kV | NM-NG | 5 | 2021-06-30 |  |  | 10/2024 | 11/2024 | 12/2024
1043 | SL Portland, LLC | SL Portland Solar | 2020-06-30 | 19.8 | 19.8 | S | Chautauqua | NY | A | Dunkirk - Falconer 115kV | NM-NG | 3 | 2021-08-31 |  |  | 12/2022 | 12/2022 | 12/2022
1045 | Bay State Wind | NY Wind Holbrook 2 | 2020-07-03 | 1050 | 1050 | W | Suffolk | NY | K | Holbrook 138kV | LIPA | 5 | 2021-01-31 |  |  | 01/2023 | 04/2024 | 05/2024
1046 | Island Park Energy Center, LLC | Barrett Energy Storage Center | 2020-07-06 | 200 | 200 | ES | Nassau | NY | K | Barrett 138 kV | LIPA | 5 | 2021-02-28 |  |  | 05/2023 | 09/2023 | 12/2023
1047 | SED NY Holdings LLC | Millers Grove Solar | 2020-07-09 | 20 | 20 | S | Herkimer | NY | E | Porter - Watkins 115kV | NM-NG | 5 | 10/31/20 |  |  | 10/2021 | 11/2021 | 12/2021
1048 | Declaration Energy Center, LLC | Declaration Energy Center | 2020-07-14 | 300 | 300 | S | Seneca | NY | C | Border City 115 kV | NYSEG | 5 | 7/31/21 |  |  | 04/2023 | 05/2023 | 11/2023
1049 | Clean Energy Generation, LLC | Holbrook Energy Center | 2020-07-14 | 150 | 150 | ES | Suffolk | NY | K | Holbrook 138 kV | LIPA | 5 | 2021-05-31 |  |  | 05/2023 | 09/2023 | 12/2023
1050 | Clean Energy Generation, LLC | Holtsville Energy Center | 2020-07-14 | 150 | 150 | ES | Suffolk | NY | K | West Bus 138 kV | LIPA | 5 | 4/30/21 |  |  | 05/2023 | 09/2023 | 12/2023
1051 | SED NY Holding LLC | Transit Solar Project | 2020-07-21 | 20 | 20 | S | Genesee | NY | B | Batavia - Golah 115kV | NM-NG | 5 | 2021-06-30 |  |  | 10/2022 | 11/2022 | 12/2022
1052 | Capital Power Solar Holdings LLC | Madison Solar | 2020-07-22 | 20 | 20 | S | Madison County | NY | E | Teal - Oneida 115kV | NM-NG | 5 | 2022-01-31 |  |  | 08/2022 | 09/2022 | 10/2022
1055 | SWEB Development USA LLC | Addison Solar Project | 2020-07-23 | 120 | 120 | S | Steuben | NY | C | Stony Ridge - Sullivan Park 115 kV | NYSEG | 5 | 2021-11-30 | FES |  | 10/2024 | 11/2024 | 12/2024
1056 | Bay State Wind | NY Wind - East Garden City | 2020-07-27 | 1272 | 1272 | W | Nassau | NY | K | Shore Road 138kV | LIPA | 4 | 2021-06-30 |  |  | 01/2026 | 07/2026 | 04/2027
1058 | Bay State Wind | NY Wind - Pilgrim | 2020-07-27 | 1276 | 1276 | W | Suffolk | NY | K | Pilgrim 138kV | LIPA | 4 | 2021-03-31 |  |  | 01/2026 | 07/2026 | 04/2027
1059 | AES DE DEVCO NC, LLC | Jaton | 2020-07-31 | 16.2 | 16.2 | S | Oswego | NY | C | South Oswego - Clay 115 kV | NM-NG | 5 | 2021-06-30 |  |  | 10/2022 | 11/2022 | 11/2022
1060 | AES DE DEVCO NC LLC | Delight Farm | 2020-07-31 | 16.8 | 16.8 | S | Cayuga | NY | C | Union Springs - Aurora 34.5 kV | NYSEG | 5 | 2021-02-28 |  |  | 10/2022 | 11/2022 | 11/2022
1061 | AES DE DEVCO NC LLC | Teele | 2020-07-31 | 19.8 | 19.8 | S | St. Lawrence | NY | E | Ogdensburg - Bradly Rd 115 kV | NM-NG | 5 | 2021-02-28 |  |  | 10/2022 | 11/2022 | 11/2022
1062 | AES DE DEVCO NC LLC | Tubolino 2 | 2020-07-31 | 19.8 | 19.8 | S | Jefferson | NY | E | West Adams - Coffeen St 115 kV | NM-NG | 5 | 2021-08-31 |  |  | 10/2022 | 11/2022 | 11/2022
1063 | AES DE DEVCO NC LLC | Morrow Farms LLC | 2020-07-31 | 19.8 | 19.8 | S | Jefferson | NY | E | Thousand Island - Coffeen St 115 kV | NM-NG | 5 | 2021-08-31 |  |  | 10/2022 | 11/2022 | 11/2022
1064 | AES DE DEVCO NC LLC | K. High | 2020-07-31 | 19.8 | 19.8 | S | Wayne | NY | B | Station 218 - Station 181 34.5kV | RG&E | 5 | 2021-09-30 |  |  | 10/2022 | 11/2022 | 11/2022
1066 | Bay State Wind | NY Wind - Mott Haven | 2020-08-04 | 1272 | 1272 | W | Bronx | NY | J | Mott Haven 345kV | ConEd | 5 | 2021-02-28 |  |  | 01/2026 | 06/2026 | 04/2027
1068 | Juno Power Management LLC | Buchanan Point BESS | 2020-08-05 | 500 | 500 | ES | Westchester | NY | H | Buchanan North 345 kV | ConEd | 5 | 2021-10-31 |  |  | 06/2024 | 03/2024 | 01/2024
1077 | Rutland Center Solar 1, LLC | Rutland Center Solar | 2020-08-14 | 110 | 110 | S | Jefferson | NY | E | Middle Rd 115kV | NM-NG | 5 | 4/30/21 |  |  | 08/2023 | 09/2023 | 10/2023
1079 | sPower Development Company, LLC | Somerset Solar | 2020-08-18 | 207 | 207 | S | Niagara | NY | A | Kintigh 345 kV | NYSEG | 5 | 2021-01-31 |  |  | 01/2023 | 02/2023 | 03/2023
1080 | Swift Current Energy - (Mineral Basin Solar Power, LLC) | Mineral Basin Solar Power | 2020-08-21 | 401.6 | 401.6 | S | Clearfield | PA | C | Homer City - Mainesburg 345kV | NYSEG | 5 | 2021-08-31 |  |  | 01/2023 | 01/2023 | 05/2023
1081 | KCE NY 28, LLC | KCE NY 28 | 2020-08-27 | 45 | 45 | ES | Suffolk | NY | K | Riverhead 138 kV | LIPA | 4 | 2021-11-30 |  |  | 10/2024 | 10/2024 | 11/2024
1083 | Juno Power Management LLC | Tremont BESS | 2020-08-28 | 300 | 300 | ES | Bronx | NY | J | Tremont 345kV | ConEd | 3 | 2021-10-31 |  |  | 08/2023 | 08/2023 | 10/2023
1084 | Juno Power Management LLC | EGC BESS | 2020-08-28 | 300 | 300 | ES | Nassau | NY | K | East Garden City 345kV | LIPA | 2 | 2021-03-31 |  |  | 08/2023 | 08/2023 | 10/2023
1085 | Juno Power Management LLC | Oyster Shore BESS | 2020-08-28 | 500 | 500 | ES | Nassau | NY | K | Shore Rd 345kV | LIPA | 2 | 2020-11-30 |  |  | 08/2023 | 08/2023 | 10/2023
1086 | Juno Power Management LLC | Buchanan Point BESS II | 2020-08-28 | 500 | 500 | ES | Westchester | NY | H | Buchanan South 345kV | ConEd | 5 | 2021-10-31 |  |  | 03/2024 | 03/2024 | 06/2024
1087 | East Wind LLC | East Wind 1 | 2020-08-31 | 1200 | 1200 | W | Kings | NY | J | Farragut 138kV | ConEd | 3 | 2021-08-31 |  |  | 02/2028 | 02/2028 | 12/2023
1088 | ConnectGen Cayuga County LLC | Harvest Hills Solar | 2020-09-01 | 200 | 200 | S | Cayuga | NY | C | Wright Avenue - Cayuga 115kV | NYSEG | 5 | 2021-06-30 |  |  | 11/2023 | 11/2023 | 12/2023
1089 | SED NY Holding LLC | Flat Creek Solar | 2020-09-04 | 200 | 200 | S | Montgomery | NY | F | Edic - Princetown 345kV | NYPA | 5 | 2022-01-31 |  |  | 09/2024 | 11/2024 | 12/2024
1090 | SED NY Holding LLC | Westmorland Solar | 2020-09-04 | 20 | 20 | S | Oneida | NY | E | Yahnundasis - Clinton 46kV | NM-NG | 5 | 7/31/21 |  |  | 10/2022 | 11/2022 | 11/2022
1092 | SED NY Holding LLC | Hampton Corners Solar | 2020-09-08 | 20 | 20 | S | Livingston | NY | B | Station 128-Station 7325 115kV | NYSEG | 5 | 7/31/21 |  |  | 10/2022 | 11/2022 | 12/2022
1096 | Northland Power U.S. Projects | Allegany 2 Solar | 2020-09-14 | 100 | 100 | S | Allegany | NY | C | Andover - Palmeter 115 kV | NYSEG | 5 | 4/30/21 |  |  | 07/2023 | 12/2023 | 01/2024
1098 | SED NY Holdings LLC | Kingbird Solar | 2020-09-16 | 20 | 20 | S | Chatauqua | NY | A | Dunkirk - Silver Creek 115 kV | NM-NG | 4 | 2021-02-28 |  |  | 10/2022 | 11/2022 | 11/2022
1100 | Hosmer Solar, LLC | Ray Solar, LLC | 2020-09-28 | 20 | 20 | S | Rensselaer | NY | F | Greenbush-Valkin 115kV | NM-NG | 5 | 2021-08-31 |  |  | 04/2024 | 06/2024 | 06/2024
1102 | SWEB Development USA | Troupsburg Solar | 2020-10-05 | 20 | 20 | S | Steuben | NY | C | Woodhull - Troupsburg 34.5 kV | NYSEG | 3 | 2021-06-30 |  |  | 10/2023 | 11/2023 | 12/2023
1103 | Cypress Creek Renewables, LLC | Thousand Island Solar | 2020-10-06 | 110 | 110 | S | Jefferson | NY | E | Coffeen St - Thousand Island 115KV | NM-NG | 5 | 2021-05-31 |  |  | 12/2024 | 11/2024 | 11/2024
1104 | Saturn Energy Storage LLC | Brockport BESS | 2020-10-07 | 20 | 20 | ES | Monroe | NY | A | Brockport - Albion 34.5kV | NM-NG | 5 | 1/31/22 |  |  | 06/2022 | 06/2022 | 10/2022
1107 | Juno Power Management LLC | Buchanan Point BESS III | 2020-10-19 | 300 | 300 | ES | Westchester | NY | H | Buchanan 345kV | ConEd | 5 | 1/31/22 |  |  | 03/2024 | 03/2024 | 06/2024
1108 | SWEB Development USA, LLC | Bangor Solar | 2020-10-26 | 106.9 | 106.9 | S | Franklin | NY | D | Malone - Nicholville 115kV | NYSEG | 2 | 2021-02-28 |  |  | 10/2023 | 11/2023 | 12/2023
1109 | SWEB Development USA, LLC | Worth Wind | 2020-10-27 | 92 | 92 | W | Jefferson | NY | E | Lighthouse Hill - E. Watertown 115kV | NM-NG | 2 | 2021-10-31 |  |  | 10/2025 | 08/2025 | 12/2025
1112 | Caithness LI Energy Storage, LLC | CLIES 10MW | 2020-11-18 | 10 | 10 | ES | Suffolk | NY | K | Sills Road 138kV | LIPA | 5 | 4/30/21 |  |  | 04/2022 | 03/2022 | 05/2022
1113 | Caithness LI Energy Storage, LLC | CLIES 20 MW | 2020-11-18 | 20 | 20 | ES | Suffolk | NY | K | Sills Road 138kV | LIPA | 5 | 4/30/21 |  |  | 04/2022 | 03/2022 | 05/2022
1114 | Clean Energy Generation, LLC | Wading River Energy Center | 2020-11-19 | 50 | 50 | ES | Suffolk | NY | K | Wading River 138 kV | LIPA | 5 | 2021-06-30 |  |  | 05/2023 | 09/2023 | 12/2023
1115 | SED NY Holdings LLC | Flat Creek Solar 2 | 2020-11-23 | 100 | 100 | S | Montgomery | NY | F | Edic - Princetown 345kV | NYPA | 4 | 2021-08-31 |  |  | 08/2024 | 08/2024 | 09/2024
1116 | Liberty Renewables Inc. | Blue Hill Wind | 2020-11-24 | 25.4 | 27 | W | Madison | NY | E | Morrisville 46kV | NYSEG | 4 | 2021-08-31 |  |  | 10/2023 | 11/2023 | 12/2023
1117 | Caithness LI Energy Storage, LLC | CLIES 70MW | 2020-11-25 | 70 | 70 | ES | Suffolk | NY | K | Sills Road 138kV | LIPA | 5 | 2021-06-30 |  |  | 09/2022 | 09/2022 | 12/2022
1119 | Granada Solar, LLC | Fuller Storage | 2020-12-04 | 20 | 20 | ES | Orange | NY | G | East Walden 115kV | CHGE | 4 | 2021-02-28 |  |  | 06/2023 | 08/2023 | 08/2023
1120 | Ravenswood Development, LLC | Catskills Renewable Connector | 2020-12-11 | 1200 | 1200 | DC | Greene/Queens | NY | F, J | New Scotland-Leeds 345kV, Rainey-Farragut | NGrid/ConEd | 4 | 2021-06-30 |  |  | 06/2026 | N/A | N/A
1121 | Ravenswood Development, LLC | Werner - Ravenswood | 2020-12-11 | 1200 | 1200 | DC | PJM/Queens | NY | J | Rainey - Farragut 345kV | ConEd | 4 | 2021-06-30 |  |  | 12/2026 | N/A | N/A
1122 | Microgrid Networks, LLC | East Fishkill | 2020-12-11 | 213 | 190 | ES | Dutchess | NY | G | Shenandoah 115kV | CHGE | 4 | 8/31/21 |  |  | 05/2023 | 03/2023 | 06/2023
1123 | KCE NY 29, LLC | KCE NY 29 | 2020-12-14 | 150 | 150 | ES | Suffolk | NY | K | Kings 138kV | LIPA | 4 | 2022-01-31 |  |  | 09/2024 | 09/2024 | 10/2024
1125 | New York Power Authority | Northern New York Priority Transmission Project (NNYPTP) | 2020-12-22 | N/A | N/A | AC | St. Lawrence-Lewis | NY | D, E | Moses/Adirondack/Poter Path | NYPA/NM-NG | 7 | 2021-12-31 | SIS |  | 12/2025 | N/A | N/A
1126 | AES DE DEVCO NC, LLC | Richardson | 2021-01-04 | 19.8 | 19.8 | S | St. Lawrence | NY | E | N. Ogdensburg - McIntyre 115 kV line | MN-NG | 5 | 2021-11-30 |  |  | 10/2022 | 11/2022 | 11/2022
1128 | Northland Power U.S. Projects | Allegany 2 Battery 2 | 2021-01-21 | 20 | 20 | ES | Allegany | NY | C | Andover - Palmeter 115kV | NYSEG | 4 | 4/30/21 |  |  | 07/2023 | 12/2023 | 01/2024
1130 | Liberty Renewables Inc. | Hoffman Falls Wind | 2021-01-27 | 65.5 | 71.9 | W | Madison | NY | C | Cortland - Fenner 115 kV | NM-NG | 4 | 2022-01-31 |  |  | 10/2023 | 11/2023 | 12/2023
1131 | Avangrid Networks, Inc. | Excelsior Connect - Edic to Rainey | 2021-01-28 | 1310 | 1310 | DC | Oneida-Queens | NY | E, J | Edic - Rainey 345kV | NM-NG, ConEd | 4 | 8/31/21 |  |  | 10/2025 | 11/2025 | 01/2026
1132 | Avangrid Networks, Inc. | Excelsior Connect - Edic to Farragut | 2021-01-28 | 1310 | 1310 | DC | Oneida-Brooklyn | NY | E, J | Edic - Farragut 345kV | NM-NG, ConEd | 4 | 2021-08-31 |  |  | 10/2025 | 11/2025 | 01/2026
1133 | EDF Renewables Development, Inc. | Moraine Storage | 2021-02-11 | 5 | 5 | ES | Allegany | NY | C | Moraine Road 115 kV | NYSEG | 4 | 2021-08-31 |  |  | 09/2023 | 09/2023 | 11/2023
1134 | EDF Renewables Development | Tracy Storage | 2021-02-11 | 5 | 5 | ES | Jefferson | NY | E | Thousand Island - Coffeen St 115 kV | NM-NG | 4 | 2021-08-31 |  |  | 09/2023 | 09/2023 | 11/2023
1135 | EDF Renewables Development, Inc. | Homer Storage | 2021-02-11 | 5 | 5 | ES | Cortland | NY | C | Cortland - Fenner 115 kV | NM-NG | 4 | 7/31/21 |  |  | 09/2023 | 09/2023 | 11/2023
1136 | Honey Ridge Solar 1, LLC | Honey Ridge Solar | 2021-02-15 | 140.6 | 140.6 | S | Jefferson | NY | E | Black River 115kV | NM-NG | 5 | 2021-11-30 |  |  | 07/2025 | 08/2025 | 09/2025
1137 | Invenergy Solar Project Development LLC | Orangeville Solar | 2021-02-16 | 75 | 75 | S | Wyoming | NY | C | Stony Creek 230kV | NYSEG | 3 | 7/31/21 |  |  | 06/2024 | 06/2024 | 12/2024
1138 | Invenergy Solar Project Development LLC | Wintergreen Solar | 2021-02-16 | 75 | 75 | S | Montgomery | NY | F | Marshville 115kV | NM-NG | 3 | 7/31/21 |  |  | 06/2024 | 06/2024 | 12/2024
1139 | Invenergy Solar Project Development LLC | Seventy-Seven Solar | 2021-02-16 | 100 | 100 | S | Wyoming | NY | C | High Sheldon 230kV | NYSEG | 4 | 4/30/21 |  |  | 06/2024 | 06/2024 | 12/2024
1140 | Invenergy Solar Project Development LLC | Taproot Solar | 2021-02-16 | 205 | 205 | S | Montgomery | NY | E | Edic - New Scotland 345kV | NM-NG | 4 | 4/30/21 |  |  | 06/2024 | 06/2024 | 12/2024
1141 | Invenergy Solar Project Development LLC | Twinleaf Solar | 2021-02-16 | 75 | 75 | S | Lewis | NY | E | Coffeen St - Taylorville 115kV | NM-NG | 4 | 2021-06-30 |  |  | 06/2024 | 06/2024 | 12/2024
1142 | Minerva Power Connection LLC | Minerva BESS I | 2021-02-16 | 600 | 600 | ES | Manhattan | NY | J | W 49th St 345kV | ConEd | 5 | 2021-09-30 |  |  | 03/2024 | 03/2024 | 06/2024
1145 | EDF Renewables Development, Inc. | Oceanside Energy Storage | 2021-02-18 | 36 | 36 | ES | Nassau | NY | K | Barrett 138 kV | LIPA | 2 | 2021-06-30 |  |  | 09/2024 | 09/2024 | 11/2024
1146 | Galehead Development, LLC | Champlain Solar | 2021-02-19 | 100 | 100 | S | Washington | NY | F | Mohican - Whitehall 115kV | NM-NG | 3 | 2022-01-31 |  |  | 08/2024 | 09/2024 | 10/2024
1147 | Wawayanda Solar 1, LLC | Wawayanda Solar | 2021-02-26 | 19.9 | 19.9 | S | Orange | NY | G | Westtown - Shoemaker 69kV | O&R | 5 | 2021-08-31 |  |  | 02/2023 | 03/2023 | 04/2023
1148 | Liberty Renewables Inc. | Agricola Wind Project | 2021-03-10 | 97 | 97 | W | Cayuga | NY | C | Milliken - Wright Ave 115 kV | NYSEG | 5 | 2022-01-31 |  |  | 04/2025 | 05/2025 | 06/2025
1150 | Moss Ridge Solar 1, LLC | Moss Ridge Solar | 2021-03-16 | 60 | 60 | S | St. Lawrence | NY | E | Colton - Battle Hill 115 kV | NM-NG | 5 | 2021-10-31 |  |  | 08/2023 | 09/2023 | 10/2023
1151 | York Run Solar, LLC | York Run Solar | 2021-03-18 | 90 | 90 | S | Chautauqua | NY | A | Falcon 115 kV | NM-NG | 5 | 2021-11-30 |  |  | 09/2024 | 10/2024 | 11/2024
1153 | Wood Street Battery Storage LLC | Wood Street Battery Storage | 2021-03-22 | 110 | 110 | ES | Putnam | NY | H | Wood Street 115kV | NYSEG | 5 | 2021-10-31 |  |  | 01/2025 | 02/2025 | 04/2025
1155 | CHPE LLC | New Scotland Interconnection | 2021-04-02 | 500 | 500 | DC | Albany | NY | F, J | New Scotland Substation | NYPA/ NM-NG | 1 | 2021-05-31 |  |  | 12/2025 | 12/2025 | 12/2025
1156 | Green Power Energy, LLC | Cody Road Wind Farm | 2021-04-08 | 19.9 | 19.9 | W | Madison | NY | C | Cortland - Fenner 115kV | NM-NG | 3 | 2022-01-31 |  |  | 09/2022 | 09/2022 | 10/2022
1159 | Innisfree Storage LLC | Innisfree Storage | 2021-04-14 | 50 | 52.5 | ES | Suffolk | NY | K | Port Jefferson - Mt. Sinai 69 kV | LIPA | 4 | 2021-06-30 |  |  | 07/2025 | 06/2025 | 07/2025
1160 | Arcade Solar, LLC | Arcade Solar | 2021-04-16 | 75 | 75 | S | Wyoming | NY | A | Freedom 115 kV | Village of Arcade | 5 | 2021-11-30 |  |  | 08/2024 | 09/2024 | 10/2024
1161 | Garnet Energy Center, LLC, | Garnett Battery Storage | 2021-04-20 | 20 | 20 | ES | Cayuga | NY | B | Clay - Pannel 345 KV | NYPA | 4 | 2021-10-31 |  |  | 09/2023 | 08/2023 | 11/2023
1162 | Ontario Valley Solar 1, LLC | Ontario Valley Solar | 2021-04-26 | 312.9 | 312.9 | CR | Jefferson | NY | E | Lyme - Thousand Island 115 kV | NM-NG | 1 | 2021-06-30 |  |  | 11/2025 | 10/2025 | 12/2025
1163 | QMB2 Energy Storage, LLC | QMB2 Energy Storage, LLC | 2021-04-27 | 200 | 200 | ES | Queens | NY | J | Jamaica 138 kV | ConEd | 2 | 2021-06-30 |  |  | 04/2026 | 03/2026 | 05/2026
1164 | Juno Power Management LLC | Glenwood BESS | 2021-05-05 | 75 | 75 | ES | Nassau | NY | K | Glenwood 4YH 138kV | LIPA | 2 | 7/31/21 |  |  | 10/2024 | 10/2024 | 12/2024
1165 | West River Solar | West River Solar | 2021-05-07 | 20 | 20 | S | Saratoga | NY | F | Battenkill - Mohican 115kV | NM-NG | 3 | 2021-11-30 |  |  | 11/2023 | 10/2023 | 12/2023
1166 | NYSERDA | BR Benson Mines Solar | 2021-05-07 | 20 | 20 | S | St. Lawrence | NY | E | Brown's Falls-Newton Falls 34.5kV | NM-NG | 5 | 2022-01-31 |  |  | 10/2023 | 10/2023 | 10/2023
1167 | Clean Path New York LLC | CPNY | 2021-05-11 | 1300 | 1300 | DC | Delaware Queens | NY | E,J | Fraser - Rainey 345kV | NYSEG/ ConEd | 1 | 2022-01-31 |  |  | 06/2026 | N/A | N/A
1169 | Excelsior Energy Center, LLC | Excelsior Battery Storage | 2021-05-11 | 20 | 20 | ES | Genesee | NY | B | New Rochester - Niagara 345kV | NYPA | 4 | 2021-08-31 |  |  | 06/2022 | 08/2022 | 11/2022
1171 | ELP Stuyvesant Solar LLC | ELP Stuyvesant Solar | 2021-05-14 | 20 | 20 | S | Columbia | NY | F | Schodack - Falls Park 115 kV | Transco | 4 | 11/30/21 |  |  | 08/2024 | 08/2024 | 08/2024
1173 | Northland Power US Projects | Christmiller Solar | 2021-05-17 | 20 | 20 | CR | Cattaraugus | NY | A | Dake Hill – Machias 34.5kV | NM-NG | 4 | 7/31/21 |  |  | 09/2023 | 09/2023 | 12/2023
1174 | Boralex US Development | NY48 - Diamond Solar | 2021-05-17 | 60 | 60 | S | Herkimer | NY | E | Porter - Watkins Rd 115kV | NM-NG | 4 | 7/31/21 |  |  | 11/2025 | 10/2025 | 12/2025
1175 | OW Ocean Winds East, LLC | OW Ocean Winds East 1 | 2021-05-18 | 1200 | 1200 | W | Nassau | NY | K | Ruland Rd 138 kV | LIPA | 2 | 1/31/22 |  |  | 09/2029 | 06/2030 | 12/2030
1176 | OW Ocean Winds East, LLC | OW Ocean Winds East 2 | 2021-05-18 | 1200 | 1200 | W | Nassau | NY | K | Valley Stream 138 kV | LIPA | 2 | 7/31/21 |  |  | 09/2029 | 06/2030 | 12/2030
1177 | Oakdale Energy Center, LLC | Oakdale Energy Center | 2021-05-19 | 200 | 200 | S | Tioga | NY | C | Oakdale - Hullsville 230 kV | NYSEG | 4 | 7/31/21 |  |  | 03/2025 | 10/2025 | 11/2025
1178 | Boralex US Development | NY115 - Newport Solar | 2021-05-19 | 130 | 130 | S | Oneida | NY | E | Porter - Deerfield 115kV | NM-NG | 4 | 2021-08-31 |  |  | 11/2025 | 10/2025 | 12/2025
1180 | BPUS Generation Development, LLC | BPUS Generation Development, LLC | 2021-05-20 | 150 | 150 | ES | Putnam | NY | H | Union Valley 115kV | NYSEG | 5 | 2021-11-30 |  |  | 11/2024 | 10/2024 | 12/2024
1181 | Altona Energy Center, LLC | Altona Energy Center | 2021-05-20 | 200 | 200 | S | Clinton | NY | D | Pathnode - Duley 230kV | NYPA | 4 | 7/31/21 |  |  | 03-2025 | 10-2025 | 11-2025
1182 | Boralex US Development | NY128 - Foothills Solar | 2021-05-20 | 40 | 40 | S | Fulton | NY | F | Vails Mills - Northville 69 kV | NM-NG | 4 | 7/31/21 |  |  | 11/2025 | 10/2025 | 12/2025
1183 | Boralex US Development | NY125A - Fort Covington Solar | 2021-05-20 | 250 | 250 | S | Franklin | NY | D | Moses - Willis 230 kV | NYPA | 4 | 2021-08-31 |  |  | 11/2025 | 10/2025 | 12/2025
1184 | Boralex US Development | NY125B - Two Rivers Solar | 2021-05-20 | 200 | 200 | S | St-Lawrence | NY | D | Moses - Willis 230 kV | NYPA | 4 | 2021-08-31 |  |  | 11/2025 | 10/2025 | 12/2025
1185 | Empire Offshore Wind LLC | EI Empire ESS I | 2021-05-21 | 1356 | 1356 | CW | Nassau | NY | K | Barrett 138 kV | LIPA | 4 | 2021-08-31 |  |  | 08/2027 | 06/2027 | 12/2028
1188 | North Seneca Solar Project | North Seneca Solar Project, LLC | 2021-05-27 | 150 | 150 | S | Onondaga | NY | C | Farmington - Elbridge 115kV | NM-NG | 4 | 2021-11-30 |  |  | 08/2025 | 07/2025 | 09/2025
1189 | OW Ocean Winds East, LLC | OW Ocean Winds East 3 | 2021-05-27 | 1600 | 1600 | W | Nassau | NY | K | East Garden City 345 kV | NYPA | 2 | 2021-08-31 |  |  | 09/2029 | 08/2030 | 12/2030
1190 | OW Ocean Winds East, LLC | OW Ocean Winds East 4 | 2021-05-28 | 1600 | 1600 | W | Brooklyn | NY | J | Farragut 345 kV | ConEd | 2 | 2021-08-31 |  |  | 09/2029 | 08/2030 | 12/2030
1191 | Northland Power U.S. Projects | Gunns Corners Solar | 2021-05-31 | 100 | 100 | CR | Jefferson | NY | E | Lyme - Thousand Island 115 kV | NM-NG | 4 | 2021-08-31 |  |  | 09/2024 | 10/2024 | 12/2024
1192 | OW Ocean Winds East, LLC | OW Ocean Winds East 6 | 2021-06-02 | 1600 | 1600 | W | Manhattan | NY | J | West 49th St 345 kV | ConEd | 2 | 2021-08-31 |  |  | 09/2029 | 08/2030 | 12/2030
1193 | OW Ocean Winds East, LLC | OW Ocean Winds East 5 | 2021-06-02 | 1600 | 1600 | W | Queens | NY | J | Rainey 345 kV | ConEd | 2 | 2021-08-31 |  |  | 09/2029 | 08/2030 | 12/2030
1194 | Crane Brook Solar Project | Crane Brook Solar Project, LLC | 2021-06-03 | 150 | 150 | S | Cayuga | NY | C | Sleight Rd - State St 115kV | NM-NG | 4 | 2022-01-31 |  |  | 04/2026 | 05/2026 | 03/2026
1197 | Northland Power U.S. Projects | West River Solar | 2021-06-08 | 100 | 100 | CR | Allegany | NY | B | Line #907 115 kV | RG&E | 4 | 2022-01-31 |  |  | 09/2024 | 10/2024 | 12/2024
1198 | Granada Solar, LLC | Stern Solar | 2021-06-09 | 20 | 20 | S | Renssalear | NY | F | Battenkill - Schaghticoke 115 kV | NM-NG | 4 | 2021-08-31 |  |  | 07/2024 | 06/2024 | 09/2024
1199 | Beacon Wind LLC | EI Steinway 1.1 | 2021-06-09 | 300 | 300 | W | Queens | NY | J | Astoria West 138 kV | ConEd | 4 | 7/31/21 |  |  | 12/2027 | 03/2027 | 11/2027
1200 | Beacon Wind LLC | EI Steinway 2.1 | 2021-06-09 | 300 | 300 | W | Queens | NY | J | Astoria East 138 kV | ConEd | 4 | 7/31/21 |  |  | 12/2027 | 03/2027 | 11/2027
1202 | Calpine Mid-Atlantic Development, LLC | Bethpage Large Battery Energy Storage Project | 2021-06-11 | 24 | 24 | ES | Nassau | NY | K | Grumman 69kV | LIPA | 3 | 2021-12-31 |  |  | 05/2023 | 05/2023 | 06/2023
1203 | EDF Renewables Development, Inc. | Suffragette Solar Energy Center | 2021-06-14 | 70 | 70 | S | Cayuga | NY | C | Hyatt 34.5kV | NYSEG | 4 | 2021-08-31 |  |  | 08/2025 | 08/2025 | 10/2025
1205 | Rocksdrift Energy Center, LLC | Rocksdrift Energy Center | 2021-06-16 | 300 | 300 | S | Herkimer | NY | E | Edic - Princetown 345 kV | NYPA | 4 | 2021-09-30 |  |  | 03/2025 | 10/2025 | 11/2025
1206 | NY Interconnection LLC | NY Interconnection 2 | 2021-06-18 | 1200 | 1200 | DC | Queens | NY | J | Rainey 345kV | ConEd | 4 | 2021-12-31 |  |  | 06/2027 | 06/2027 | 06/2028
1207 | NY Interconnection LLC | NY Interconnection 1 | 2021-06-18 | 1200 | 1200 | DC | New York | NY | J | East 13th St. 345kV | ConEd | 4 | 2021-12-31 |  |  | 06/2027 | 06/2027 | 06/2028
1209 | Equinor Wind US LLC | Battoria | 2021-06-21 | 300 | 300 | ES | Queens | NY | J | Astoria East 138 kV | ConEd | 4 | 2021-09-30 |  |  | 09/2024 | 11/2024 | 12/2024
1210 | Northland Power U.S. Projects | Gunns Corners Solar 2 | 2021-06-22 | 100 | 100 | CR | Jefferson | NY | E | Lyme-Thousand Island 115 kV | NM-NG | 4 | 2021-08-31 |  |  | 12/2024 | 12/2024 | 12/2024
1211 | Renesola Power Holdings LLC | Hardscrabble Solar LLC | 2021-06-25 | 19.9 | 19.9 | CR | Clinton | NY | D | Highfalls-Mill 46 kV | NYSEG | 4 | 2021-08-31 |  |  | 12/2024 | 12/2024 | 12/2024
1212 | ReneSola Power Holdings LLC | Roosevelt Solar LLC | 2021-06-25 | 19.9 | 19.9 | CR | St. Lawrence | NY | D | Akwesasne 34.5kV | NM-NG | 4 | 2021-08-31 |  |  | 12/2024 | 12/2024 | 12/2024
1213 | Petawatt Holdings, Inc. | St Lawrence Data and Agricultural Center | 2021-06-28 | 200 | 200 | L | St. Lawrence | NY | D | Dennison 115kV | NM-NG | 4 | 2021-12-31 |  |  | 01/2022 | N/A | N/A
1217 | ReneSola Power Holdings LLC | New Boston Solar LLC | 2021-07-09 | 49.9 | 49.9 | CR | Madison | NY | C | Teal - Oneida 115kV | NM-NG | 4 | 2021-11-30 |  |  | 12/2025 | 12/2025 | 12/2025
1219 | Nexamp Solar | 74972 Cicero | 2021-07-26 | 20 | 20 | S | Oneida | NY | C | Transmission line to the east of the property close to Interstate 81. | NM-NG | 2 | 2021-10-31 |  |  | 08/2022 | 08/2022 | 08/2022
1221 | Anbaric Development Partners | Long Island Storage Center I | 2021-07-26 | 50 | 50 | ES | Suffolk | NY | K | Brookhaven 138kV | LIPA | 2 | 2021-10-31 |  |  | 01/2025 | 02/2025 | 05/2025
1222 | Anbaric Development Partners | Long Island Storage Center II | 2021-07-26 | 100 | 100 | ES | Suffolk | NY | K | Brookhaven 138kV | LIPA | 2 | 2021-10-31 |  |  | 01/2025 | 02/2025 | 05/2025
1223 | Fresh Air Energy II | Moffitt ESC | 2021-07-28 | 100 | 100 | ES | Suffolk | NY | K | Watson - Brightwaters 69kV | LIPA | 4 | 2021-10-31 |  |  | 10/2025 | 09/2025 | 11/2025
1226 | Nexamp Solar | 47763 Cayuta | 2021-08-04 | 20 | 20 | S | Schuyler | NY | C | Montour Falls - Ridge Rd 34.5kV | NYSEG | 4 | 2021-11-30 |  |  | 09/2023 | 09/2023 | 09/2023
1227 | Nexamp Solar | 18405 Scotch Ridge | 2021-08-04 | 20 | 20 | S | Schenectady | NY | F | Rotterdam - Schoharie 69kV | NM-NG | 4 | 2022-01-31 |  |  | 08/2022 | 08/2022 | 08/2022
1228 | SWEB Development USA, LLC | Cuba Wind Project | 2021-08-12 | 86.5 | 86.5 | W | Alleghany | NY | A | Homer Hill – Andover 115 kV | NM-NG | 2 | 2021-12-31 |  |  | 10/2024 | 12/2024 | 12/2024
1229 | Stonewall Solar, LLC | Stonewall Solar, LLC. | 2021-08-16 | 145 | 145 | S | Delaware | NY | E | Colliers - Delhi 115KV | NYSEG | 1 | 2021-08-31 |  |  | 11/2024 | 08/2024 | 12/2024
1230 | ConnectGen Erie-Wyoming LLC | Erie-Wyoming County Solar II | 2021-08-17 | 20 | 50 | S | Erie | NY | C | Stolle Rd - High Sheldon 230kV | NYSEG | 4 | 2021-11-30 |  |  | 11/2025 | 10/2025 | 12/2025
1231 | ConnectGen Montgomery County LLC | Mill Point Solar II | 2021-08-17 | 100 | 100 | S | Montgomery | NY | E | New Scotland - Marcy 345kV | NM-NG | 4 | 2021-10-31 |  |  | 11/2024 | 10/2024 | 12/2024
1233 | ACE Development Company | Maplewood Energy Storage | 2021-08-20 | 250 | 250 | ES | Albany | NY | F | Maplewood 115 kV | NM-NG | 2 | 2021-11-30 |  |  | 09/2023 | 06/2023 | 12/2023
1234 | ACE Development Company | Horseblock Energy Storage | 2021-08-20 | 100 | 100 | ES | Suffolk | NY | K | West Yaphank 69 kV | LIPA | 2 | 2021-11-30 |  |  | 09/2023 | 06/2023 | 12/2023
1235 | ACE Development Company | Peconic Energy Storage | 2021-08-20 | 100 | 100 | ES | Suffolk | NY | K | Holbrook - North Bellport 69 kV | LIPA | 1 | 2021-10-31 |  |  | 06/2023 | 09/2023 | 12/2023
1236 | Gravel Road Solar, LLC | Gravel Road Solar | 2021-08-23 | 125 | 125 | S | Seneca | NY | C | Hook Rd-Elbridge, Mortimer-Elbridge 115 kV | NM-NG | 4 | 2021-11-30 |  |  | 08/2025 | 08/2025 | 10/2025
1237 | Sugar Maple Solar | Sugar Maple Energy Storage | 2021-08-24 | 20 | 20 | ES | Jefferson | NY | E | North Carthage-Taylorville, Black River-Taylorville | NM-NG | 4 | 2021-12-31 |  |  | 06/2023 | 09/2023 | 12/2023
1238 | ConnectGen Cayuga County LLC | Harvest Hills Solar 2 | 2021-08-25 | 100 | 100 | S | Cayuga County | NY | C | Wright Avenue - Cayuga 115kV | NYSEG | 4 | 2021-11-30 |  |  | 11/2025 | 10/2025 | 12/2025
1239 | NY Interconnection LLC | NY Interconnection 3 | 2021-09-02 | 1200 | 1200 | DC | New York | NY | J | Goethals - Fresh Kills 345kV | ConEd | 1 | 2021-11-30 |  |  | 06/2027 | 06/2027 | 06/2028
1240 | Astoria Generating Company, L.P. | Gowanus Bay Energy Storage 1 | 2021-09-03 | 100 | 100 | ES | Kings | NY | J | Gowanus 138 kV | ConEd | 1 | 2021-09-30 |  |  | 04/2025 | 04/2025 | 05/2025
1241 | Astoria Generating Company, L.P. | Gowanus Bay Energy Storage 2 | 2021-09-03 | 49.2 | 49.2 | ES | Kings | NY | J | Gowanus 138 kV | ConEd | 1 | 2021-09-30 |  |  | 04/2025 | 04/2025 | 05/2025
1243 | Astoria Generating Company, L.P. | Whale Square Energy Storage 2 | 2021-09-03 | 95.7 | 95.7 | ES | Kings | NY | J | Greenwood 138kV | ConEd | 4 | 2021-12-31 |  |  | 04/2025 | 04/2025 | 05/2025
1244 | Astoria Generating Company, L.P. | Whale Square Energy Storage 3 | 2021-09-03 | 49.2 | 49.2 | ES | Kings | NY | J | Greenwood 138 kV | ConEd | 4 | 2021-12-31 |  |  | 04/2025 | 04/2025 | 05/2025
1245 | CBB PARK LLC | CBB PARK | 2021-09-13 | 50 | 50 | ES | Dutchess | NY | G | Pleasant Valley 115 Kv | CHG&E | 1 | 2021-11-30 |  |  | 09/2023 | 09/2023 | 09/2023
1246 | Hanwha Q CELLS USA | Amber Solar and Storage | 2021-09-14 | 232 | 232 | S | St. Lawrence County | NY | D | Massena 230 kV | NYPA | 1 | 2021-11-30 |  |  | 06/2025 | 06/2025 | 06/2025
1247 | Hanwha Q CELLS USA | Emerald Solar and Storage | 2021-09-14 | 174 | 174 | S | Genesee | NY | B | Lapp - East Batavia 115 kV | NM-NG | 2 | 2021-12-31 |  |  | 06/2025 | 06/2025 | 06/2025
1248 | Hanwha Q CELLS USA | Garnet Solar and Storage | 2021-09-14 | 174 | 174 | S | Orleans | NY | B | Sour Springs 115 kV | NM-NG | 1 | 2021-10-31 |  |  | 06/2025 | 06/2025 | 06/2025
1249 | Hanwha Q CELLS USA | Ruby Solar and Storage | 2021-09-14 | 232 | 232 | S | Ontario | NY | C | Farmington - Elbridge 115 kV | NM-NG | 1 | 2021-10-31 |  |  | 06/2025 | 06/2025 | 06/2025
1250 | Hanwha Q CELLS USA | Sapphire Solar and Storage | 2021-09-14 | 232 | 232 | S | Monroe | NY | B | Meyer - South Perry 115 kV | NM-NG | 1 | 2022-01-31 |  |  | 06/2025 | 06/2025 | 06/2025
1251 | Hanwha Q CELLS USA | Topaz Solar and Storage | 2021-09-14 | 232 | 232 | S | Rensselaer | NY | F | Knickerbocker 345 kV | Transco | 2 | 2021-12-31 |  |  | 06/2025 | 06/2025 | 06/2025
1254 | Barrett Hempstead Battery Storage | Barrett Hempstead Battery Storage | 2021-09-22 | 40 | 40 | ES | Nassau | NY | K | Barrett - Long Beach 33 kV | LIPA | 1 | 2021-10-31 |  |  | 08/2024 | 09/2024 | 11/2024
1255 | Holtsville Brookhaven Battery Storage | Holtsville Brookhaven Battery Storage | 2021-09-22 | 80 | 80 | ES | Suffolk | NY | K | West Yaphank - North Bellport | LIPA | 4 | 2021-12-31 |  |  | 08/2024 | 09/2024 | 11/2024
1256 | Canal Southampton Battery Storage | Canal Southampton Battery Storage | 2021-09-22 | 100 | 100 | ES | Suffolk | NY | K | Canal Substation 69 kV | LIPA | 1 | 2021-10-31 |  |  | 08/2024 | 09/2024 | 11/2024
1257 | Edwards Calverton Battery Storage | Edwards Calverton Battery Storage | 2021-09-22 | 60 | 60 | ES | Suffolk | NY | K | Edwards Avenue 138 kV | LIPA | 4 | 2021-12-31 |  |  | 08/2024 | 09/2024 | 11/2024
1258 | Oriden LLC | Deerpark Energy Storage | 2021-09-22 | 50 | 50 | ES | Orange | NY | G | Deerpark 69 kV | O&R | 1 | 2021-10-31 |  |  | 11/2024 | 10/2024 | 12/2024
1260 | BW Solar Holding | St. Regis River | 2021-09-23 | 85 | 85 | S | St. Lawrence | NY | D, E | Dennison - Colton Line 115kV | NM-NG | 1 | 2021-11-30 |  |  | 10/2024 | 08/2024 | 12/2024
1261 | Empire Offshore Wind LLC | EI Sunset Park 2 | 2021-09-24 | 864 | 864 | W | Kings | NY | J | Gowanus 345 kV | ConEd | 1 | 2021-11-30 |  |  | 11/2025 | 04/2025 | 12/2026
1265 | Liberty Renewables Inc. | Monticello Hills Wind | 2021-09-28 | 30.7 | 31.5 | W | Otsego | NY | E | West Winfield - Richfield Springs 46 kV | NYSEG | 4 | 2021-12-31 |  |  | 10/2025 | 11/2025 | 12/2025
1271 | LS Power Grid New York Corporation I | Atlantic Gateway | 2021-10-07 | N/A | N/A | AC | Nassau,Suffolk,Westchester | NY | H, K | Barrett 138 kV, Ruland Road 138 kV, Millwood 345 kV | LIPA/ConEd | 1 | 2021-10-31 |  |  | 12/2026 | N/A | N/A
1272 | Equinor Wind US LLC | EI Sunset BESS | 2021-10-08 | 100 | 100 | ES | Kings | NY | J | Greenwood South 138 kV | ConEd | 1 | 2021-11-30 |  |  | 02/2024 | 01/2024 | 03/2024
1273 | Anbaric Development Partners,LLC | Downstate Clean Powerlink | 2021-10-08 | N/A | N/A | AC | Nassau, Suffolk, Bronx, Westchester | NY | I,J,K | Mott Haven, Sprainbrook, Dunwoodie, Ruland Road, Newbridge, East Garden City, Syosset, Shore Road | ConEd/LIPA | 1 | 2021-10-31 |  |  | 12/2028 | N/A | N/A
1274 | New York Power Authority / New York Transco LLC. | Propel NY Energy - Base Solution 2 | 2021-10-08 | N/A | N/A | AC | Nassau, Queens, Bronx, Westchester | NY | I,J,K | New 345kV New Rochelle; New/Existing 345/138kV Shore; New/Existing 345/138kV Ruland; New/Existing 345/138kV Barrett; Existing 345/138kV EGC; Existing 345kV Tremont, Sprain Brook, and Rainey; Existing 138kV Syosset, Holbrook, and Lake Success. | LIPA/ConEd/ NYPA | 1 | 2021-10-31 |  |  | 12/2028 | N/A | N/A
1275 | New York Power Authority / New York Transco LLC. | Propel NY Energy - Base Solution 4 | 2021-10-08 | N/A | N/A | AC | Nassau, Suffolk, Queens, Bronx | NY | J, K | New 345 Barrett Substation; Existing 345kV Tremont Substation; Existing 138kV Ruland Road Substation; Existing 138kV Shore Road Substation; Existing 138kV East Garden City Substation | ConEd/LIPA/ NYPA | 1 | 2021-10-31 |  |  | 12/2028 | N/A | N/A
1276 | New York Power Authority / New York Transco LLC. | Propel NY Energy - Base Solution 1 | 2021-10-08 | N/A | N/A | AC | Nassau, Queens, Bronx, and Westchester | NY | I,J,K | 345kV New Rochelle; New/existing 345/138kV Shore; New/existing 345/138kV Ruland; New 345kV Barrett; Existing 345kV Tremont; Existing 345kV Sprain Brook; Existing 138kV Holbrook; Existing 138kV Newbridge; New/Existing 345/138kV EGC; Existing 345kV Rainey | LIPA/ConEd/ NYPA | 1 | 2021-10-31 |  |  | 12/2028 | N/A | N/A
1277 | New York Power Authority / New York Transco LLC. | Propel NY Energy - Base Solution 3 | 2021-10-09 | N/A | N/A | AC | Nassau, Queens, Bronx, Westchester | NY | I,J,K | New 345kV substation at New Rochelle, Shore Road, Ruland Road, and Barrett; Existing 345kV substation at Tremont, Sprain Brook, Rainey, and East Garden City; Existing 138kV substation at Ruland Road, Shore Road, Holbrook, New Bridge, and East Garden City. | LIPA/ConEd/ NYPA | 1 | 2021-10-31 |  |  | 12/2028 | N/A | N/A
1278 | NextEra Energy Transmission New York, Inc | New York Renewable Connect - Core 1 | 2021-10-10 | N/A | N/A | AC | Nassau, Suffolk, Westchester | NY | I,J,K | East Garden City 345 kV, Sprain Brook 345 kV, Dunwoodie 345 kV, Jamaica 138 kV, Valley Stream 138 kV | ConEd/LIPA | 1 | 2021-10-31 |  |  | 12/2030 | N/A | N/A
1279 | NextEra Energy Transmission New York, Inc | New York Renewable Connect - Core 2 | 2021-10-10 | N/A | N/A | AC | Nassau, Suffolk, Westchester | NY | I,J,K | East Garden City, Ruland Road, Sprain Brook, Dunwoodie, Jamaica, Valley Stream, Farragut | ConEd/LIPA | 1 | 2021-10-31 |  |  | 12/2030 | N/A | N/A
1280 | NextEra Energy Transmission New York, Inc | New York Renewable Connect - Core 3 | 2021-10-10 | N/A | N/A | AC | Nassau, Suffolk, Westchester | NY | I,J,K | East Garden City, Ruland Road, Sprain Brook, Dunwoodie, Jamaica, Valley Stream, Farragut, Northport, Pilgrim | ConEd/LIPA | 1 | 2021-10-31 |  |  | 12/2030 | N/A | N/A
1281 | NextEra Energy Transmission New York, Inc | New York Renewable Connect - Core 4 | 2021-10-10 | N/A | N/A | AC | Nassau, Suffolk, Westchester | NY | I,J,K | East Garden City, Ruland Road, Sprain Brook, Dunwoodie, Jamaica, Valley Stream, Farragut, Northport, Pilgrim | ConEd/LIPA | 1 | 2021-10-31 |  |  | 12/2030 | N/A | N/A
1282 | NextEra Energy Transmission New York, Inc | New York Renewable Connect - Core 5 | 2021-10-10 | N/A | N/A | AC | Nassau, Suffolk, Westchester | NY | I,J,K | East Garden City, Ruland Road, Sprain Brook, Dunwoodie, Jamaica, Valley Stream, Northport | ConEd/LIPA | 1 | 2021-10-31 |  |  | 12/2030 | N/A | N/A
1283 | NextEra Energy Transmission New York, Inc | New York Renewable Connect - Core 6 | 2021-10-10 | N/A | N/A | AC | Nassau, Queens, Suffolk, Westchester | NY | I,J,K | East Garden City, Ruland Road, Sprain Brook, Dunwoodie, Jamaica, Valley Stream, Northport, Pilgrim | ConEd/LIPA | 1 | 2021-10-31 |  |  | 12/2030 | N/A | N/A
1284 | NextEra Energy Transmission New York, Inc | New York Renewable Connect - Core 7 | 2021-10-10 | N/A | N/A | AC | Nassau, Suffolk, Westchester | NY | H,I,J,K | East Garden City, Ruland Road, Sprain Brook, Dunwoodie, Jamaica, Valley Stream, Northport, Pilgrim, Buchanan | ConEd/LIPA | 1 | 2021-10-31 |  |  | 12/2030 | N/A | N/A
1285 | NextEra Energy Transmission New York, Inc | New York Renewable Connect - Enhanced 1 | 2021-10-10 | N/A | N/A | AC | Nassau, Suffolk, Westchester | NY | H,I,J,K | East Garden City, Ruland Road, Sprain Brook, Dunwoodie, Farragut, Holbrook, Jamaica, Valley Stream, Northport, Pilgrim, Buchanan, Barrett | ConEd/LIPA | 1 | 2021-10-31 |  |  | 12/2030 | N/A | N/A
1286 | NextEra Energy Transmission New York, Inc | New York Renewable Connect - Enhanced 2 | 2021-10-10 | N/A | N/A | AC | Nassau, Suffolk, Westchester | NY | G,H,I,J,K | East Garden City, Ruland Road, Sprain Brook, Dunwoodie, Farragut, Holbrook, Jamaica, Valley Stream, Northport, Pilgrim, Buchanan, Ramapo | O&R/ConEd/ LIPA | 1 | 2021-10-31 |  |  | 12/2030 | N/A | N/A
1287 | NextEra Energy Transmission New York, Inc | New York Renewable Connect - Plus 3 | 2021-10-10 | N/A | N/A | AC | Nassau, Suffolk, Westchester | NY | I,J,K | East Garden City, Ruland Road, Sprain Brook, Dunwoodie, Jamaica, Valley Stream, Northport, Pilgrim | ConEd/LIPA | 1 | 2021-10-31 |  |  | 12/2030 | N/A | N/A
1288 | Clean Path New York LLC | CPNY-X | 2021-10-11 | 1300 | 1300 | DC | Delaware, Queens | NY | E,J | Fraser 345kV-Sending, Rainey 345kV-Receiving | NYSEG/ConEd | 4 | 2021-12-31 |  |  | 12/2026 | 12/2026 | 06/2027
1289 | New York Power Authority / New York Transco LLC. | Propel NY Energy - Alternate Solution 5 | 2021-10-11 | N/A | N/A | AC | Nassau, Queens, Bronx, Westchester | NY | I,J,K | New 345kV substations: New Rochelle, Shore Road, Ruland Road, Barrett, East Garden City; Existing 345kV substations: Tremont, Sprain Brook, Rainey; Existing 138kV substations: Ruland Road, Shore Road, Holbrook, New Bridge, East Garden City, Syosset, North | LIPA/ConEd/ NYPA | 1 | 2021-10-31 |  |  | 12/2028 | N/A | N/A
1290 | New York Power Authority / New York Transco LLC. | Propel NY Energy - Alternate Solution 6 | 2021-10-11 | N/A | N/A | AC | Nassau, Queens, Bronx, Westchester | NY | I,J,K | New 345kV substations: New Rochelle, Eastern Queens, Shore Rd, Ruland Rd, Barrett, EGC; Existing 345kV substations: Tremont, Sprain Brook, Dunwoodie, Rainey; Existing 138kV substations: Ruland Rd, Shore Rd, Holbrook, New Bridge, EGC, Syosset, Northport | LIPA/ConEd/ NYPA | 1 | 2021-10-31 |  |  | 12/2030 | N/A | N/A
1291 | New York Power Authority / New York Transco LLC. | Propel NY Energy - Alternate Solution 7 | 2021-10-11 | N/A | N/A | AC | Nassau, Queens, Bronx, Westchester | NY | I,J,K | New 345kV: New Rochelle, Shore Rd, Ruland Rd, Eastern Queens, Barrett, Northport; HVDC at Sprainbrook & Northport; Exist 345kV: EGC, Tremont, Sprain Brook, Dunwoodie; Exist 138kV: Ruland Rd, Shore Rd, Syosset, Holbrook, Barrett, EGC, Lake Success | LIPA/ConEd/ NYPA | 1 | 2021-10-31 |  |  | 12/2030 | N/A | N/A
1292 | Liberty Renewables Inc. | Hemlock Hollow Wind | 2021-10-20 | 89.1 | 89.1 | W | Cattaraugus | NY | A | Homer Hill - Dugan Rd 115 kV | NM-NG | 1 | 2021-12-31 |  |  | 04/2026 | 05/2026 | 06/2026
1293 | ACE DevCo NC | White Springs Solar | 2021-10-22 | 20 | 20 | S | Ontario | NY | C | Haley Road 115 kV Substation | NYSEG | 4 | 2021-12-31 |  |  | 07/2024 | 09/2024 | 11/2024
1294 | ACE DevCo NC | Moran Solar | 2021-10-22 | 20 | 20 | S | Fulton | NY | F | Inghams - Center Street 115 kV | NM-NG | 1 | 2021-12-31 |  |  | 09/2024 | 07/2024 | 11/2024
1295 | Galehead Development, LLC | Putnam Mountain Solar | 2021-10-26 | 40 | 40 | S | Washington | NY | F | Whitehall - Cedar 115 kV | NM-NG | 1 | 2021-11-30 |  |  | 04/2025 | 04/2025 | 05/2025
1299 | KCE NY 33, LLC | KCE NY 33 | 2021-10-29 | 20 | 20 | ES | Broome | NY | C | Langdon 34.5kV Substation | NYSEG | 1 | 2021-12-31 |  |  | 12/2025 | 10/2025 | 12/2025
1301 | Pine Barrens Storage LLC | Pine Barrens Storage | 2021-11-09 | 75 | 75 | ES | Suffolk | NY | K | Brookhaven 138 kV Substation | LIPA | 1 | 2021-12-31 |  |  | 06/2025 | 06/2025 | 07/2025
1305 | Hanwha Q CELLS USA | Crystal Storage Project | 2021-11-12 | 198.8 | 198.8 | ES | Seneca | NY | C | Hyatt Rd 115 kV substation | NYSEG | 1 | 2021-12-31 |  |  | 12/2025 | 06/2025 | 12/2025
1306 | Hanwha Q CELLS USA | Opal Storage Project | 2021-11-12 | 226.1 | 226.1 | ES | Orange | NY | G | East Walden 115 kV substation | CHG&E | 1 | 2021-12-31 |  |  | 12/2025 | 06/2025 | 12/2025
1310 | QMB1 Energy Storage | QMB1 Energy Storage | 2021-12-08 | 300 | 300 | ES | Nassua | NY | K | Ruland Rd. 138 kV | LIPA | 1 | 2021-12-31 |  |  | 11/2025 | 10/2025 | 12/2025
1311 | Bronx Shores Energy Storage | Bronx Shores Energy Storage | 2021-12-08 | 300 | 300 | ES | Bronx | NY | J | Mott Haven 138 kV | ConEd | 1 | 2021-12-31 |  |  | 11/2025 | 10/2025 | 12/2025
| Number of new projects during January |  | 6
| Number of new projects year to date |  | 6
| Number withdrawn during January |  | 7
| Number withdrawn year to date |  | 7
NOTES: | ● The column labeled 'SP' refers to the maximum summer megawatt electrical output. The column labeled 'WP' refers to the maximum winter megawatt electrical output.
● Type / Fuel. Key: ST=Steam Turbine, CT=Combustion Turbine, CC=Combined Cycle, CS= Steam Turbine & Combustion Turbine, H=Hydro, PS=Pumped Storage, W=Wind, NU=Nuclear, NG=Natural Gas, M=Methane, SW=Solid Waste, S=Solar, Wo=Wood, F=Flywheel ES=Energy Storage, O=Oil, C=Coal, D=Dual Fuel, AC=AC Transmission,
DC=DC Transmission, L=Load, FC=Fuel Cell, CW=CSR - ES + Wind, CR=CSR - ES + Solar,
● The column labeled 'Z' refers to the zone
● The column labeled 'S' refers to the status of the project in the NYISO's LFIP. Key: 1=Scoping Meeting Pending, 2=FES Pending, 3=FES in Progress, 4=SRIS/SIS Pending, 5=SRIS/SIS in Progress, 6=SRIS/SIS Approved, 7=FS Pending, 8=Rejected Cost Allocation/Next FS Pending, 9=FS in Progress, 10=Accepted Cost Allocation/IA in Progress,
11=IA Completed, 12=Under Construction, 13=In Service for Test, 14=In Service Commercial, 0=Withdrawn
● Availability of Studies Key: None=Not Available, FES=Feasibility Study Available, SRIS=System Reliability Impact Study Available, FS=Facilities Study and/or ATRA Available
● FS Complete/SGIA Tender refers to the Attachment X milestone used to apply the 4-year COD limitation.
● Proposed in-service dates and Commercial Operation Dates (COD) are shown in format Year/Qualifier, where Qualifier may indicate the month, season, or quarter.
DPS/State - SIR Interconnection Queue (for Projects not subject to the NYISO process):
http://www3.dps.ny.gov/W/PSCWeb.nsf/All/286D2C179E9A5A8385257FBF003F1F7E?OpenDocument

## Withdrawn
Queue Pos. | Owner/Developer | Project Name | Date of IR | SP (MW) | WP (MW) | Type/ Fuel | County | State | Z | Interconnection Point | Utility | S | Last Update | Availability of Studies | FS Complete/ SGIA Tender | Proposed In-Service | Proposed Initial-Sync | Proposed COD
0005 | Sithe Energies | Torne Valley Station | 1999-01-28 | 860 | [5 empty] | Ramapo | CONED | 0
0006 | Sunset Energy Fleet LLC | Sunset Energy Fleet | 1999-02-17 | 520 | [5 empty] | Gowanus | CONED | 0
0007 | American National Power | Ramapo Energy | 1999-02-23 | 1100 | [5 empty] | Ramapo | CONED | 0
0008 | Columbia Electric Corp. | Grassy Point | 1999-02-23 | 1100 | [5 empty] | West Haverstraw | CONED | 0
0009 | Millennium Power Gen Co. LLC | Millennium 1 | 1999-02-23 | 160 | [5 empty] | Hell Gate/Bruckner | CONED | 0
0010 | Millennium Power Gen Co. LLC | Millennium 2 | 1999-02-23 | 320 | [5 empty] | Hell Gate/Bruckner | CONED | 0
0012 | East Coast Power, LLC | East Coast Power Linden | 1999-03-25 | 70 |  | ST | Richmond-NJ | NY | J | Goethals 345kV | CONED | 0 | 2008-07-10
0013 | East Coast Power, LLC | Linden 7 | 1999-03-25 | 100 |  | ST | Richmond-NJ | NY | J | Goethals 345kV | CONED | 0 | 2008-07-10
0014 | East Coast Power, LLC | Linden Plant Improvement | 1999-03-25 | 20 |  | ST | Richmond-NJ | NY | J | Goethals 345kV | CONED | 0 | 2008-07-10
0015 | AEP Resources Service Corp. | CT-LI AC Tie-line | 1999-04-13 | 600 | [5 empty] | Shoreham, Long Island | LIPA | 0
0016 | Oak Point Property, LLC | Oak Point Yard | 1999-04-15 | 500 |  | CC | Bronx | NY | J | Hell Gate/Bruckner 138kV | CONED | 0 | 2008-07-10
0019 | NYC Energy LLC | NYC Energy LLC | 1999-05-07 | 79.9 |  | CT | Kings | NY | J | Kent Ave 138kV | CONED | 0 | 2010-09-30
0020 | KeySpan Energy, Inc. | Spagnoli Road CC Unit | 1999-05-17 | 250 |  | CC | Suffolk | NY | K | Spagnoli Road 138kV | LIPA | 0 | 2012-03-01
0021 | KeySpan Energy, Inc. | Shoreham Gen Station | 1999-05-17 | 250 | [5 empty] | Shoreham | LIPA | 0
0022 | Calpine Eastern Corporation | Wawayanda Energy Center | 1999-06-10 | 500 |  | CC | Orange | NY |  | Coop Corn-Rock Tav Lines 345kV | NYPA | 0 | 2006-06-26
0023 | Calpine Eastern Corporation | Sullivan County Power Project | 1999-06-25 | 1080 |  | CC | Sullivan | NY |  | Coop Corn-Rock Tav Lines 345kV | NYPA | 0 | 2006-03-31
0024 | Reliant Energy | Astoria Repowering-Phase 1 | 1999-07-13 | 367 |  | CC | Queens | NY |  | Astoria 138kV | CONED | 0 | 2006-08-09
0026 | Twin Tier Power, LLC | Twin Tier Power | 1999-08-20 | 520 | [5 empty] | Watercure-Oakdale 31 Line | NYSEG | 0
0027 | ENRON | Far Rockaway Barge | 1999-09-08 | 60 | [5 empty] | Far Rockaway | LIPA | 0
0028 | KeySpan Energy, Inc. | Spagnoli Road GT Unit | 1999-09-08 | 79.9 | [5 empty] | Spagnoli Road | LIPA | 0
0029 | Mirant | Bowline Point Unit 3 | 1999-10-13 | 750 |  | CC | Rockland | NY |  | W. Haverstraw 345kV | CONED | 0 | 2006-07-10
0030 | Sithe Energies | Heritage Station | 1999-10-29 | 800 | [5 empty] | Independence (Oswego) | NM-NG | 0
0032 | American National Power | Brookhaven Energy | 1999-11-22 | 580 |  | CC | Suffolk | NY |  | Holbrook-Brookhaven 138kV | LIPA | 0
0033 | Glenville Energy Park, LLC | Glenville Energy Park | 1999-11-30 | 540 |  | CC | Schenectady | NY | F | Rotterdam 230kV | NM-NG | 0 | 2008-07-10
0034 | York Research Corp. | North First Street | 2000-01-11 | 500 | [5 empty] | Con Ed System | CONED | 0
0035 | Gotham Power Zerega, LLC | Gotham Power - Bronx I | 2000-01-12 | 79.9 |  | CT | Bronx | NY | J | Parkchester/Tremont 138kV | CONED | 0 | 2008-07-10
0036 | Boundless Energy, LLC | Project Neptune DC NB-NYC | 2000-01-21 | 1200 |  | DC | Kings | NY | J | Farragut 345kV | CONED | 0 | 2008-07-10
0037 | Caithness Energy, LLC | Kitchen | 2000-01-28 | 750 | [5 empty] | Riverh'd-Brookh'n-Holb'k | LIPA | 0
0038 | KeySpan Energy, Inc. | Far Rochaway Gen Ext. | 2000-02-01 | 79 | [5 empty] | Far Rockaway | LIPA | 0
0039 | KeySpan Energy, Inc. | E. F. Barrett Gen Ext | 2000-02-01 | 79 | [5 empty] | Barrett | LIPA | 0
0040 | KeySpan Energy, Inc. | Riverhead Gen Station | 2000-02-01 | 79 | [5 empty] | Riverhead | LIPA | 0
0041 | KeySpan Energy, Inc. | Southampton Gen Ext. | 2000-02-01 | 79 | [5 empty] | Southampton | LIPA | 0
0042 | PP&L Global, Inc. | Holbrook Energy | 2000-02-01 | 300 | [5 empty] | Holbrook | LIPA | 0
0043 | PP&L Global, Inc. | PPL Kings Park | 2000-02-01 | 300 | [5 empty] | Pilgrim | LIPA | 0
0044 | PP&L Global, Inc. | Ruland Energy | 2000-02-01 | 300 | [5 empty] | Ruland Road | LIPA | 0
0045 | PP&L Global, Inc. | Freeport Energy | 2000-02-01 | 100 | [5 empty] | Freeport | LIPA | 0
0046 | PP&L Global, Inc. | Brookhaven Energy | 2000-02-03 | 300 | [5 empty] | Brookhaven | LIPA | 0
0047 | GenPower, LLC | GenPower DC Tie-line | 2000-02-09 | 800 | [5 empty] | West 49th Sreet | CONED | 0
0048 | PP&L Global, Inc. | PPL Kings Park Ext. | 2000-02-10 | 300 | [5 empty] | Pilgrim | LIPA | 0
0049 | PP&L Global, Inc. | Brookhaven Energy Ext. | 2000-02-10 | 300 | [5 empty] | Brookhaven | LIPA | 0
0050 | AES Long Island, LLC | AES Smithtown Gen | 2000-02-10 | 510 | [5 empty] | LIPA System | LIPA | 0
0051 | KeySpan Energy, Inc. | Wading River Gen Ext. | 2000-02-15 | 150 | [5 empty] | Wading River | LIPA | 0
0052 | NIMO/Black River Power | Fort Drum Gen Exp. | 2000-03-06 | 50 | [5 empty] | Fort Drum | NM-NG | 0
0053 | TransEnergie US, Ltd | CT-Ruland, LI DC Tie | 2000-03-07 | 300 | [5 empty] | Ruland Road | LIPA | 0
0054 | TransEnergie US, Ltd | CT-Pilgrim, LI DC Tie | 2000-03-07 | 300 | [5 empty] | Pilgrim | LIPA | 0
0056 | 1st Rochdale Coop Group | Gotham Power/Brooklyn | 2000-03-17 | 79 | [5 empty] | Kent Ave | CONED | 0
0057 | Flat Rock Windpower, LLC | Flat Rock Windpower | 2000-03-21 | 100 |  | W |  |  |  | Lowville-Boonville | NM-NG | 0
0058 | Mirant | Lovett #3 Repowering | 2000-03-23 | 180 | [5 empty] | Lovett | CONED | 0
0059 | Mirant | Hillburn Unit #2 | 2000-03-23 | 79.9 | [5 empty] | Hillburn | CONED | 0
0060 | Mirant | Hillburn #2 Conversion | 2000-03-23 | 40 | [5 empty] | Hillburn | CONED | 0
0061 | GTM Energy, LLC | Greenpoint Energy Park | 2000-04-19 | 500 | [5 empty] | Rainey-Farragut Lines | CONED | 0
0062 | Project Orange Associates, LP | Project Orange | 2000-05-08 | 420 | [5 empty] | Temple St. | NM-NG | 0
0063 | Lewis Staley Associates, Inc. | LSA Station A | 2000-05-11 | 650 | [5 empty] | Homer City-Stolle Rd Line | NYSEG | 0
0064 | Lewis Staley Associates, Inc. | LSA Station B | 2000-05-12 | 600 | [5 empty] | Dunkirk-Gardenville Line | NM-NG | 0
0065 | Fortistar-Lockport Merchant | Lockport II Gen Station | 2000-05-15 | 79.9 |  | CT | Niagara | NY | A | Harrison Station 115kV | NYSEG | 0 | 2008-07-10
0067 | Titan Development, LLC | Wallkill Energy | 2000-06-21 | 1080 | [5 empty] | Coop Corn-Rock Tav Lines | NYPA | 0
0068 | PP&L Global, Inc. | Ruland Energy Ext. | 2000-06-23 | 300 | [5 empty] | Ruland Road | LIPA | 0
0070 | Reliant Energy | Astoria Repowering-Phase 2 | 2000-08-18 | 173 |  | CT | Queens | NY |  | Astoria 138kV | CONED | 0 | 2006-08-09
0071 | Mill Creek Wind Plant, LLC | Mill Creek Wind Plant | 2000-09-08 | 50 | [5 empty] | Lowville | NM-NG | 0
0072 | Fortistar Power Marketing, LLC | Island Gen. Station | 2000-09-08 | 79.9 | [5 empty] | Fresh Kills | CONED | 0
0073 | Fortistar Power Marketing, LLC | Island Gen. Station #2 | 2000-09-08 | 500 | [5 empty] | Fresh Kills | CONED | 0
0074 | FPL Energy, LLC | Oceanside Energy Center | 2000-10-10 | 330 | [5 empty] | Barrett | LIPA | 0
0075 | 1st Rochdale Coop Group | Gotham Power - Bronx II | 2000-10-17 | 79 | [5 empty] | Hell Gate/Bruckner | CONED | 0
0076 | Calpine Eastern Corporation | Waterford | 2000-10-30 | 530 |  | CT | Saratoga | NY |  | NM-NG 230 or 115 kV | NM-NG | 0 | 2019-03-06
0077 | Titan Development, LLC | Dover Energy | 2000-11-17 | 1000 | [5 empty] | Pl. Valley-Long Mt. Tie-Line | CONED | 0
0078 | KeySpan Ravenswood | Ravenswood Repower Ph I | 2000-12-04 | 440 | [5 empty] | Vernon | CONED | 0
0086 | NRG/ Berrians I GT Power, LLC | Berrians GT Replacement | 2001-01-15 | 79.9 | [5 empty] | Astoria | CONED | 0
0087 | Titan Development, LLC | Buchanan Energy | 2001-02-26 | 500 | [5 empty] | Buchanan | CONED | 0
0088 | Titan Development, LLC | Halfmoon Energy | 2001-02-26 | 500 | [5 empty] | Rotterdam-Bear Swamp line | NM-NG | 0
0089A | Atlantic Energy, LLC | Neptune DC PJM-NYC | 2001-03-15 | 600 | [5 empty] | W49th St | CONED | 0
0089B | Atlantic Energy, LLC | Neptune DC PJM-NYC | 2001-03-15 | 600 | [5 empty] | W49th St | CONED | 0
0090 | Fortistar, LLC | Fortistar VP | 2001-03-20 | 79.9 |  | CT | Richmond | NY | J | Fresh Kills 138kV | CONED | 0 | 2009-05-27
0091 | Fortistar, LLC | Fortistar VAN | 2001-03-20 | 79.9 |  | CT | Richmond | NY | J | Goethals/Fresh Kills 138kV | CONED | 0 | 2009-05-27
0092 | Amerada Hess Corp. | Redhook Energy | 2001-05-01 | 79.9 | [5 empty] | ConEd 138 kV (tbd) | CONED | 0
0093 | In-City I, LLC | Cross Hudson Project | 2001-05-11 | 550 |  | CC | New York | NY |  | W49th Street 345kV | CONED | 0 | 2007-08-23
0096 | Calpine Eastern Corporation | CPN 3rd Turbine, Inc. (JFK) | 2001-05-29 | 45 |  | CT | Queens | NY | J | Jamaica 138kV | CONED | 0 | 2008-07-10
0097 | NYSEG Solutions | South Glens Falls Expansion | 2001-06-15 | 40 | [5 empty] | Mohican-Butler#18 line | NM-NG | 0
0098 | TransEnergie US Ltd. | PJM-New York City HVDC | 2001-06-22 | 990 | [5 empty] | W49th St and/or Farragut | CONED | 0
0100 | Titan Development, LLC | Blooming Grove Power | 2001-07-02 | 500 | [5 empty] | Rock Tavern-Ramapo line | CONED | 0
0101 | Northeast Utilities Service Co. | NU CT-LI HVDC Cable | 2001-07-13 | 660 | [5 empty] | Shore Road | LIPA | 0
0102 | Entergy Power Gen. Corp. | Indian Point Energy Center | 2001-07-23 | 400 |  | CT | Westchester | NY |  | Buchanan 345kV | CONED | 0
0103 | Pegasus Trans. Co., Ltd. | Niagara Reinforcement Inter. | 2001-08-15 | 1200 |  | DC | Oneida-New York | NY |  | Marcy,Edic,Porter - W49th St. | NYPA/NM/CE | 0
0104 | PG&E/Liberty Gen. Co., LLC | Jupiter PJM-NYC Cable | 2001-08-24 | 1200 | [5 empty] | W49th St or Farragut | CONED | 0
0105 | Calpine Eastern Corporation | Titan Smith Street | 2001-10-05 | 79.9 |  | CT | Kings | NY |  | Gowanus 138 or 345 kV | CONED | 0 | 2019-03-06
0106 | TransGas Energy, LLC | TransGas Energy | 2001-10-05 | 1100 |  | CC | Kings | NY | J | E13St, Rainey, or Farragut-345kV | CONED | 0 | 2012-03-01
0108 | Sempra Generation | SE Long Island | 2001-11-29 | 575 |  | CT | Suffolk | NY |  | Shoreham-Holbrook lines 138kV | LIPA | 0
0109 | Calpine Eastern Corporation | Maspeth | 2002-01-25 | 79.9 | [5 empty] | Vernon-Glendale line | CONED | 0
0110 | PG&E/Liberty Gen. Co., LLC | Liberty Generation | 2002-02-04 | 400 |  | CT | Richmond-NJ | NY |  | Goethals 345kV | CONED | 0 | 2019-03-06
0111 | River Hill Power Co., LLC | River Hill Project | 2002-02-05 | 290 |  | CT | Chemung-PA | NY | C | Homer City-Watercure 345kV | NYSEG | 0 | 2008-07-10
0112 | TransEnergie US Ltd. | PJM-Rainey HVDC | 2002-04-09 | 660 |  | DC | Queens-NJ | NY |  | Rainey 345kV | CONED | 0 | 2006-05-31
0113 | Windfarm Prattsburgh, LLC | Prattsburgh Wind Park | 2002-04-22 | 55.5 |  | W | Yates | NY | C | Eelpot Rd-Flat St. 115kV | NYSEG | 0 | 2010-03-31
0114 | Global Winds Harvest, Inc. | Cherry Valley Wind Park | 2002-04-22 | 40.5 | [5 empty] | East Springfield | NYSEG | 0
0116 | PG&E/Liberty Gen. Co., LLC | Liberty Gen Co, LLC | 2002-04-29 | 600 | [5 empty] | Goethals | CONED | 0
0117 | Chautauqua Windpower, LLC | Chautauqua Windpower | 2002-05-14 | 50 |  | W | Chautauqua | NY |  | Dunkirk-S. Ripley 230kV | NM-NG | 0 | 2007-03-27
0118 | Global Winds Harvest, Inc. | Prattsburgh Wind Park II | 2002-05-15 | 75 | [5 empty] | Eelpot Rd-Flat St. line | NYSEG | 0
0119 | ECOGEN, LLC | Prattsburgh Wind Farm | 2002-05-20 | 78.2 |  | W | Yates | NY | C | Eelpot Rd-Flat St. 115kV | NYSEG | 0 | 2013-10-31
0120 | ECOGEN, LLC | Springwater Wind Farm | 2002-05-20 | 79.5 | [5 empty] | Eelpot Rd | NYSEG | 0
0124 | Bay Energy, LLC | Bay Energy Project | 2002-07-01 | 79.9 |  | CT | Kings | NY |  | Gowanus 138kV | CONED | 0
0126 | TransEnergie US Ltd. | PJM-Newbridge Rd HVDC | 2002-09-10 | 350 |  | DC |  |  |  | Newbridge Road 138kV | LIPA | 0 | 2006-05-31
0127 | KeySpan Energy for LIPA | Northport-Norwalk Upgrade | 2002-09-19 | 150 | [5 empty] | Northport | LIPA | 0
0127A | Airtricity Munnsville Wind Farm, LLC | Munnsville | 2002-10-09 | 6 |  | W | Madison | NY | E | 46kV line | NYSEG | 0 | 2014-01-31
0128 | Flat Rock Wind Power, LLC | Flat Rock Wind Power 230 kV | 2002-11-20 | 240 |  | W |  |  |  | Adirondack-Porter line | NM-NG | 0
0129 | Conjunction, LLC | Empire Connection | 2002-12-10 | 2000 |  | DC |  |  |  | New Scotland / ConEd | NM-NG/CONED | 0
0130 | Electrotek Concepts, Inc. | Grace Corona Generation | 2003-01-14 | 79.9 | [5 empty] | Corona | CONED | 0
0131 | Green Power Energy, LLC | Cody Road Wind Farm | 2003-03-05 | 10.5 |  | W |  |  |  | Oneida-Cortland line | NM-NG | 0
0132 | Airtricity Developments, LLC | Munnsville Windpower | 2003-05-11 | 40 |  | W |  |  |  | NYSEG Ckt 806 | NYSEG | 0
0134 | TransEnergie US Ltd. | PJM-Barrett HVDC | 2003-05-21 | 650 | [5 empty] | Barrett 138 kV | LIPA | 0
0137 | Conjunction, LLC | Empire Connection DC | 2003-06-16 | 2000 | [5 empty] | N. Scotland/Leeds, ConEd | NM/CONED | 0
0140 | National Grid | Leeds-PV Reconductoring | 2003-08-26 | N/A |  | AC | Greene-Dutchess | NY | G | Leeds/Athens-Pl. Valley 345kV | NM-NG | 0 | 2008-07-10
0141A | Atlantic Renewable Energy Corp. | Bishop | 2003-09-09 | 23.1 |  | W | Livingston | NY |  | Springwater 34.5kV line | NYSEG | 0
0142 | EC&R Northeast, LLC | Steuben Wind | 2003-10-30 | 50 |  | W | Steuben | NY | C | Bennett-Palmiter 115kV line | NYSEG | 0 | 2010-06-04
0147 | NY Windpower, LLC | West Hill Windfarm | 2004-04-16 | 31.5 |  | W | Madison | NY | C | Oneida-Fenner 115kV | NM-NG | 0 | 2012-08-31
0148 | Trigen Nassau Gen Co., LLC | Trigen-Nassau | 2004-05-18 | 79.9 | [5 empty] | Uniondale Substation | LIPA | 0
0150 | Reunion Power, LLC | Cherry Valley Wind Power | 2004-06-17 | 70 |  | W | Ostego | NY | E | Marshville - Sharon 69kV | NM-NG | 0 | 2010-03-31
0151 | Con Edison | West Side Switching Station | 2004-06-30 | N/A |  | AC | New York | NY | J | West 49th St & Farragut 345kV | CONED | 0 | 2011-03-31
0152 | Moresville Energy LLC | Moresville Energy Center | 2004-07-23 | 99 | 99 | W | Delaware | NY | E | Axtell Road-Grand Gorge 115kV | NYSEG | 0 | 2011-06-30
0154 | KeySpan Energy for LIPA | Holtsville-Brentwood-Pilgrim | 2004-08-19 | N/A | N/A | AC | Suffolk | NY | K | Holtsville & Pilgrim 138kV | LIPA | 0 | 2017-02-28
0155 | Invenergy NY, LLC | Canisteo Hills Windfarm | 2004-09-17 | 148.5 |  | W | Steuben | NY | C | Bennett-Bath 115kV | NYSEG | 0 | 2012-03-01
0157 | BP Alternative Energy NA, Inc. | Orion Energy NY I | 2004-10-12 | 100 | 100 | W | Herkimer | NY | E | Watkins Rd.-Inghams 115kV | NM-NG | 0 | 2012-03-01
0158 | Orion Energy, LLC | Orion Energy NY II | 2004-10-12 | 100 | 100 | W | Montgomery | NY |  | Inghams-Meco 115kV | NM-NG | 0 | 2019-01-06
0159 | Orion Energy, LLC | Orion Energy NY III | 2004-10-12 | 150 |  |  | Clinton | NY |  | TBD | NYSEG | 0
0160 | Jericho Rise Wind Farm, LLC | Jericho Rise Wind Farm | 2004-10-12 | 79.2 | 79.2 | W | Franklin | NY | D | Willis 115 kV | NYPA | 0 | 2011-04-30
0162 | AES Somerset, LLC | Niagara Windpower | 2004-12-15 | 70 |  | W | Niagara | NY |  | Somerset Switch Yard | NYSEG | 0 | 2019-08-05
0163 | Clipper Windpower Dev. Co. Inc. | Paragon I Wind Generation | 2005-01-13 | 100 | 100 | W | Steuben | NY | C | Bath-Montour Falls 115kV | NYSEG | 0 | 2008-08-19
0164 | FPL Energy | Long Island Offshore Wind | 2005-01-28 | 140 | 140 | W | Suffolk | NY |  | Sterling Substation | LIPA | 0 | 2008-02-26
0165 | UPC Wind Management, LLC | Genesee Wind Farm | 2005-01-31 | 500 | 500 | W | Genesee | NY |  | Batavia Substation 115kV | NM-NG | 0 | 2019-11-05
0166 | Cape Vincent Wind Power, LLC | St. Lawrence Wind Farm | 2005-02-08 | 75.9 | 75.9 | W | Jefferson | NY | E | Rockledge Substation 115kV | NM-NG | 0 | 2014-02-28
0167 | AES New York Wind, LLC | St. Lawrence Wind Farm II | 2005-02-08 | 80 |  | W | Jefferson | NY |  | Lyme Substation | NM-NG | 0 | 2019-06-05
0168 | Dairy Hills Wind Farm, LLC | Dairy Hills Wind Farm | 2005-02-08 | 120 | 120 | W | Wyoming | NY | C | Stolle Rd.-Meyer 230kV | NYSEG | 0 | 2012-03-01
0169 | Alabama Ledge Wind Farm, LLC | Alabama Ledge Wind Farm | 2005-02-08 | 79.8 | 79.8 | W | Genesee | NY | B | Oakfield-Lockport 115kV | NM-NG | 0 | 2012-06-01
0170 | Machias Wind Farm, LLC | Machias Wind Farm | 2005-02-08 | 90 | 90 | W | Cattaraugus | NY |  | Homer Hill-Gardenville 115kV | NM-NG | 0 | 2006-10-11
0176 | Noble Environmental Power, LLC | Wethersfield Windfield 115kV | 2005-02-14 | 129 | 129 | W | Wyoming | NY |  | Arcade Substation 115kV | Village of Arcade | 0 | 2006-07-18
0178 | Noble Allegany Windpark, LLC | Allegany Windpark | 2005-02-14 | 100.5 | 100.5 | W | Cattaraugus | NY | A | Freedom Substation 115kV | Village of Arcade | 0 | 2010-06-28
0179 | Noble Environmental Power, LLC | Cherry Hill Windpark | 2005-02-14 | 102 | 102 | W | Franklin | NY | E | Nicholville-Malone 115kV | NYSEG | 0 | 2009-02-05
0180 | Invenergy Wind, LLC | Buffalo Rd. Wind Farm | 2005-02-23 | 165 | 165 | W | Wyoming | NY |  | Stolle Rd.-Meyer 230kV | NYSEG | 0 | 2007-01-09
0180A | Green Power | Cody Rd | 2005-03-17 | 10 | 10 | W | Madison | NY | C | Fenner - Cortland 115kV | NM-NG | 0 | 2017-02-28
0181 | Everpower Global | Cold Spring Wind | 2005-03-21 | 69.3 |  | W | Cattaraugus | NY |  | Falconer-Homer Hill 115kV | NM-NG | 0 | 2019-09-05
0183 | Invenergy Wind, LLC | Buffalo Rd. Wind Farm II | 2005-03-28 | 165 | 165 | W | Wyoming | NY |  | Batavia 115kV | NYSEG/NM-NG | 0 | 2019-12-05
0184 | Invenergy Wind, LLC | Ripley Hill | 2005-03-28 | 75.9 |  | W | Onondaga | NY |  | Town of Spafford | NYSEG/NM-NG | 0 | 2019-08-05
0186 | Jordanville Wind, LLC | Jordanville Wind | 2005-04-01 | 80 | 80 | W | Herkimer | NY | E | Porter-Rotterdam 230kV | NM-NG | 0 | 2011-09-30
0187 | North Slope Wind Farm, LLC | North Slope Wind | 2005-04-05 | 109.5 | 109.5 | W | Clinton | NY | D | Willis-Plattsburgh 230kV | NYPA | 0 | 2009-02-05
0188 | NY Windpower, LLC | Orangeville Wind | 2005-04-05 | 96 |  | W | Wyoming | NY |  | 115kV | NYSEG | 0 | 2019-08-05
0189 | Atlantic Wind, LLC | Horse Creek Wind | 2005-04-08 | 126 | 126 | W | Jefferson | NY | E | Coffeen St-Thousand Island 115kV | NM-NG | 0 | 2014-04-30
0190 | PPM Energy, Inc. | Mixer Road Wind | 2005-04-08 | 66 | 66 | W | Jefferson | NY |  | West Adams 115kV | NM-NG | 0 | 2006-10-11
0191 | New York Regional | New York Regional | 2005-05-13 | 1200 | 1200 | DC | Oneida-Orange | NY | E, G | Edic - Rock Tavern | NM-NG/CH | 0 | 2009-04-08
0192 | Orion Energy, LLC | Orion Livingston | 2005-05-17 | 75 | 75 | W | Livingston | NY |  | Stolle Rd.-Meyer 230kV | NYSEG | 0 | 2019-01-06
0193 | Orion Energy, LLC | Orion Wyoming | 2005-05-17 | 60 | 60 | W | Wyoming | NY |  | South Perry 115kV | NYSEG | 0 | 2007-01-09
0194 | Calpine Energy Services | Bayonne | 2005-05-26 | 300 | 300 | ST | New York | NY |  | World Trade Center 138kV | CONED | 0 | 2019-02-06
0195 | Brookfield Power US | Harbor Cable Project II | 2005-06-14 | 200 | 200 | DC | Richmond | NY | J | Goethal 345kV | CONED | 0 | 2009-07-31
0196 | Roaring Brook Windpower, LLC | Roaring Brook | 2005-07-01 | 79.9 | 79.8 | W | Lewis | NY |  | Adirondak-Porter 230kV | NM-NG | 0 | 2006-07-10
0197 | PPM Roaring Brook, LLC / PPM | Roaring Brook Wind | 2005-07-01 | 78 | 78 | W | Lewis | NY | E | Boonville-Lowville 115kV | NM-NG | 0 | 2016-04-30
0198 | Arkwright Summit Wind Farm, LLC | Arkwright Summit Wind Farm | 2005-07-21 | 79.8 | 79.8 | W | Chautauqua | NY | A | Dunkirk-Falconer 115kV | NM-NG | 0 | 2013-09-30
0200 | Cavallo Power | Linden Power I | 2005-08-16 | 845 | 915 | CC | New York-NJ | NY |  | Goethal Substation | CONED | 0 | 2019-02-06
0201 | NRG Energy | Berrians GT | 2005-08-17 | 200 | 200 | CC | Queens | NY | J | Astoria West Substation 138kV | CONED | 0 | 2015-07-31
0202 | Liberty Generating Co. | 130 MW Uprate | 2005-08-25 | 130 | 130 | CT | New York-NJ | NY |  | Goethal 345kV | CONED | 0 | 2019-03-06
0203 | GenWy Wind, LLC | GenWy Wind Farm | 2005-10-21 | 478.5 | 478.5 | W | Genesee | NY | A | Stolle Rd - Homer City 345kV | NYSEG | 0 | 2010-03-31
0204 | Clipper Windpower Dev. Co. Inc. | Paragon II Wind Generation | 2005-10-27 | 150 | 150 | W | Steuben | NY | C | Avoca - Hillside 230kV | NYSEG | 0 | 2008-08-19
0204A | Duer's Patent Project, LLC | Beekmantown Windfarm | 2005-10-31 | 19.5 | 19.5 | W | Clinton | NY | D | Kents Falls - Sciota 115kV | NYSEG | 0 | 2013-03-31
0207 | Cape Vincent Wind Power, LLC | Cape Vincent | 2006-01-12 | 209.3 | 209.3 | W | Jefferson | NY | E | Rockledge Substation 115kV | NM-NG | 0 | 2014-02-28
0208 | CRC Development, LLC | Roundhouse Renewable | 2006-01-17 | 35 | 36 | ST | Otsego | NY |  | City of Oneonta | NYSEG | 0 | 2006-09-25
0209 | SUEZ Energy Generating NA, Inc | Nassau Generating | 2006-02-10 | 88 | 100 | CT | Nassau | NY |  | Garden City Substation 138kV | LIPA | 0 | 2007-07-10
0210 | Canadian Niagara Power, Inc. | Fortran | 2006-03-14 | 150 | 150 | AC | Niagara | NY | A | Huntley Station 115kV | NM-NG | 0 | 2010-03-31
0213 | Noble Environmental Power, LLC | Ellenburg II Windfield | 2006-04-03 | 21 | 21 | W | Clinton | NY | D | Willis-Plattsburgh WP-2 230kV | NYPA | 0 | 2013-04-30
0215 | Noble Burke Windpark, LLC | Noble Burke Windpark | 2006-04-03 | 120 | 120 | W | Franklin-Clinton | NY | D | Willis Substation 230kV | NYPA | 0 | 2009-02-05
0217 | AES Keystone Wind, LLC | Cherry Flats | 2006-06-06 | 90 | 90 | W | Tioga | PA | C | Homer City-Watercure 345kV | NYSEG | 0 | 2008-12-22
0218 | Gamesa Energy USA | Endless Mountain Wind | 2006-07-03 | 150 | 150 | W | Tioga - Bradford | PA |  | Homer City-Watercure 345kV | NYSEG | 0 | 2006-07-27
0219 | NRG Energy, Inc. | Huntley | 2006-07-12 | 752 | 752 | CC | Niagara | NY | A | Tonawanda | NM-NG | 0 | 2008-12-22
0220 | AES Keystone Wind, LLC | Armenia Mountain I | 2006-07-19 | 175 | 175 | W | Bradford | PA | C | Homer City-Watercure 345kV | NYSEG | 0 | 2008-08-19
0221 | AES Keystone Wind, LLC | Armenia Mountain II | 2006-07-19 | 75 | 75 | W | Bradford | PA | C | Homer City-Watercure 345kV | NYSEG | 0 | 2009-04-08
0222 | Ball Hill Windpark, LLC | Ball Hill Windpark | 2006-07-21 | 90 | 90 | W | Chautauqua | NY | A | Dunkirk-Gardenville 230kV | NM-NG | 0 | 2013-11-30
0223 | Noble Environmental Power, LLC | Arkwright Windpark | 2006-07-21 | 99 | 99 | W | Chautauqua | NY |  | Dunkirk-Falconer 115kV | NM-NG | 0 | 2007-03-12
0224 | NRG Energy, Inc. | Berrians GT II | 2006-08-23 | 50 | 90 | CC | Queens | NY | J | Astoria West Substation 138kV | CONED | 0 | 2015-07-31
0224B | Casella Waste Systems | Chemung Landfill | 2006-09-05 | 6.4 | 6.4 | M | Chemung | NY | C | 115kV | NYSEG | 0 | 2008-04-15
0225A | Schenectady International, Inc. | SII Rotterdam Junction | 2006-09-08 | 9.3 | 9.3 | Wo | Rotterdam | NY | F | 69kV | NM-NG | 0 | 2010-08-31
0225B | Burrstone Energy | Faxton/ St. Luke | 2006-09-15 | 2.2 | 2.2 | NG | Herkimer | NY | E | TBD | NM-NG | 0 | 2008-07-10
0226 | Cavallo Power | Linden | 2006-09-08 | 1200 | 1200 | CC | New York-NJ | NY |  | East 13th, West 49th | CONED | 0 | 2006-11-14
0227 | EC&R Northeast, LLC | Orleans Wind | 2006-09-28 | 120 | 120 | W | Orleans | NY | A | Shelby Substation - 115kV | NM-NG | 0 | 2008-10-14
0227A | Laidlaw Energy Group Inc. | Laidlaw Energy & Env. | 2006-10-30 | 7 | 7 | Wo | Cattaraugus | NY | A | 13.2kV | NM-NG | 0 | 2013-05-31
0228 | AES Bainbridge, LLC | Jennison | 2006-10-30 | 516 | 536 | C | Chenango | NY |  | TBD | NYSEG | 0 | 2007-04-24
0229 | AES Somerset 2, LLC | Somerset | 2006-11-01 | 687 | 706 | C | Niagara | NY |  | Somerset Substation 345kV | NYSEG | 0 | 2007-03-27
0230 | Cornell University | Cornell CHPP | 2006-11-02 | 30 | 30 | NG |  |  |  | Maple Ave. Substation 115kV |  | 0 | 2006-11-21
0231 | Seneca Energy II, LLC | Seneca | 2006-11-02 | 6.4 | 6.4 | M | Seneca | NY | C | Goulds Substation 34.5kV | NYSEG | 0 | 2012-04-30
0235 | Gamesa Energy USA, LLC | Canfield Wind | 2006-12-12 | 120 | 120 | W | Tioga - Bradford | PA |  | Homer City-Watercure 345kV | NYSEG | 0 | 2007-10-16
0236 | Gamesa Energy USA, LLC | Dean Wind | 2006-12-14 | 150 | 150 | W | Tioga - Schuyler | NY | C | Watercure-Oakdale 345kV | NYSEG | 0 | 2011-04-30
0237 | Allegany Wind, LLC | Allegany Wind | 2007-01-09 | 72.5 | 72.5 | W | Cattaraugus | NY | A | Homer Hill Ð Dugan Rd. 115kV | NM-NG | 0 | 2015-02-28
0238 | Tonawanda Creek Wind, LLC | Tonawanda Creek Wind | 2007-01-30 | 75 | 75 | W | Genesee | NY | A | Lockport Ð Batavia 115kV | NM-NG | 0 | 2009-07-31
0239 | Western Door Wind, LLC | Western Door Wind | 2007-01-30 | 100 | 100 | W | Yates | NY | C | Greenidge Ð Haley Rd. 115kV | NYSEG | 0 | 2012-01-30
0239A | Innovative Energy System, Inc. | Modern Innovative Plant | 2007-01-31 | 6.4 | 6.4 | M | Niagara | NY | A | Youngstown Ð Sanborn 34.5kV | NM-NG | 0 | 2013-04-30
0240 | Noble Environmental Power, LLC | Farmersville Windpark | 2007-02-26 | 100 | 100 | W | Cattaraugus-PA | NY | A | Stolle Rd - Farmer's Valley 345kV | NM-NG | 0 | 2009-07-31
0241 | Noble Chateaugay Windpark II, LLC | Chateaugay II Windpark | 2007-03-15 | 19.5 | 19.5 | W | Franklin | NY | D | Chateaugay Substation 34.5kV | NYSEG | 0 | 2012-08-31
0242 | RG&E | Brown's Race Uprate | 2007-04-09 | 6 | 6 | H | Monroe | NY |  | Brown's Race Substation | NYSEG | 0 | 2007-06-05
0243 | Astoria Energy, LLC | Astoria Uprate | 2007-04-12 | 100 | 230 | CC | Queens | NY | J | Astoria East Substation 138kV | ConEd | 0 | 2010-03-31
0244 | AES Bainbridge, LLC | Jennison | 2007-04-13 | 650 | 650 | C | Chenango | NY |  | Oakdale Ð Fraser 345kV | NYSEG | 0 | 2008-03-20
0246 | PPM Energy, Inc | Dutch Gap Wind | 2007-06-01 | 250 | 250 | W | Jefferson | NY | E | Indian River - Black Rive 115kV | NM-NG | 0 | 2012-03-01
0247 | RG&E | Russell Station | 2007-06-11 | 300 | 325 | CC | Monroe | NY | B | Russell Station 115kV | RG&E | 0 | 2012-04-30
0248 | RG&E | Russell Station II | 2007-06-11 | 300 | 300 | C | Monroe | NY |  | Russell Station 115kV | NYSEG | 0 | 2007-10-02
0249 | Hess Corporation | Bayone Energy Center II | 2007-06-20 | 250 | 250 | D | Bayonne | NJ |  | Gowanus Substation 138kV | ConEd | 0 | 2007-10-02
0252 | Brookfield Power | Manhattan Cable | 2007-08-01 | 350 | 350 | DC | New York | NY | J | World Trade Center 138 kV | ConEd | 0 | 2008-07-10
0253 | Marble River, LLC | Marble River SPS | 2007-08-13 | TBD | TBD | AC | Clinton | NY | D | Moses-Willis-Plattsburgh 230kV | NYPA | 0 | 2012-06-30
0254 | Ripley-Westfield Wind LLC | Ripley-Westfield Wind | 2007-08-14 | 124.2 | 124.2 | W | Cahatauqua | NY | A | Ripley - Dunkirk 230kV | NM-NG | 0 | 2012-03-01
0255 | In-City, LLC | Cross Hudson | 2007-08-23 | 550 | 550 | CC | New York-NJ | NY | J | W49th Street 345kV | ConEd | 0 | 2008-07-01
0256 | Niagara Shore Winds, LLC | Niagara Shore Wind | 2007-09-04 | 70.5 | 70.5 | W | Niagara | NY | A | Somerset Switch Yard 345kV | NYSEG | 0 | 2010-03-31
0257 | RG&E | Brown's Race Uprate | 2007-09-12 | 2 | 2 | H | Monroe | NY | B | Beebee Station 34kV | RG&E | 0 | 2011-03-31
0258 | Babcock & Brown, LP | Ripley-Westfield Wind II | 2007-09-24 | 124.8 | 124.8 | W | Chautauqua | NY |  | Ripley - Dunkirk 230kV | NM-NG | 0 | 2007-10-16
0259 | Delaware County Electric | Delaware County Landfill | 2007-09-24 | 1 | 1 | M | Delaware | NY |  | TBD | NYSEG | 0 | 2008-01-29
0261 | Astoria Generating Company | South Pier Improvement | 2007-10-02 | 105 | 108 | CT | Kings | NY | J | Gowanus 138kV | ConEd | 0 | 2012-03-01
0262 | RP Wind NY, LLC | Schoharie Highlands | 2007-10-05 | 70 | 70 | W | Schoharie | NY | F | 69kV | NM-NG | 0 | 2009-05-12
0264 | RG&E | Seth Green | 2007-10-23 | 2.8 | 2.8 | H | Monroe | NY | B | 11kV | RG&E | 0 | 2014-03-31
0265 | CityGreen Transmission | CityGreen | 2007-11-16 | 1100 | 1100 | DC | Westchester-Queens | NY | H, J | Millwood - Farragut/Rainey 345kV | ConEd | 0 | 2010-03-31
0266 | NRG Energy, Inc. | Berrians GT III | 2007-11-28 | 250 | 290 | CC | Queens | NY | J | Astoria Annex 345kV | NYPA | 0 | 2015-06-30
0267 | Winergy Power, LLC | Winergy NYC Wind Farm | 2007-11-30 | 600 | 600 | W | New York | NY | J | Gowanus Substation 345kV | ConEd | 0 | 2012-07-31
0268 | NRG Energy, Inc. | Arthur Kill | 2007-12-07 | 800 | 800 | CC | New York | NY | J | Gowanus Substation | ConEd | 0 | 2008-07-10
0269 | WM Renewable Energy, LLC | Madison County Landfill | 2007-12-10 | 2 | 2 | M | Madison | NY |  | Canastota | NM-NG | 0 | 2008-01-29
0270 | Wind Development Contract Co LLC | Hounsfield Wind | 2007-12-13 | 244.8 | 244.8 | W | Jefferson | NY | E | Fitzpatrick - Edic 345kV | NYPA | 0 | 2016-07-31
0271 | State Line Wind Power LLC | State Line Wind | 2007-12-20 | 124.8 | 124.8 | W | Chautauqua | NY | A | South Ripley - Dunkirk 230kV | NM-NG | 0 | 2011-10-31
0272 | NYPA | Benchmark Generator | 2007-12-20 | 900 | 1080 | CT | Queens | NY | J | Astoria 345kV | NYPA | 0 | 2009-04-08
0273 | Winergy Power, LLC | Winergy Long Island Wind | 2007-12-21 | 299 | 299 | W | Suffolk | NY | K | Sterling Substation | LIPA | 0 | 2008-07-10
0274 | In City I, LLC | PSEG Fossil Bergen Unit 2 | 2008-01-23 | 100 | 100 | CC | New York-NJ | NY | J | W49th Street 345kV | ConEd | 0 | 2008-07-10
0275 | Shell Wind Energy Inc. | Cayuga County Wind | 2008-01-24 | 120 | 120 | W | Cayuga | NY | C | Milliken - Wright Ave. 115kV | NYSEG | 0 | 2009-04-08
0277 | UniStar Nuclear Energy | Nine Mile Point Station Unit #3 | 2008-02-04 | 1640 | 1660 | NU | Oswego | NY | C | Scriba Substation 345kV | NM-NG | 0 | 2009-12-22
0278 | Riverbank Power Corporation | Riverbank Power A | 2008-02-20 | 1000 | 1000 | PS | Niagara | NY | A | Niagara - Rochester 345kV | NYPA | 0 | 2009-06-24
0279 | Riverbank Power Corporation | Riverbank Power D1 | 2008-02-20 | 1000 | 1000 | PS | St. Lawrence | NY | E | Massena 765kV | NYPA | 0 | 2010-03-31
0280 | Riverbank Power Corporation | Riverbank Power D2 | 2008-02-20 | 1000 | 1000 | H | St. Lawrence | NY | E | Massena 765kV | NYPA | 0 | 2008-10-14
0281 | Riverbank Power Corporation | Riverbank Power G | 2008-02-20 | 1000 | 1000 | PS | Rockland | NY | G | West Haverstraw 345kV | ConEd/O&R | 0 | 2010-11-30
0282 | Concord Wind Power LLC | Concord Wind | 2008-02-28 | 101.2 | 101.2 | W | Chautauqua | NY | A | Dunkirk - South Ripley 230kV | NM-NG | 0 | 2011-05-31
0283 | Riverbank Power Corporation | Riverbank Power J | 2008-03-03 | 1000 | 1000 | H | Queens | NY | J | Poletti Substation 345kV | NYPA | 0 | 2008-04-15
0285 | Machias Wind Farm, LLC | Machias I | 2008-03-27 | 79.2 | 79.2 | W | Cattaraugus | NY | A | Gardenville - Homer Hill 115kV | NM-NG | 0 | 2012-06-30
0286 | Machias Wind Farm, LLC | Machias II | 2008-03-27 | 199.5 | 199.5 | W | Cattaraugus | NY | A | 345kV | NYSEG | 0 | 2009-04-08
0287 | Horizon Wind Energy, LLC | Pomfret | 2008-03-27 | 73.5 | 73.5 | W | Chautauqua | NY | A | Dunkirk - Falconer 115kV | NM-NG | 0 | 2010-09-30
0288 | Chateaugay River Wind Farm, LLC | Chateaugay River | 2008-03-31 | 120 | 120 | W | Franklin | NY | E | Willis Substation 230kV | NYPA | 0 | 2009-02-05
0290 | National Grid | Paradise | 2008-04-03 | N/A | N/A | AC | Niagara | NY | A | Paradise Station 115kV | NM-NG | 0 | 2011-03-31
0291 | Long Island Cable, LLC | LI Cable - Phase 1 | 2008-04-14 | 440 | 440 | W | Suffolk | NY | K | Ruland Road 138kV | LIPA | 0 | 2012-07-31
0292 | Long Island Cable, LLC | LI Cable - Phase 2a | 2008-04-14 | 220 | 220 | W | Suffolk | NY | K | Ruland Road 138kV | LIPA | 0 | 2012-07-31
0293 | Long Island Cable, LLC | LI Cable - Phase 2b | 2008-04-14 | 280 | 280 | W | Suffolk | NY | K | Ruland Road 138kV | LIPA | 0 | 2008-12-22
0295 | CCH Holdings Group, LLC | Cross Hudson II | 2008-05-06 | 800 | 800 | AC | New York-NJ | NY | J | West 49th St. Substation 345kV | ConEd | 0 | 2012-06-01
0296 | Noble Environmental Power, LLC | Harrigan Hill Wind | 2008-05-12 | 100.5 | 100.5 | W | Clinton-Ellenburg | NY | D | Lyon Mt - Willis 115kV | NYSEG | 0 | 2009-07-31
0297 | Ashford Wind Farm, LLC | Ashford Wind | 2008-05-16 | 19.9 | 19.9 | W | Cattaraugus | NY | A | Otto-West Valley 34.5kV | NM-NG | 0 | 2010-03-31
0298 | TCI Renewable, LLC | Leicester Wind | 2008-05-22 | 57 | 57 | W | Livingston | NY | A | Highbank - Mortimer 115kV | NYSEG | 0 | 2010-08-31
0299 | Erie Boulevard Hydropower | Great Bend | 2008-06-03 | 14.4 | 14.4 | H | Jefferson | NY | E | Deferiet 115 kV substation | NM-NG | 0 | 2009-04-08
0300 | Auburn Public Power Agency | Auburn Sewage Treatment | 2008-06-26 | 3 | 3 |  | Onondaga | NY | C | Auburn, NY | NYSEG | 0 | 2008-10-14
0301 | Hamlin Wind, LLC | Hamlin Wind Farm | 2008-07-15 | 80 | 80 | W | Monroe | NY | A | West Hamlin 115kV | NM-NG | 0 | 2010-03-31
0302 | Barre Wind, LLC | Barre Wind Farm | 2008-07-15 | 120 | 120 | W | Orleans | NY | A | Lockport - Mortimer 115 KV | NM-NG | 0 | 2008-12-22
0303 | Invenergy Thermal Devel., LLC | Tioga County Energy | 2008-07-17 | 620 | 700 | CT | Tioga | NY | C | Oakdale - Watercure 345kV | NYSEG | 0 | 2009-04-08
0304 | Transmission Developers Inc. | Clay HVDC | 2008-07-18 | 2000 | 2000 | DC | New York | NY | J | Clay to Farragut 345kV | NM-NG/ConEd | 0 | 2008-08-28
0305 | TDI-USA Holdings Corporation | Champlain Hudson Power Express | 2008-07-18 | 1000 | 1000 | DC | Quebec - NY | NY | J | Astoria Annex Substation 345kV | NYPA | 0 | 2017-01-31
0306 | Transmission Developers Inc. | Clay HVDC | 2008-07-18 | 2000 | 2000 | DC | Onondaga/New York | NY | C, J | Clay 345kV - Sherman Creek 138 kV | NM-NG/ConEd | 0 | 2011-11-30
0307 | New York Wire, LLC | New York Wire-Phase 1 | 2008-07-29 | 550 | 550 | DC | NJ-Kings | NY | J | Gowanus Substation 345kV | ConEd | 0 | 2012-07-31
0309 | AP Dutchess Properties Inc. | Wingdale Energy Center | 2008-09-11 | 650 | 650 | CC | Dutchess | NY | G | Pleasant Valley - Long Mt. | ConEd | 0 | 2009-05-12
0310 | Cricket Valley Energy Center, LLC | Cricket Valley Energy Center | 2008-09-22 | 1019.9 | 1136 | CC | Dutchess | NY | G | Pleasant Valley - Long Mt. 345kV | ConEd | 0 | 2014-12-31
0311 | New York State Electric & Gas | Concord Casino | 2008-09-24 | 48 | 48 | L | Sullivan | NY | E | Coopers Corner - Rock Hill | NYSEG | 0 | 2013-04-30
0312 | RP Wind NY, LLC | Gateway Wind Energy | 2008-09-25 | 79.2 | 79.2 | W | Schenectady | NY | F | Princetown - Rotterdam | NM-NG | 0 | 2009-04-08
0313 | Atlantic Wind, LLC | Stone Church Wind | 2008-09-30 | 150 | 150 | W | St. Lawrence | NY | E | Mc Intyre Substation 115 kV | NM-NG | 0 | 2011-03-31
0314 | Riverbank Power Corporation | Oswego | 2008-10-07 | 1000 | 1000 | PS | Oswego | NY | C | Oswego complex 345kV | NM-NG | 0 | 2009-06-24
0315 | CRC Renewables, LLC | Onondaga Renewables | 2008-10-23 | 47 | 47 | Wo | Onondaga | NY | C | Geres Lock 115kV | NM-NG | 0 | 2012-01-30
0316 | State Line Wind Power, LLC | State Line Wind II | 2008-10-31 | 124.8 | 124.8 | W | Chautauqua | NY | A | Dunkirk - South Ripley 230kV | NM-NG | 0 | 2009-10-28
0317 | CityGreen Transmission Inc. | CityGreen AC | 2008-11-05 | 1100 | 1100 | AC | Wsch'r/Bkln/Qns | NY | H, J | Millwood 345kV - Farragut/Rainey | ConEd | 0 | 9/30/09
0319 | AES Energy Storage, LLC | Cayuga Energy Storage | 2008-12-03 | 20 | 20 | ES | Onondaga | NY | C | Milliken 115kV | NYSEG | 0 | 2012-06-01
0320 | AES Energy Storage, LLC | Somerset Energy Storage | 2008-12-03 | 20 | 20 | ES | Niagara | NY | A | Somerset 69kV | NYSEG | 0 | 2012-06-01
0321 | Monroe County | Monroe County Landfill | 2009-01-02 | 6.4 | 6.4 | M | Monroe | NY | B | Sanford Rd. | NM-NG | 0 | 2009-09-30
0322 | Rolling Upland Wind Farm, LLC | Rolling Upland Wind | 2009-01-13 | 59.9 | 59.9 | W | Madison | NY | E | County Line - Brothertown 115kV | NYSEG | 0 | 2014-08-31
0323 | Riverbank Power Corporation | Verplanck | 2009-01-23 | 1000 | 1000 | PS | Westchester | NY | H | Indian Point 345kV | ConEd/O&R | 0 | 2009-06-24
0324 | Belltown Biogas, LLC | Belltown Bio | 2009-03-06 | 2 | 2 | M | Cayuga | NY | C | King Ferry | NYSEG | 0 | 2009-04-08
0325 | Synergy Biogas, LKc | Synergy Bio | 2009-03-06 | 2 | 2 | M | Wyoming | NY | A | Wyoming | NM-NG | 0 | 2009-04-08
0327 | Con Edison | Offshore Wind | 2009-03-20 | 700 | 700 | W | New York-Suffolk | NY | J, K | Far Rockaway 69kV | LIPA | 0 | 2011-06-30
0328 | Steuben Rural | Steuben County Landfill | 2009-03-23 | 4.8 | 4.8 | M | Steuben | NY | C | Quarry - Bath 34.5 | NYSEG | 0 | 2009-05-27
0329 | Horizon Wind Energy, LLC | Madison Wind Expansion | 2009-03-23 | 8.3 | 8.3 | W | Madison | NY | E | County Line - Brothertown 115kV | NYSEG | 0 | 2009-05-27
0332 | FitzPatrick Nuclear Station | FitzPatrick Nuclear Uprate | 2009-05-01 | 112 | 112 | NU | Oswego | NY | C | FitzPatrick Substation | NYPA | 0 | 2009-06-24
0334 | Atlantic Wind, LLC | Sangerfield Wind | 2009-05-28 | 46 | 46 | W | Onieda | NY | E | TBD | NM-NG/NYSEG | 0 | 2009-07-31
0335 | NextEra Energy Resources, LLC | Cold Creek Spring Wind | 2009-06-09 | 150.7 | 150.7 | W | Cattaraugus | NY | A | Carrs Corners - Salamanca 115kV | NM-NG | 0 | 2012-08-31
0336 | Enfield Energy, LLC | Black Oak Wind | 2009-06-29 | 50 | 50 | W | Thompkins | NY | C | Black Oak Rd 115kV | NYSEG | 0 | 2012-06-30
0338 | RG&E | Brown's Race II | 2009-08-11 | 6.3 | 6.3 | H | Monroe | NY | B | Station 137 11kV | RG&E | 0 | 2019-12-31
0341 | Covanta Energy | Hempstead Expansion | 2009-09-02 | 37 | 39 | ST | Nassau | NY | K | Hempstead 138kV | LIPA | 0 | 2010-08-31
0343 | Champlain Wind Link, LLC | Champlain Wind Link I | 2009-09-29 | 600 | 600 | AC | Clinton | NY | D | Plattsburgh - New Haven, VT 230kV | NYPA | 0 | 2012-07-31
0344 | Champlain Wind Link, LLC | Champlain Wind Link II | 2009-09-29 | 600 | 600 | AC | Clinton | NY | D | Plattsburgh - New Haven, VT 345kV | NYPA | 0 | 2012-04-30
0345 | St. Elizabeth Medical Center | St. Elizabeth Medical Center | 2009-11-02 | 2.3 | 2.3 | NG | Herkimer | NY | E |  | NM-NG | 0 | 2009-11-30
0346 | Beacon Power | Scotia Industrial Park | 2009-11-24 | 20 | 20 | F | Schenectady | NY | F | Spier - Rotterdam | NM-NG | 0 | 2012-08-31
0347 | Franklin Wind Farm, LLC | Franklin Wind | 2009-12-02 | 50.4 | 50.4 | W | Delaware | NY | E | Oakdale - Delhi 115kV | NYSEG | 0 | 2019-01-31
0348 | Casella Waste Systems | Hyland Landfill | 2009-12-02 | 0.8 | 0.8 | M | Allegany | NY | B | Station 249 | RG&E | 0 | 2010-04-30
0349 | Taylor Biomass Energy-Montgomery, LLC | Taylor Biomass | 2009-12-30 | 19 | 22.5 | SW | Orange | NY | G | Maybrook - Rock Tavern 69kV | CHGE | 0 | 2021-06-30
0350 | Lake Erie Wind, LLC | Lake Erie Wind | 2010-02-16 | 810 | 810 | W | Chautauqua | NY | A | Dunkirk - Gardenville 230kV | NM-NG | 0 | 2012-01-30
0351 | Linden VFT, LLC | Linden VFT Uprate | 2010-03-02 | 15 | 15 | AC | Richmond | NY | J | Goethals 345kV | CONED | 0 | 2013-02-28
0352 | WM Renewable Energy | Oneida-Herkimer Landfill | 2010-04-08 | 3.2 | 3.2 | M | Oneida | NY | E |  |  | 0 | 2010-06-04
0354 | Atlantic Wind, LLC | North Ridge Wind | 2010-05-13 | 100 | 100 | W | St. Lawrence | NY | E | Nicholville - Parishville 115kV | NM-NG | 0 | 2015-01-31
0356 | Pattern Renewables | Hounsfield Wind | 2010-09-07 | 249.4 | 249.4 | W | Jefferson | NY | E | Oswego Substation 345kV | NYPA | 0 | 2010-11-30
0357 | West Point Partners, LLC | NY Power Pathway | 2010-09-10 | 1000 | 1000 | DC | Albany-Westchester | NY | F, H | New Scotland - Buchanan South 345kV | NM-NG/Coned | 0 | 2013-02-28
0358 | West Point Partners, LLC | West Point Transmission | 2010-09-13 | 1000 | 1000 | DC | Greene, Westchester | NY | F, H | Leeds - Buchanan North 345kV | NM-NG/ConEd | 0 | 2018-01-31
0359 | National Grid | Verizon - Project Oasis | 2010-12-20 | 75 | 75 | L | Niagara | NY | A | Somerset - Kintigh 345kV | NYSEG | 0 | 2011-02-28
0360 | NextEra Energy Resources, LLC | Watkins Glen Wind | 2010-12-22 | 122.4 | 122.4 | W | Schuyler | NY | C | Bath - Montour Falls 115 kV | NYSEG | 0 | 2015-05-31
0361 | US PowerGen Co. | Luyster Creek Energy | 2011-02-15 | 401 | 444 | D | Queens | NY | J | Astoria West Substation 138kV | CONED | 0 | 2020-02-29
0362 | Monticello Hills Wind, LLC | Monticello Hills Wind | 2011-03-07 | 19.8 | 19.8 | W | Ostego | NY | E | W. Winfield - Richfield Spring 46kV | NYSEG | 0 | 2017-04-30
0363 | Anbaric Development Partners, LLC | Poseidon Offshore | 2011-04-27 | 500 | 500 | W | NY - Suffolk | NY | K | Ruland Rd. 138kV | LIPA | 0 | 2020-07-31
0364 | Bruce Hill Wind, LLC | Bruce Hill Wind | 2011-05-04 | 18 | 18 | W | Delaware | NY | E | Axtell Road Substation 115 kV | NYSEG | 0 | 2012-09-30
0365 | Transmission Developers Inc. | Champlain Hudson SPS | 2011-07-15 | TBD | TBD | AC | Queens | NY | J | Astoria and Farragut Subsations | ConEd/NYPA | 0 | 2012-12-31
0366 | NextEra Energy Resources, LLC | Watkins Glen East | 2011-08-02 | 150.6 | 150.6 | W | Schuyler | NY | C | Montour Falls Substation | NYSEG | 0 | 2012-10-31
0367 | Orange & Rockland | North Rockland Transformer | 2011-09-14 | N/A | N/A | AC | Rockland | NY | G | Line Y94 345kV | ConEd | 0 | 2018-07-31
0369 | Clover Leaf Power, LLC | Clover Leaf Hollers Ave | 2011-10-24 | 173.9 | 192.8 | CT | Bronx | NY | J | E 179th St. Subsation 138kV | ConEd | 0 | 2013-12-31
0370 | Smokey Avenue Wind, LLC | Smokey Avenue Wind | 2011-10-28 | 18 | 18 | W | Otsego | NY | F | Worcester - Schenevus 23kV | NM-NG | 0 | 2014-01-31
0371 | South Mountain Wind, LLC | South Mountain Wind | 2011-10-31 | 18 | 18 | W | Delaware | NY | E | River Rd Substation 46kV | NYSEG | 0 | 2018-01-31
0372 | Dry Lots Wind, LLC | Dry Lots Wind | 2011-10-31 | 33 | 33 | W | Herkimer | NY | E | Schuyler - Whitesboro 46kV | NM-NG | 0 | 2021-02-28
0374 | CPV Valley, LLC | CPV Valley II | 2012-02-21 | 820 | 820 | CC | Wawayanda | NY | G | Rock Tavern-Coopers Corners 345kV | NYPA | 0 | 2015-09-30
0376 | Ridgeline Energy, LLC | Troups Creek Wind | 2012-03-07 | 32 | 32 | W | Steuben | NY | C | Troupsburg Substation | NYSEG | 0 | 2012-04-30
0376A | Atlantic Development, LLC | Atlantice Development | 2012-03-15 | N/A | N/A | W | N/A |  | N/A | N/A | N/A | 0 | 2009-07-31
0377 | Monroe County | Monroe County Mill Seat | 2012-03-16 | 3.2 | 3.2 | M | Monroe | NY | B | Sanford Rd. 34.5kV | NM-NG | 0 | 2016-04-30
0379 | Seneca Energy II, LLC | Seneca II Expansion | 2012-04-24 | 6.4 | 6.4 | M | Seneca | NY | C | Seneca - Waterloo 34.5kV | NYSEG | 0 | 2013-05-31
0381 | Clipper Wind Power Development | Paragon Wind | 2012-05-15 | 79.9 | 79.9 | W | Steuben-Schuyler | NY | C | Stony Ridge - Hillside 230kV | NYSEG | 0 | 2012-10-31
0382 | Astoria Generating Co. | South Pier Improvement | 2012-05-30 | 91.2 | 95.5 | CT | Kings | NY | J | Gowanus Substation 138kV | ConEd | 0 | 2018-03-31
0383 | NRG Energy, Inc. | Bowline Gen. Station Unit #3 | 2012-05-30 | 775 | 814 | CC | Rockland | NY | G | Ladentown Substation 345kV | O&R | 0 | 2019-07-31
0384 | National Grid | Knickerbocker Pleasant Valley | 2012-06-15 | TBD | TBD | AC | Columbia-Dutchess | NY | F, G | Knickerbocker - P. Valley 345kV | NM-NG/ConEd | 0 | 2016-05-31
0385 | National Grid | Hudson Valley Reinforcement | 2012-06-15 | TBD | TBD | AC | Alb.-Col.-Dutch. | NY | F, G | N. Scotland-Leeds-P. Valley 345kV | NM-NG/ConEd | 0 | 2015-02-28
0388 | Enel Green Power North America | Dexter Solar | 2012-07-24 | 17 | 17 | S | Jefferson | NY | E | Dexter Stubstation | NM-NG | 0 | 2012-09-30
0389 | GUSC Energy, Inc. | Griffiss Technology Park | 2012-08-14 | 0.9 | 0.9 | ST | Oneida | NY | E | Boonville - Rome 115kV | NM-NG | 0 | 2012-09-30
0391 | North America Transmission, LLC | Edic - Fraser #2 | 2012-09-21 | TBD | TBD | AC | Oneida-Delaware | NY | E | Edic - Fraser 345kV | NM-NG/NYSEG | 0 | 2016-01-31
0392 | Exelon Corporation | Scriba-Volney | 2012-10-05 | TBD | TBD | AC | Oswego | NY | C | Scriba - Volney 345kV | NM-NG/NYSEG | 0 | 2016-05-31
0398 | Black Oak Wind Farm, LLC | Black Oak Wind | 2013-01-10 | 12.5 | 12.5 | W | Thompkins | NY | C | Montour - Coddington 115kV | NYSEG | 0 | 2017-08-31
0399 | American Electric Power | Mohawk Valley HVDC | 2013-02-27 | 1000 | 1000 | DC | Oneida-Bronx | NY | E, J | Marcy - Mott Haven 345kV | NYPA/ConEd | 0 | 2013-06-30
0400 | East Coast Power LLC | Linden Cogen Uprate | 2013-03-04 | 208 | 204 | CT | Linden | NJ | J | Linden Cogen 345kV | ConEd | 0 | 2015-10-31
0401 | Caithness Long Island II, LLC | Caithness Long Island II | 2013-03-22 | 599 | 632 | D | Suffolk | NY | K | Sills Road Substation 138kV | LIPA | 0 | 2018-09-30
0402 | NextEra Energy Transmission | Marcy - PV 345 | 2013-05-17 | TBD | TBD | AC | Oneida-Dutchess | NY | E-G | Marcy - P. Valley 345kV | NM-NG/NYPA/ ConEd | 0 | 2015-02-28
0404 | NextEra Energy Transmission | Princetown - Rotterdam 230 | 2013-06-04 | TBD | TBD | AC | Schenectady | NY | F | Princetown - Rotterdam 230kV | NM-NG | 0 | 2016-05-31
0405 | NextEra Energy Transmission | Oakdale - Fraser 345 | 2013-06-21 | TBD | TBD | AC | Broome-Delaware | NY | C, E | Oakdale - Fraser 345kV | NYSEG | 0 | 2015-12-31
0406 | NextEra Energy Transmission | Marcy - KB - PV 345 | 2013-06-21 | TBD | TBD | AC | Oneida-Dutchess | NY | E-G | Marcy - P. Valley 345kV | NM-NG/NYPA/ ConEd | 0 | 2015-02-28
0407 | National Grid | Edic-N.Scotland-Leed-PV | 2013-07-01 | TBD | TBD | AC | Oneida-Dutchess | NY | E-G | Edic - Pleasant Valley 345kV | NM-NG | 0 | 2015-02-28
0408 | National Grid | Edic-Princetown-N.Scotland-Leeds-PV | 2013-07-01 | TBD | TBD | AC | Oneida-Dutchess | NY | E, G | Edic - Pleasant Valley 345kV | NM-NG | 0 | 2015-02-28
0409 | National Grid | Edic-Knickerbocker-PV | 2013-07-01 | TBD | TBD | AC | Oneida-Dutchess | NY | E, G | Edic - Pleasant Valley 345kV | NM-NG | 0 | 2015-02-28
0410 | National Grid | Edic-Princetown-Knickerbocker-PV | 2013-07-01 | TBD | TBD | AC | Oneida-Dutchess | NY | E, G | Edic - Pleasant Valley 345kV | NM-NG | 0 | 2015-02-28
0411 | BCDC Transmission LLC | BCDC Transmission | 2013-07-01 | 400 | 400 | AC | New York | NY | J | NJ - Farragut Substation 345kV | ConEd | 0 | 2013-12-31
0412 | New York State Electric & Gas | Oakdale - Fraser 345 | 2013-08-20 | N/A | N/A | AC | Broome-Delaware | NY | C, E | Oakdale - Fraser 345kV | NYSEG | 0 | 2016-07-31
0413 | National Grid | Edic-Prince.-N.Scotland-Knick.-PV | 2013-08-21 | TBD | TBD | AC | Oneida-Dutchess | NY | E, G | Edic - Pleasant Valley 345kV | NM-NG | 0 | 2015-02-28
0414 | North America Transmission, LLC | Segment B Enhanced | 2013-09-05 | N/A | N/A | AC | Albany-Dutchess | NY | F, G | New Scotland - P. Valley 345kV | NM-NG/ConEd/ O&R/CHGE | 0 | 2019-04-30
0415 | Iberdrola USA | Connect New York | 2013-09-06 | 1000 | 1000 | DC | Albany-Dutchess | NY | F, G | New Scotland - Hurley Ave 345kV | NM-NG/Cen Hud | 0 | 2014-10-31
0416 | NextEra Energy Transmission | Marcy - KB - PV 345 (2) | 2013-09-09 | TBD | TBD | AC | Oneida-Dutchess | NY | E, G | Marcy - P. Valley 345kV | NM-NG/NYPA/ ConEd | 0 | 2015-02-28
0417 | NextEra Energy Transmission | Marcy - KB - PV 345 (3) | 2013-09-09 | TBD | TBD | AC | Oneida-Dutchess | NY | E, G | Marcy - P. Valley 345kV | NM-NG/NYPA/ ConEd | 0 | 2016-05-31
0418 | NextEra Energy Transmission | Marcy - NS - PV 345 | 2013-09-09 | TBD | TBD | AC | Oneida-Dutchess | NY | E, G | Marcy - P. Valley 345kV | NM-NG/NYPA/ ConEd | 0 | 2015-03-31
0419 | NextEra Energy Transmission | Marcy - NS - KB - PV 345 | 2013-09-16 | TBD | TBD | AC | Oneida-Dutchess | NY | E, G | Marcy - P. Valley 345kV | NM-NG/NYPA/ ConEd | 0 | 2016-05-31
0420 | NextEra Energy Transmission | Marcy - KB - PV 345 (4) | 2013-09-16 | TBD | TBD | AC | Oneida-Dutchess | NY | E, G | Marcy - P. Valley 345kV | NM-NG/NYPA/ ConEd | 0 | 2015-02-28
0423 | Rochester Gas & Electric | University of Rochester | 2013-11-17 | 25 | 25 | L | Monroe | NY | B | Station 251 | NYSEG | 0 | 2014-07-31
0424 | Boundless Energy NE, LLC | Leeds Path West | 2013-11-26 | N/A | N/A | AC | Greene-Westchester | NY | G-J | Leeds - Millwood 345kV | NM-NG/NYPA/ Cen Hud/ConEd/NYSEG | 0 | 2017-02-28
0425 | NextEra Energy Resources, LLC | Brookfield Wind Energy | 2013-12-11 | 100.3 | 100.3 | W | Chenango, Madison | NY | E | Chadwicks - Yahnundadis 115kV | NM-NG/NYSEG | 0 | 2015-05-31
0426 | North America Transmission, LLC | NS-Knickerbocker-PV | 2013-12-11 | TBD | TBD | AC | Albany-Dutchess | NY | F-G | New Scotland - P. Valley 345kV | NM-NG/ConEd | 0 | 2014-02-28
0427 | Island Park Energy Center, LLC | Island Park Energy Center CCPP | 2014-01-24 | 268 | 295 | CT | Nassau | NY | K | Barrett Power Station 138kV | LIPA | 0 | 2017-02-28
0428 | Island Park Energy Center, LLC | Island Park Energy Center SCPP | 2014-01-24 | 262 | 252 | CT | Nassau | NY | K | Barrett Power Station 138kV | LIPA | 0 | 2017-02-28
0433 | East Hampton Solar Farm, LLC | East Hampton - Phase 1 | 2014-04-21 | 20 | 20 | S | Suffolk | NY | K | Amagansett Substation 69KV | LIPA | 0 | 2014-05-31
0434 | East Hampton Solar Farm 2, LLC | East Hampton - Phase 2 | 2014-04-21 | 20 | 20 | S | Suffolk | NY | K | Amagansett Substation 69KV | LIPA | 0 | 2014-05-31
0435 | East Hampton Solar Farm 2, LLC | East Hampton - Phase 3 | 2014-04-21 | 20 | 20 | S | Suffolk | NY | K | Amagansett Substation 69KV | LIPA | 0 | 2014-05-31
0436 | East Hampton Solar Farm 2, LLC | Riverhead - Phase 1 | 2014-04-21 | 20 | 20 | S | Suffolk | NY | K | Edwards Substation 69KV | LIPA | 0 | 2014-05-31
0437 | East Hampton Solar Farm 2, LLC | Riverhead - Phase 2 | 2014-04-21 | 20 | 20 | S | Suffolk | NY | K | Edwards Substation 69KV | LIPA | 0 | 2014-05-31
0438 | East Hampton Solar Farm 2, LLC | Riverhead - Phase 3 | 2014-04-21 | 20 | 20 | S | Suffolk | NY | K | Edwards Substation 69KV | LIPA | 0 | 2014-05-31
0439 | Boston Energy Trading | East Garden City-Valley Stream | 2014-05-09 | TBD | TBD | AC | Nassau | NY | K | E. Garden City-Valley Stream 138kV | LIPA | 0 | 2016-04-30
0440 | Erie Power, LLC | Erie Power | 2014-06-02 | 79.4 | 88 | CC | Chautauqua | NY | A | South Ripley Substation 230kV | NM-NG | 0 | 2018-02-28
0441 | East Hampton Solar Farm, LLC | East Hampton Solar | 2014-06-09 | 60 | 60 | S | Suffolk | NY | K | Buell Substation 69kV | LIPA | 0 | 2015-01-31
0442 | Riverhead Solar Farm, LLC | Riverhead Solar | 2014-06-09 | 24 | 24 | S | Suffolk | NY | K | Edwards Substation 138kV | LIPA | 0 | 2015-05-31
0443 | Manorville Solar, LLC | Manorville Solar | 2014-06-09 | 16 | 16 | S | Suffolk | NY | K | Riverhead - Eastport 69kV | LIPA | 0 | 2015-04-30
0445 | Lighthouse Wind, LLC | Lighthouse Wind | 2014-06-30 | 201.3 | 201.3 | W | Niagara | NY | A | AES Somerset Substation 345kV | NYSEG | 0 | 2021-02-28
0446 | Solar Alliance Freedom, Inc. | Jockey Hill Solar | 2014-07-21 | 2 | 2 | S | Ulster | NY | G | Hurley Substation 345kV | CenHud | 0 | 2014-09-30
0447 | FTS Devco LLC | East Hampton Expansion | 2014-07-25 | 20 | 20 | S | Suffolk | NY | K | Amagansett Substation 69kV | LIPA | 0 | 2015-01-31
0448 | Alps Interconnector, LLC | Alps HVDC | 2014-08-12 | 600 | 600 | DC |  |  | F | Alps Substation 345kV | NM-NG | 0 | 2018-11-30
0449 | Stockbridge Wind, LLC | Stockbridge Wind | 2014-08-13 | 72.6 | 72.6 | W | Madison | NY | C | Whitman - Oneida 115kV | NM-NG | 0 | 2021-02-28
0450 | Stacy Solar Center, LLC | Stacy Solar | 2014-08-20 | 20 | 20 | S | Greene | NY | G | Coxsackie Substation 69kV | CenHud | 0 | 2015-02-28
0451 | Shortsville Solar Center, LLC | Shortsville Solar | 2014-08-20 | 20 | 20 | S | Ontario | NY | B | Substation #168 34.5kV | NYSEG | 0 | 2014-10-31
0452 | Taconic Solar Center, LLC | Taconic Solar | 2014-08-20 | 10 | 10 | S | Columbia | NY | F | Craryville Substation 34.5kV | NYSEG | 0 | 2014-10-31
0453 | Blue Hill Solar Center, LLC | Blue Hill Solar | 2014-08-20 | 20 | 20 | S | Columbia | NY | F | Blue Stores Substation 115kV | NM-NG | 0 | 2014-10-31
0454 | Sabin Solar Center, LLC | Sabin Solar | 2014-08-20 | 20 | 20 | S | Herkimer | NY | E | Salisbury Substation 115kV | NM-NG | 0 | 2014-10-31
0455 | Roseway Solar, LLC | Roseway Solar | 2014-08-21 | 19.9 | 19.9 | S | Sullivan | NY | E | 34.5kV | NYSEG | 0 | 2015-02-28
0456 | ESA Solar NY, LLC | Woodhull Solar | 2014-09-09 | 0.7 | 0.7 | S | Steuben | NY | C | Woodhull Substation | NYSEG | 0 | 2015-07-31
0457 | RES America Developments Inc. | Bellmont Wind | 2014-09-22 | 19.8 | 19.8 | W |  |  |  | Brainardsville, NY | NYSEG | 0 | 2014-12-31
0458 | TDI-USA Holdings, Inc. | CH Interconnection | 2014-10-24 | 1000 | 1000 | DC | Quebec-New York | NY | J | Astoria Annex Substation 345kV | NYPA | 0 | 2021-05-31
0459 | ESA Solar NY, LLC | Warsaw Solar | 2014-11-05 | 2 | 2 | S | Wyoming | NY | B | Wethersfield Substation 115kV | NYSEG | 0 | 2014-12-31
0460 | Dryden Solar, LLC | Dryden Solar | 2014-11-10 | 5 | 5 | S | Thompkins | NY | C |  | NYSEG | 0 | 2014-12-31
0463 | Long Island Clean Energy Project LLC | 62 Weeks Rd. Fuel Cell | 2014-12-05 | 19.9 | 19.9 |  | Suffolk | NY | K | 69kV | LIPA | 0 | 2015-01-31
0464 | Long Island Clean Energy Project LLC | Pulaski Rd. Fuel Cell | 2014-12-05 | 19.9 | 19.9 |  | Suffolk | NY | K | 138kV | LIPA | 0 | 2015-01-31
0465 | Hudson Transmission Partners | Hudson Transmission NY to PJM | 2014-12-15 | 675 | 675 | DC | New York | NY | J | W49th St 345kV - Bergen 230kV | ConEd | 0 | 2021-01-31
0466 | Atlantic Wind, LLC | Bone Run Wind | 2014-12-16 | 132 | 132 | W | Cattaraugus | NY | A | Falconer - Homer Hill 115kV | NM-NG | 0 | 2021-02-28
0468 | Apex Clean Energy LLC | Galloo Island Wind | 2014-12-30 | 110.4 | 110.4 | W | Oswego | NY | C | Hammermill - Wine Creek 115kV | NM-NG | 0 | 2021-02-28
0469 | NextEra Energy Transmission | Edic-PV 345 | 2015-01-06 | TBD | TBD | AC | Oneida-Dutchess | NY | E, G | Edic - Pleasant Valley 345kV | NM-NG/ConEd | 0 | 2015-05-31
0470 | NextEra Energy Transmission | Knickerbocker 115 | 2015-01-06 | TBD | TBD | AC | Columbia-Rensselaer | NY | F | Greenbush - Churchtown 115kV | NM-NG/NYSEG/ CHGE | 0 | 2016-05-31
0471 | NextEra Energy Transmission | Marcy-Princetown 345 | 2015-01-06 | TBD | TBD | AC | Oneida-Albany | NY | E, F | Marcy - Princetown 345kV | NM-NG/NYPA/ ConEd | 0 | 2016-05-31
0472 | NextEra Energy Transmission | Knickerbocker 345 | 2015-01-06 | TBD | TBD | AC | Rensselaer-Dutchess | NY | F | Knickerbocker - P. Valley 345kV | NM-NG/ConEd | 0 | 2016-05-31
0473 | Calverton Solar LLC | Calverton Solar | 2015-01-21 | 10 | 10 | S | Suffolk | NY | K | Riverhead - Wildwood 69kV | LIPA | 0 | 2019-02-28
0474 | EDP Renewables North America | North Slope Wind | 2015-01-30 | 200 | 200 | W | Franklin-Clinton | NY | D | Patnode 230kV | NYPA | 0 | 2021-02-28
0475 | OneEnergy Development, LLC | Windy Hill Solar | 2015-02-02 | 20 | 20 | W | Washington | NY | F | Battenkill Substation 115kV | NM-NG | 0 | 2015-07-31
0476 | New York State Electric & Gas | Edic-PV, Oakdale-Fraser | 2015-02-12 | N/A | N/A | AC | Oneida-Delaware | NY | E | Edic-PV, Oakdale-Fraser 345kV | NM-NG/NYSEG | 0 | 2016-07-31
0478 | Central Hudson Gas & Electric | Hurley Ave PARs | 2015-02-17 | TBD | TBD | AC | Dutchess | NY | G | Hurley Ave 345kV | CHGE/NM-NG/NYSEG | 0 | 2016-03-31
0479 | Central Hudson Gas & Electric | Edic-NS, Hurley PARs | 2015-02-17 | TBD | TBD | AC | Oneida-Dutchess | NY | E-G | Edic-NS, Hurley Ave 345kV | CHGE/NM-NG/NYSEG/NYPA | 0 | 2016-03-31
0480 | National Grid | Edic-NS, Knickerbocker-PV | 2015-02-20 | TBD | TBD | AC | Oneida-Dutchess | NY | E-G | Edic-NS, Knickerbocker-PV 345kV | NM-NG/ConEd | 0 | 2016-05-31
0481 | National Grid | Leeds - Pleasant Valley | 2015-02-20 | TBD | TBD | AC | Greene-Dutchess | NY | G | Leeds - P. Valley 345kV | NM-NG/ConEd | 0 | 2015-12-31
0482 | National Grid | Edic-NS, NS-Leeds-PV | 2015-02-20 | TBD | TBD | AC | Oneida-Dutchess | NY | E, G | Edic-NS, NS-Leeds-PV 345kV | NM-NG/ConEd | 0 | 2015-12-31
0483 | National Grid | NS-Leeds, Leeds-PV | 2015-02-20 | TBD | TBD | AC | Albany-Dutchess | NY | F, G | NS-Leeds, Leeds-PV 345kV | NM-NG/ConEd | 0 | 2015-12-31
0484 | National Grid | Edic-NS, NS-Leeds, Leeds-PV | 2015-02-20 | TBD | TBD | AC | Oneida-Dutchess | NY | E, G | Edic-NS, NS-Leeds, Leeds-PV 345kV | NM-NG/ConEd | 0 | 2015-12-31
0485 | National Grid | Knickerbocker-PV | 2015-03-04 | TBD | TBD | AC | Columbia-Dutchess | NY | F, G | Knickerbocker - P. Valley 345kV | NM-NG/ConEd | 0 | 2016-05-31
0486 | LI Energy Storage System | Buell Battery Storage | 2015-03-09 | 20 | 20 | ES | Suffolk | NY | K | East Hampton Substation 69kV | LIPA | 0 | 2015-10-31
0488 | LI Energy Storage System | Glenwood Battery Storage | 2015-03-09 | 20 | 20 | ES | Suffolk | NY | K | Glenwood Substation 69kV | LIPA | 0 | 2017-04-30
0489 | LI Energy Storage System | Southampton Battery Storage | 2015-03-09 | 20 | 20 | ES | Suffolk | NY | K | Southampton 69kV | LIPA | 0 | 2015-10-31
0491 | Yaphank Fuel Cell Park, LLC | Yaphank Fuel Cell Park | 2015-03-23 | 19.6 | 19.6 | ES | Suffolk | NY | K | Yaphank Substation 69kV | LIPA | 0 | 2015-07-31
0492 | Setauket Fuel Cell Park, LLC | Setauket Fuel Cell Park | 2015-03-23 | 19.6 | 19.6 | FC | Suffolk | NY | K | Terryville Substation 69kV | LIPA | 0 | 2016-09-30
0493 | EPCAL Fuel Cell Park, LLC | EPCAL Fuel Cell Park | 2015-03-30 | 19.6 | 19.6 | FC | Suffolk | NY | K | Riverhead 69 kV | LIPA | 0 | 2016-01-31
0494 | Alabama Ledge Wind Farm LLC | Alabama Ledge Wind | 2015-03-31 | 79.8 | 79.8 | W | Genesee | NY | B | Lockport - Oakfield 115kV | NM-NG | 0 | 2020-01-31
0496 | Renovo Energy Center, LLC | Renovo Energy Center | 2015-04-13 | 480 | 504 | CC | Clinton | PA | C | Homer City - Mainsburg 345kV | NYSEG | 0 | 2021-02-28
0498 | ESC Tioga County Power, LLC | Tioga County Power | 2015-04-29 | 550 | 550 | CC | Tioga | PA | C | Homer City - Mainsburg 345kV | NYSEG | 0 | 2021-02-28
0499 | Sharon Solar LLC | Sharon Solar | 2015-05-07 | 19.6 | 19.6 | S | Schoharie | NY | F | Sharon Substation 69kV | NM-NG | 0 | 2015-10-31
0500 | Regeneron Solar LLC | Regeneron Solar | 2015-05-12 | 2 | 2 | S | Rensselaer | NY | F | East Greenbush, NY | NM-NG | 0 | 2015-08-31
0501 | Regeneron Solar LLC | Mariaville 2 Solar | 2015-05-12 | 2 | 2 | S | Schenectady | NY | F | Mariaville, NY | NM-NG | 0 | 2015-08-31
0502 | Lincoln Park DG LLC | Lincoln Park | 2015-05-22 | 18.3 | 18.3 |  | Dutchess | NY | F | Lincoln Park Substation | CHGE | 0 | 2015-06-30
0503 | East Kingstson DG LLC | East Kingston | 2015-05-22 | 18.3 | 18.3 |  | Dutchess | NY | F | East Kingston Substation | CHGE | 0 | 2015-06-30
0504 | NY DG Holding LLC | Saugerties | 2015-05-22 | 18.3 | 18.3 |  | Dutchess | NY | F | Saugerties Substation | CHGE | 0 | 2015-06-30
0505A | Central Hudson | Hurley Ave & Saugerties | 2015-06-05 | TBD | TBD | AC | Greene-Ulster | NY | G | Hurley Ave & Saugerties 69kV | CHGE | 0 | 2015-10-31
0507 | Erie Boulevard Hydropower, LP | Glens Falls Hydro | 2015-07-02 | 14.8 | 14.8 | H | Washington | NY | F | Henry St. - Glens Falls 34.5kV | NM-NG | 0 | 2016-12-31
0508 | Blue Circle DG LLC | Blue Circle | 2015-07-17 | 18.2 | 18.2 | FC | Greene | NY | G | LaFarge - PV 115 kV | NM-NG | 0 | 2016-02-29
0509 | North Catskill DG LLC | North Catskill | 2015-07-17 | 18.2 | 18.2 |  | Greene | NY | G | North Catskill Substation | CHGE | 0 | 2015-08-31
0511 | AG Energy, LP | Ogdensburg | 2015-09-04 | 79 | 90.1 | CC | St. Lawrence | NY | E | North Ogdensburg Substation | NM-NG | 0 | 2019-09-30
0512 | Northbrook Lyons Falls | Lyons Fills Mill Hydro | 2015-09-11 | 2.5 | 2.5 | H | Lewis | NY | E | Taylorville- Boonville 115 kV | NM-NG | 0 | 2019-06-30
0514 | RES Americas Developments Inc. | Empire Wind | 2015-10-01 | 120 | 120 | W | Rensselaer | NY | F | Stephentown - Greenbush 115kV | NM-NG | 0 | 2018-07-31
0515 | North Bergen Liberty Generation Center LLC | Liberty Generation | 2015-10-07 | 1000 | 1000 | CC | New York | NY | J | W49th St 345kV | ConEd | 0 | 2018-01-31
0516 | East Coast Power LLC | Linden Cogen Uprate | 2015-10-12 | 234.4 | 234.4 | CT | Union | NJ | J | Linden Cogen 345kV | ConEd | 0 | 2020-02-29
0518 | PPL Electric Utilities | Compass | 2015-10-27 | N/A | N/A | AC | Rockland | NY | G | Lackawanna - Ramapo 345kV | ConEd | 0 | 2021-05-31
0523 | Dunkirk Power LLC | Dunkirk Unit 2 | 2015-12-17 | 75 | 75 | ST | Chautauqua | NY | A | Dunkirk 115kV | NM-NG | 0 | 2020-06-30
0524 | Dunkirk Power LLC | Dunkirk Unit 3 & 4 | 2015-12-17 | 370 | 370 | ST | Chautauqua | NY | A | Dunkirk 230kV | NM-NG | 0 | 2020-06-30
0525 | New York Power Authority | Western NY Energy Link | 2015-12-18 | N/A | N/A | AC | Niagara | NY | A | Niagara - Stolle - Gardenville | NYPA/NYSEG | 0 | 2018-02-28
0527 | Atlantic Wind, LLC | Horse Creek Wind | 2015-12-23 | 250 | 250 | W | Jefferson | NY | E | Indian River 115kV | NM-NG | 0 | 2017-07-31
0528 | National Grid | Moderate Power Transfer | 2015-12-30 | N/A | N/A | AC | Niagara-Erie | NY | A | Niagara, Erie, Stolle, Gardenville | NM-NG | 0 | 2017-09-30
0529 | National Grid | High Power Transfer | 2015-12-30 | N/A | N/A | AC | Niagara-Erie | NY | A | Niagara, Erie, Stolle, Gardenville | NM-NG | 0 | 2017-09-30
0530 | NextEra Energy Transmission New York, Inc. | Empire State Line | 2016-01-04 | N/A | N/A | AC | Niagara-Erie | NY | A | Dysinger - Stolle 345kV | NYPA/NYSEG | 0 | 2018-01-31
0532 | Invenergy Wind Development LLC | Allegany Wind | 2016-02-01 | 100 | 100 | W | Allegany | NY | B | Freedom Substation | Village of Arcade | 0 | 2019-03-31
0533 | Delano Management LLC | Empire Interconnection | 2016-02-03 | 275 | 275 | DC | Nassau | NY | K | Far Rockaway Substation 69kV | LIPA | 0 | 2017-11-30
0534 | OneEnergy Development, LLC | Great Valley Solar | 2016-02-03 | 20 | 20 | S | Washington | NY | F | Battenkill 34.5kV Substation | NM-NG | 0 | 2019-07-31
0536 | Empire Interconnection LLC | Glenwood | 2016-04-19 | 275 | 275 | AC | Suffolk | NY | K | Glenwood/Far Rockaway Station 69kV | LIPA | 0 | 2017-11-30
0537 | NextEra Energy Transmission New York, Inc. | Segment A | 2016-04-25 | N/A | N/A | AC | Oneida-Albany | NY | E, F | Edic - New Scotland 345kV | NM-NG/NYPA | 0 | 2018-01-31
0538 | NextEra Energy Transmission New York, Inc. | Segment B | 2016-04-25 | N/A | N/A | AC | Albany-Dutchess | NY | F, G | Greenbush - PV 345kV | NM-NG/NYSEG/ CHGE/ConEd | 0 | 2018-10-31
0539 | NextEra Energy Transmission New York, Inc. | Segment B Alt | 2016-04-25 | N/A | N/A | AC | Albany-Dutchess | NY | F, G | Greenbush - PV 345kV | NM-NG/NYSEG/ CHGE/ConEd | 0 | 2018-10-31
0542 | National Grid | Segment A Edic-New Scotland | 2016-05-04 | N/A | N/A | AC | Oneida-Albany | NY | E, F | Edic - New Scotland 345kV | NM-NG | 0 | 2018-01-31
0544 | Invenergy Wind Development LLC | Alle Catt Wind | 2016-05-04 | 100.5 | 100.5 | W | Cattaraugus | NY | A | Freedom Substation 115kV | Village of Arcade | 0 | 2017-08-31
0547 | North America Transmission, LLC | Dysinger-Stolle | 2016-05-25 | N/A | N/A | AC | Niagara-Erie | NY | A | Dysinger - Stolle 345kV | NYPA/NYSEG/ NM-NG | 0 | 2019-04-30
0548 | North America Transmission, LLC | Dysinger-Stolle-Gardenville | 2016-05-25 | N/A | N/A | AC | Niagara-Erie | NY | A | Dysinger - Gardenville 345kV | NYPA/NYSEG/ NM-NG | 0 | 2017-10-31
0549 | North America Transmission, LLC | Niagara-Dysinger-Stolle-Gardenville | 2016-05-25 | N/A | N/A | AC | Niagara-Erie | NY | A | Niagara - Gardenville 345kV | NYPA/NYSEG/ NM-NG | 0 | 2017-10-31
0550 | North America Transmission, LLC | Dysinger-Stolle-Gardenville II | 2016-06-02 | N/A | N/A | AC | Niagara-Erie | NY | A | Dysinger - Gardenville 345kV | NYPA/NYSEG/ NM-NG | 0 | 2017-10-31
0551 | OneEnergy Development, LLC | Caprock Solar | 2016-06-24 | 20 | 20 | S | Monroe | NY | B | South Union - Sweden 115kV | NM-NG | 0 | 2017-08-31
0552 | OneEnergy Development, LLC | Flotilla Solar | 2016-06-24 | 20 | 20 | S | Monroe | NY | B | Brockport - Hamlin 115kV | NM-NG | 0 | 2017-08-31
0553 | OneEnergy Development, LLC | Caspian Solar | 2016-06-24 | 20 | 20 | S | Monroe | NY | B | Sweden - South Union 115kV | NM-NG | 0 | 2016-08-31
0554 | Lookheed Martin | Lockheed Matin MST Syracuse | 2016-06-27 | [6 empty] | Lockheed Martin switch 13.8kV | NM-NG | 0 | 2016-07-31
0555 | North America Transmission, LLC | Segment A Base | 2016-07-06 | N/A | N/A | AC | Oneida-Albany | NY | E, F | Edic - New Scotland 345kV | NM-NG | 0 | 2019-04-30
0557 | North America Transmission, LLC | Segment A Enhanced | 2016-07-06 | N/A | N/A | AC | Oneida-Albany | NY | E, F | Edic - New Scotland 345kV | NM-NG | 0 | 2019-04-30
0558 | North America Transmission, LLC | Segment A 765 | 2016-07-06 | N/A | N/A | AC | Oneida-Albany | NY | E, F | Edic - New Scotland 345kV | NM-NG/ NYPA | 0 | 2019-04-30
0559 | North America Transmission, LLC | Segment B Base | 2016-07-06 | N/A | N/A | AC | Oneida-Albany | NY | E, F | Knickerbocker - PV 345kV | NM-NG/O&R CHGE/ConEd | 0 | 2019-04-30
0561 | Astoria Generating Company LP | Astoria Generating Unit 4 | 2016-07-18 | 385 | 385 | ST | New York | NY | J | Astoria West Substation 138 kV | ConEd | 0 | 2020-02-29
0562 | OneEnergy Development, LLC | Hidden Meadow Solar | 2016-07-22 | 20 | 20 | S | Columbia-Dutchess | NY | F, G | Milan - Churchtown 115kV | NM-NG | 0 | 2017-03-31
0563 | Double Lock Solar, LLC | Double Lock Solar | 2016-07-25 | 20 | 20 | S | Herkimer | NY | E | St. Johnsville - Marshville 115kV | NM-NG | 0 | 2019-07-31
0567 | Tribes Hill Solar, LLC | Tribes Hill Solar | 2016-08-10 | 20 | 20 | S | Montgomery | NY | F | Ephrata - Florida 69KV | NM-NG | 0 | 2018-06-30
0568 | Turkey Hollow Solar, LLC | Turkey Hollow Solar | 2016-08-16 | 20 | 20 | S | Delaware | NY | F | Grand Gorge - Axtell Road 115kV | NYSEG | 0 | 2018-01-31
0569 | Hecate Energy, LLC | Greene County | 2016-08-17 | 50 | 50 | S | Greene | NY | G |  | CHGE | 0 | 2016-09-30
0576 | Astoria Generating Company LP | Astoria Generating Unit 4 | 2016-09-16 | 385 | 385 | ST | New York | NY | J | Astoria East Substation 138kV | ConEd | 0 | 2020-02-29
0578 | Sharon Solar LLC | Sharon Solar | 2016-09-20 | 20 | 20 | S | Schoharie | NY | F | Sharon Substation 69kV | NM-NG | 0 | 2017-06-30
0582 | Sunny Knoll Solar LLC | Sunny Knoll Solar | 2016-10-18 | 20 | 20 | S | Schoharie | NY | F | Cobleskill - Schoharie 69kV | NM-NG | 0 | 2019-05-31
0585 | Caledonia Solar LLC | Caledonia I Solar | 2016-11-07 | 20 | 20 | S | Livingston | NY | A | Golah - South Perry 69kV | NM-NG | 0 | 2018-06-30
0587 | Fork Valley Solar LLC | Fork Valley Solar | 2016-11-08 | 20 | 20 | S | Steuben | NY | C | Eelpot Rd 345.5kV Substation | NYSEG | 0 | 2018-07-31
0588 | Exelon Transmission Co., LLC | Niagara Transmission Expansion | 2016-11-15 | N/A | N/A | AC | Niagara-Erie | NY | A | Niagara - Gardenville | NYPA/NYSEG/ NM-NG | 0 | 2017-09-30
0593 | OneEnergy Development, LLC | Raceway Solar | 2016-12-28 | 20 | 20 | S | Rensselaer | NY | F | Cobb Hill Substation | NYSEG | 0 | 2017-04-30
0595 | North Park Energy, LLC | SW Energy | 2016-12-29 | 100 | 100 | ES | Cattaraugus | NY | A | Five Mile Rd Substation 115kV | NM-NG | 0 | 2021-08-31
0599 | LeRoy, LLC | LeRoy Solar | 2017-01-11 | 20 | 20 | S | Genesee | NY | B | LeRoy Substation 115kV | NGrid | 0 | 2017-04-30
0600 | Conti Enterprises, Inc. | Darby Solar | 2017-01-12 | 20 | 20 | S | Washington | NY | G | Mechanicville - Schaghticoke 34.5kV | NM-NG | 0 | 2019-04-30
0601 | HP Hood LLC | Hood Cogen | 2017-01-20 | 4 | 4 | CT | Madison | NY | C | Oneida - Fenner 115kV | NGrid | 0 | 2018-12-31
0602 | Cypress Creek Renewables | Keesog Solar | 2017-01-30 | 50 | 50 | S | Franklin | NY | D | Moses - Willis 230kV | NYPA | 0 | 2017-05-31
0603 | Hecate Energy Riverhead, LLC | Riverhead | 2017-02-03 | 7.5 | 7.5 | S | Suffolk | NY | K | Wildwood - Riverhead 69kV | LIPA | 0 | 2018-05-31
0604 | Hecate Energy Columbia County 1, LLC | Columbia County 1 | 2017-02-07 | 20 | 20 | S | Columbia | NY | G | Craryville Substation 34.5kV | NYSEG | 0 | 2017-07-31
0605 | Hecate Energy Columbia County 2, LLC | Columbia County 2 | 2017-02-07 | 20 | 20 | S | Columbia | NY | G | Craryville Substation 34.5kV | NYSEG | 0 | 2017-07-31
0606 | Hecate Energy Craryville 3, LLC | Columbia County 3 | 2017-02-07 | 10 | 10 | S | Columbia | NY | G | Craryville Substation 34.5kV | NYSEG | 0 | 2017-07-31
0607 | Empire State Connector Corporation | Empire State Connector II | 2017-02-08 | 1000 | 1000 | DC | Oneida-New York | NY | E, J | Marcy - Astoria 345kV | NYPA/NM-NG/ ConEd | 0 | 2017-03-31
0608 | ITC New York Development, LLC | Segment A | 2017-02-08 | N/A | N/A | AC | Oneida-Albany | NY | E, F | Edic - New Scotland 345kV | NM-NG | 0 | 2019-04-30
0609 | ITC New York Development, LLC | Segment B | 2017-02-08 | N/A | N/A | AC | Oneida-Albany | NY | E, F | Knickerbocker - PV 345kV | NM-NG/NYSEG/ CHGE/ConEd | 0 | 2019-04-30
0610 | Woodruff Solar, LLC | Woodruff Solar | 2017-02-10 | 20 | 20 | S | Livingston | NY | A | Golah - N. Lakeville 34.5KV | NM-NG | 0 | 2019-06-30
0611 | Badra Solar, LLC | Badra Solar | 2017-02-10 | 20 | 20 | S | Franklin | NY | D | Nicholville - Malone 115kV | NM-NG | 0 | 2017-03-31
0613 | OneEnergy Development, LLC | Sugar Maple Solar | 2017-02-17 | 20 | 20 | S | Herkimer | NY | E | Trenton Falls - Poland 46kV | NM-NG | 0 | 2019-06-30
0614 | Sabertooth Solar, LLC | Sabertooth Solar | 2017-02-22 | 20 | 20 | S | Cortland | NY | B | Willett - Lapeer 115kV | NYSEG | 0 | 2017-06-30
0615 | West Point Partners, LLC | West Point II HVDC | 2017-03-02 | 1000 | 1000 | DC | Albany-Westchester | NY | F, H | New Scotland - Buchanan South 345kV | NM-NG/ConEd | 0 | 2019-02-28
0616 | Heelstone Development, LLC | Mohawk Solar | 2017-03-23 | 20 | 20 | S | Herkimer | NY | E | Watkins Rd - Ilion 115kV | NM-NG | 0 | 2019-04-30
0621 | Blue Stone Solar Energy, LLC | Saugerties Solar | 2017-03-27 | 20 | 20 | S | Ulster | NY | G | Saugerties - Woodstock 69kV | CHGE | 0 | 2020-10-31
0622 | Geronimo Solar Energy, LLC | Alcoa Solar | 2017-03-27 | 20 | 20 | S | St. Lawrence | NY | E | 13.8kV | NM-NG | 0 | 2017-06-30
0623 | Conti Enterprises, Inc. | Puckett Solar | 2017-04-05 | 20 | 20 | S | Chenango | NY | C | Chenango Forks 34.5kV Substation | NYSEG | 0 | 2017-06-30
0625 | Whitehart Solar, LLC | Whitehart Solar | 2017-04-13 | 20 | 20 | S | Sullivan | NY | E | Hyatt Rd.- Border City 115kV | NYSEG | 0 | 2018-09-30
0626 | KCE NY 1, LLC | KCE NY 1 | 2017-04-14 | 20 | 20 |  | Saratoga | NY | F | Luther Forest 34.5kV Substation | NM-NG | 0 | 2017-06-30
0627 | OneEnergy Development, LLC | Southtown 2 Solar | 2017-04-17 | 20 | 20 | S |  |  |  | North Angola 34.5kV Substation | NM-NG | 0 | 2017-06-30
0628 | OneEnergy Development, LLC | Slingshot 2 Solar | 2017-04-17 | 20 | 20 | S | Steuben | NY | C | Hammondsport 34.5 kV Substation | NYSEG | 0 | 2017-08-31
0630 | Cayuga Operating Co. | Cayuga Solar | 2017-04-27 | 20 | 20 | S | Lansing | NY | C | Milliken 34.5 Substation | NYSEG | 0 | 2018-01-31
0633 | Conti Enterprises, Inc. | Janis Solar | 2017-05-15 | 20 | 20 | S |  |  | B | Willet - Tarbell 34.5 kV | NYSEG | 0 | 2017-06-30
0634 | Champagne Storage, LLC | Champagne Storage | 2017-05-18 | 20 | 20 | ES | Madison | NY | E | Oneida - Cortland 115kV | NM-NG | 0 | 2018-01-31
0635 | Rising Solar, LLC | Rising Solar | 2017-06-14 | 20 | 20 | S | Orange | NY | G | Sugarloaf - Wisner 69kV | O&R | 0 | 2018-12-31
0636 | Daybreak Solar, LLC | Daybreak Solar | 2017-06-15 | 25 | 25 | S | Ulster | NY | G | East Walden Substation 69kV | CHGE | 0 | 2019-01-31
0639 | Owego Solar LLC | Owego Solar | 2017-07-19 | 20 | 20 | S | Tioga | NY | C | South Owego - Stagecoach 115kV | NYSEG | 0 | 2017-11-30
0640 | Granada Solar, LLC | Grissom Solar | 2017-07-19 | 20 | 20 | S | Fulton | NY | F | Vail Mills Substation 69kV | NM-NG | 0 | 2017-11-30
0641 | AVANGRID | Oakdale - Lafayette | 2017-07-24 | N/A | N/A | AC | Broome-Onondaga | NY | C | Oakdale - Lafayette | NM-NG/NYSEG | 0 | 2019-10-04
0642 | AVANGRID | Jennison - Edic | 2017-07-24 | N/A | N/A | AC | Chenango - Oneida | NY | E | Jennison - Edic | NM-NG/NYSEG | 0 | 2019-10-04
0643 | AVANGRID | Multiple Areas | 2017-07-24 | N/A | N/A | AC | Steuben - Otsego | NY | C, E | Transmission Reinforcements | NM-NG/NYSEG | 0 | 2019-10-04
0645 | Oya Solar NY LP | Manny Corner Solar | 2017-08-01 | 20 | 20 | S | Montgomery | NY | F | Meco - Rotterdam 115kV | NM-NG | 0 | 2018-03-31
0646 | Oya Solar NY LP | Shaw Solar | 2017-08-01 | 20 | 20 | S | Jefferson | NY | E | Thousand Island 115kV | NM-NG | 0 | 2017-12-31
0647 | Oya Solar NY LP | Robinson Solar | 2017-08-01 | 20 | 20 | S | Jefferson | NY | E | Thousand Island 115kV | NM-NG | 0 | 2018-03-31
0648 | Oya Solar NY LP | Black Creek Solar | 2017-08-01 | 20 | 20 | S | Jefferson | NY | E | Thousand Island - Coffeen 115kV | NM-NG | 0 | 2017-12-31
0649 | CR Fuel Cell, LLC | Clare Rose | 2017-08-03 | 13.9 | 13.9 | FC | Suffolk | NY | K | William Floyd 69kV | LIPA | 0 | 2021-12-31
0650 | BRT Fuel Cell, LLC | Brookhaven Rail Terminal | 2017-08-03 | 18.5 | 18.5 | FC | Suffolk | NY | K | W. Yaphank - Yaphank 69kV | LIPA | 0 | 2021-12-31
0651 | Yaphank Fuel Cell Park, LLC | Yaphank Solid Waste Management | 2017-08-04 | 7.4 | 7.4 | FC | Suffolk | NY | K | W. Yaphank - North Bellport 69kV | LIPA | 0 | 2018-10-31
0652 | Somerset Operating Company LLC | Somerset Solar | 2017-08-04 | 19.9 | 19.9 | S | Monroe | NY | B | Kintigh Switchyard 69kV | NYSEG | 0 | 2018-02-01
0653 | Plattsburgh Solar, LLC | Moffitt Solar | 2017-08-07 | 20 | 20 | S | Clinton | NY | D | Northend - Woodruff Pond 46kV | NYSEG | 0 | 2018-09-30
0655 | Admiral Wind LLC | Admiral Wind LLC | 2017-08-11 | 20 | 20 | W | Madison | NY | C | Fenner - Oneida 115kV | NM-NG | 0 | 2019-09-30
0656 | Taku Wind LLC | Taku Wind | 2017-08-11 | 20 | 20 | W | Genesee | NY | A | Akron - Attica 34.5kV | NM-NG | 0 | 2018-01-31
0657 | Mistral Wind LLC | Mistral Wind LLC | 2017-08-11 | 20 | 20 | W | Genesee | NY | B | Lockport - Batavia 115kV | NM-NG | 0 | 2018-11-30
0658 | CVE North America, Inc. | Volney Solar Park | 2017-08-29 | 19.8 | 19.8 | S | Fulton | NY | F | South Oswego - Clay 115kV | NM-NG | 0 | 2018-01-31
0659 | Solar Liberty Energy Systems, Inc. | Westwood Rd | 2017-09-19 | 10.1 | 11.3 | S | Erie | NY | A | Erie St - Alden 34.5kV | NYSEG | 0 | 2018-03-31
0660 | Solar Liberty Energy Systems, Inc. | Liberty Dr | 2017-09-07 | 7.4 | 7.4 | S | Niagara Falls | NY | A | Packard - Erie St 115 kV | NM-NG | 0 | 2018-03-31
0661 | Solar Liberty Energy Systems, Inc. | Eden Evans Rd | 2017-09-07 | 18 | 18 | S | Erie | NY | A | Shelton - Angola 34.5kV | NM-NG | 0 | 2018-03-31
0662 | EDP Renewables North America LLC | Coldwater Solar | 2017-09-07 | 80 | 80 | S | Chautauqua | NY | A | Dunkirk - Gardenville 115kV | NM-NG | 0 | 2019-04-30
0663 | Solar Liberty Energy Systems, Inc. | Main St | 2017-09-08 | 10.8 | 10.8 | S | York | NY | A | Golah - South Perry 69 kV | NM-NG/NYSEG | 0 | 2018-03-31
0664 | South Cooper Solar LLC | South Cooper Solar | 2017-09-14 | 20 | 20 | S | Cattaraugus | NY | A | Five Mile - Gardenville 115 kV | NM-NG | 0 | 2018-05-31
0665 | Forest Glen Solar LLC | Forest Glen Solar | 2017-09-14 | 20 | 20 | S | Allagany | NY | A | Five Mile - Homer Hill 115kV | NM-NG | 0 | 2018-03-31
0669 | SED NY Holdings LLC | Clay Solar | 2017-09-21 | 20 | 20 | S | Clay | NY | C | Clay - Lockheed 115kV | NM-NG | 0 | 2021-05-31
0671 | East Coast Power LLC | Linden Cogen Uprate | 2017-09-25 | 32 | 23 | CT | Union | NJ | J | Linden Cogen 345kV | ConEd | 0 | 2020-11-30
0672 | LS Power Development, LLC | Helix Ravenswood I | 2017-10-06 | 30.2 | 30.2 | CT | New York | NY | J | Rainey Substation 345kV | ConEd | 0 | 2018-09-30
0673 | LS Power Development, LLC | Helix Ravenswood II | 2017-10-06 | 72.4 | 72.4 | CT | New York | NY | J | Rainey Substation 345kV | ConEd | 0 | 2018-09-30
0674 | Helix Ravenswood, LLC | Vernon Battery Storage I | 2017-10-24 | 10 | 10 | ES | Queens | NY | J | Vernon Substation | ConEd | 0 | 2018-08-31
0675 | Helix Ravenswood, LLC | Vernon Battery Storage II | 2017-10-24 | 10 | 10 | ES | Queens | NY | J | Vernon Substation | ConEd | 0 | 2018-08-31
0676 | Granada Solar, LLC | Regan Solar | 2017-10-25 | 20 | 20 | S | Chenango | NY | C | Guilford 46kV | NYSEG | 0 | 2018-03-31
0677 | Granada Solar, LLC | Grange Solar | 2017-10-25 | 20 | 20 | S | Broome | NY | C | Vincent Cors 34.5kV | NYSEG | 0 | 2018-01-31
0681 | Granada Solar, LLC | Magruder Solar | 2018-01-02 | 20 | 20 | S | Ulster | NY | G | Modena - Galeville 115kV | CHGE | 0 | 2018-02-28
0685 | sPower Development Company, LLC | EPCAL 1 | 2018-01-19 | 20 | 20 | S | Suffolk | NY | K | Riverhead - Brookhaven 138kV | LIPA | 0 | 2018-04-30
0687 | sPower Development Company, LLC | EPCAL 2 | 2018-01-29 | 150 | 150 | S | Suffolk | NY | K | Edwards - Brookhaven 69kV | LIPA | 0 | 2018-06-30
0688 | EDF Renewable Development Inc. | East Walden Solar | 2018-02-02 | 20 | 20 | S | Orange | NY | G | East Waldon Sutbation | CHGE | 0 | 2018-03-31
0689 | EDF Renewable Development Inc. | Goshen Solar | 2018-02-02 | 20 | 20 | S | Orange | NY | G | Huntley Station 115kV | O&R | 0 | 2018-03-31
0690 | EDF Renewable Development Inc. | Slate Hill 1 Solar | 2018-02-02 | 20 | 20 | S | Orange | NY | G | Shoemaker - Westtown | O&R | 0 | 2018-03-31
0691 | EDF Renewable Development Inc. | Slate Hill 2 Solar | 2018-02-02 | 20 | 20 | S | Orange | NY | G | Shoemaker - Westtown | O&R | 0 | 2018-03-31
0692 | Consolidated Edison Company of New York, Inc. | Astoria Storage on Demand | 2018-02-07 | 15 | 15 | ES | Queens | NY | J | North Queens Substation | ConEd | 0 | 2018-03-31
0699 | Helix Ravenswood, LLC | Ravenswood Gas | 2018-03-09 | 238.5 | 243.8 | CT | Queens | NY | J | Rainey - Farragut 345kV | ConEd | 0 | 2021-12-31
0702 | Anbaric Development Partners, LLC | Long Island Offshore AC | 2018-03-15 | 800 | 800 | W | Suffolk | NY | K | Ruland Rd. 138kV | LIPA | 0 | 2020-05-31
0703 | Anbaric Development Partners, LLC | New York City Offshore AC | 2018-03-15 | 800 | 800 | W | Kings | NY | J | Farragut 345kV | ConEd | 0 | 2020-05-31
0705 | Oya Solar NY, LP | Chaumont Solar | 2018-04-10 | 160 | 160 | S | Sullivan | NY | G | Thousand Island - Coffeen 115kV | NM-NG | 0 | 2018-07-31
0707 | PSEG Power New York LLC | Bethlehem Battery | 2018-05-04 | 10 | 10 | ES | Albany | NY | F | Albany Substation 115kV | NM-NG | 0 | 2018-11-30
0708 | PSEG Power New York LLC | Bethlehem Solar | 2018-05-04 | 1 | 1 | S | Albany | NY | F | 13.2kV Substation | NM-NG | 0 | 2018-06-30
0711 | Somerset Solar Development LLC | Somerset Solar | 2018-05-31 | 19.9 | 19.9 | S | Monroe | NY | B | Kintigh Substation 345 kV | NYSEG | 0 | 2018-10-31
0712 | Cayuga Solar LLC | Cayuga Solar | 2018-05-31 | 19.9 | 19.9 | S | Thompkins | NY | C | Milliken Substation 34.5kV | NYSEG | 0 | 2018-11-30
0713 | EDF Renewables Development, Inc. | Edora B Solar Energy Center | 2018-06-01 | 20 | 20 | S | Orange | NY | G | Hartley Substation 69kV | O&R | 0 | 2020-05-31
0714 | EDF Renewables Development, Inc. | Edora C Solar Energy Center | 2018-06-01 | 20 | 20 | S | Orange | NY | G | Shoemaker-Westtown 69kV | O&R | 0 | 2019-07-31
0715 | EDF Renewables Development, Inc. | Suffragette Solar Energy Center | 2018-06-01 | 20 | 20 | S | Cayuga | NY | C | Hyatt Substation 34.5kV | NYSEG | 0 | 2021-05-31
0722 | SED NY Holdings LLC | Manchester Solar | 2018-06-07 | 20 | 20 | S | Ontario | NY | C | Station 168 34.5 kV line #704 | RG&E | 0 | 2021-02-28
0723 | Lyonsdale Biomass, LLC | Lyonsdale Solar | 2018-06-08 | 19.9 | 19.9 | S | Lewis | NY | E | Lyonsdale Substation 115kV | NM-NG | 0 | 2019-04-30
0724 | Brewster Solar, LLC | Brewster Solar | 2018-06-08 | 25 | 25 | S | Putnam | NY | G | Pawling - Croton Falls 115kV | NYSEG | 0 | 2018-11-30
0725 | York Solar, LLC | York Solar | 2018-06-08 | 24.9 | 24.9 | S | Livingston | NY | A | Line #863 - 69kV | NM-NG | 0 | 2018-11-30
0726 | Niagara Falls Solar, LLC | Niagara Falls Solar | 2018-06-08 | 24.9 | 24.9 | S | Niagara | NY | A | Line #181 - 115kV | NM-NG | 0 | 2018-09-30
0727 | Alden Solar, LLC | Alden Solar | 2018-06-11 | 24.9 | 24.9 | S | Erie | NY | A | Cold Springs - Pulteny 34.5kV | NYSEG | 0 | 2018-09-30
0728 | EDF Renewables Development, Inc. | Champlain Solar | 2018-06-11 | 20 | 20 | S | Clinton | NY | E | Mason Corners-Sciota Flatrock 115kV | NYSEG | 0 | 2018-07-31
0729 | EDF Renewables Development, Inc. | Quiet Meadows Solar | 2018-06-11 | 20 | 20 | S | Oneida | NY | E | Oneida - Oneida Energy 115kV | NM-NG | 0 | 2018-08-31
0732 | Machias Solar, LLC | Machias Solar | 2018-06-11 | 20 | 20 | S | Cattaraugus | NY | A | Fivemile - Gardenville 115kV | NM-NG | 0 | 2018-12-31
0733 | Arcade Solar, LLC | Arcade Solar | 2018-06-11 | 19.9 | 19.9 | S | Wyoming | NY | A | Arcade - Bliss 115kv | Village of Arcade | 0 | 2018-11-30
0736 | Empire State Solar, LLC | Meads Hill Solar | 2018-06-12 | 20 | 20 | S | Schuyler | NY | C | Montour Falls - Greenidge 115kV | NYSEG | 0 | 2018-11-30
0739 | Hecate Energy Cody Road LLC | Cody Road | 2018-06-12 | 19.9 | 19.9 | W | Madison | NY | C | Fenner - Cortland 115kV | NM-NG | 0 | 2019-07-31
0741 | Bluestone Wind, LLC | Bluestone Battery Storage | 2018-07-02 | 10 | 10 | ES | Broome | NY | E | Afton - Stilesville 115kV | NYSEG | 0 | 2020-04-30
0742 | Consolidated Edison Co. of NY, Inc. | Astoria Storage on Demand | 2018-07-05 | 1.5 | 1.5 | ES | Queens | NY | J | North Queens 27kV | ConEd | 0 | 2022-01-31
0743 | Invenergy Solar Development North America LLC | Hornell Solar | 2018-07-16 | 20 | 20 | S | Steuben | NY | C | Bennett 34.5kV | NYSEG | 0 | 2019-10-31
0747 | White Creek Solar LLC | White Creek Solar | 2018-07-30 | 100 | 100 | S | Livingston | NY | A | Jones - Mortimer 115kV | NM-NG | 0 | 2018-10-31
0749 | KCE NY 11 LLC | KCE NY 11 | 2018-08-10 | 20 | 20 | ES | Orange | NY | G | Coldenham Substation 115kV | CHGE | 0 | 2019-02-28
0750 | Calpine Mid Atlantic Development, LLC | Bethpage Storage | 2018-08-14 | 50 | 50 | ES | Nassau | NY | K | Grumman Substation 69kV | LIPA | 0 | 2019-05-31
0751 | Calpine Mid Atlantic Development, LLC | Stony Brook Storage | 2018-08-14 | 24 | 24 | ES | Suffolk | NY | K | 8LR substation 69kV | LIPA | 0 | 8/31/21
0752 | Granada Solar, LLC (Conti) | Goldenrod Solar | 2018-08-15 | 90 | 90 | S | Herkimer | NY | E | Meco - Rotterdam 115 kV | NM-NG | 0 | 2018-10-31
0753 | Granada Solar, LLC (Conti) | Blue Star Solar | 2018-08-15 | 100 | 100 | S | Washington | NY | F | Mohican - Luther Forest 115kV | NM-NG | 0 | 2018-10-31
0754 | Anbaric Development Partners, LLC | New York Ocean Grid - Canal | 2018-08-20 | 800 | 800 | W | Suffolk | NY | K | Canal Substation 138kV | LIPA | 0 | 2020-08-31
0755 | Anbaric Development Partners, LLC | New York Ocean Grid - Shoreham | 2018-08-20 | 800 | 800 | W | Suffolk | NY | K | Shoreham Substation 138kV | LIPA | 0 | 2020-07-31
0756 | Rising Solar, LLC | Rising Solar II | 2018-08-24 | 20 | 20 | S | Orange | NY | G | Sugarloaf Substation - 69kV | O&R | 0 | 2021-01-31
0757 | Granada Solar, LLC | Monarda Solar | 2018-08-29 | 20 | 20 | S | Herkimer | NY | E | Meco - Rotterdam 115 kV | NM-NG | 0 | 2018-12-31
0760 | New York Power Authority | Moses-Adirondack | 2018-09-07 | N/A | N/A | AC | St. Lawrence-Lewis | NY | D, E | Moses - Adirondack 230kV | NYPA | 0 | 3/31/21
0761 | Invenergy Solar Development LLC | Athens Energy Center | 2018-09-17 | 100 | 100 |  | Greene | NY | G | New Scotland - North Catskill 115kV | NM-NG | 0 | 2018-10-31
0762 | Invenergy Storage Development LLC | Riverhead Storage Energy Center | 2018-09-17 | 75 | 75 | ES | Suffolk | NY | K | Brookhaven - Edwards Ave 138kV | LIPA | 0 | 2020-03-31
0763 | Invenergy Solar Development LLC | Cicero Storage | 2018-09-25 | 10 | 10 | ES | Onondaga | NY | C | Pine Grove Substation 13.2kV | NM-NG | 0 | 2020-01-31
0764 | Bay State Wind LLC | NY Wind Canal | 2018-09-28 | 440 | 440 | W | Suffolk | NY | K | Canal Substation 138kV | LIPA | 0 | 2020-10-31
0765 | Bay State Wind LLC | NY Wind Brookhaven | 2018-09-28 | 880 | 880 | W | Suffolk | NY | K | Brookhaven 138kV | LIPA | 0 | 2020-12-31
0767 | Bay State Wind LLC | NY Wind Gowanus | 2018-09-28 | 1200 | 1200 | W | New York | NY | J | Gowanus Substation 345kV | ConEd | 0 | 8/31/21
0771 | Mistral Wind LLC | Mistral Wind Alternative | 2018-10-10 | 20 | 20 | W | Genesee | NY | B | N. Akron - Attica 34.5 kV | NM-NG | 0 | 2020-01-31
0772 | Hollyhock Solar, LLC | Hollyhock Solar | 2018-10-15 | 20 | 20 | S | Albany | NY | F | Leeds - New Scotland 115kV | NM-NG | 0 | 2018-12-31
0773 | Charboneau Solar, LLC | Charboneau Solar | 2018-10-15 | 20 | 20 | S | Essex | NY | F | Ticonderoga - Hague Road 115kV | NM-NG | 0 | 2019-04-30
0782 | Invenergy Solar Development North America LLC | Hornell Storage | 2018-12-04 | 20 | 20 | ES | Steuben | NY | C | Bennett 34.5kV | NYSEG | 0 | 2020-04-30
0786 | Ravenswood Development, LLC | Ravenswood Energy Storage | 2018-12-20 | 187 | 187 | ES | Queens | NY | J | Rainey - Farragut 345kV | ConEd | 0 | 2021-12-31
0788 | Atlantic Shores Offshore Wind Project 3, LLC | Atlantic Shores Offshore Wind 7 | 2019-01-14 | 880 | 880 | W | Nassau | NY | K | East Garden City 345kV Substation | NYPA | 0 | 2021-06-30
0793 | esVolta, LP | Ladybug Energy Storage | 2019-02-06 | 75 | 75 | ES | Westchester | NY | I | Sprainbrook Substation | ConEd | 0 | 2019-07-31
0794 | esVolta, LP | Bluebird Energy Storage | 2019-02-06 | 40 | 40 | ES | Westchester | NY | I | Dunwoodie Substation | ConEd | 0 | 2019-07-31
0795 | esVolta, LP | Appleseed Energy Storage | 2019-02-06 | 50 | 50 | ES | Greene | NY | G | Leeds Substation | NM-NG | 0 | 2019-07-31
0802 | EDF Renewables Development, Inc. | Bunker Solar Energy Center | 2019-03-06 | 125 | 125 | ES | Franklin | NY | D | Willis - Lyon Mt 115kV | NYSEG | 0 | 2020-03-31
0808 | Barrett Ridge Energy, LLC | Barrett Ridge Energy | 2019-04-01 | 107 | 107 | ES | Orange | NY | G | Sugar Loaf - Vernon 115kV | CHGE | 0 | 2021-04-20
0809 | Seven Creek Energy, LLC | Seven Creek Energy | 2019-04-01 | 240 | 240 | ES | Chautauqua | NY | A | South Ripley Substation 230kV | NM-NG | 0 | 2021-04-20
0812 | Diamond Generating Corporation | CWW 200 Wind | 2019-04-03 | 200 | 200 | W | Erie | NY | A | Harbor Front 115kV | NM-NG | 0 | 2021-03-31
0813 | Diamond Generating Corporation | CWW 300 Wind | 2019-04-03 | 300 | 300 | W | Erie | NY | A | Harbor Front 115kV | NM-NG | 0 | 2021-02-28
0814 | Diamond Generating Corporation | CWW 300 MW DUN | 2019-04-03 | 300 | 300 | W | Chautauqua | NY | A | Dunkirk Substation 230kV | NM-NG | 0 | 2021-02-28
0816 | LIPA | NNC TTC Increase | 2019-04-05 | N/A | N/A | AC | Suffolk | NY | K | Northport Substation 138kV | LIPA | 0 | 2021-06-30
0817 | Quogue Energy Storage, LLC | Quogue Energy Storage | 2019-04-12 | 20 | 20 | ES | Suffolk | NY | K | Quogue Substation 69kV | LIPA | 0 | 2019-06-30
0818 | Setauket Energy Storage, LLC | Port Jeff 1-Terryville Energy Storage | 2019-04-15 | 20 | 20 | ES | Suffolk | NY | K | Port Jefferson - Terryville 69kV | LIPA | 0 | 2019-06-30
0819 | Setauket Energy Storage, LLC | Port Jeff 2-Terryville Energy Storage | 2019-04-15 | 20 | 20 | ES | Suffolk | NY | K | Port Jefferson - Terryville 69kV | LIPA | 0 | 2019-06-30
0820 | Setauket Energy Storage, LLC | Port Jeff 2-Stony Brook Energy Storage | 2019-04-15 | 20 | 20 | ES | Suffolk | NY | K | Port Jefferson - Stony Brook 69kV | LIPA | 0 | 2019-06-30
0821 | Setauket Energy Storage, LLC | Port Jeff -Mt. Sinai Energy Storage | 2019-04-15 | 20 | 20 | ES | Suffolk | NY | K | Port Jefferson - Mt. Sinai 69kV | LIPA | 0 | 2019-06-30
0823 | Wildwood Energy Storage, LLC | Wildwood Energy Storage | 2019-04-15 | 116.7 | 116.7 | ES | Suffolk | NY | K | Wildwood Substation 138kV | LIPA | 0 | 2020-04-30
0824 | Wildwood Energy Storage, LLC | Wildwood Shoreham Energy Storage | 2019-04-15 | 76.9 | 76.9 | ES | Suffolk | NY | K | Shoreham Substation 69kV | LIPA | 0 | 2020-04-30
0829 | NRG Arthur Kill Storage LLC | Arthur Kill Energy Storage 2 | 2019-04-24 | 60 | 60 | ES | Richmond | NY | J | Arthur Kill 138kV | ConEd | 0 | 2020-01-31
0831 | Dimension NY 1 LLC | NY-19-0002 Sheredy | 2019-04-29 | 10.2 | 10.2 | ES | Broome | NY | C | Northside Substation 34.5kV | NYSEG | 0 | 2020-01-31
0836 | Astoria Generating Company, LP | Dock Battery Energy Storage 2 | 2019-05-07 | 56.3 | 56.3 | ES | Queens | NY | J | Astoria East Substation 138kV | ConEd | 0 | 2020-02-29
0837 | Astoria Generating Company, LP | Parking Lot Battery Energy Storage 2 | 2019-05-07 | 79 | 79 | ES | Queens | NY | J | Astoria East Substation 138kV | ConEd | 0 | 2020-02-29
0839 | NRG Astoria Storage LLC | Astoria Energy Storage 4 | 2019-05-09 | 20 | 20 | ES | Queens | NY | J | Astoria West 138kV Substation | ConEd | 0 | 2020-02-29
0841 | TJA Clean Energy, LLC | Sharon Springs Interconnection | 2019-05-10 | 20 | 20 | S | Schoharie | NY | F | Sharon - Cobleskill 69kV Substation | NM-NG | 0 | 2021-07-31
0842 | Mitsubishi Hitachi Power Systems Americas, Inc. | Comet Solar | 2019-05-17 | 20 | 20 | S | Monroe | NY | B | Mortimer - Golah 115kV | NM-NG | 0 | 2020-01-31
0844 | Boralex US Development, LLC | NY37 Energy Storage | 2019-05-17 | 4 | 4 | ES | Jefferson | NY | E | Coffeen - West Adams 115kV Substation | NM-NG | 0 | 2020-12-31
0845 | sPower Development Company, LLC | Bloom Energy Storage Center | 2019-05-20 | 120 | 120 | ES | Kings | NY | J | Farragut 345kV Substation | ConEd | 0 | 2020-03-31
0846 | sPower Development Company, LLC | Rescue Energy Storage Center | 2019-05-20 | 300 | 300 | ES | New York | NY | J | East 13th Street 138kV Substation | ConEd | 0 | 2020-04-30
0847 | sPower Development Company, LLC | Chelsea Energy Storage Center | 2019-05-20 | 300 | 300 | ES | New York | NY | J | West 49th St Substation 345kV | ConEd | 0 | 2020-04-30
0851 | ConnectGen Madison County LLC | Madison County Solar | 2019-05-23 | 20 | 20 | S | Madison | NY | E | Bouckville Substation | NYSEG | 0 | 2020-01-31
0853 | Boralex US Development, LLC | NY16 Solar | 2019-05-24 | 20 | 20 | S | Washington | NY | F | Mohican - Schaghticoke 115kV | NM-NG | 0 | 2021-03-31
0854 | Boralex US Development, LLC | NY16 Energy Storage | 2019-05-24 | 4 | 4 | ES | Washington | NY | F | Battenkill - Mohican 115kV | NM-NG | 0 | 2019-10-04
0856 | Boralex US Development, LLC | NY13 Energy Storage | 2019-05-24 | 4 | 4 | ES | Washington | NY | F | Battenkill - Mohican 115kV | NM-NG | 0 | 2019-10-04
0861 | Mitsubishi Hitachi Power Systems Americas, Inc. | Tonawanda Solar | 2019-05-29 | 20 | 20 | S | Niagara | NY | B | Lockport - Batavia 115kV | NM-NG | 0 | 2020-12-31
0862 | Mitsubishi Hitachi Power Systems Americas, Inc. | Farwell Solar | 2019-05-29 | 20 | 20 | S | Orleans | NY | B | Lockport - Mortimer 115kV | NM-NG | 0 | 2021-02-28
0867 | Somerset Solar Development LLC | Somerset Solar Development LLC | 2019-06-03 | 20 | 20 | S | Niagara | NY | A | Kintigh 345kV | NYSEG | 0 | 2020-01-31
0868 | Cayuga Solar LLC | Cayuga Solar LLC | 2019-06-03 | 19.9 | 19.9 | S | Cayuga | NY | C | Milliken Substation | NYSEG | 0 | 2020-01-31
0969 | esVolta, LP | Modena Energy Storage I | 2020-01-09 | 6 | 6 | ES | Ulster | NY | G | Modena Substation | CHGE | 0 | 2020-02-29
0970 | esVolta, LP | Modena Energy Storage II | 2020-01-09 | 6 | 6 | ES | Ulster | NY | G | Modena Substation | CHGE | 0 | 2020-02-29
0872 | Invenergy Solar Project Development LLC | Taproot Solar Energy Energy | 2019-06-05 | 300 | 300 | S | Montgomery | NY | E | Porter - Rotterdam 230kV | NM-NG | 0 | 2019-12-31
0875 | SL Portland, LLC | SL Portland Solar | 2019-06-06 | 19.9 | 19.9 | S | Chautauqua | NY | A | Dunkirk - Falconer 115 kV | NM-NG | 0 | 2020-04-30
0876 | SL Selkirk, LLC | SL Selkirk Solar | 2019-06-06 | 19.9 | 19.9 | S | Albany | NY | F | New Scotland - Alps 345kV | NM-NG | 0 | 2019-10-31
0877 | SL York, LLC | SL York Solar | 2019-06-06 | 19.9 | 19.9 | S | Livingston | NY | B | Golah - S. Perry 115 kV | NM-NG | 0 | 2020-04-30
0884 | Dimension NY 1 LLC | Blooming Farm LLC | 2019-06-12 | 10.2 | 10.2 | ES | Orange | NY | G | Blooming Grove Substation 69kV | O&R | 0 | 2019-10-04
0886 | Empire State Land Holdings, LLC | Turin Highlands Solar | 2019-06-12 | 20 | 20 | S | Oneida | NY | E | Taylorville - Boonville 115kV | NM-NG | 0 | 2019-07-31
0888 | Sky Solar Inc. | Hornell Center 16 | 2019-06-13 | 17.6 | 17.6 | S | Allegany | NY | C | Moraine Substation 115kV | NYSEG | 0 | 2019-10-31
0889 | Energy Storage Resources, LLC | Peconic River II | 2019-06-20 | 19.2 | 19.2 | ES | Suffolk | NY | K | 8RX Moriches | LIPA | 0 | 2019-08-31
0890 | Energy Storage Resources, LLC | Queen City | 2019-06-20 | 19.2 | 19.2 | ES | Dutchess | NY | K | Knapps Corners | CHGE | 0 | 2019-10-04
0891 | Energy Storage Resources, LLC | Meredith Woods | 2019-06-24 | 19.2 | 19.2 | ES | New York | NY | J | Baron Blvd | ConEd | 0 | 2019-10-04
0892 | FourGen LLC | Holtsville Fuel Cell | 2019-07-15 | 20 | 20 | FC | Suffolk | NY | K | Holtsville 69kV | LIPA | 0 | 2020-07-31
0893 | FourGen LLC | Setauket Fuel Cell | 2019-07-15 | 20 | 20 | FC | Suffolk | NY | K | Terryville Substation 69kV | LIPA | 0 | 2020-07-31
0894 | Montgomery Energy Storage 1, LLC | Montgomery Energy Storage | 2019-07-15 | 20 | 20 | ES | Orange | NY | G | Walden - Montgomery 69kV | CHG&E | 0 | 2020-05-31
0895 | Dimension NY 1 LLC | Road Property | 2019-07-15 | 19.9 | 19.9 | ES | Suffolk | NY | K | Central Islip 138kV | LIPA | 0 | 2020-01-31
0896 | Sky Solar Inc. | Hornell Center 16 BESS | 2019-07-18 | 8 | 8 | ES | Allegany | NY | C | Moraine Substation 115kV | NYSEG | 0 | 2019-10-31
0897 | Mitsubishi Hitachi Power Systems Americas, Inc. | Bluejay Solar | 2019-08-01 | 5 | 5 | S | Allegany | NY |  |  | RG&E | 0 | 2019-10-31
0898 | Mitsubishi Hitachi Power Systems Americas, Inc. | Oak Orchard Solar | 2019-08-01 | 5 | 5 | S | Orleans | NY | A, B | Shelby | NM-NG | 0 | 2019-12-31
0900 | Granada Solar, LLC | Fowler Solar | 2019-08-09 | 20 | 20 | S | Madison | NY | E | Fenner - Whitman 115kV | NM-NG | 0 | 2020-02-29
0901 | TJA Clean Energy, LLC | Lacona Solar | 2019-08-16 | 20 | 20 | S | Oswego | NY | E | Lighthouse Hill - Black River 115kV | NM-NG | 0 | 2021-12-31
0902 | sPower Development Company, LLC | Yacht Club Energy Storage | 2019-08-16 | 300 | 300 | ES | New York | NY | J | Gowanus 345kV | ConEd | 0 | 2021-04-30
0903 | sPower Development Company, LLC | Goethals Energy Storage | 2019-08-16 | 300 | 300 | ES | New York | NY | J | Goethals 345kV | ConEd | 0 | 2021-04-30
0904 | Agilitas Energy, LLC | South Conduit Avenue Energy Storage | 2019-08-20 | 10 | 10 | ES | New York | NY | J | South Conduit Ave | ConEd | 0 | 2019-10-31
0905 | Agilitas Energy, LLC | Liberty Avenue Energy Storage | 2019-08-20 | 10 | 10 | ES | New York | NY | J | Liberty Ave | ConEd | 0 | 2019-10-31
0906 | NRG Arthur Kill Storage LLC | Arthur Kill Energy Storage 2 | 2019-08-28 | 20 | 20 | ES | New York | NY | J | Fresh Kills Substation | ConEd | 0 | 2020-02-29
0908 | NRG Astoria Storage LLC | Astoria Energy Storage 5 | 2019-09-12 | 20 | 20 | ES | Queens | NY | J | North Queens Substation 27kV | ConEd | 0 | 2020-02-29
0909 | PetaWatt Holdings, Inc. | Massena Load | 2019-09-18 | 100 | 100 | L | St. Lawrence | NY | E | Dennison 115kV substation | NM-NG | 0 | 2021-04-30
0910 | Hartley Rd Energy Storage 1, LLC | 114 Hartley Rd-Goshen | 2019-09-24 | 10 | 10 | ES | Orange | NY | G | Hartley Substation 13.2kV | O&R | 0 | 2020-02-29
0914 | sPower Development Company, LLC | Loomis Creek Solar | 2019-10-07 | 100 | 100 | S | Columbia | NY | F | Churchtown Substation 115 kV | NYSEG | 0 | 2020-04-30
0915 | EDF Renewables Development, Inc. | Staten Island 1 Battery Storage | 2019-10-07 | 20 | 20 | ES | Richmond | NY | J | Fox Hills Substation 33kV | ConEd | 0 | 2020-09-30
0916 | EDF Renewables Development, Inc. | Hartley Battery Storage | 2019-10-07 | 20 | 20 | ES | Orange | NY | G | Hartley Road Substation 69kV | O&R | 0 | 2020-03-31
0917 | sPower Development Company, LLC | Loomis Creek ES | 2019-10-07 | 50 | 50 | ES | Columbia | NY | F | Churchtown Substation 115 kV | NYSEG | 0 | 2020-04-30
0919 | sPower Development Company, LLC | White Spring ES | 2019-10-10 | 100 | 100 | ES | Ontario | NY | C | Haley Road Substation 115 kV | NYSEG | 0 | 2021-06-30
0920 | sPower Development Company, LLC | White Spring Solar | 2019-10-10 | 200 | 200 | S | Ontario | NY | C | Haley Road Substation 115 kV | NYSEG | 0 | 2021-06-30
0921 | sPower Development Company, LLC | Line Creek ES | 2019-10-10 | 30 | 30 | ES | Schoharie | NY | F | Schoharie 69 kV | NM-NG | 0 | 2020-04-30
0922 | sPower Development Company, LLC | Line Creek Solar | 2019-10-10 | 50 | 50 | S | Schoharie | NY | F | Schoharie 69 kV | NM-NG | 0 | 2020-04-30
0923 | sPower Development Company, LLC | Far Rockaway Energy Storage Center | 2019-10-11 | 150 | 150 | ES | Queens | NY | K | Far Rockaway Substation 69 kV | LIPA | 0 | 2020-05-31
0924 | RICAL LLC | CBB | 2019-10-15 | 115 | 115 | ES | Dutchess | NY | G | Shenandoah Substation | CHGE | 0 | 2020-06-30
0926 | Enel Energy Storage Holdings, LLC | Enel NYPA Astoria | 2019-10-18 | 100 | 100 | ES | Queens | NY | J | Astoria 138 kV substation | ConEd | 0 | 1/31/20
0927 | JERA Americas Inc. | Brunswick Energy Storage | 2019-10-21 | 100 | 100 | ES | Union | NJ | J | Goethals Substation 345kV | ConEd | 0 | 1/31/20
0928 | JERA Americas Inc. | Willow Bay Energy Storage | 2019-10-21 | 40 | 40 | ES | Richmond | NY | J | Fox Hills Substation 33kV | ConEd | 0 | 2020-03-31
0933 | Seven Creek Energy, LLC | Seven Creek Energy - Squab Hollow | 2019-10-31 | 290 | 290 | ES | Elk | PA | A | Homer City - Pierce Brook 345kV | NYSEG | 0 | 2021-04-30
0934 | Saturn Energy Storage LLC | Astoria BESS | 2019-10-31 | 70 | 68.6 | ES | Queens | NY | J | Astoria West Substation 138 kV | ConEd | 0 | 2020-04-30
0936 | AE - ESS Petracca, LLC | Petracca Place Energy Storage | 2019-11-01 | 10 | 10 | ES | Queens | NY | J | Corona 4kV | ConEd | 0 | 2020-05-31
0937 | Boralex US Development, LLC | NYSD Energy Storage | 2019-11-04 | 5.5 | 5.5 | ES | Saratoga | NY | F | Mechanicville 34.5 kV | NM-NG | 0 | 2020-03-31
0938 | KCE NY 12, LLC | KCE NY 12 | 2019-11-04 | 100 | 100 | ES | Suffolk | NY | K | Moriches Substation 69kV | LIPA | 0 | 2020-03-31
0943 | Vistra Operations Company, LLC | Sithe Independence BESS | 2019-11-08 | 20 | 20 | ES | Oswego | NY | C | Sithe Independence 345kV | NM-NG | 0 | 2020-03-31
0944 | Invenergy Solar Development LLC | Verona Storage | 2019-11-12 | 100 | 100 | ES | Oneida | NY | C | Edic-Clay 345kV Line | NYPA | 0 | 2020-05-31
0946 | Dimension NY 1 LLC | Helmer | 2019-11-14 | 21.3 | 21.3 | ES | Herkimer | NY | E | Old Forge - Raquette Lake 46 kV | NM-NG | 0 | 2020-01-31
0948 | Dimension NY 1 LLC | Webster BESS | 2019-11-18 | 8.8 | 8.8 | ES | Monroe | NY | B | 34.5 kV | RG&E | 0 | 2020-05-31
0955 | VESI 26 LLC | Craillo Plaza | 2019-12-06 | 20 | 20 | ES | Rensselaer | NY | F | NGrid Rensselaer 34.5/ 13.2KV Substation | NM-NG | 0 | 2020-02-29
0963 | Invenergy Storage Development LLC | Crooked Lake Storage | 2019-12-19 | 7 | 7 | ES | Yorktown | NY | H | Mohansic 13.2kV Substation | NYSEG | 0 | 2020-04-30
0964 | Invenergy Storage Development LLC | Berry Place Storage | 2019-12-20 | 10 | 10 | ES | Livingston | NY | A | Lakeville 34.5kV substation | NM-NG | 0 | 2020-01-31
0968 | SED NY Holdings LLC | Gouverneur Solar Project | 2020-01-09 | 20 | 20 | S | St. Lawrence | NY | E | North Gouverneur - Battle Hill 115kV | NM-NG | 0 | 2020-05-31
0973 | Wildwood Energy Storage, LLC | Wildwood-Riverhead Energy Storage | 2020-01-13 | 293.5 | 297.9 | ES | Suffolk | NY | K | Wildwood-Riverhead 138 kV | LIPA | 0 | 2021-08-30
0975 | Dimension NY 1 LLC | Webb BESS | 2020-01-15 | 20 | 20 | ES | Herkimer | NY | E | Old Forge-Raquette Lake 46 kV | NM-NG | 0 | 2020-06-30
0976 | Invenergy Storage Development LLC | Esopus Valley Storage | 2020-01-16 | 10 | 10 | ES | Ulster | NY | G | Hurley Ave 34.5kV Substation | CHGE | 0 | 2020-04-30
0977 | Dimension NY 1 LLC | Dutchess BESS | 2020-01-16 | 6.6 | 6.6 | ES | Dutchess | NY | G | Pawling - Haviland Hollow 46kV | NYSEG | 0 | 2020-05-31
0978 | Hydroelectric Corporation | New York Hydro-Kinetic Project 1 | 2020-01-18 | 550 | 480 | H | Kings | NY |  | Sayreville Station 345kV |  | 0 | 2020-03-31
0980 | Invenergy Storage Development LLC | Heritage Storage | 2020-01-22 | 8 | 8 | ES | Erie | NY | A | Erie 34.5kV Substation | NYSEG | 0 | 2020-08-31
0981 | Invenergy Storage Development LLC | Oblong Storage | 2020-01-22 | 6 | 6 | ES | Dutchess | NY | G | Pawling 46kV Substation | NYSEG | 0 | 9/30/20
0983 | JERA Americas Inc. | Winter Drive Energy Storage | 2020-01-28 | 8 | 8 | ES | Lancaster | NY | A | Erie Street Substation -34.5kV | NYSEG | 0 | 2020-05-31
0984 | JERA Americas Inc. | Empire Energy Storage | 2020-01-28 | 8 | 8 | ES | Monroe | NY | B | Station 55 34.5kV | RG&E | 0 | 2020-05-31
0985 | JERA Americas Inc. | Bristol Energy Storage | 2020-01-28 | 6 | 6 | ES | Ontario | NY | B | 34.5kV line | RG&E | 0 | 2020-05-31
0986 | JERA Americas Inc. | Pawling Energy Storage | 2020-01-29 | 6 | 6 | ES | Putnam | NY | G | 46kV line | NYSEG | 0 | 2020-05-31
0988 | Saturn Energy Storage LLC | Lancaster BESS | 2020-01-30 | 8 | 8 | ES | Erie | NY | A | Cemetery Rd - Erie St 34.5 kV | NYSEG | 0 | 2020-07-31
0989 | Saturn Energy Storage LLC | Pawling BESS | 2020-01-30 | 6 | 6 | ES | Dutchess | NY | H | Pawling-Corbin Rd 46 kV | NYSEG | 0 | 2020-07-31
0990 | Saturn Energy Storage LLC | Mohansic BESS | 2020-01-30 | 7 | 7 | ES | Westchester County | NY | H | The 13.2 kV 403 (1106340) line from Mohansic Substation running along Baldwin Rd | NYSEG | 0 | 2020-03-31
0991 | Saturn Energy Storage LLC | Bristol BESS | 2020-01-30 | 6 | 6 | ES | Ontario | NY | B | S Bristol-State Rt 28 34.5 kV | RG&E | 0 | 2020-07-31
0992 | KCE NY 25, LLC | KCE NY 25 | 2020-01-31 | 6 | 6 | ES | Ontario | NY | B | Station 146 34.5kV | RG&E | 0 | 2020-06-30
0996 | SWEB Development USA, LLC | East Otto Solar Project | 2020-02-28 | 20 | 20 | S | Cattaraugus | NY | A | Line 803 near Snake Run Road | NM-NG | 0 | 2020-06-30
0997 | 212 Solar Development, LLC | 187 Finchville Turnpike, Mount Hope | 2020-03-05 | 20 | 20 | ES | Orange | NY | G | Cuddleback - Shoemaker 69kV | O&R | 0 | 9/30/20
0998 | 212 Solar Development, LLC | 0 Highland Lake Rd - Wallkill | 2020-03-05 | 20 | 20 | ES | Orange | NY | G | Cuddleback - Shoemaker 69kV | O&R | 0 | 2020-10-31
0999 | Suffolk BESS LLC | Suffolk BESS | 2020-03-06 | 79.7 | 79.7 | ES | Suffolk | NY | K | Port Jefferson 69 kV Substation | LIPA | 0 | 2020-09-30
1002 | 212 Solar Development, LLC | 2143 Mount Hope Road | 2020-04-03 | 20 | 20 | ES | Orange | NY | G | Cuddleback - Shoemaker | O&R | 0 | 2020-10-31
1005 | sPower Development Company, LLC | East End Energy Storage Center | 2020-04-17 | 51.5 | 51.5 | ES | Suffolk | NY | K | Edwards Ave. 138 kV Substation | LIPA | 0 | 2020-09-30
1006 | NYC Energy | NYC Energy BNY Phase 1 | 2020-04-20 | 79.9 | 79.9 | ES | Kings | NY | J | Hudson Ave Substation | ConEd | 0 | 2020-12-31
1014 | ConnectGEN Chautauqua County LLC | South Ripley BESS | 2020-05-05 | 20 | 20 | ES | Chautauqua | NY | A | South Ripley 230kV substation | NM-NG | 0 | 5/31/21
1024 | Renewable Energy Aggregators, Inc. | Cuomo Hydro 1 | 2020-06-03 | 300 | 300 | PS | Westchester | NY | H | Millwood 345kV Substation | ConEd | 0 | 2021-03-31
1025 | Renewable Energy Aggregators, Inc. | Cuomo Hydro 2 | 2020-06-03 | 300 | 300 | PS | Westchester | NY | I | Dunwoodie 345kV Substation | ConEd | 0 | 2021-03-31
1026 | Oriden LLC | Bonny Hill Solar | 2020-06-05 | 20 | 20 | S | Steuben | NY | C | Bath - Bath Muni 34.5 kV | NYSEG | 0 | 2020-09-30
1032 | 212 Solar Development, LLC | 129 Round Hill Road | 2020-06-19 | 20 | 20 | ES | Orange | NY | G | Blooming Grove substation | O&R | 0 | 2020-10-31
1033 | 212 Solar Development, LLC | E Main Street, Wallkill | 2020-06-19 | 20 | 20 | ES | Ulster | NY | G | Shoemaker - E Wallkill line | O&R | 0 | 2020-10-31
1034 | 212 Solar Development, LLC | 30-35-90 Zwart Ln - Walden | 2020-06-19 | 20 | 20 | ES | Orange | NY | G | CHG&E WM Line | CHGE | 0 | 2020-08-31
1044 | Delaware River Solar | Broadway Road | 2020-07-01 | 19.9 | 19.9 | S | Genesee | NY | A | Attica - Darien Lake 34.5kV | NM-NG | 0 | 2020-10-31
1053 | Hydroelectric Corporation | New York Kinetic Plant 1 | 2020-07-22 | 141.9 | 144 | H | New York | NY | J | Con Edison Gowanus Substation | ConEd | 0 | 2020-08-31
1054 | Birdie Energy Storage, LLC | Birdie Energy Storage | 2020-07-23 | 83 | 83 | ES | Westchester | NY | I | Elmsford 138 kV Substation | ConEd | 0 | 2020-09-30
1057 | Bay State Wind | NY Wind - New Bridge Road | 2020-07-27 | 1325 | 1325 | W | Nassau | NY | K | New Bridge Road 138kV | LIPA | 0 | 2020-10-31
1065 | Delaware River Solar | Hance Road | 2020-08-03 | 19.9 | 19.9 | S | Wayne | NY | B | Station 13A - Station 121 115kV | RG&E | 0 | 2020-10-31
1067 | Viridity Energy Solutions, Inc. | Hudson Valley Storage | 2020-08-05 | 20 | 20 | ES | Ulster | NY | G | E Kingston Substation | CHGE | 0 | 2020-10-31
1069 | AES DE DEVCO NC LLC | Richardson Solar | 2020-08-05 | 24 | 22 | S | St. Lawrence | NY |  | Ogdensburg - McIntyre115 kV | NM-NG | 0 | 2021-02-28
1070 | Delaware River Solar | 311 Douglas Road | 2020-08-05 | 19.9 | 19.9 | S | Tompkins | NY | C | Montour Falls-Coddington 115kV | NYSEG | 0 | 2021-02-28
1071 | Delaware River Solar | Katrina Falls | 2020-08-06 | 19.9 | 19.9 | S | Sullivan | NY | E | Coopers Corners-Rock Tavern 345kV | NYPA | 0 | 2021-02-28
1072 | Delaware River Solar | Route 318 | 2020-08-06 | 19.9 | 19.9 | S | Seneca | NY | C | Hook Road - Elbridge 115 kV | NM-NG | 0 | 2021-02-28
1073 | AES DE DEVCO NC LLC | Forrence Orchards | 2020-08-07 | 19.8 | 19.8 | S | Clinton | NY | D | Hallock Hill - Kents Falls 115kV | NYSEG | 0 | 2021-11-30
1074 | Honey Ridge Solar 1 | Honey Ridge Solar | 2020-08-11 | 80 | 80 | S | Jefferson | NY | C, E | Black River 115kV Substation | NM-NG | 0 | 2020-10-31
1075 | Moss Ridge Solar 1 | Moss Ridge Solar | 2020-08-11 | 46 | 46 | S | St. Lawrence | NY | E | Colton - Battle Hill, 115 kV | NM-NG | 0 | 2020-09-30
1076 | Minisink Valley Solar 1, LLC | Minisink Valley Solar | 2020-08-28 | 15 | 15 | S | Orange | NY | G | Shoemaker - Westtown 69kV | O&R | 0 | 2020-10-31
1078 | sPower Development Company, LLC | Cayuga Solar | 2020-08-18 | 207 | 207 | S | Tompkins | NY | C | Milliken 115 kV | NYSEG | 0 | 2021-01-31
1082 | CDG Owego 2 | CDG Owego 2, LLC | 2020-08-27 | 19.6 | 19.6 | S | Tioga | NY | C | Line 513 - 34.5KV | NYSEG | 0 | 2021-02-28
1091 | ELP Middleburgh Solar LLC | ELP Middleburgh Solar | 2020-09-08 | 20 | 20 | S | Schoharie | NY | F | Middleburgh - Cobleskill 115kV | NM-NG | 0 | 2020-12-31
1093 | Con Edison Transmission, Inc. | Clean Path New York | 2020-09-10 | 1300 | 1300 | DC | Oneida | NY | E,J | Marcy - Rainey 345kV | ConEd/ NYSEG | 0 | 2021-08-30
1094 | SED NY Holdings LLC | Chase Mills Solar | 2020-09-14 | 20 | 20 | S | St. Lawrence | NY | D | 115kV Line Brady to Alcoa (5.82miles from Brady, 13.9 miles from Alcoa) | NM-NG | 0 | 12/31/20
1095 | Northland Power U.S. Projects | Chautauqua Solar | 2020-09-14 | 20 | 20 | S | Chautauqua | NY | A | Line 123975 | NM-NG | 0 | 2020-10-31
1097 | Juno Power Management LLC | Hicksville Storage | 2020-09-16 | 125 | 125 | ES | Nassau | NY | K | Newbridge Road 138kV | LIPA | 0 | 2021-03-31
1099 | Brownfield Group, LLC | Canal Solar | 2020-09-17 | 20 | 20 | S | Madison | NY | E | Bouckville Substation 46kV | NYSEG | 0 | 2020-10-31
1101 | Saturn Energy Storage LLC | Chestertown BESS | 2020-10-01 | 20 | 20 | ES | Warren | NY | F | Chestertown-Warrensburg #6 | NM-NG | 0 | 2021-04-30
1106 | Northland Power U.S. Projects | Allegany 2 Battery | 2020-10-16 | 10 | 10 | ES | Allegany | NY | C | Andover - Palmeter 115 kV line | NYSEG/NM-NG | 0 | 2021-02-28
1110 | Saturn Energy Storage LLC | Hurley BESS | 2020-10-27 | 20 | 20 | ES | Ulster | NY | G | Hurley Ave Substation, 69 kV | CHGE | 0 | 12/31/20
1111 | Saturn Energy Storage LLC | Kingston BESS | 2020-10-30 | 20 | 20 | ES | Ulster | NY | G | Boulevard Substation 69kV | CHGE | 0 | 12/31/20
1118 | BWBP Origination, LLC | Lyonsdale Marmon Rd | 2020-12-04 | 19 | 19 | S | Lewis | NY | E | Lyonsdale Substation | NM-NG | 0 | 2021-03-31
1124 | Liberty Renewables | Smokey Ave Wind | 2020-12-22 | 18 | 18 | W | Otsego | NY |  | Worcester - Schenevus 23 kV |  | 0 | 2021-05-31
1127 | CBB PARK LLC | CBB PARK | 2021-01-20 | 50 | 50 | ES | Dutchess | NY | G | Pleasant Valley 115 kV | CHGE | 0 | 2021-07-31
1129 | Boundless Energy NY, LLC | Phoenix | 2021-01-21 | 2000 | 2000 | DC | Oneida-Manhattan & Bronx | NY | E, J | Edic & Marcy - W. 49 St & Farragut | NM-NG, NYPA, ConEd | 0 | 2021-07-31
1143 | Minerva Power Connection LLC | Minerva BESS II | 2021-02-16 | 600 | 600 | ES | Manhattan | NY | J | W 49th st 345kV | ConEd | 0 | 6/30/21
1144 | Boundless Energy NY, LLC | HG-Phoenix | 2021-02-18 | 2000 | 2000 | DC | Erie, Onondaga,New York, KIngs | NY | A,E,J | Gardenville and Edic/Marcy - W49th St & Farragut | NM-NG/NYPA/ NYSEG/ConEd | 0 | 2021-12-31
1149 | Con Edison Transmission, Inc. | Clean Path New York II | 2021-03-12 |  |  |  | Delaware/Queens | NY | E, J | Fraser 345kv and Mott Haven 345 kv | NYSEG/ ConEd | 0 | 2021-08-30
1152 | BWC Rexmere Lakes, LLC | Harpersfield Bruce Hill Rd. | 2021-03-18 | 19.9 | 19.9 | S | Delaware | NY | E | Axtell Rd. Substation | NYSEG | 0 | 2021-08-30
1154 | OYA Solar CDG LLC | OYA Fort Plain Solar | 2021-03-29 | 115 | 115 | S | Montgomery | NY | F | Clinton Road substation 115 kV | NM-NG | 0 | 2021-07-31
1157 | Minerva Power Connection LLC | Minerva Transmission | 2021-04-09 | 1200 | 1200 | DC | Manhattan | NY | J | W 49th St 345kV | ConEd | 0 | 10/31/21
1158 | Tyre Solar Energy Center | Gravel Road Solar | 2021-04-09 | 125.6 | 125 | S | Seneca | NY | C | Elbridge - Hook Rd 115kV | NM-NG/ NYSEG | 0 | 2022-01-31
1168 | Invenergy Transmission LLC | CPNY-MH | 2021-05-11 | 1300 | 1300 | DC | Delaware, Bronx | NY | E, J | Fraser - Mott Haven 345kV | NYSEG/ ConEd | 0 | 12/31/21
1170 | Tier Four Connector, LLC | Bowline to West 49th Street | 2021-05-12 | 1228 | 1228 | AC | Rockland/New York | NY | G, J | Bowline - West 49th St 345 kV | O&R/ConEd | 0 | 2022-01-31
1172 | Northland Power US Projects | Cowens Corners Solar | 2021-05-17 | 20 | 20 | CR=CSR - ES + Solar | Cattaraugus | NY | A | Ellington - Randolph 34.5 kV | NYSEG | 0 | 2021-08-30
1179 | Boralex US Development, LLC | NY38 B Solar | 2021-05-19 | 20 | 20 | S | Jefferson | NY | E | Coffeen - West Adams 115 kV | NM-NG | 0 | 2021-08-31
1186 | Empire Offshore Wind LLC | EI Empire ESS II | 2021-05-21 | 1440 | 1440 | CW | Nassau | NY | K | Barrett 138 kV Substation | LIPA | 0 | 6/30/21
1187 | Northland Power US Projects | Balcom Corners | 2021-05-27 | 20 | 20 | CR | Chautauqua | NY | A | Ellington - Frog Valley 34.5 kV | NYSEG | 0 | 2021-09-30
1195 | Dexter Solar, LLC | Dexter Solar | 2021-06-04 | 19.8 | 19.8 | S | Jefferson | NY | E | Dexter 23 kV Substation | NM-NG | 0 | 2021-07-31
1196 | Chelsea Road Energy Storage 1, LLC | Chelsea Energy Storage | 2021-06-07 | 30.4 | 30.4 | ES | Richmond | NY | J | Goethals Substation | ConEd | 0 | 2021-08-31
1201 | PetaWatt Holdings, Inc. | St Lawrence Data and Agricultural Center | 2021-06-10 | 200 | 200 |  | St. Lawrence | NY | D | Dennison 115kV substation | NM-NG | 0 | 2021-08-31
1204 | Morrow Street Storage 2, LLC | Morrow Street Energy Storage | 2021-06-15 | 38 | 38 | ES | Richmond | NY | J | Goethals Substation | ConEd | 0 | 2021-08-31
1208 | Bluepoint Grid, LLC | Bluepoint Grid | 2021-06-20 | 20 | 20 | ES | Suffolk | NY | K | W. Yaphank - Holtsville 69kV | LIPA | 0 | 2021-11-30
1214 | Nexus Renewables U.S. Inc. | Ancram Solar Farm | 2021-06-30 | 20 | 20 | CR | Columbia | NY |  | Pulvers Corners 34.5kV | CHGE | 0 | 2021-08-31
1215 | Renesola Power Holdings LLC | Blank Hill Solar LLC | 2021-07-05 | 19.9 | 19.9 | CR | Livingston | CT | C | Moraine Road 115kV | NYSEG | 0 | 2021-09-30
1216 | ReneSola Power Holdings LLC | Cronk Solar LLC | 2021-07-08 | 19.9 | 19.9 | CR | Schuyler | NY | C | Bath - Montour Falls 115 kV | NYSEG | 0 | 2021-09-30
1218 | Farm East LLC | Locke Solar Farm | 2021-07-12 | 19.8 | 19.8 | S | Cayuga | NY | C | NYS-Locke 718 Substation | NYSEG | 0 | 2021-10-31
1220 | Fresh Air Energy II | Lincoln ESC | 2021-07-26 | 100 | 100 | ES | Suffolk | NY | K | Holbrook - Saxville 69kV | LIPA | 0 | 2021-11-30
1224 | Northland Power U.S. Projects | Sunwine Solar | 2021-07-28 | 50 | 50 | CR | Westfield | NY |  | Westfield Electric 115kV |  | 0 | 2021-10-31
1225 | Nexamp Solar | 26338 Westmoreland | 2021-07-29 | 20 | 20 | S | Oneida | NY |  | Oneida - Walesville 115kV | NM-NG | 0 | 2021-09-30
1232 | ConnectGen Cayuga County LLC | Harvest Hills Solar II | 2021-08-19 | 50 | 50 | S | Cayuga | NY | C | Wright Avenue - Cayuga 115kV | NYSEG | 0 | 2021-10-31
1252 | Alliance Energy Storage, LLC | Hillburn Energy Storage | 2021-09-15 | 10 | 10 | ES | Rockland | NY | G | Hillburn | O&R | 0 | 2021-11-30
1253 | Alliance Energy Storage, LLC | Shoemaker Energy Storage | 2021-09-15 | 5.5 | 5.5 | ES | Orange | NY | G | Shoemaker | O&R | 0 | 2021-11-30
1242 | Light & Power Development, LLC | Ravenswood Energy Storage 3 | 2021-09-03 | 70 | 70 | ES | Queens | NY | J | Vernon 138kV | ConEd | 0 | 2021-11-30
1259 | Oriden LLC | Middletown Energy Storage | 2021-09-22 | 50 | 50 | ES | Orange | NY | G | Shoemaker 69 kV | O&R | 0 | 2021-11-30
1262 | East Coast Power LLC | Brunswick Energy Storage | 2021-09-24 | 150 | 165 | ES | Union | NJ | J | Goethals 345kV | ConEd | 0 | 2022-01-31
1263 | Ravenswood Energy Storage 4 | Ravenswood Energy Storage 4 | 2021-09-27 | 12 | 12 | ES | Queens | NY | J | Vernon 138kV | ConEd | 0 | 2021-11-30
1264 | ELP Claverack Solar II LLC | ELP Claverack Solar II LLC | 2021-09-27 | 20 | 20 | CR | Columbia | NY | F | Hudson - Churchtown 115kV | NYTransco/ NM-NG | 0 | 2022-01-31
1266 | Microgrid Networks, LLC | Rust Street 21.8MW ESS | 2021-09-28 | 21.8 | 22.8 | ES | Queens | NY | J | Glendale 27kV | ConEd | 0 | 2021-11-30
1267 | Microgrid Networks, LLC | Rust Street 20 MW ESS Project | 2021-09-28 | 20 | 20 | ES | Queens | NY | J | Glendale 27kV | ConEd | 0 | 2021-11-30
1268 | Microgrid Networks, LLC | 1st Avenue 20 MW ESS Project | 2021-09-28 | 20 | 20 | ES | Kings | NY | J |  | ConEd | 0 | 2021-11-30
1269 | 174 Power Global Properties, LLC | The Bruckner | 2021-09-28 | 11.6 | 11.6 | ES | Bronx | NY | J |  | ConEd | 0 | 2021-11-30
1297 | Algonquin Power Fund (America), Inc. | Deerpark Energy Storage | 2021-10-29 | 20 | 20 | ES | Orange | NY | G | Cuddebackville substation | O&R | 0 | 2022-01-31
1270 | Microgrid Networks, LLC | Hinsdale 21.8MW Bulk Storage Project | 2021-09-29 | 21.8 | 21.8 | ES | Kings | NY | J | Brownsville 27kV | ConEd | 0 | 2021-11-30
1296 | Nexamp Solar | 90662 Sing Sing Standalone Storage | 2021-10-28 | 20 | 20 | ES | Chemung | NY | J |  | ConEd | 0 | 2021-11-30
1298 | Nexamp Solar | 87677 Clifton Springs Standalone Storage | 2021-10-29 | 20 | 20 | ES | Ontario | NY | J |  | ConEd | 0 | 2021-11-30
1300 | KCE NY 25, LLC | KCE NY 25, LLC | 2021-11-02 | 6 | 6 | ES | Ontario | NY | B | Substation 146 | RG&E | 0 | 2021-12-31
1318 | Algonquin Power Fund (America), Inc. | Saugerties Energy Storage | 2021-12-21 | 12.9 | 12.9 | ES | Ulster | NY | G | Saugerties substation 13.8 kV | CHGE | 0 | 2022-01-31

## In Service
Queue |  |  | Date | SP | WP | Type/ | Location |  | Z | Interconnection |  |  | Last Update | Availability | FS Complete/ | Proposed | Proposed
Pos. | Owner/Developer | Project Name | of IR | (MW) | (MW) | Fuel | County | State |  | Point | Utility | S |  | of Studies | SGIA Tender | In-Service | COD
1 | Con Edison | Middletown Station | 1989-09-15 | N/A | N/A | AC | Orange County | NY | G | Coop Corn-Rock Tav Lines | NYPA | 14 | 2002-03-31 | None |  | I/S | N/A
2 | Athens Gen Co./ PG&E | Athens Gen | 1998-04-27 | 1080 |  | CC-NG | Athens | NY | F | Leeds-Pl.Val. 91 Line | NM-NG | 14 | 2004-05-31 | SRIS |  | I/S | N/A
3 | PSEG Power NY | Bethlehem Energy Center | 1998-04-27 | 350 |  | CC-NG | Albany | NY | F | Albany 115kV | NM-NG | 14 | 2005-07-31 | SRIS |  | I/S | N/A
4 | TransEnergie US, Ltd | CT-LI DC Tie-line | 1998-07-20 | 330 |  | DC | Shoreham | NY | K | Shoreham, Long Island | LIPA | 14 | 2003-12-31 | SRIS,CY01 |  | I/S | I/S
11 | East Coast Power-Linden Venture LP | East Coast Power-Linden | 1999-03-25 | 20 |  | NG | Linden | NY | J | Goethals | CONED | 14 | 2002-03-31 |  |  | I/S | I/S
17 | KeySpan Energy, Inc. | KeySpan Ravenswood | 1999-04-21 | 270 |  | CC-NG | New York | NY | J | Vernon | CONED | 14 |  | SRIS,CY01,CY02 |  | I/S | I/S
18 | NYPA | Poletti Expansion | 1999-04-30 | 500 |  | CC-NG | Queens | NY | J | Astoria 138kV | CONED | 14 | 2/26/08 | SRIS, CY01 |  | I/S | I/S
25 | Consolidated Edison of NY | East River Repowering | 1999-08-10 | 288 |  | CC-NG | New York | NY | J | E. 13th St. 138kV | CONED | 14 |  | SRIS, CY01 |  | I/S | I/S
31 | SCS Energy, LLC | Astoria Energy | 1999-11-16 | 1000 |  | CC-NG | Queens | NY | J | Astoria 138kV | CONED | 12,14 | 2/26/08 | SRIS, CY01 |  | Part I/S | Part I/S
55 | Canastota Wind Power, LLC | Fenner Wind Energy Fac. | 2000-03-14 | 30 |  | W |  |  |  | Fenner-Whitman | NM-NG | 14 |  | SRIS,CY02 |  | I/S | I/S
66 | TransEnergie HQ | Langlois Converter | 2000-06-02 | 100 | N/A | AC |  |  |  | Langlois, Quebec | NM-NG | 14 |  | SRIS |  | I/S | N/A
69 | Empire Generating Co., LLC | Empire Generating | 2000-07-14 | 635 |  | CC-NG | Rensselaer | NY | F | Reynolds Road 345kV | NM-NG | 14 | 9/30/10 | SRIS, CY05 |  | I/S | N/A
79 | NYPA | Harlem River Yards | 2000-12-05 | 79.9 |  | CT | New York | NY | J | Hell Gate Substation | CONED | 14 |  | SRIS,CY01 |  | I/S | N/A
80 | NYPA | Hell Gate | 2000-12-05 | 79.9 |  | CT | New York | NY | J | Hell Gate Substation | CONED | 14 |  | SRIS,CY01 |  | I/S | I/S
81 | NYPA | Vernon Blvd | 2000-12-05 | 79.9 |  | CT | New York | NY | J | Vernon Substation | CONED | 14 |  | SRIS,CY01 |  | I/S | I/S
82 | NYPA | N First St and Grand Ave | 2000-12-05 | 44 |  | CT | New York | NY | J | Vernon-Greenwood line | CONED | 14 |  | SRIS,CY01 |  | I/S | I/S
83 | NYPA | 23rd St and 3rd Ave | 2000-12-05 | 79.9 |  | CT | New York | NY | J | Gowanus Substation | CONED | 14 |  | SRIS,CY01 |  | I/S | I/S
84 | NYPA | Fox Hills | 2000-12-05 | 44 |  | CT | New York | NY | J | Fox Hills Substation | CONED | 14 |  | SRIS,CY01 |  | I/S | I/S
85 | NYPA | Brentwood | 2000-12-05 | 44 |  | CT |  |  | K | Brentwood 69 kV | LIPA | 14 |  | SRIS,CY01 |  | I/S | I/S
94 | Atlantic Energy, LLC | Project Neptune DC PJM-LI | 2001-05-22 | 660 |  | DC | Nassau | NY-NJ | K | Newbridge Road 138kV | LIPA | 14 | 10/14/08 | SRIS, CY05 |  | I/S | I/S
95 | KeySpan Energy Development Corp. | Glenwood Gas Plant | 2001-05-22 | 79.9 |  | CT |  |  | K | Glenwood 69 kV | LIPA | 14 |  |  |  | I/S | I/S
99 | Central Hudson Gas & Electric | Rock Tavern Transformer | 2001-06-28 | N/A | N/A | AC |  |  | G | Rock Tavern | CHG&E | 14 |  | SRIS |  | I/S | N/A
107 | Caithness Long Island, LLC | Caithness Long Island | 2001-10-09 | 310 |  | CC-NG | Suffolk | NY | K | Brookhaven-Holbrook or H'ville 138kV | LIPA | 14 | 11/30/09 | SRIS, CY06 |  | I/S | N/A
115 | Central Hudson Gas & Electric | East Fishkill Transformer | 2002-04-24 | N/A | N/A | AC | Dutchess | NY | G | East Fishkill 345kV/115kV | CONED/CHG&E | 14 | 3/31/13 | None |  | I/S | N/A
121 | KeySpan Energy for LIPA | Holtsville Emergency Gen | 2002-05-31 | 66 |  | CT |  |  |  | Holtsville | LIPA | 14 |  | SRIS |  | I/S | N/A
122 | KeySpan Energy for LIPA | Shoreham Emergency Gen | 2002-05-31 | 66 |  | CT |  |  |  | Holtsville | LIPA | 14 |  | SRIS |  | I/S | N/A
123 | KeySpan Energy for LIPA | Wading River Emergency Gen | 2002-05-31 | 79.9 |  | CT |  |  |  | Holtsville | LIPA | 14 |  | SRIS |  | I/S | I/S
125 | East Coast Power, LLC | Linden VFT Inter-Tie | 2002-07-18 | 300 | N/A | AC | Richmond | NY-NJ | J | Goethals 345kV | CONED | 14 | 11/30/09 | SRIS, CY06 |  | I/S | I/S
127A | Airtricity Munnsville Wind Farm, LLC | Munnsville | 2002-10-09 | 40 |  | W | Madison | NY | E | 46kV line | NYSEG | 11,14 | 3/31/13 | SRIS, CY06 |  | Part I/S | Part I/S
133 | KeySpan Energy for LIPA | Holtsville Emergency Gen | 2003-05-15 | 66 |  | CT |  |  |  | Holtsville | LIPA | 14 |  | SRIS |  | I/S | I/S
135 | UPC Wind Management, LLC | Canandaigua Wind Farm | 2003-05-30 | 82.5 | 82.5 | W | Steuben | NY | C | Avoca 230kV line | NYSEG | 14 | 3/2/09 | SRIS, CY06 |  | I/S | I/S
136 | Rochester Gas & Electric | Rochester Transmission | 2003-06-12 | N/A | N/A | AC | Monroe | NY | B | RG&E System | RG&E | 14 | 4/8/09 | SRIS |  | I/S | N/A
138 | Entergy Nuclear Operations, Inc. | Indian Point 2 Uprate | 2003-07-23 | 36 |  | NU | Westchester | NY | H | Buchanan 345kV | CONED | 14 | 4/8/09 | SRIS, CY05 |  | I/S | I/S
139 | Entergy Nuclear Operations, Inc. | Indian Point 3 Uprate | 2003-07-23 | 38 |  | NU | Westchester | NY | H | Indian Point 345kV | CONED | 14 | 4/8/09 | SRIS, CY05 |  | I/S | I/S
141 | Flat Rock Wind Power, LLC | Flat Rock Wind Power | 2003-08-27 | 321 |  | W | Lewis | NY | E | Adirondack-Porter 230kV | NM-NG | 14 | 2/26/08 | SRIS, CY05 |  | I/S | I/S
143 | Constellation | Ginna Uprate Project | 2004-01-30 | 95 |  | NU | Wayne | NY | B | Ginna-115kV | RG&E | 14 | 2/26/08 | SRIS, CY05 |  | I/S | I/S
144 | Sheldon Energy, LLC | High Sheldon Windfarm | 2004-02-18 | 112.5 | 112.5 | W | Wyoming | NY | C | Stolle Rd-Meyer 230kV | NYSEG | 14 | 6/24/09 | SRIS, CY06,CY07 |  | I/S | I/S
145 | KeySpan Energy for LIPA | LIPA Summer Mobile Gens | 2004-03-02 | 96 |  | CT-NG | Suffolk | NY | K | Holtsville and Shoreham 138kV | LIPA | 14 | 2/26/08 | SRIS |  | I/S | I/S
146 | Con Edison | Mott Haven Substation | 2004-03-16 | N/A | N/A | AC | Westchester | NY | J | Dunwoodie-Rainey lines | CONED | 14 | 4/8/09 | SRIS |  | I/S | N/A
149 | KeySpan Energy for LIPA | LIPA Wading River Em Gen | 2004-06-03 | 79.9 |  | CT |  |  |  | Wading River | LIPA | 14 |  | SRIS |  | I/S | I/S
153 | Con Edison | Sprain Brook-Sherman Creek | 2004-08-13 | 500 | N/A | AC | Westchester | NY | I, J | Sprain Brook & Sherman Creek | CONED | 14 | 3/31/11 | SIS |  | I/S | N/A
156 | Hardscrabble Wind Power, LLC | Fairfield Wind Project | 2004-09-28 | 74 | 74 | W | Herkimer | NY | E | Valley-Inghams 115kV | NM-NG | 14 | 2/28/11 | SRIS, CY06 |  | I/S | I/S
160A | Innovative Energy Systems Inc. | DANC | 2004-11-19 | 6.4 | 6.4 | M | Jefferson | NY | E | 115kV | NM-NG | 14 | 10/14/08 |  |  | I/S | I/S
161 | Marble River, LLC | Marble River Wind Farm | 2004-12-07 | 83 | 83 | W | Clinton | NY | D | Willis-Plattsburgh WP-1 230kV | NYPA | 14 | 3/31/13 | SRIS, FS |  | I/S | I/S
171 | Marble River, LLC | Marble River II Wind Farm | 2005-02-08 | 132.2 | 132.2 | W | Clinton | NY | D | Willis-Plattsburgh WP-2 230kV | NYPA | 14 | 3/31/13 | SRIS, FS |  | I/S | I/S
172 | Noble Environmental Power, LLC | Clinton Windfield | 2005-02-14 | 79.5 | 79.5 | W | Clinton | NY | D | Willis-Plattsburgh WP-2 230kV | NYPA | 14 | 10/14/08 | SRIS, CY06 |  | I/S | I/S
173 | Noble Environmental Power, LLC | Bliss Windfield | 2005-02-14 | 72 | 72 | W | Wyoming | NY | A | Arcade Substation 115kV | Village of Arcade | 14 | 10/14/08 | SRIS, CY06 |  | I/S | I/S
174 | Noble Environmental Power, LLC | Altona Windfield | 2005-02-14 | 99 | 99 | W | Clinton | NY | D | Willis-Plattsburgh WP-1 230kV | NYPA | 14 | 3/2/09 | SRIS, CY06 |  | I/S | I/S
175 | Noble Environmental Power, LLC | Ellenburg Windfield | 2005-02-14 | 81 | 81 | W | Clinton | NY | D | Willis-Plattsburgh WP-2 230kV | NYPA | 14 | 10/14/08 | SRIS, CY06 |  | I/S | I/S
177 | Noble Wethersfield Windpark, LLC | Wethersfield 230kV | 2005-02-14 | 126 | 126 | W | Wyoming | NY | C | Stolle-Meyer 230kV | NYSEG | 14 | 3/2/09 | FES,SRIS,CY07 |  | I/S | I/S
182 | Howard Wind, LLC | Howard Wind | 2005-03-21 | 57.4 | 57.4 | W | Steuben | NY | C | Bennett-Bath 115kV | NYSEG | 14 | 12/31/11 | FES, SRIS, CY07 |  | I/S | I/S
185 | New York Power Authority | Blenheim Gilboa Storage | 2005-03-29 | 120 | 120 | PS | Schoharie | NY | F | Valenti Rd., Gilboa 345kV | NYPA | 14 | 6/30/10 | SRIS, CY06 |  | I/S | I/S
199 | UPC Wind Management, LLC | Canandaigua II | 2005-07-26 | 42.5 | 42.5 | W | Steuben | NY | C | Meyer - Avoca 230kV | NYSEG | 14 | 4/8/09 | SRIS, CY07 |  | I/S | I/S
201A | Innovative Energy Systems | Seneca Energy Expansion | 2005-09-02 | 17.6 | 17.6 | M | Seneca | NY | C | 34.5kV | NYSEG | 14 | 4/22/08 |  |  | I/S | I/S
201B | Minnesota Methane, LLC | MM Albany Landfill | 2005-09-15 | 1.9 | 3.8 | M | Albany | NY | F | 34.5kV | NM-NG | 14 | 10/14/08 |  |  | I/S | I/S
205 | National Grid | Luther Forest | 2005-11-02 | 40 | 40 | L | Saratoga | NY | F | Round Lake 115kV | NM-NG | 14 | 3/31/13 | SIS |  | I/S | I/S
206 | Hudson Transmission Partners | Hudson Transmission | 2005-12-14 | 660 | 660 | DC/AC | NY - Bergen | NY-NJ | J | West 49th Street 345kV | CONED | 14 | 6/30/13 | FES, SRIS, FS | 2010-02-01 | I/S | I/S
209A | Casella Waste Systems | Hyland Landfill | 2006-02-28 | 6.4 | 6.4 | M | Livingston | NY | C | 34.5kV | NYSEG | 14 | 10/14/08 |  |  | I/S | I/S
211 | Noble Environmental Power, LLC | Clinton II Windfield | 2006-04-03 | 21 | 21 | W | Clinton | NY | D | Willis-Plattsburgh WP-2 230kV | NYPA | 14 | 10/14/08 | SRIS, CY07 |  | I/S | I/S
212 | Noble Environmental Power, LLC | Bliss II Windfield | 2006-04-03 | 28.5 | 28.5 | W | Wyoming | NY | A | Freedom Substation 115kV | Village of Arcade | 14 | 10/14/08 | SRIS, CY07 |  | I/S | I/S
214 | Noble Chateaugay Windpark, LLC | Chateaugay Windpark | 2006-04-03 | 106.5 | 106.5 | W | Franklin-Clinton | NY | D | Willis-Plattsburgh 230kV | NYPA | 14 | 3/2/09 | FES, SRIS, CY07 |  | I/S | I/S
216 | Nine Mile Point Nuclear, LLC | Nine Mile Point Uprate | 2006-05-05 | 168 | 168 | NU | Oswego | NY | C | Scriba Station 345kV | NM-NG | 14 | 3/31/13 | SRIS, FS |  | I/S | I/S
217A | New Athens Generating Co., LLC | Athens SPS Project | 2006-06-30 | N/A | N/A | AC | Greene-W.Chester | NY | F, H | Athens - Millwood | NM-NG/CONED | 14 | 4/8/09 | SIS |  | I/S | N/A
224A | Bio-Energy Partners | High Acres Landfill | 2006-08-25 | 6.4 | 6.4 | M | Monroe | NY | C | 34.5 | NYSEG | 14 | 12/22/08 |  |  | I/S | I/S
225 | New York State Electric & Gas | Ithaca Transmission | 2006-09-07 | N/A | N/A | AC | Thompkins | NY | C | Oakdale - Lafayette 345kV | NYSEG | 14 | 1/31/11 | SIS |  | I/S | N/A
232 | Bayonne Energy Center, LLC | Bayonne Energy Center | 2006-11-27 | 500 | 500 | CT-D | Bayonne | NJ | J | Gowanus Substation 345kV | ConEd | 14 | 3/31/13 | FES, SRIS, CY09 |  | I/S | I/S
233 | Erie Boulevard Hydro Power, LP | Sherman Island Uprate | 2006-11-27 | 8.5 | 8.5 | H | Warren | NY | F | Spier - Queensbury 115kV | NM-NG | 14 | 2/16/10 | SRIS,CY08 |  | I/S | I/S
234 | Steel Winds, LLC | Steel Winds II | 2006-12-08 | 15 | 15 | W | Erie | NY | A | Substation 11A 115kV | NM-NG | 14 | 1/31/12 | SRIS, CY08 |  | I/S | I/S
237A | Chautauqua County | Chautauqua Landfill | 2007-01-11 | 6.4 | 6.4 | M | Chautauqua | NY | A | Hartfield – South Dow 34.5kV | NM-NG | 14 | 10/28/09 | FES,SIS,FS |  | I/S | I/S
245 | Innovative Energy System, Inc. | Fulton County Landfill | 2007-04-17 | 3.2 | 3.2 | M | Montgomary | NY | F | Ephratah – Amsterdam 69kV | NM-NG | 14 | 11/30/11 | FES,SIS,CY09 | 2008/Q3 | I/S | I/S
250 | Seneca Energy II, LLC | Ontario | 2007-07-02 | 5.6 | 5.6 | M | Ontario | NY | C | Haley Rd. - Hall 34.5kV | NYSEG | 14 | 3/31/13 | FES,FS |  | I/S | I/S
251 | CPV Valley, LLC | CPV Valley Energy Center | 2007-07-05 | 677.6 | 690.6 | CC-D | Orange | NY | G | Coopers – Rock Tavern 345kV | NYPA | 14 | 3/31/18 | FES, SRIS, FS | 2013-10-15 | I/S | I/S
260 | Stephentown Regulation Services, LLC | Stephentown | 2007-09-25 | 20 | 20 | F | Rensselaer | NY | F | Stephentown 115kV | NYSEG | 14 | 11/30/11 | SIS,CY10 | 2008/10 | I/S | I/S
263 | Stony Creek Wind Farm, LLC | Stony Creek Wind Farm | 2007-10-12 | 92.8 | 92.8 | W | Wyoming | NY | C | Stolle Rd - Meyer 230kV | NYSEG | 14 | 3/31/14 | FES, SRIS, CY10 | 2011-11-30 | I/S | I/S
270A | National Grid | Luther Forest Transmission | 2007-12-18 | N/A | N/A | AC | Saratoga | NY | F | Ngrid 115kV | NM-NG | 14 | 10/14/08 | SIS |  | I/S | N/A
284 | Broome Energy Resources, LLC | Nanticoke Landfill | 2008-03-06 | 1.6 | 1.6 | M | Broome | NY | C | Nanticoke Landfill Plant 34.5kV | NYSEG | 14 | 9/30/13 | FES | 2012-06-15 | I/S | I/S
289 | New York State Electric & Gas | Corning Valley Trans. | 2008-04-01 | N/A | N/A | AC | Steuben | NY | C | Avoca and Hillside 230kV | NYSEG | 14 | 9/30/11 | SIS |  | I/S | N/A
290A | Green Island Power Authority | Green Island Power | 2008-04-07 | 20 | 20 | L | Albany | NY | F | Maplewood - Johnson Rd 115kV | NM-NG | 14 | 11/30/11 | SIS |  | I/S | I/S
294 | Orange & Rockland | Ramapo-Sugarloaf | 2008-04-29 | N/A | N/A | AC | Orange/Rockland | NY | G | Ramapo - Sugarloaf 138kV | O&R | 14 | 4/30/15 | SIS |  | I/S | N/A
308 | Astoria Energy II, LLC | Astoria Energy II | 2008-08-20 | 576 | 617.2 | CS-NG | Queens | NY | J | Astoria 345kV | NYPA | 14 | 11/30/11 | SRIS | 2011/05 | I/S | I/S
318 | AES Energy Storage, LLC | Westover Energy Storage | 2008-12-03 | 20 | 20 | ES | Broome | NY | C | Westover 115kV | NYSEG | 14 | 12/31/10 | None | 2010/01 | I/S | I/S
326 | NYSEG/RG&E | Rochester SVC/PST Trans. | 2009-03-09 | N/A | N/A | AC | Monroe | NY | B | Station 124 115kV | NYSEG | 14 | 4/30/14 | SIS |  | I/S | N/A
330 | Long Island Solar Farm LLC | Upton Solar Farms | 2009-04-07 | 31.5 | 32 | S | Suffolk | NY | K | 8ER Substation 69kV | LIPA | 14 | 11/30/11 | SRIS | 2011/05 | I/S | I/S
331 | National Grid | Northeast NY Reinforcement | 2009-04-22 | N/A | N/A | AC | Saratoga | NY | F | NGrid 230kV | NM-NG | 14 | 3/31/19 | SIS |  | I/S | N/A
333 | National Grid | Western NY Reinforcement | 2009-05-05 | N/A | N/A | AC | Cattaraugus | NY | A | NGrid 115kV | NM-NG | 14 | 3/31/19 | SIS |  | I/S | N/A
337 | Long Island Power Authority | Northport Norwalk Harbor | 2009-07-14 | N/A | N/A | AC | Suffolk | NY | K | Northport 138kV | LIPA | 14 | 1/31/11 | SIS |  | I/S | N/A
339 | RG&E | Transmission Reinforcement | 2009-08-17 | N/A | N/A | AC | Monroe | NY | B | Niagara - Kintigh 345kV | RG&E | 14 | 2021-05-31 | SIS | N/A | I/S | N/A
340 | RG&E | Brown's Race III | 2009-09-02 | 2 | 2 | H | Monroe | NY | B | Station 6 34.5 kV | RG&E | 14 | 1/31/12 | None | 2010/12 | I/S | I/S
342 | Albany Energy, LLC | Albany Landfill | 2009-09-03 | 6.4 | 6.4 | M | Albany | NY | F | 34.5kV | NM-NG | 14 | 3/31/13 | None |  | I/S | I/S
353 | Chautauqua County | Chautauqua County Landfill | 2010-04-26 | 3.2 | 3.2 | M | Chautauqua | NY | A | Hartfield – South Dow 34.5kV | NM-NG | 14 | 6/30/11 | None | 2011/03 | I/S | I/S
355 | Brookfield Renewable Power | Stewarts Bridge Hydro | 2010-08-03 | 3 | 3 | H | Saratoga | NY | F | Spier Falls - EJ West 115kV | NM-NG | 14 | 4/30/15 | SRIS, FS |  | I/S | I/S
368 | Consolidated Edison Co. of NY | Feeder 76 Ramapo to Rock Tavern | 2011-10-13 | N/A | N/A | AC | Orange, Rockland | NY | G | Ramapo to Rock Tavern 345 kV | ConEd/CenHud | 14 | 5/31/16 | SIS |  | I/S | N/A
373 | New York Power Authority | Coopers Corners Shunt Reactor | 2011-12-21 | N/A | N/A | AC | Sullivan | NY | E | Coopers Corners 345 kV | NYSEG | 14 | 8/31/15 | SIS |  | I/S | N/A
375 | Eagle Creek Hydro, LLC | Eagle Creek Hydro | 2012-03-06 | 0.8 | 0.8 | H | Sullivan | NY | E | Rio 69kV Switchyard | O&R | 14 | 1/31/14 | None | 2013-03-06 | I/S | I/S
378 | Invenergy NY LLC | Marsh Hill Wind | 2012-03-29 | 16.2 | 16.2 | W | Steuben | NY | C | Jasper - Marshall Warriner 34.5kV | NYSEG | 14 | 12/31/14 | None | 2013-10-09 | I/S | I/S
380 | New York Power Authority | Marcy South Reinforcement | 2012-05-14 | N/A | N/A | AC | Oneida-Sullivan | NY | E | Marcy/Edic-Coopers Corners 345kV | NYSEG | 14 | 7/31/16 | SIS |  | I/S | N/A
390 | Trail Co. | Farmers Valley Substation | 2012-09-14 | N/A | N/A | AC | Cattaraugus | NY-PA | A | Homer City - Stolle Rd. 345kV | NM-NG/NYSEG | 14 | 6/30/16 | SIS |  | I/S | N/A
394 | Trail Co. | Mainesburg Substation | 2012-10-16 | N/A | N/A | AC | Chemung | NY-PA | C | Homer City - Watercure 345kV | NYSEG | 14 | 12/31/15 | SIS |  | I/S | N/A
395 | Copenhagen Wind Farm, LLC | Copenhagen Wind | 2012-11-12 | 79.9 | 79.9 | W | Lewis | NY | E | Black River-Lighthouse Hill 115kV | NM-NG | 14 | 3/31/19 | FES, SRIS, FS | 2017-02-02 | I/S | I/S
397 | Jericho Rise Wind Farm, LLC | Jericho Rise Wind | 2012-12-21 | 77.7 | 77.7 | W | Franklin | NY | D | Willis Substation 115kV | NYPA | 14 | 2/28/17 | SRIS, FS | 2017-02-02 | I/S | I/S
403 | PSEG Power New York | Bethlehem Energy Center Uprate | 2013-05-28 | 72 | 51.2 | CC-D | Albany | NY | F | Bethlehem Energy Center | NM-NG | 14 | 3/31/19 | FES, SRIS, FS | 2017-02-02 | I/S | I/S
0421 | EDP Renewables North America LLC | Arkwright Summit | 2013-11-01 | 78.4 | 78.4 | W | Chautauqua | NY | A | Dunkirk - Falconer 115 kV | NM-NG | 14 | 2020-04-30 | SRIS, FS | 2019-07-09 | IS | I/S
431 | Greenidge Generation | Greenidge Unit #4 | 2014-04-11 | 106.3 | 106.3 | ST-NG | Yates | NY | C | Greenidge Substation 115kV | NYSEG | 14 | 2/28/18 | SRIS, FS |  | I/S | I/S
432 | New York State Electric & Gas | South Perry Transformer | 2014-04-15 | N/A | N/A | AC | Wyoming | NY | B | South Perry Substation 115kV | NYSEG | 14 | 7/31/18 | SIS |  | I/S | N/A
0444 | Cricket Valley Energy Center, LLC | Cricket Valley Energy Center II | 2014-06-18 | 1020 | 1132 | CC | Dutchess | NY | G | Pleasant Valley - Long Mt. 345kV | ConEd | 14 | 2020-04-30 | SRIS, FS | 2019-07-09 | IS | I/S
0461 | Consolidated Edison Co. of NY | East River 1 Uprate | 2014-12-01 | 2 | 2 | CT | New York | NY | J | East River Complex | ConEd | 14 | 2020-04-30 | SRIS, FS | 2019-07-09 | IS | I/S
0462 | Consolidated Edison Co. of NY | East River 2 Uprate | 2014-12-01 | 2 | 2 | CT | New York | NY | J | East River Complex | ConEd | 14 | 2020-04-30 | SRIS, FS | 2019-07-09 | IS | I/S
0467 | Shoreham Solar Commons LLC | Shoreham Solar | 2014-12-22 | 25 | 25 | S | Suffolk | NY | K | Ridge - Wildwood 69kV | LIPA | 14 | 2020-04-30 | SRIS, FS | 2019-07-09 | IS | I/S
0477 | Riverhead Solar Farm LLC | Riverhead Solar | 2015-02-18 | 20 | 20 | S | Suffolk | NY | K | Edwards Substation 138kV | LIPA | 14 | 2020-04-30 | FES, SIS, FS | 2018-03-16 | IS | I/S
490 | New York Power Authority | Marcy South Series Comp | 2015-03-16 | N/A | N/A | AC | Oneida-Sullivan | NY | E | Marcy/Edic-Coopers Corners 345kV | NYSEG/NM-NG | 14 | 7/31/16 | SIS |  | I/S | N/A
0510 | Bayonne Energy Center | Bayonne Energy Center II | 2015-08-03 | 120.4 | 129.4 | D | Hudson | NJ | J | Gowanus Substation 345kV | ConEd | 14 | 2020-04-30 | SRIS, FS | 2019-07-09 | IS | I/S
517 | National Grid | Western NY Reactors & Capacitors | 2015-10-14 | N/A | N/A | AC | Niagara | NY | A | Packard - Huntley 230kV | NM-NG | 14 | 6/30/16 | SIS |  | I/S | N/A
583 | Erie Boulevard Hydropower, LP | Fulton | 2016-10-31 | 1.3 | 1.3 | H | Oswego | NY | C | Fay St. 34.5kV | NM-NG | 14 | 3/31/18 | FS | 2017-07-12 | I/S | I/S
0696 | Eagle Creek Hydro Power, LLC | Swinging Bridge Unit 3 | 2018-03-21 | 1.2 | 1.2 | H | Orange | NY | G | Swing Bridge 69 kV | O&R | 14 | 2020-04-30 |  | 2018-06-20 | IS | I/S
0701 | KCE NY 1, LLC | KCE NY 1 | 2018-03-15 | 20 | 20 | ES | Saratoga | NY | F | Luther - Forest Substation 34.5kV | NYSEG | 14 | 2020-04-30 |  | 2018-06-20 | IS | I/S
0781 | New York Power Authority | Marcy South SSR Detection | 2018-12-03 | N/A | N/A | AC | Delaware | NY | E | Fraser - Annex 345 kV Substation | NYPA | 14 | 2020-04-30 | SIS | N/A | IS | I/S