## Active
Queue |  |  | Date | SP | WP | Type/ | Location | Z | Interconnection |  |  | Last Update | Availability | FS Complete/ | Proposed | Proposed | Proposed
Pos. | Owner/Developer | Project Name | of IR | (MW) | (MW) | Fuel | County/State |  | Point | Utility | S |  | of Studies | SGIA Tender | In-Service | Initial-Sync | COD
276 | EDF Renewables Development, Inc. | Homer Solar Energy Center | 2008-01-30 | 90 | 90 | S | Cortland, NY | C | Cortland - Fenner 115kV | NM-NG | 9 | 11/30/19 | FES, SRIS |  | 2023/11 | 2023/11 | 2023/12
338 | RG&E | Brown's Race II | 2009-08-11 | 6.3 | 6.3 | H | Monroe, NY | B | Station 137 11kV | RG&E | 11 | 9/30/18 | FS | 2014-11-24 | 2019/10 | 2019/10 | 2019/10
339 | RG&E | Transmission Reinforcement | 2009-08-17 | N/A | N/A | AC | Monroe, NY | B | Niagara - Kintigh 345kV | RG&E | 12 | 9/30/19 | SIS | N/A | 2021/S | N/A | N/A
349 | Taylor Biomass Energy-Montgomery, LLC | Taylor Biomass | 2009-12-30 | 19 | 22.5 | SW | Orange, NY | G | Maybrook - Rock Tavern 69kV | CHGE | 12 | 12/31/17 | SRIS, FS | 2013-10-15 | 2020/08 |  | 2021/04
361 | US PowerGen Co. | Luyster Creek Energy | 2011-02-15 | 401 | 444 | CC-D | Queens, NY | J | Astoria West Substation 138kV | ConEd | 7 | 6/30/17 | FES, SRIS |  | 2021/06 | 2021/06 | 2021/06
363 | Anbaric Development Partners, LLC | Poseidon Offshore | 2011-04-27 | 500 | 500 | W | NY - Suffolk, NY | K | Ruland Rd. 138kV | LIPA | 10 | 3/31/19 | FES, SRIS, FS | 2017-02-02 | 2020/07 | 2020/11 | 2021/01
372 | Dry Lots Wind, LLC | Dry Lots Wind | 2011-10-31 | 33 | 33 | W | Herkimer, NY | E | Schuyler - Whitesboro 46kV | NM-NG | 7 | 1/31/18 | FES, SRIS |  | 2020/11 | 2020/10 | 2020/12
386 | Vermont Green Line Devco, LLC | Grand Isle Intertie | 2012-06-28 | 400 | 400 | DC | Clinton, NY - VT | D | Plattsburgh 230kV-New Haven, VT 345kV | NYPA | 6 | 11/30/18 | FES, SRIS |  | 2023 | N/A | N/A
387 | Cassadaga Wind, LLC | Cassadaga Wind | 2012-07-19 | 126 | 126 | W | Chautauqua, NY | A | Dunkirk – Moon Station 115 kV | NM-NG | 11 | 10/31/19 | FES, SRIS, FS | 2019-07-09 | 2020/05 | 2020/05 | 2020/12
393 | NRG Berrians East Development, LLC | Berrians East Replacement | 2012-10-16 | 94.2 | 57 | CT-D | Queens , NY | J | Astoria East Substation 138kV | ConEd | 10 | 9/30/19 | FES, SRIS, FS | 2019-07-09 | 2022/07 | 2022/10 | 2023/02
396 | Baron Winds, LLC | Baron Winds | 2012-11-30 | 300 | 300 | W | Steuben, NY | C | Hillside - Meyer 230kV | NYSEG | 10 | 7/31/19 | FES, SRIS, FS | 2019-07-09 | 2020/05 | 2020/05 | 2020/12
396A | New York State Electric & Gas | Wood Street Transformer | 2012-12-14 | N/A | N/A | AC | Putnam, NY | G | Wood St. 345/115kV | NYSEG | 6 | 1/31/18 | SIS |  | 2021/12 | N/A | N/A
421 | EDP Renewables North America LLC | Arkwright Summit | 2013-11-01 | 78.4 | 78.4 | W | Chautauqua, NY | A | Dunkirk – Falconer 115 kV | NM-NG | 14 | 7/31/19 | SRIS, FS | 2019-07-09 |  |  | I/S
422 | NextEra Energy Resources, LLC | Eight Point Wind Energy Center | 2013-11-07 | 101.2 | 101.2 | W | Steuben-Allegany, NY | C | Bennett 115kV | NYSEG | 10 | 7/31/19 | FES, SRIS, FS | 2019-07-09 | 2020/07 | 2020/07 | 2020/12
429 | Orange & Rockland | North Rockland Station | 2014-02-12 | N/A | N/A | AC | Steuben, NY | G | Line Y88 345kV | ConEd | 6 | 9/30/19 | SIS |  | 2021/06 | N/A | N/A
430 | H.Q. Energy Services U.S. Inc. | Cedar Rapids Transmission | 2014-03-05 | N/A | N/A | AC | St. Lawrence, NY | D | Dennison - Alcoa 115kV | NM-NG | 11 | 10/31/18 | SIS, FS | 2018-10-02 | 2020/12 | N/A | N/A
444 | Cricket Valley Energy Center, LLC | Cricket Valley Energy Center II | 2014-06-18 | 1020 | 1132 | CC-NG | Dutchess, NY | G | Pleasant Valley - Long Mt. 345kV | ConEd | 13 | 10/31/19 | SRIS, FS | 2019-07-09 | 2017/12 |  | 2020/03
445 | Lighthouse Wind, LLC | Lighthouse Wind | 2014-06-30 | 201.3 | 201.3 | W | Niagara, NY | A | AES Somerset Substation 345kV | NYSEG | 7 | 8/31/17 | FES, SRIS |  | 2020/08 |  | 2020/12
449 | Stockbridge Wind, LLC | Stockbridge Wind | 2014-08-13 | 72.6 | 72.6 | W | Madison, NY | C | Whitman - Oneida 115kV | NM-NG | 7 | 7/31/19 | SRIS |  | 2019/08 |  | 2019/12
458 | TDI-USA Holdings, Inc. | CH Interconnection | 2014-10-24 | 1000 | 1000 | DC | Quebec - NY, NY | J | Astoria Annex Substation 345kV | NYPA | 9 | 10/31/19 | FES, SRIS |  | 2021/Q3 | 2024/Q3 | 2024/Q4
461 | Consolidated Edison Co. of NY | East River 1 Uprate | 2014-12-01 | 2 | 2 | CT-NG | New York, NY | J | East River Complex | ConEd | 14 | 7/31/19 | SRIS, FS | 2019-07-09 |  |  | I/S
462 | Consolidated Edison Co. of NY | East River 2 Uprate | 2014-12-01 | 2 | 2 | CT-NG | New York, NY | J | East River Complex | ConEd | 14 | 7/31/19 | SRIS, FS | 2019-07-09 |  |  | I/S
465 | Hudson Transmission Partners | Hudson Transmission NY to PJM | 2014-12-15 | 675 | 675 | DC | New York, NY | J | W49th St 345kV - Bergen 230kV | ConEd | 9 | 11/30/19 | SRIS |  | 2021/03 | N/A | N/A
466 | Atlantic Wind, LLC | Bone Run Wind | 2014-12-16 | 132 | 132 | W | Cattaraugus, NY | A | Falconer - Homer Hill 115kV | NM-NG | 7 | 1/31/18 | FES, SRIS |  | 2021/11 | 2021/11 | 2021/12
467 | Shoreham Solar Commons LLC | Shoreham Solar | 2014-12-22 | 25 | 25 | S | Suffolk, NY | K | Ridge - Wildwood 69kV | LIPA | 14 | 7/31/19 | SRIS, FS | 2019-07-09 |  |  | I/S
468 | Apex Clean Energy LLC | Galloo Island Wind | 2014-12-30 | 110.4 | 110.4 | W | Oswego, NY | C | Hammermill - Wine Creek 115kV | NM-NG | 8 | 7/31/19 | FES, SRIS |  | 2019/10 |  | 2019/12
474 | EDP Renewables North America | North Slope Wind | 2015-01-30 | 200 | 200 | W | Franklin-Clinton, NY | D | Patnode 230kV | NYPA | 7 | 3/31/17 | FES, SRIS |  | 2021/10 | 2021/10 | 2021/10
477 | Riverhead Solar Farm LLC | Riverhead Solar | 2015-02-18 | 20 | 20 | S | Suffolk, NY | K | Edwards Substation 138kV | LIPA | 14 | 5/31/19 | FES, SIS, FS | 2018-03-16 |  |  | I/S
487 | LI Energy Storage System, LLC | Far Rockaway Battery Storage | 2015-03-09 | 20 | 20 | ES | Nassau, NY | K | Far Rockaway Substation 69kV | LIPA | 9 | 9/30/19 | FES, SIS |  | 2021/10 | 2021/11 | 2021/12
495 | Mohawk Solar LLC | Mohawk Solar | 2015-04-02 | 98 | 98 | S | Montgomery, NY | F | St. Johnsville - Marshville 115kV | NM-NG | 9 | 11/30/19 | FES, SRIS |  | 2021/05 | 2021/6 | 2021/11
496 | Renovo Energy Center, LLC | Renovo Energy Center | 2015-04-13 | 480 | 504 | CC-NG | Chemung, NY - PA | C | Homer City - Mainsburg 345kV | NYSEG | 8 | 9/30/19 | FES, SRIS |  | 2019/09 |  | 2020/06
497 | Invenergy Wind Development LLC | Bull Run Wind | 2015-04-24 | 303.6 | 303.6 | W | Clinton, NY | D | Patnode 230kV | NYPA | 7 | 9/30/18 | FES, SRIS |  |  |  | 2022/12
498 | ESC Tioga County Power, LLC | Tioga County Power | 2015-04-29 | 550 | 550 | CC-NG | Chemung, NY - PA | C | Homer City - Mainsburg 345kV | NYSEG | 8 | 9/30/10 | FES, SRIS |  | 2020/06 |  | 2021/05
505 | Ball Hill Wind Energy, LLC | Ball Hill Wind | 2015-06-02 | 100 | 100 | W | Chautauqua, NY | A | Dunkirk - Gardenville 230kV | NM-NG | 11 | 9/30/19 | SRIS, FS | 2019-07-09 | 2019/09 | 2019/09 | 2019/12
506 | Empire State Connector Corp. | Empire State Connector | 2015-06-10 | 1000 | 1000 | DC | Onondaga-New York, NY | E, J | Marcy - Gowanus 345kV | NYPA/ConEd | 7 | 8/31/19 | FES, SRIS |  | 2021/10 |  | 2022/01
510 | Bayonne Energy Center | Bayonne Energy Center II | 2015-08-03 | 120.4 | 129.4 | CT-D | Bayonne, NJ | J | Gowanus Substation 345kV | ConEd | 14 | 7/31/19 | SRIS, FS | 2019-07-09 |  |  | I/S
513 | Orangeville Energy Storage LLC | Orangeville | 2015-09-21 | 20 | 20 | ES | Wyoming, NY | C | Stony Creek 230kV | NYSEG | 10 | 01/31/19 | SIS, FS | 2018-01-29 | 2020/10 |  | 2020/12
516 | East Coast Power LLC | Linden Cogen Uprate | 2015-10-12 | 234.4 | 234.4 | CT-NG | Linden, NJ-NY,NY | J | Linden Cogen 345kV | ConEd | 10 | 7/31/19 | SRIS, FS | 2019-07-09 | 2020/05 |  | 2020/05
518 | PPL Electric Utilities | Compass | 2015-10-27 | N/A | N/A | AC | PA-Rockland, NY | G | Lackawanna - Ramapo 345kV | ConEd | 5 | 1/31/18 | FES |  | 2023/12 | N/A | N/A
519 | Canisteo Wind Energy LLC | Canisteo Wind | 2015-11-02 | 290.7 | 290.7 | W | Steuben, NY | C | Bennett 115kV | NYSEG | 9 | 10/31/18 | FES, SRIS |  | 2020/09 | 2020/09 | 2020/12
520 | EDP Renewables North America | Rolling Upland Wind | 2015-12-03 | 72.6 | 72.6 | W | Madison, NY | E | County Line - Brothertown 115kV | NYSEG | 7 | 3/31/18 | FES, SRIS |  | 2019/07 |  | 2019/10
521 | Invenergy NY, LLC | Bull Run II Wind | 2015-12-15 | 145.4 | 145.4 | W | Clinton, NY | D | Patnode-Duley, Ryan-Platts 230kV | NYPA | 7 | 11/30/18 | FES, SRIS |  | 2021/12 |  | 2022/12
523 | Dunkirk Power LLC | Dunkirk Unit 2 | 2015-12-17 | 75 | 75 | ST-NG | Chautauqua, NY | A | Dunkirk 115kV | NM-NG | 8 | 7/31/18 | SRIS |  | 2020/01 |  | 2020/04
524 | Dunkirk Power LLC | Dunkirk Unit 3 & 4 | 2015-12-17 | 370 | 370 | ST-NG | Chautauqua, NY | A | Dunkirk 230kV | NM-NG | 8 | 7/31/18 | SRIS |  | 2020/01 |  | 2020/04
526 | Atlantic Wind, LLC | North Ridge Wind | 2015-12-23 | 100 | 100 | W | St. Lawrence, NY | D | Malone - Colton 115kV | NM-NG | 7 | 1/31/18 | FES, SRIS |  | 2020/11 | 2020/11 | 2020/12
531 | Invenergy Wind Development LLC | Number 3 Wind Energy | 2016-01-11 | 105.8 | 105.8 | W | Lewis, NY | E | Taylorville - Boonville 115kV | NM-NG | 9 | 10/31/18 | FES, SRIS |  | 2020/09 | 2020/09 | 2020/12
535 | sPower Development Company, LLC | Riverhead Expansion | 2016-02-23 | 36 | 36 | S | Suffolk, NY | K | Edwards Substation 138kV | LIPA | 9 | 11/30/19 | FES, SRIS |  | 2021/07 | 2021/08 | 2021/10
540 | AVANGRID | Connect NY Edic - PV | 2016-04-28 | 1000 | 1000 | DC | Oneida-Dutchess, NY | E, G | Edic - PV 345kV | NM-NG/NYSEG/ ConEd | 6 | 7/31/18 | SIS |  | 2020/12 | N/A | N/A
541 | AVANGRID | Connect NY Edic - Ramapo | 2016-04-28 | 1000 | 1000 | DC | Oneida-Dutchess, NY | E, G | Edic - Ramapo 345kV | NM-NG/NYSEG/ O&R | 6 | 10/31/18 | SIS |  | 2020/12 | N/A | N/A
543 | National Grid | Segment B Knickerbocker-PV | 2016-05-04 | N/A | N/A | AC | Albany-Dutchess, NY | F, G | Greenbush - PV 345kV | NM-NG/NYSEG/ CHGE/ConEd | 9 | 11/30/19 | SIS |  | 2022/09 | N/A | N/A
545 | Delaware River Solar, LLC | Sky High Solar | 2016-05-10 | 20 | 20 | S | Onondaga, NY | C | Tilden -Tully Center 115kV | NM-NG | 10 | 11/30/19 | FES, SIS | 2019-10-01 | 2019/12 | 2019/11 | 2019/12
545A | NextEra Energy Transmission New York, Inc. | Empire State Line Alt | 2016-05-17 | N/A | N/A | AC | Niagara-Erie, NY | A | Dysinger - Stolle 345kV | NYPA/NYSEG | 10 | 9/30/19 | SIS, FS | 2019-06-23 | 2022/06 | N/A | N/A
546 | Atlantic Wind, LLC | Roaring Brook Wind | 2016-05-19 | 78 | 78 | W | Lewis, NY | E | Chases Lake Substation 230kV | NM-NG | 9 | 10/31/19 | FES, SRIS |  | 2020/09 | 2020/09 | 2020/12
556 | LS Power Grid New York, LLC | Segment A Double Circuit | 2016-07-06 | N/A | N/A | AC | Oneida-Albany NY | E, F | Edic - New Scotland 345kV | NM-NG | 9 | 11/30/19 | SIS |  | 2023/06 | N/A | N/A
560 | Atlantic Wind, LLC | Deer River Wind | 2016-07-08 | 100 | 100 | W | Lewis, NY | E | Black River-Lighthouse Hill 115kV | NM-NG | 9 | 7/31/19 | FES, SRIS |  | 2021/09 | 2021/10 | 2021/12
561 | Astoria Generating Company LP | Astoria Generating Unit 4 | 2016-07-18 | 385 | 385 | ST-D | New York, NY | J | Astoria West Substation 138 kV | ConEd | 7 | 4/30/19 | SRIS |  | 2020/05 | 2020/05 | 2020/05
564 | Rock District Solar, LLC | Rock District Solar | 2016-07-25 | 20 | 20 | S | Schoharie, NY | F | Sharon - Cobleskill 69kV | NM-NG | 9 | 11/30/19 | SIS |  | 2021/01 | 2021/02 | 2021/04
565 | Tayandenega Solar, LLC | Tayandenega Solar | 2016-07-25 | 20 | 20 | S | Herkimer, NY | F | St. Johnsville - Inghams 115kV | NM-NG | 9 | 11/30/19 | SIS |  | 2021/01 | 2021/02 | 2021/04
566 | New York Power Authority | MA 1 & 2 Rebuild | 2016-08-04 | N/A | N/A | AC | St. Lawrence-Lewis, NY | D, E | Moses & Adirondack 230kV | NYPA | 6 | 4/30/18 | SIS |  | 2022/12 | N/A | N/A
570 | Hecate Energy Albany 1 LLC | Albany County 1 | 2016-08-17 | 20 | 20 | S | Albany, NY | F | Long Lane - Lafarge 115kV | NM-NG | 9 | 6/30/19 | SIS |  | 2020/05 | 2020/05 | 2020/06
571 | Heritage Renewables, LLC | Heritage Wind | 2016-09-01 | 200.1 | 200.1 | W | Genesee, NY | B | Lockport - Mortimer 115kV | NM-NG | 9 | 11/30/19 | FES, SRIS |  | 2021/07 | 2021/08 | 2021/10
572 | Hecate Energy Greene 1 LLC | Greene County 1 | 2016-09-06 | 20 | 20 | S | Greene, NY | G | Coxsackie - North Catskill 69kV | CHGE | 9 | 7/31/19 | SIS |  | 2020/11 | 2020/11 | 2020/12
573 | Hecate Energy Greene 2 LLC | Greene County 2 | 2016-09-06 | 10 | 10 | S | Greene, NY | G | Coxsackie Substation 13.8kV | CHGE | 9 | 7/31/19 | SIS |  | 2020/11 | 2020/11 | 2020/12
574 | Atlantic Wind, LLC | Mad River Wind | 2016-09-16 | 450 | 450 | W | Jefferson-Oswego, NY | E | Volney - Marcy 345kV | NM-NG | 7 | 4/30/19 | FES, SRIS |  | 2021/11 | 2021/11 | 2021/12
575 | Little Pond Solar, LLC | Little Pond Solar | 2016-09-16 | 20 | 20 | S | Rockland, NY | G | Mongaup - Shoemaker 69kV | O&R | 9 | 12/31/18 | FES, SIS |  | 2020/09 | 2020/10 | 2020/12
576 | Astoria Generating Company LP | Astoria Generating Unit 4 | 2016-09-16 | 385 | 385 | ST-D | New York, NY | J | Astoria East Substation 138kV | ConEd | 7 | 4/30/18 | SRIS |  | 2020/05 | 2020/05 | 2020/05
577 | Greene County Energy Properties, LLC | Greene County Energy | 2016-09-20 | 20 | 20 | S | Greene, NY | G | New Baltimore - Coxsackie 69 kV | CHGE | 7 | 11/30/19 | SIS |  | 2020/12 |  | 2020/12
579 | Bluestone Wind, LLC | Bluestone Wind | 2016-09-21 | 124.2 | 124.2 | W | Broome, NY | E | Afton - Stilesville 115kV | NYSEG | 9 | 12/31/18 | FES, SRIS |  | 2020/09 | 2020/09 | 2020/12
580 | Genesee County Economic Devel. | WNY STAMP | 2016-09-27 | 500 | 500 | L | Genesee, NY | A | Kintigh/Niagara - Rochester 345kV | NYPA | 6 | 12/31/18 | SIS |  | 2020/06 | N/A | NA
581 | SED NY Holdings LLC | Hills Solar | 2016-10-06 | 20 | 20 | S | Herkimer, NY | E | Fairfield - Inghams 115kV | NM-NG | 9 | 9/30/19 | FES, SIS |  | 2020/06 | 2020/06 | 2020/07
584 | SunEast Dog Corners Solar LLC | Dog Corners Solar | 2016-11-02 | 20 | 20 | S | Cayuga, NY | C | Aurora Substation 34.5kV | NYSEG | 10 | 11/30/19 | SIS, FS | 2029-06-21 | 2020/06 | 2020/08 | 2020/08
586 | SED NY Holdings LLC | Watkins Rd Solar | 2016-11-08 | 20 | 20 | S | Herkimer, NY | E | Watkins Rd - Ilion 115kV | NM-NG | 10 | 11/30/19 | SIS, FS |  | 2020/04 | 2020/04 | 2020/04
589 | Duke Energy Renewables Solar, LLC | North Country Solar | 2016-12-02 | 15 | 15 | S | Lewis, NY | E | Boonville 46kV Substation | NM-NG | 9 | 9/30/19 | FES, SIS |  | 2020/09 | 2020/09 | 2020/12
590 | Duke Energy Renewables Solar, LLC | Scipio Solar | 2016-12-02 | 18 | 18 | S | Cayuga, NY | C | Scipio 34.5kV Substation | NYSEG | 10 | 9/30/19 | SIS, FS | 2019-05-22 | 2020/08 | 2020/09 | 2020/11
591 | SED NY Holdings LLC | Highview Solar | 2016-12-02 | 20 | 20 | S | Wyoming, NY | C | South Perry 34.5kV Substation | NYSEG | 9 | 11/30/19 | SIS |  | 2021/07 | 2021/09 | 2021/11
592 | Duke Energy Renewables Solar, LLC | Niagara Solar | 2016-12-02 | 20 | 20 | S | Wyoming, NY | B | Bennington 34.5kV Substation | NYSEG | 10 | 9/30/19 | SIS, FS | 2019-05-22 | 2020/08 | 2020/09 | 2020/11
594 | North Park Energy, LLC | NW Energy | 2016-12-29 | 60 | 60 | ES | Wyoming, NY | C | Wethersfield Substation 230kV | NYSEG | 9 | 8/31/19 | SRIS |  | 2021/10 | 2021/10 | 2021/12
595 | North Park Energy, LLC | SW Energy | 2016-12-29 | 100 | 100 | ES | Cattaraugus, NY | A | Five Mile Rd Substation 115kV | NM-NG | 9 | 7/31/19 | FES, SRIS |  | 2021/10 | 2021/10 | 2021/12
596 | Invenergy Wind Development LLC | Alle Catt II Wind | 2017-01-04 | 339.1 | 339.1 | W | Cattaraugus, NY | A | Stolle Rd - Five Mile Rd 345kV | NM-NG | 9 | 12/31/18 | SRIS |  | 2021/10 | 2021/10 | 2021/12
597 | Hecate Energy Greene County 3 LLC | Greene County 3 | 2017-01-10 | 20 | 20 | S | Greene, NY | G | North Catskill - Coxsackie 69kV | CHGE | 9 | 7/31/19 | SIS |  | 2020/11 | 2020/11 | 2020/12
598 | Hecate Energy Albany 2 LLC | Albany County 2 | 2017-01-10 | 20 | 20 | S | Albany, NY | F | Long Lane - Lafarge 115kV | NM-NG | 9 | 9/30/19 | SIS |  | 2020/05 | 2020/05 | 2020/06
612 | Deepwater Wind South Fork, LLC | South Fork Wind Farm | 2017-02-14 | 96 | 96 | W | Suffolk, NY | K | East Hampton 69kV | LIPA | 9 | 11/30/19 | SRIS |  | 2022/01 | 2022/08 | 2022/11
617 | North Park Energy, LLC | Watkins Glen Solar | 2017-03-27 | 50 | 50 | S | Schuyler, NY | C | Bath - Montour Falls 115kV | NYSEG | 9 | 11/30/19 | SRIS |  | 2020/09 | 2020/10 | 2020/12
618 | North Park Energy, LLC | High River Solar | 2017-03-27 | 90 | 90 | S | Schenectady, NY | F | Stoner - Rotterdam 115kV | NM-NG | 9 | 4/30/19 | SRIS |  | 2020/09 | 2020/10 | 2020/11
619 | North Park Energy, LLC | East Point Solar | 2017-03-27 | 50 | 50 | S | Schoharie, NY | F | Sharon - Marshville 69kV | NM-NG | 9 | 11/30/19 | SRIS |  | 2021/09 | 2021/10 | 2021/10
620 | North Park Energy, LLC | North Side Solar | 2017-03-27 | 180 | 180 | S | St. Lawrence, NY | D | Massena - Moses 230kV | NYPA | 9 | 8/31/19 | FES, SRIS |  | 2022/07 | 2022/09 | 2022/11
621 | Blue Stone Solar Energy, LLC | Saugerties Solar | 2017-03-27 | 20 | 20 | S | Ulster, NY | G | Saugerties - Woodstock 69kV | CHGE | 10 | 9/30/19 | SIS, FS | 2019-08-21 | 2020/10 | 2020/10 | 2020/12
624 | Franklin Solar, LLC | Franklin Solar | 2017-04-11 | 150 | 150 | S | Franklin, NY | D | Malone 115kV Substation | NM-NG | 7 | 9/30/18 | SRIS |  | 2020 | 2020 | 2020
629 | Silver Lake Solar, LLC | Silver Lake Solar | 2017-04-27 | 24.9 | 24.9 | S | Wyoming, NY | C | South Perry 34.5kV Substation | NYSEG | 7 | 4/30/19 | FES, SRIS |  | 2020 | 2020 | 2020
631 | Champlain Hudson Power Express, Inc. | NS Power Express | 2017-05-02 | 1000 | 1000 | DC | Quebec - NY, NY | J | New Scotland, Astoria Annex 345kV | NM-NG/NYPA | 7 | 1/31/19 | SRIS |  | 2021/12 | 2021/12 | 2021/12
632 | GridAmerica Holdings Inc. | Alps - Berkshire | 2017-05-04 | N/A | N/A | AC | Rensselaer, NY-NE | F | Alps - Berkshire 345kV | NM-NG | 6 | 2/28/19 | SIS |  | 2021/09 | N/A | N/A
637 | Flint Mine Solar LLC | Flint Mine Solar | 2017-06-29 | 100 | 100 | S | Greene, NY | G | LaFarge - Pleasant Valley 115kV, Feura Bush - North Catskill 115kV | NM-NG | 9 | 11/30/19 | FES, SRIS |  | 2021/10 | 2021/10 | 2021/11
638 | Pattersonville Solar Facility, LLC | Pattersonville | 2017-07-11 | 20 | 20 | S | Montgomery, NY | F | Rotterdam - Meco 115kV | NM-NG | 9 | 9/30/19 | FES, SIS |  | 2020/08 | 2020/10 | 2020/10
644 | Hecate Energy Columbia County 1 LLC | Columbia County 1 | 2017-07-26 | 60 | 60 | S | Columbia, NY | F | Craryville Substation 115kV | NYSEG | 9 | 10/31/19 | FES, SRIS |  | 2021/10 | 2021/10 | 2021/10
649 | CR Fuel Cell, LLC | Clare Rose | 2017-08-03 | 13.9 | 13.9 | FC | Suffolk, NY | K | William Floyd Substation 69kV | LIPA | 9 | 10/31/19 | FES, SIS |  | 2022/09 | 2022/10 | 2023/04
650 | BRT Fuel Cell, LLC | Brookhaven Rail Terminal | 2017-08-03 | 18.5 | 18.5 | FC | Suffolk, NY | K | W. Yaphank - Yaphank 69kV | LIPA | 9 | 11/30/19 | FES, SIS |  | 2021/04 | 2022/01 | 2022/05
654 | Renovo Energy Center LLC | Renovo Energy Center | 2017-08-11 | N/A | N/A | AC | Chemung, NY - PA | C | Homer City - Mainsburg 345kV | NYSEG | 9 | 8/31/19 | SIS |  | 2020/10 | N/A | N/A
666 | Martin Rd Solar LLC | Martin Rd Solar | 2017-09-14 | 20 | 20 | S | Machias, NY | A | Arcade - Five Mile 115kV | NM-NG | 9 | 11/30/19 | SIS |  | 2021/09 | 2021/10 | 2021/10
667 | Bakerstand Solar LLC | Bakerstand Solar | 2017-09-14 | 20 | 20 | S | Cattaraugus, NY | A | Machias - Maplehurst 34.5kV | NM-NG | 9 | 9/30/19 | SIS |  | 2021/09 | 2021/10 | 2021/10
668 | North Bergen Liberty Generating, LLC | Liberty Generating Alternative | 2017-09-15 | 1171 | 1172 | CC-NG | New York, NY | J | West 49th St Substation 345kV | ConEd | 9 | 4/30/19 | SRIS |  | 2023/04 | 2023/10 | 2024/02
669 | SED NY Holdings LLC | Clay Solar | 2017-09-21 | 20 | 20 | S | Clay, NY | C | Clay - Lockheed 115kV | NM-NG | 7 | 9/30/19 | FES, SIS |  | 2019/08 | 2019/08 | 2019/08
670 | SED NY Holdings LLC | Skyline Solar | 2017-09-21 | 20 | 20 | S | Westmoreland, NY | E | Campus Rd - Clinton 46kV | NM-NG | 7 | 9/30/19 | FES, SIS |  | 2020/12 | 2020/11 | 2020/12
671 | East Coast Power LLC | Linden Cogen Uprate | 2017-09-25 | 32 | 23 | CT-NG | Linden, NJ-NY,NY | J | Linden Cogen 345kV | ConEd | 9 | 7/31/19 | SRIS |  | 2023/03 | 2023/05 | 2023/05
678 | LI Solar Generation, LLC | Calverton Solar Energy Center | 2017-10-26 | 22.9 | 22.9 | S | Suffolk, NY | K | Edwards Substation 138kV | LIPA | 9 | 9/30/19 | SRIS |  | 2020/10 | 2020/11 | 2020/12
679 | Anbaric Development Partners, LLC | New York City Offshore Wind | 2017-11-07 | 1200 | 1200 | W | Kings, NY | J | Farragut 345kV | ConEd | 3 | 4/30/19 | None |  | 2025/07 | 2025/11 | 2025/12
680 | Anbaric Development Partners, LLC | Long Island Offshore Wind | 2017-11-07 | 700 | 700 | W | Suffolk, NY | K | Ruland Rd. 138kV | LIPA | 4 | 10/31/19 | None |  | 2025/07 | 2025/11 | 2025/12
682 | Grissom Solar, LLC | Grissom Solar | 2018-01-17 | 20 | 20 | S | Johnstown, NY | F | Ephratah - Florida 115kV | NM-NG | 7 | 11/30/19 | FES, SIS |  | 2020/05 | 2020/06 | 2020/12
683 | KCE NY 2, LLC | KCE NY 2 | 2018-01-18 | 200 | 200 | ES | Montgomery, NY | G | Coldenham Substation 115kV | CHGE | 9 | 10/31/19 | SRIS |  | 2021/05 | 2021/05 | 2021/06
684 | ITC Lake Erie Connector, LLC | Lake Erie Connector | 2018-01-18 | N/A | N/A | AC | Chautauqua, NY | A | S. Ripley 230kV | NM-NG | 10 | 9/30/19 | FS | 2019-04-22 | 2024/03 | N/A | N/A
686 | Invenergy Solar Development North America LLC | Bull Run Solar Energy Center | 2018-01-26 | 170 | 170 | S | Clinton, NY | D | Patnode - Duley 230kV | NYPA | 7 | 5/31/19 | SRIS |  | 2020/10 | 2020/10 | 2020/12
693 | Renovo Energy Center, LLC | Renovo Energy Center Uprate | 2018-02-13 | 515 | 548 | CC-NG | Chemung, NY - PA | C | Homer City - Mainesburg 345kV | NYSEG | 7 | 4/30/19 | SRIS |  | 2020/10 | 2020/11 | 2021/04
694 | Sunset Hill Solar, LLC | Sunset Hill Solar | 2018-02-16 | 20 | 20 | S | Albany, NY | G | New Baltimore - Westerlo NW 69 kV | CHGE | 5 | 9/30/19 | FES |  | 2020/08 | 2020/07 | 2020/08
695 | Deepwater Wind, LLC | South Fork Wind Farm II | 2018-02-16 | 40 | 40 | W | Suffolk, NY | K | East Hampton 69kV | LIPA | 9 | 11/30/19 | SRIS |  | 2022/01 | 2022/08 | 2022/12
696 | Eagle Creek Hydro Power, LLC | Swinging Bridge Unit 3 | 2018-03-21 | 1.2 | 1.2 | H | Orange, NY | G | Swing Bridge 69 kV | O&R | 12 | 5/31/19 | None | 2018-06-20 | 2019/07 | 2019/07 | 2019/07
697 | Helix Ravenswood, LLC | Ravenswood Energy Storage 1 | 2018-03-09 | 129 | 129 | ES | Queens, NY | J | Rainey - Farragut 345kV | ConEd | 9 | 10/31/19 | SRIS |  | 2021/12 | 2022/03 | 2022/05
698 | Helix Ravenswood, LLC | Ravenswood Energy Storage 2 | 2018-03-09 | 129 | 129 | ES | Queens, NY | J | Vernon-Rainey 138kV | ConEd | 9 | 10/31/19 | SRIS |  | 2021/12 | 2022/03 | 2022/05
699 | Helix Ravenswood, LLC | Ravenswood Gas | 2018-03-09 | 238.45 | 243.79 | CT-NG | Queens, NY | J | Rainey - Farragut 345kV | ConEd | 7 | 7/31/19 | SRIS |  | 2022/03 | 2022/01 | 2022/06
700 | Able Grid Energy Solutions, LLC | Robinson Grid | 2018-03-13 | 300 | 300 | ES | Kings, NY | J | Gowanus Substation 345kV | ConEd | 5 | 4/30/19 | FES |  | 2020/10 | 2020/11 | 2020/12
701 | KCE NY 1, LLC | KCE NY 1 | 2018-03-15 | 20 | 20 | ES | Saratoga, NY | F | Luther - Forest Substation 34.5kV | NYSEG | 14 | 3/31/19 | None | 2018-06-20 |  |  | I/S
702 | Anbaric Development Partners, LLC | Long Island Offshore AC | 2018-03-15 | 800 | 800 | W | Suffolk, NY | K | Ruland Rd. 138kV | LIPA | 3 | 4/30/19 | None |  | 2025/07 | 2025/11 | 2025/12
703 | Anbaric Development Partners, LLC | New York City Offshore AC | 2018-03-15 | 800 | 800 | W | Kings, NY | J | Farragut 345kV | ConEd | 3 | 11/30/18 | None |  | 2025/07 | 2025/11 | 2025/12
704 | Bear Ridge Solar, LLC | Bear Ridge Solar | 2018-03-20 | 100 | 100 | S | Niagara, NY | A | Mountain - Lockport 115kV | NM-NG | 9 | 10/31/19 | SRIS |  | 2022/09 | 2022/10 | 2022/12
706 | High Bridge Wind, LLC | High Bridge Wind | 2018-04-25 | 100.8 | 100.8 | W | Chenango, NY | E | E. Norwich - Jennison 115kV | NYSEG | 9 | 9/30/19 | SRIS |  | 2021/08 | 2021/09 | 2021/11
709 | Alder Creek Solar, LLC | Alder Creek Solar | 2018-05-18 | 205 | 205 | S | Oneida, NY | E | Chases Lake – Porter 230kV | NM-NG | 4 | 4/30/19 | None |  | 2020/07 | 2020/07 | 2020/12
710 | Invenergy Solar Development North America LLC | Horseshoe Solar | 2018-05-29 | 180 | 180 | S | Livingston, NY | B | Golah Substation 115kV | NM-NG | 5 | 9/30/19 | FES |  | 2021/10 | 2021/10 | 2021/12
713 | EDF Renewables Development, Inc. | Edora B Solar Energy Center | 2018-06-01 | 20 | 20 | S | Orange, NY | G | Hartley Substation 69kV | O&R | 3 | 2/28/19 | None |  | 2021/10 | 2021/10 | 2021/11
715 | EDF Renewables Development, Inc. | Suffragette Solar Energy Center | 2018-06-01 | 20 | 20 | S | Cayuga, NY | C | Hyatt Substation 34.5kV | NYSEG | 7 | 9/30/19 | FES, SIS |  | 2021/10 | 2021/10 | 2021/11
716 | EDF Renewables Development, Inc. | Moraine Solar Energy Center | 2018-06-04 | 87.4 | 93.5 | S | Allegany, NY | C | Moraine Substation 115kV | NYSEG | 5 | 9/30/19 | FES |  | 2021/09 | 2021/09 | 2021/10
717 | EDF Renewables Development, Inc. | Morris Ridge Solar Energy Center | 2018-06-04 | 177 | 177 | S | Steuben, NY | C | South Perry - Meyer 230kV | NYSEG | 5 | 9/30/19 | FES |  | 2021/09 | 2021/09 | 2021/10
718 | Cortland Energy Center, LLC | Cortland Energy Center | 2018-06-07 | 50 | 50 | S | Cortland, NY | C | Cortland - SUNY 115 kV | NM-NG | 9 | 9/30/19 | SRIS |  | 2022/08 | 2022/09 | 2022/11
719 | East Light Energy Center, LLC | East Light Energy Center | 2018-06-07 | 40 | 40 | S | Montgomery, NY | F | Meco - Rotterdam 115 kV | NM-NG | 8 | 10/31/19 | SRIS |  | 2022/08 | 2022/09 | 2022/11
720 | North Light Energy Center, LLC | North Light Energy Center | 2018-06-07 | 80 | 80 | S | Seneca, NY | C | Border City - Station 168 115 KV | NYSEG | 9 | 9/30/19 | SRIS |  | 2022/08 | 2022/09 | 2022/11
721 | Excelsior Energy Center, LLC | Excelsior Energy Center | 2018-06-07 | 280 | 280 | S | Genesee, NY | A | N. Rochester-Niagara Falls 345 kV | NYPA | 9 | 10/31/19 | SRIS |  | 2022/06 | 2022/08 | 2022/11
722 | SED NY Holdings LLC | Manchester Solar | 2018-06-07 | 20 | 20 | S | Ontario, NY | C | Hook Rd - Elbridge 115kV | NM-NG | 5 | 9/30/19 | FES |  | 2020/09 | 2020/10 | 2020/12
730 | Darby Solar, LLC | CS Easton Solar 1 | 2018-06-11 | 20 | 20 | S | Washington, NY | F | Mohican - Schaghticoke 115kV | NM-NG | 9 | 11/30/19 | FES, SIS |  | 2020/12 | 2021/01 | 2021/03
731 | Branscomb Solar, LLC | CS Easton Solar 2 | 2018-06-11 | 20 | 20 | S | Washington, NY | F | Battenkill - Eastover 115kV | NM-NG | 9 | 11/30/19 | FES, SIS |  | 2020/12 | 2021/01 | 2021/03
734 | ELP Ticonderoga Solar LLC | Ticonderoga Solar | 2018-06-12 | 20 | 20 | S | Essex, NY | F | Ticonderoga 115kV - Republic Line 2 | NM-NG | 7 | 11/30/19 | FES, SIS |  | 2021/04 |  | 2021/06
735 | ELP Stillwater Solar LLC | ELP Stillwater Solar | 2018-06-12 | 20 | 20 | S | Saratoga, NY | F | Luther Forest - Mohican 115kV | NM-NG | 9 | 9/30/19 | FES, SIS |  | 2020/07 | 2020/07 | 2020/08
737 | Equinor Wind US LLC | Empire Wind | 2018-06-12 | 816 | 816 | W | New York, NY | J | Gowanus Substation 345kV | ConEd | 9 | 9/30/19 | SRIS |  | 2023/06 | 2024/02 | 2024/12
738 | Equinor Wind US LLC | Empire Wind II | 2018-06-12 | 816 | 816 | W | Suffolk, NY | K | Ruland Rd. Substation 138kV | LIPA | 9 | 9/30/19 | SRIS |  | 2023/06 | 2024/02 | 2024/12
740 | Oakdale Battery Storage LLC | Oakdale Battery Storage | 2018-06-18 | 120 | 120 | ES | Broome, NY | C | Oakdale Substation 115kV | NYSEG | 5 | 2/28/19 | None |  | 2021/07 | 2021/05 | 2021/08
741 | Bluestone Wind, LLC | Bluestone Battery Storage | 2018-07-02 | 10 | 10 | ES | Broome, NY | E | Afton - Stilesville 115kV | NYSEG | 5 | 11/30/18 | None |  | 2020/08 | 2020/10 | 2020/11
742 | Consolidated Edison Co. of NY, Inc. | Astoria Storage on Demand | 2018-07-05 | 1.5 | 1.5 | ES | Queens, NY | J | North Queens Substation | Con Ed | 5 | 9/30/19 | None |  | 2019/12 | 2020/05 | 2020/06
744 | Granada Solar, LLC | Magruder Solar | 2018-07-18 | 20 | 20 | S | Ulster, NY | G | East Walden - Modena 115kV | CHGE | 7 | 11/30/19 | SIS |  | 2020/11 | 2020/11 | 2020/12
745 | Energy Storage Resources, LLC | Huckleberry Ridge Energy | 2018-07-25 | 100 | 100 | ES | Orange, NY | G | Shoemaker-Westtown 69kV | O&R | 5 | 1/31/19 | None |  | 2022/03 | 2022/03 | 2022/04
746 | Energy Storage Resources, LLC | Peconic River Energy Storage | 2018-07-30 | 150 | 150 | ES | Suffolk, NY | K | Brookhaven - Sills 138kV | LIPA | 9 | 10/31/19 | SRIS |  | 2022/02 | 2022/02 | 2022/06
748 | Regan Solar, LLC | Grissom Solar II | 2018-08-09 | 20 | 20 | S | Fulton, NY | F | Market Hill - Johnstown 69kV | NM-NG | 7 | 11/30/19 | SIS |  | 2020/05 | 2020/06 | 2020/12
751 | Calpine Mid Atlantic Development, LLC | Stony Brook Storage | 2018-08-14 | 40 | 40 | ES | Suffolk, NY | K | 8MR Substation 69kV | LIPA | 3 | 9/30/19 | None |  | 2021/01 | 2021/03 | 2021/06
754 | Anbaric Development Partners, LLC | New York Ocean Grid - Canal | 2018-08-20 | 800 | 800 | W | Suffolk, NY | K | Canal Substation 138kV | LIPA | 3 | 4/30/19 | None |  | 2025/07 | 2025/11 | 2025/12
755 | Anbaric Development Partners, LLC | New York Ocean Grid - Shoreham | 2018-08-20 | 800 | 800 | W | Suffolk, NY | K | Shoreham Substation 138kV | LIPA | 3 | 4/30/19 | None |  | 2025/07 | 2025/11 | 2025/12
756 | Rising Solar, LLC | Rising Solar II | 2018-08-24 | 20 | 20 | S | Orange, NY | G | Sugarloaf Substation - 69kV | O&R | 5 | 1/31/19 | None |  | 2019/10 | 2019/10 | 2019/10
758 | Sithe/Independence Power Partners, LP | Sithe Independence | 2018-09-06 | 9 | 27 | CC-NG | Oswego, NY | C | Sithe 345kV Substation | NM-NG | 7 | 5/31/19 | SRIS |  | I/S | I/S | I/S
759 | KCE NY 6, LLC | KCE NY 6 | 2018-09-06 | 20 | 20 | ES | Erie, NY | A | Gardenville - Bethlehem Steel Wind 115kV | NM-NG | 7 | 11/30/19 | SIS |  | 2019/11 | 2019/12 | 2019/12
760 | New York Power Authority | Moses-Adirondack | 2018-09-07 | N/A | N/A | AC | St. Lawrence-Lewis, NY | D, E | Moses - Adirondack 230kV | NYPA | 5 | 4/30/19 | None |  | 2020/12 | N/A | N/A
762 | Invenergy Storage Development LLC | Riverhead Storage Energy Center | 2018-09-17 | 75 | 75 | ES | Suffolk, NY | K | Riverhead 69kV | LIPA | 3 | 9/30/19 | None |  | 2021/10 | 2021/10 | 2021/12
763 | Invenergy Solar Development LLC | Cicero Storage | 2018-09-25 | 10 | 10 | ES | Onondaga, NY | C | Pine Grove Substation 13.2kV | NM-NG | 7 | 11/30/19 | SIS |  | 2020/10 | 2020/10 | 2020/12
764 | Bay State Wind LLC | NY Wind Canal | 2018-09-28 | 440 | 440 | W | Suffolk, NY | K | Canal Substation 138kV | LIPA | 5 | 9/30/19 | None |  | 2023/01 | 2023/05 | 2024/01
765 | Bay State Wind LLC | NY Wind Brookhaven | 2018-09-28 | 880 | 880 | W | Suffolk, NY | K | Brookhaven 138kV | LIPA | 5 | 6/30/19 | None |  | 2023/01 | 2023/05 | 2024/01
766 | Bay State Wind LLC | NY Wind Holbrook | 2018-09-28 | 880 | 880 | W | Suffolk, NY | K | Holbrook 138kV | LIPA | 3 | 6/30/19 | None |  | 2023/01 | 2023/05 | 2024/01
767 | Bay State Wind LLC | NY Wind Gowanus | 2018-09-28 | 1200 | 1200 | W | New York, NY | J | Gowanus Substation 345kV | ConEd | 3 | 6/30/19 | None |  | 2023/01 | 2024/04 | 2024/05
768 | Janis Solar, LLC | Janis Solar | 2018-10-01 | 20 | 20 | S | Broome, NY | C | Willet 34.5kV | NYSEG | 9 | 10/31/19 | SIS |  | 2020/12 | 2021/01 | 2021/03
769 | New York Power Authority | North County Energy Storage | 2018-10-05 | 20 | 20 | ES | Franklin, NY | D | Willis Substation 115kV | NYPA | 5 | 6/30/19 | None |  | 2020/04 | 2020/04 | 2020/04
770 | KCE NY8 LLC | KCE NY 8a | 2018-10-09 | 20 | 20 | ES | Greene, NY | G | South Cairo Substation 13.2kV | CHGE | 5 | 9/30/19 | None |  | 2020/05 |  | 2020/05
774 | EDF Renewables Development, Inc. | Tracy Solar Energy Centre | 2018-10-18 | 119 | 119 | S | Jefferson, NY | E | Thousand Island - Lyme 115kV | NM-NG | 5 | 4/30/19 | None |  | 2022/12 | 2022/12 | 2023/01
775 | Puckett Solar, LLC | Puckett Solar | 2018-10-22 | 20 | 20 | S | Chenango, NY | E | Chenango Forks Substation 34.5kV | NYSEG | 7 | 11/30/19 | SIS |  | 2020/03 | 2020/03 | 2020/04
776 | Greenidge Generation LLC | Greenidge Load | 2018-10-22 | N/A | N/A | L | Yates, NY | C | Greenidge 115kV | NYSEG | 5 | 9/30/19 | None |  | 2019 | N/A | N/A
777 | Community Energy Solar, LLC | White Creek Solar | 2018-11-01 | 135 | 135 | S | Livingston, NY | B | Sta 82 - Sta 128 115kV | RG&E | 5 | 4/30/19 | None |  | 2021/12 | 2021/11 | 2021/12
778 | Astoria Generating Company L.P. | Gowanus Gas Turbine Facility Repowering | 2018-11-08 | 549 | 588 | CT-NG | Kings, NY | J | Gowanus Substation 345kV | ConEd | 9 | 10/31/19 | SRIS |  | 2024/03 | 2023/12 | 2024/03
779 | Hecate Energy Gedney Hill LLC | Gedney Hill Solar | 2018-11-09 | 20 | 20 | S | Albany, NY | G | New Baltimore - Westerlo 69kV | CHGE | 3 | 4/30/19 | None |  | 2020/03 | 2020/03 | 2020/04
780 | Hecate Energy Johnstown LLC | Johnstown Solar | 2018-11-09 | 20 | 20 | S | Schenectady, NY | F | Stoner - Rotterdam 115kV | NM-NG | 5 | 6/30/19 | None |  | 2020/03 | 2020/03 | 2020/04
781 | New York Power Authority | Marcy South SSR Detection | 2018-12-03 | N/A | N/A | AC | Delaware, NY | E | Fraser - Annex 345 kV Substation | NYPA | 12 | 9/30/19 | SIS | N/A | 2019/12 | N/A | N/A
782 | Invenergy Solar Development North America LLC | Hornell Storage | 2018-12-04 | 20 | 20 | ES | Steuben, NY | C | Bennett 34.5kV | NYSEG | 5 | 4/30/19 | None |  | 2020/10 | 2020/10 | 2020/12
783 | ConnectGen Chautauqua County LLC | South Ripley Solar | 2018-12-07 | 270 | 270 | S | Chautauqua, NY | A | South Ripley Substation 230kV | NM-NG | 4 | 9/30/19 | FES |  | 2022/09 | 2022/09 | 2022/11
784 | High Bridge Wind, LLC | High Bridge Battery | 2018-12-11 | 5 | 5 | ES | Chenango, NY | E | E. Norwich - Jennison 115kV | NYSEG | 5 | 9/30/19 | None |  | 2021/09 | 2021/10 | 2021/12
785 | ConnectGen Erie-Wyoming LLC | Erie-Wyoming County Solar | 2018-12-12 | 175 | 175 | S | Wyoming, NY | C | Stolle Road - High Sheldon 230kV | NYSEG | 3 | 5/31/19 | None |  | 2022/09 | 2022/09 | 2022/11
786 | Ravenswood Development, LLC | Ravenswood Energy Storage | 2018-12-20 | 187 | 187 | ES | Queens, NY | J | Rainey - Farragut 345kV | ConEd | 5 | 9/30/19 | None |  | 2021/01 | 2020/10 | 2021/03
787 | Levy Grid, LLC | Levy Grid, LLC | 2018-12-20 | 150 | 150 | ES | Erie, NY | A | Gardenville Subsation 115kV | NM-NG | 5 | 9/30/19 | None |  | 2021/04 | 2021/04 | 2021/05
788 | Atlantic Shores Offshore Wind Project 3, LLC (EDF) | Atlantic Shores Offshore Wind 7 | 2019-01-14 | 880 | 880 | W | Nassau, NY | K | East Garden City 345kV Substation | LIPA | 2 | 2/28/19 | None |  | 2025/06 | 2025/08 | 2025/12
789 | Atlantic Shores Offshore Wind Project 3, LLC (EDF) | Atlantic Shores Offshore Wind 8 | 2019-01-14 | 880 | 880 | W | Kings, NY | J | Gowanus Substation 345kV | ConEd | 5 | 9/30/19 | None |  | 2025/06 | 2025/08 | 2025/12
790 | Atlantic Shores Offshore Wind Project 2, LLC (EDF) | Atlantic Shores Offshore Wind 9 | 2019-01-14 | 880 | 880 | W | Richmond, NY | J | Fresh Kills 345kV | ConEd | 5 | 9/30/19 | None |  | 2025/06 | 2025/08 | 2025/12
791 | Danskammer Energy LLC | Danskammer Energy Center | 2019-01-14 | 84.4 | 88.9 | CC-NG | Orange, NY | G | Danskammer 115kV Substation | CHGE | 9 | 10/31/19 | SRIS |  | 2023/10 | 2023/08 | 2023/10
792 | Anbaric Development Partners, LLC | Long Island Offshore Wind Connection | 2019-01-29 | 300 | 300 | W | Suffolk, NY | K | Ruland Road 138kV Substation | LIPA | 4 | 4/30/19 | None |  | 2025/07 | 2025/11 | 2025/12
800 | EDF Renewables Development, Inc. | Rich Road Solar Energy Center | 2019-02-20 | 240 | 240 | S | St. Lawrence, NY | E | Moses - Adirondack 230kV | NYPA | 3 | 9/30/19 | None |  | 2024/11 | 2024/12 | 2024/12
801 | Prattsburgh Wind, LLC | Prattsburgh Wind Farm | 2019-02-21 | 147 | 147 | W | Steuben, NY | C | Stoney Ridge - Canadaigua 230kV | NYSEG | 2 | 9/30/19 | None |  | 2022/10 | 2022/11 | 2022/12
802 | EDF Renewables Development, Inc. | Bunker Solar Energy Center | 2019-03-06 | 125 | 125 | ES | Franklin, NY | D | Willis - Lyon Mt 115kV | NYSEG | 3 | 9/30/19 | None |  | 2023/11 | 2023/12 | 2023/12
803 | Yonkers Grid, LLC | Yonkers Grid, LLC | 2019-03-11 | 200 | 200 | ES | Westchester, NY | I | Dunwoodie - 138kV Bus | ConEd | 3 | 9/30/19 | None |  | 2022/04 | 2022/04 | 2022/05
804 | KCE NY 10, LLC | KCE NY 10 | 2019-03-22 | 20 | 20 | ES | Erie, NY | A | Erie Substation 34.5kV | NYSEG | 3 | 9/30/19 | None |  | 2020/08 | 2020/08 | 2020/09
805 | Oxbow Hill Solar, LLC | Oxbow Hill Solar | 2019-03-22 | 140 | 140 | S | Madison, NY | C | Fenner - Whitman 115kV | NM-NG | 2 | 4/30/19 | None |  | 2022/08 | 2022/09 | 2022/09
806 | SED NY Holdings LLC | Limestone Solar | 2019-03-25 | 20 | 20 | S | Fulton, NY | F | Stoner - Rotterdam 115kV | NM-NG | 3 | 9/30/19 | None |  | 2021/10 | 2021/11 | 2021/11
807 | SED NY Holdings LLC | Hilltop Solar | 2019-03-28 | 20 | 20 | S | Rensselaer, NY | F | Eastover - Schaghticoke 115kV | NM-NG | 5 | 9/30/19 | None |  | 2021/10 | 2021/11 | 2021/11
808 | Barrett Ridge Energy, LLC | Barrett Ridge Energy | 2019-04-01 | 107 | 107 | ES | Orange, NY | G | Sugar Loaf - Vernon 115kV | CHGE | 2 | 5/31/19 | None |  | 2022/03 | 2022/01 | 2022/03
809 | Seven Creek Energy, LLC | Seven Creek Energy | 2019-04-01 | 240 | 240 | ES | Chautauqua, NY | A | South Ripley Substation 230kV | NM-NG | 2 | 5/31/19 | None |  | 2022/03 | 2022/01 | 2022/03
811 | Hecate Energy Cider Solar LLC | Cider Solar | 2019-04-03 | 800 | 800 | S | Genesee, NY | A | Kintigh - Niagara 345kV | NYSEG | 5 | 9/30/19 | None |  | 2023/08 | 2023/10 | 2023/12
812 | Diamond Generating Corporation | CWW 200 Wind | 2019-04-03 | 200 | 200 | W | Erie, NY | A | Harbor Front 115kV | NM-NG | 2 | 9/30/19 | None |  | 2023/12 | 2023/12 | 2023/12
813 | Diamond Generating Corporation | CWW 300 Wind | 2019-04-03 | 300 | 300 | W | Erie, NY | A | Harbor Front 115kV | NM-NG | 2 | 9/30/19 | None |  | 2023/12 | 2023/12 | 2023/12
814 | Diamond Generating Corporation | CWW 300 Wind Dun | 2019-04-03 | 300 | 300 | W | Chautauqua, NY | A | Dunkirk Substation 230kV | NM-NG | 2 | 9/30/19 | None |  | 2023/12 | 2023/12 | 2023/12
815 | Bayonne Energy Center | Bayonne Energy Center III | 2019-04-05 | 49.8 | 49.8 | ES | Kings, NY | J | Gowanus Substation 345kV | ConEd | 2 | 5/31/19 | None |  | 2021/01 | 2021/01 | 2021/02
816 | LIPA | NNC TTC Increase | 2018-04-05 | N/A | N/A | AC | Suffolk, NY | K | Northport Substation 138kV | LIPA | 4 | 9/30/19 | None |  | 2023 | N/A | N/A
822 | Astoria Generating Company LP | Narrows Generating Barge Battery Energy Storage | 2019-04-15 | 58 | 58 | ES | Kings, NY | J | Narrows Barge Feeder 23162 | Con Ed | 5 | 9/30/19 | None |  | 2022/07 | 2022/09 | 2022/12
823 | Wildwood Energy Storage, LLC | Wildwood Energy Storage | 2019-04-15 | 116.72 | 116.72 | ES | Suffolk, NY | K | Wildwood Substation 138kV | LIPA | 2 | 6/30/19 | None |  | 2022/09 | 2022/10 | 2022/12
824 | Wildwood Energy Storage, LLC | Wildwood Shoreham Energy Storage | 2019-04-15 | 76.86 | 76.86 | ES | Suffolk, NY | K | Shoreham Substation 69kV | LIPA | 2 | 6/30/19 | None |  | 2022/10 | 2022/11 | 2022/12
825 | Setauket Energy Storage, LLC | Setauket Energy Storage | 2019-04-15 | 76.86 | 76.86 | ES | Suffolk, NY | K | Port Jefferson - Terryville 69kV | LIPA | 2 | 6/30/19 | None |  | 2021/10 | 2021/11 | 2021/12
826 | NRG Astoria Storage LLC | Astoria Energy Storage 1 | 2019-04-18 | 66 | 66 | ES | Queens, NY | J | North Queens 27kV Bus | ConEd | 4 | 6/30/19 | None |  | 2021/05 | 2021/08 | 2021/10
827 | NRG Arthur Kill Storage LLC | Arthur Kill Energy Storage 1 | 2019-04-22 | 15 | 15 | ES | Richmond, NY | J | Fresh Kills 13.8kV | ConEd | 4 | 9/30/19 | None |  | 2022/05 | 2022/08 | 2022/10
828 | SED NY Holdings LLC | Valley Solar | 2019-04-24 | 20 | 20 | S | Tioga, NY | C | Owego 34.5kV Substation | NYSEG | 4 | 6/30/19 | None |  | 2021/10 | 2021/11 | 2021/11
830 | NRG Astoria Storage LLC | Astoria Energy Storage 2 | 2019-04-26 | 100 | 100 | ES | Queens, NY | J | Astoria West 138kV Substation | ConEd | 4 | 7/31/19 | None |  | 2024/01 | 2024/04 | 2024/06
831 | Dimension NY 1 LLC | NY-19-0002 Sheredy | 2019-04-29 | 10.3 | 10.3 | ES | Broome, NY | C | Northside Substation 34.5kV | NYSEG | 4 | 9/30/19 | None |  | 2020/05 | 2020/05 | 2020/05
832 | Granada Solar, LLC (Conti) | CS Hawthorn Solar | 2019-05-06 | 20 | 20 | S | Rensselaer, NY | F | North Troy - Hoosick 115kV | NM-NG | 2 | 6/30/19 | None |  | 2020/10 | 2020/11 | 2020/12
833 | Granada Solar, LLC (Conti) | CS Dolan Solar | 2019-05-06 | 20 | 20 | S | Washington, NY | F | Battenkill - Mohican 115kV | NM-NG | 4 | 6/30/19 | None |  | 2020/10 | 2020/11 | 2020/12
834 | Astoria Generating Company, LP | Parking Lot Battery Energy Storage | 2019-05-07 | 86.5 | 86.5 | ES | Queens, NY | J | Astoria West 138kV Substation | ConEd | 4 | 6/30/19 | None |  | 2022/09 | 2022/10 | 2022/11
835 | Astoria Generating Company, LP | Dock Battery Energy Storage | 2019-05-07 | 57.3 | 57.3 | ES | Queens, NY | J | Astoria West 138kV Substation | ConEd | 4 | 6/30/19 | None |  | 2022/09 | 2022/10 | 2022/11
836 | Astoria Generating Company, LP | Dock Battery Energy Storage 2 | 2019-05-07 | 57.3 | 57.3 | ES | Queens, NY | J | Astoria East 138kV Substation | ConEd | 4 | 6/30/19 | None |  | 2022/09 | 2022/10 | 2022/11
837 | Astoria Generating Company, LP | Parking Lot Battery Energy Storage 2 | 2019-05-07 | 86.5 | 86.5 | ES | Queens, NY | J | Astoria East 138kV Substation | ConEd | 4 | 6/30/19 | None |  | 2022/09 | 2022/10 | 2022/11
840 | Hecate Grid Swiftsure LLC | Swiftsure Energy Storage | 2019-05-09 | 650 | 650 | ES | Richmond, NY | J | Fresh Kills 345kV Substation | ConEd | 4 | 7/31/19 | None |  | 2022/05 | 2022/06 | 2022/06
841 | TJA Clean Energy, LLC | Sharon Springs Interconnection | 2019-05-10 | 20 | 20 | S | Schoharie, NY | F | Sharon - Cobleskill 69kV Substation | NM-NG | 2 | 9/30/19 | None |  | 2021/06 | 2022/05 | 2022/06
842 | Mitsubishi Hitachi Power Systems Americas, Inc. | Comet Solar | 2019-05-17 | 20 | 20 | S | Monroe, NY | B | Mortimer - Golah 115kV Circuit | NM-NG | 4 | 9/30/19 | None |  | 2021/04 | 2021/04 | 2021/05
843 | Boralex US Development, LLC | NY37 Solar | 2019-05-17 | 20 | 20 | S | Jefferson, NY | E | Coffeen - West Adams 115kV Substation | NM-NG | 4 | 9/30/19 | None |  | 2022/10 | 2022/11 | 2022/12
844 | Boralex US Development, LLC | NY37 Energy Storage | 2019-05-17 | 4 | 4 | ES | Jefferson, NY | E | Coffeen - West Adams 115kV Substation | NM-NG | 4 | 9/30/19 | None |  | 2022/10 | 2022/11 | 2022/12
845 | sPower Development Company, LLC | Bloom Energy Storage Center | 2019-05-20 | 120 | 120 | ES | Kings, NY | J | Farragut 345kV Substation | ConEd | 2 | 9/30/19 | None |  | 2023/10 | 2023/10 | 2023/12
846 | sPower Development Company, LLC | Rescue Energy Storage Center | 2019-05-20 | 300 | 300 | ES | New York, NY | J | East 13th Street 138kV Substation | ConEd | 2 | 7/31/19 | None |  | 2023/10 | 2023/10 | 2023/12
847 | sPower Development Company, LLC | Chelsea Energy Storage Center | 2019-05-20 | 300 | 300 | ES | New York, NY | J | West 49th St Substation 345kV | ConEd | 2 | 7/31/19 | None |  | 2023/10 | 2023/10 | 2023/12
848 | SED NY Holdings LLC | Fairway Solar | 2019-05-20 | 20 | 20 | S | St. Lawrence, NY | E | McIntyre - Colton 115kV Substation | NM-NG | 4 | 6/30/19 | None |  | 2021/10 | 2021/11 | 2021/11
849 | Somerset Operating Company, LLC | Somerset Load | 2019-05-21 | 250 | 250 | L | Niagara, NY | A | Kintigh 345kV | NYSEG | 4 | 6/30/19 | None |  | 2020/08 | N/A | N/A
850 | Cayuga Operating Company, LLC | Cayuga Load | 2019-05-21 | 50 | 50 | L | Cayuga, NY | C | Milliken Substation | NYSEG | 4 | 6/30/19 | None |  | 2020/10 | N/A | N/A
851 | ConnectGen Madison County LLC | Madison County Solar | 2019-05-23 | 20 | 20 | S | Madison, NY | E | Bouckville Substation | NYSEG | 2 | 9/30/19 | None |  | 2021/03 | 2021/03 | 2021/05
852 | Niagara Dolomite Solar, LLC | Niagara Dolomite Solar | 2019-05-24 | 360 | 360 | S | Niagara, NY | A | Robinson Rd - Stolle Rd 230kV | NYSEG | 2 | 9/30/19 | None |  | 2022/09 | 2022/09 | 2022/10
853 | Boralex US Development, LLC | NY16 Solar | 2019-05-24 | 19.9 | 19.9 | S | Washington, NY | F | Mohican - Schaghticoke 115kV | NM-NG | 4 | 9/30/19 | None |  | 2023/09 | 2023/10 | 2023/11
855 | Boralex US Development, LLC | NY13 Solar | 2019-05-24 | 19.9 | 19.9 | S | Washington, NY | F | Mohican - Schaghticoke 115kV | NM-NG | 4 | 9/30/19 | None |  | 2023/09 | 2023/10 | 2023/11
857 | EDF Renewables Development, Inc. | Columbia Solar Energy Center | 2019-05-28 | 350 | 350 | S | Herkimer, NY | E | Edic - Marcy 345kV | NYPA | 2 | 7/31/19 | None |  | 2024/09 | 2024/10 | 2024/10
858 | EDF Renewables Development, Inc. | Genesee Road Solar Energy Center | 2019-05-28 | 350 | 350 | S | Erie, NY | A | Stolle Rd - Five Mile Rd 345kV | NYSEG | 2 | 9/30/19 | None |  | 2024/09 | 2024/10 | 2024/10
859 | EDF Renewables Development, Inc. | Ridge View Solar Energy Center | 2019-05-28 | 350 | 350 | S | Niagara, NY | A | Somerset - Dysinger 345kV | NYSEG | 4 | 10/31/19 | None |  | 2024/09 | 2024/10 | 2024/10
860 | EDF Renewables Development, Inc. | Rosalen Solar Energy Center | 2019-05-28 | 350 | 350 | S | Wayne, NY | E | Edic - Fraser 345kV | NYPA | 2 | 7/31/19 | None |  | 2024/09 | 2024/10 | 2024/10
861 | Mitsubishi Hitachi Power Systems Americas, Inc. | Tonawanda Solar | 2019-05-29 | 20 | 20 | S | Niagara, NY | B | Lockport - Batavia 115kV | NM-NG | 2 | 7/31/19 | None |  | 2021/04 | 2021/04 | 2021/05
862 | Mitsubishi Hitachi Power Systems Americas, Inc. | Farwell Solar | 2019-05-29 | 20 | 20 | S | Orleans, NY | B | Lockport - Mortimer 115kV | NM-NG | 2 | 7/31/19 | None |  | 2021/04 | 2021/04 | 2021/05
863 | Mitsubishi Hitachi Power Systems Americas, Inc. | Cloverdale Solar | 2019-05-29 | 20 | 20 | S | Livingston, NY | C | Highbanks - South Perry 115kV | NYSEG | 2 | 7/31/19 | None |  | 2021/04 | 2021/04 | 2021/05
864 | Boralex US Development, LLC | NY38 Solar | 2019-05-29 | 120 | 120 | S | Jefferson, NY | E | Coffeen - East Watertown 115kV | NM-NG | 4 | 8/31/19 | None |  | 2024/01 | 2024/02 | 2024/03
865 | SED NY Holdings LLC | Flat Hill Solar | 2019-05-31 | 20 | 20 | S | Herkimer, NY | E | Inghams - Little Falls Hydro Plant | NM-NG | 4 | 8/31/19 | None |  | 2021/10 | 2021/11 | 2021/11
866 | RES Americas Developments, Inc. | North Country Wind | 2019-06-03 | 298.2 | 298.2 | W | Franklin, NY | D | Willis Substation 230kV | NYPA | 2 | 7/31/19 | None |  | 2023/09 | 2023/09 | 2023/12
867 | Somerset Solar Development LLC | Somerset Solar Development LLC | 2019-06-03 | 20 | 20 | S | Niagara, NY | A | Kintigh 345kV | NYSEG | 2 | 9/30/19 | None |  | 2021/06 | 2021/04 | 2021/06
868 | Cayuga Solar LLC | Cayuga Solar LLC | 2019-06-03 | 19.9 | 19.9 | S | Cayuga, NY | C | Milliken Substation | NYSEG | 2 | 7/31/19 | None |  | 2021/06 | 2021/04 | 2021/06
869 | SED NY Holdings LLC | Tabletop Solar | 2019-06-04 | 80 | 80 | S | Montgomery, NY | F | Clinton Substation 115kV | NM-NG | 2 | 6/30/19 | None |  | 2022/09 | 2022/09 | 2022/10
871 | Invenergy Solar Project Development LLC | Verona Solar Energy Center I | 2019-06-05 | 250 | 250 | S | Oneida, NY | C | Clay - Edic 345kV | NYPA | 2 | 7/31/19 | None |  | 2023/10 | 2023/10 | 2023/12
872 | Invenergy Solar Project Development LLC | Taproot Solar Energy Energy | 2019-06-05 | 300 | 300 | S | Montgomery, NY | E | Porter - Rotterdam 230kV | NM-NG | 2 | 7/31/19 | None |  | 2023/10 | 2023/10 | 2023/10
873 | Invenergy Solar Project Development LLC | Verona Solar Energy Center II | 2019-06-05 | 250 | 250 | S | Oneida, NY | C | Clay - Edic 345kV | NYPA | 2 | 7/31/19 | None |  | 2023/10 | 2023/10 | 2023/10
875 | SL Portland, LLC | SL Portland Solar | 2019-06-06 | 19.9 | 19.9 | S | Chautauqua, NY | A | Dunkirk – Falconer 115 kV | NM-NG | 2 | 9/30/19 | None |  | 2020/12 | 2020/12 | 2020/12
876 | SL Selkirk, LLC | SL Selkirk Solar | 2019-06-06 | 19.9 | 19.9 | S | Albany, NY | F | New Scotland - Alps 345kV | NM-NG | 2 | 9/30/19 | None |  | 2020/12 | 2020/12 | 2020/12
877 | SL York, LLC | SL York Solar | 2019-06-06 | 19.9 | 19.9 | S | Livingston, NY | B | Golah - S. Perry 115 kV | NM-NG | 2 | 9/30/19 | None |  | 2020/12 | 2020/12 | 2020/12
878 | Energy Storage Resources, LLC | Pirates Island | 2019-06-10 | 100 | 100 | ES | Erie, NY | A | Huntley - Elm 115kV | NM-NG | 2 | 7/31/19 | None |  | 2022/01 | 2022/02 | 2022/04
879 | Empire Community Solar LLC | Holley Road Solar | 2019-06-10 | 19.9 | 19.9 | S | Orleans, NY | B | Lockport - Mortimer 115kV | NM-NG | 2 | 7/31/19 | None |  | 2021/09 | 2021/11 | 2021/11
880 | Brookside Solar, LLC | Brookside Solar | 2019-06-10 | 100 | 100 | S | Franklin, NY | D | Chateaugay Substation | NYSEG | 2 | 9/30/19 | None |  | 2023/07 | 2023/09 | 2023/11
881 | New Bremen Solar, LLC | New Bremen Solar | 2019-06-10 | 100 | 100 | S | Lewis, NY | E | Bremen - Lowville 115kV | NM-NG | 2 | 7/31/19 | None |  | 2023/07 | 2023/09 | 2023/11
882 | Riverside Solar, LLC | Riverside Solar | 2019-06-10 | 100 | 100 | S | Jefferson, NY | E | Lyme Substation 115kV | NM-NG | 2 | 7/31/19 | None |  | 2023/07 | 2023/09 | 2023/11
883 | North Park Energy, LLC | Garnet Energy Center | 2019-06-11 | 200 | 200 | S | Cayuga, NY | B | Pannell - Clay 345kV | NYPA | 4 | 8/31/19 | None |  | 2023/08 | 2023/09 | 2023/11
885 | SED NY Holdings LLC | Grassy Knoll Solar | 2019-06-12 | 20 | 20 | S | Herkimer, NY | E | Watkins Rd - Inghams 115kV | NM-NG | 2 | 9/30/19 | None |  | 2021/10 | 2021/11 | 2021/11
887 | TDI-USA Holdings Corp. | CH Uprate | 2019-06-12 | 250 | 250 | DC | Quebec - NY, NY | J | Astoria Annex Substation 345kV | NYPA | 4 | 10/31/19 | None |  | 2026/10 | 2026/10 | 2026/12
888 | Sky Solar Inc. | Hornell Center 16 | 2019-06-13 | 17.6 | 17.6 | S | Allegany, NY | C | Moraine Substation 115kV | NYSEG | 2 | 9/30/19 | None |  | 2021/09 | 2021/09 | 2021/12
892 | FourGen LLC | Holtsville Fuel Cell | 2019-07-15 | 20 | 20 | FC | Suffolk, NY | K | Holtsville 69kV | LIPA | 2 | 9/30/19 | None |  | 2020/06 | 2020/06 | 2020/06
893 | FourGen LLC | Setauket Fuel Cell | 2019-07-15 | 20 | 20 | FC | Suffolk, NY | K | Terryville Substation 8kV | LIPA | 2 | 9/30/19 | None |  | 2020/06 | 2020/06 | 2020/06
894 | Montgomery Energy Storage 1, LLC | Montgomery Energy Storage | 2019-07-15 | 20 | 20 | ES | Orange, NY | G | Walden - Montgomery 69kV | O&R | 2 | 9/30/19 | None |  | 2020/01 | 2020/01 | 2020/01
895 | Dimension NY 1 LLC | Road Property | 2019-07-15 | 19.9 | 19.9 | ES | Suffolk, NY | K | Central Islip 138kV | LIPA | 2 | 9/30/19 | None |  | 2020/07 | 2020/07 | 2020/07
898 | Mitsubishi Hitachi Power Systems Americas, Inc. | Oak Orchard Solar | 2019-08-01 | 5 | 5 | S | Orleans, NY | A | Shelby Substation 13.2kV | NM-NG | 2 | 10/31/19 | None |  | 2021/04 | 2021/04 | 2021/05
899 | Sithe/Independence Power Partners, LP | Scriba-Volney Series Reactor | 2019-08-02 | N/A | N/A | AC | Oswego, NY | C | Volney - Scriba 345kV | NYSEG | 2 | 9/30/19 | None |  | 2021/05 | N/A | N/A
900 | Granada Solar, LLC | Fowler Solar | 2019-08-09 | 20 | 20 | S | Madison, NY | C | Fenner - Whitman 115kV | NM-NG | 2 | 10/31/19 | None |  | 2021/09 | 2021/10 | 2021/11
901 | TJA Clean Energy, LLC | Lacona Solar | 2019-08-16 | 20 | 20 | AC | Oswego, NY | C | Lighthouse Hill - Black River 115kV | NM-NG | 2 | 10/31/19 | None |  | 2021/10 | 2022/09 | 2022/10
902 | sPower Development Company, LLC | Yacht Club Energy Storage | 2019-08-16 | 300 | 300 | ES | New York, NY | J | Gowanus 345kV | ConEd | 2 | 9/30/19 | None |  | 2022/10 | 2022/11 | 2022/12
903 | sPower Development Company, LLC | Goethals Energy Storage | 2019-08-16 | 300 | 300 | ES | New York, NY | J | Goethals 345kV | ConEd | 2 | 9/30/19 | None |  | 2022/10 | 2022/11 | 2022/12
906 | NRG Arthur Kill Storage LLC | Arthur Kill Energy Storage 2 | 2019-08-28 | 20 | 20 | AC | Richmond, NY | J | Fresh Kills 138kV Substation | ConEd | 2 | 10/31/19 | None |  | 2022/05 | 2022/08 | 2022/10
907 | 174 Power Global | Harlem River Yard | 2019-09-04 | 100 | 100 | ES | Bronx, NY | J | Hell Gate 138kV Substation | ConEd | 2 | 10/31/19 | None |  | 2022/10 | 2022/10 | 2022/12
908 | NRG Astoria Storage LLC | Astoria Energy Storage 5 | 2019-09-12 | 20 | 20 | ES | Queens, NY | J | North Queens Substation | ConEd | 2 | 10/31/19 | None |  | 2022/05 | 2022/08 | 2022/10
909 | PetaWatt Holdings, Inc. | Massena Load | 2019-09-18 | 100 | 100 | L | St. Lawrence | E | TBD | NYPA | 4 | 10/31/19 | None |  | 2020 | N/A | N/A
911 | Dimension NY 1 LLC | NY-19-0027 - Greenport Group LLC | 2019-10-01 | 19.9 | 19.9 | ES | Suffolk, NY | K | Peconic - Southold 69kV | LIPA | 1 | 11/30/19 | None |  | 2019/10 | 2019/10 | 2019/10
914 | sPower Development Company, LLC | Loomis Creek Solar | 2019-10-07 | 150 | 150 | S | Columbia, NY | F | Churchtown 115kV Substation | NYSEG | 1 | 11/30/19 | None |  | 2022/10 | 2022/11 | 2022/12
917 | sPower Development Company, LLC | Loomis Creek ES | 2019-10-09 | 150 | 150 | S | Columbia, NY | F | Churchtown 115kV Substation | NYSEG | 1 | 11/30/19 | None |  | 2022/10 | 2022/11 | 2022/12
919 | sPower Development Company, LLC | White Spring ES | 2019-10-10 | 200 | 200 | S | Ontario, NY | B | Haley Road | NYSEG | 1 | 11/30/19 | None |  | 2022/10 | 2022/11 | 2022/12
920 | sPower Development Company, LLC | White Spring Solar | 2019-10-10 | 200 | 200 | S | Ontario, NY | B | Haley Road | NYSEG | 1 | 11/30/19 | None |  | 2022/10 | 2022/11 | 2022/12
921 | sPower Development Company, LLC | Line Creek ES | 2019-10-10 | 80 | 80 | ES | Schoharie, NY | F | Schoharie 69kV | NM-NG | 1 | 11/30/19 | None |  | 2022/10 | 2022/11 | 2022/12
922 | sPower Development Company, LLC | Line Creek Solar | 2019-10-10 | 80 | 80 | S | Schoharie, NY | F | Schoharie 69kV | NM-NG | 1 | 11/30/19 | None |  | 2022/10 | 2022/11 | 2022/12
923 | sPower Development Company, LLC | Far Rockaway Energy Storage Center | 2019-10-11 | 150 | 150 | ES | Queens, NY | K | Far Rockaway Substation 69kV | LIPA | 1 | 11/30/19 | None |  | 2022/10 | 2022/11 | 2022/12
924 | RICAL LLC | CBB | 2019-10-15 | 115 | 115 | ES | Dutchess, NY | G | Shenandoah Substation | CHGE | 1 | 11/30/19 | None |  | 2021/10 | 2022/01 | 2022/05
926 | Enel Energy Storage Holdings, LLC | Enel NYPA Astoria | 2019-10-19 | 100 | 100 | ES | Queens, NY | K | Astoria 138kV Substation | ConEd | 1 | 11/30/19 | None |  | 2021/01 | 2021/06 | 2022/01
927 | JERA Americas Inc. | Brunswick Energy Storage | 2019-10-21 | 100 | 100 | ES | Union, NJ | J | Goethals 345kV | ConEd | 1 | 11/30/19 | None |  | 2022/08 | 2022/08 | 2022/09
928 | JERA Americas Inc. | Willow Bay Energy Storage | 2019-10-21 | 40 | 40 | ES | Richmond, NY | J | Fox Hills 33kV Substation | ConEd | 1 | 11/30/19 | None |  | 2022/08 | 2022/08 | 2022/09
934 | Saturn Energy Storage LLC | Astoria BESS | 2019-10-31 | 70 | 70 | ES | Queens, NY | J | Astoria West 138kV Substation | ConEd | 1 | 11/30/19 | None |  | 2022/06 | 2022/06 | 2022/11
935 | SED NY Holdings LLC | SunEast Oriskany Solar LLC | 2019-11-01 | 20 | 20 | S | Oneida, NY | E | Oriskany Falls Substation | NYSEG | 1 | 11/30/19 | None |  | 2021/09 | 2021/10 | 2021/12
938 | KCE NY 12, LLC | KCE NY 12 | 2019-11-04 | 100 | 100 | ES | Suffolk, NY | K | Moriches 69kV Substation | LIPA | 1 | 11/30/19 | None |  | 2021/11 | 2021/11 | 2021/12
942 | KCE NY 21, LLC | KCE NY 21 | 2019-11-08 | 60 | 60 | ES | Suffolk, NY | K | Deposit - Indian Head 69kV | LIPA | 1 | 11/30/19 | None |  | 2021/11 | 2021/11 | 2021/12
| Number of new projects during November |  | 16
| Number of new projects year to date |  | 162
| Number withdrawn during November |  | 3
| Number withdrawn year to date |  | 69
NOTES: ● The column labeled 'SP' refers to the maximum summer megawatt electrical output. The column labeled 'WP' refers to the maximum winter megawatt electrical output.
● Type / Fuel. Key: ST=Steam Turbine, CT=Combustion Turbine, CC=Combined Cycle, CS= Steam Turbine & Combustion Turbine, H=Hydro, PS=Pumped Storage, W=Wind, NU=Nuclear, NG=Natural Gas, M=Methane, SW=Solid Waste, S=Solar, Wo=Wood, F=Flywheel ES=Energy Storage, O=Oil, C=Coal, D=Dual Fuel, AC=AC Transmission, DC=DC Transmission, L=Load, FC=Fuel Cell
● The column labeled 'Z' refers to the zone
● The column labeled 'S' refers to the status of the project in the NYISO's LFIP. Key: 1=Scoping Meeting Pending, 2=FES Pending, 3=FES in Progress, 4=SRIS/SIS Pending, 5=SRIS/SIS in Progress, 6=SRIS/SIS Approved, 7=FS Pending, 8=Rejected Cost Allocation/Next FS Pending, 9=FS in Progress, 10=Accepted Cost Allocation/IA in Progress, 11=IA Completed, 12=Under Construction, 13=In Service for Test, 14=In Service Commercial, 0=Withdrawn
● Availability of Studies Key: None=Not Available, FES=Feasibility Study Available, SRIS=System Reliability Impact Study Available, FS=Facilities Study and/or ATRA Available
● FS Complete/SGIA Tender refers to the Attachment X milestone used to apply the 4-year COD limitation.
● Proposed in-service dates and Commercial Operation Dates (COD) are shown in format Year/Qualifier, where Qualifier may indicate the month, season, or quarter.
DPS/State - SIR Interconnection Queue (for Projects not subject to the NYISO process):
http://www3.dps.ny.gov/W/PSCWeb.nsf/All/286D2C179E9A5A8385257FBF003F1F7E?OpenDocument

## Withdrawn
Queue Pos. | Owner/Developer | Project Name | Date of IR | SP (MW) | WP (MW) | Type/ Fuel | Location County/State | Z | Interconnection Point | Utility | S | Last Update | Availability of Studies | Proposed In-Service
[14 empty] | Original | Current
5 | Sithe Energies | Torne Valley Station | 1999-01-28 | 860 |  |  |  |  | Ramapo | CONED | 0 |  |  | Withdrawn
6 | Sunset Energy Fleet LLC | Sunset Energy Fleet | 1999-02-17 | 520 |  |  |  |  | Gowanus | CONED | 0 |  |  | Withdrawn
7 | American National Power | Ramapo Energy | 1999-02-23 | 1100 |  |  |  |  | Ramapo | CONED | 0 |  |  | Withdrawn
8 | Columbia Electric Corp. | Grassy Point | 1999-02-23 | 1100 |  |  |  |  | West Haverstraw | CONED | 0 |  |  | Withdrawn
9 | Millennium Power Gen Co. LLC | Millennium 1 | 1999-02-23 | 160 |  |  |  |  | Hell Gate/Bruckner | CONED | 0 |  |  | Withdrawn
10 | Millennium Power Gen Co. LLC | Millennium 2 | 1999-02-23 | 320 |  |  |  |  | Hell Gate/Bruckner | CONED | 0 |  |  | Withdrawn
13 | East Coast Power, LLC | Linden 7 | 1999-03-25 | 100 |  | ST-NG | Richmond, NY-NJ | J | Goethals 345kV | CONED | 0 | 7/10/08 |  | Withdrawn
15 | AEP Resources Service Corp. | CT-LI AC Tie-line | 1999-04-13 | 600 |  |  |  |  | Shoreham, Long Island | LIPA | 0 |  |  | Withdrawn
16 | Oak Point Property, LLC | Oak Point Yard | 1999-04-15 | 500 |  | CC-NG | Bronx, NY | J | Hell Gate/Bruckner 138kV | CONED | 0 | 7/10/08 |  | Withdrawn
19 | NYC Energy LLC | NYC Energy LLC | 1999-05-07 | 79.9 |  | CT-NG | Kings, NY | J | Kent Ave 138kV | CONED | 0 | 9/30/10 |  | Withdrawn
20 | KeySpan Energy, Inc. | Spagnoli Road CC Unit | 1999-05-17 | 250 |  | CC-NG | Suffolk, NY | K | Spagnoli Road 138kV | LIPA | 0 | 3/1/12 |  | Withdrawn
21 | KeySpan Energy, Inc. | Shoreham Gen Station | 1999-05-17 | 250 |  |  |  |  | Shoreham | LIPA | 0 |  |  | Withdrawn
22 | Calpine Eastern Corporation | Wawayanda Energy Center | 1999-06-10 | 500 |  | CC-NG | Orange, NY |  | Coop Corn-Rock Tav Lines 345kV | NYPA | 0 | 6/26/06 |  | Withdrawn
24 | Reliant Energy | Astoria Repowering-Phase 1 | 1999-07-13 | 367 |  | CC-NG | Queens, NY |  | Astoria 138kV | CONED | 0 | 8/9/06 |  | Withdrawn
23 | Calpine Eastern Corporation | Sullivan County Power Project | 1999-06-25 | 1080 |  | CC-NG | Sullivan, NY |  | Coop Corn-Rock Tav Lines 345kV | NYPA | 0 | 3/06 |  | Withdrawn
26 | Twin Tier Power, LLC | Twin Tier Power | 1999-08-20 | 520 |  |  |  |  | Watercure-Oakdale 31 Line | NYSEG | 0 |  |  | Withdrawn
27 | ENRON | Far Rockaway Barge | 1999-09-08 | 60 |  |  |  |  | Far Rockaway | LIPA | 0 |  |  | Withdrawn
28 | KeySpan Energy, Inc. | Spagnoli Road GT Unit | 1999-09-08 | 79.9 |  |  |  |  | Spagnoli Road | LIPA | 0 |  |  | Withdrawn
29 | Mirant | Bowline Point Unit 3 | 1999-10-13 | 750 |  | CC-NG | Rockland, NY |  | W. Haverstraw 345kV | CONED | 0 | 7/10/06 |  | Withdrawn
30 | Sithe Energies | Heritage Station | 1999-10-29 | 800 |  |  |  |  | Independence (Oswego) | NM-NG | 0 |  |  | Withdrawn
32 | American National Power | Brookhaven Energy | 1999-11-22 | 580 |  | CC-NG | Suffolk, NY |  | Holbrook-Brookhaven 138kV | LIPA | 0 |  |  | Withdrawn
33 | Glenville Energy Park, LLC | Glenville Energy Park | 1999-11-30 | 540 |  | CC-NG | Schenectady, NY | F | Rotterdam 230kV | NM-NG | 0 | 7/10/08 |  | Withdrawn
34 | York Research Corp. | North First Street | 2000-01-11 | 500 |  |  |  |  | Con Ed System | CONED | 0 |  |  | Withdrawn
35 | Gotham Power Zerega, LLC | Gotham Power - Bronx I | 2000-01-12 | 79.9 |  | CT-NG | Bronx, NY | J | Parkchester/Tremont 138kV | CONED | 0 | 7/10/08 |  | Withdrawn
36 | Boundless Energy, LLC | Project Neptune DC NB-NYC | 2000-01-21 | 1200 |  | DC | Kings, NY | J | Farragut 345kV | CONED | 0 | 7/10/08 |  | Withdrawn
37 | Caithness Energy, LLC | Kitchen | 2000-01-28 | 750 |  |  |  |  | Riverh'd-Brookh'n-Holb'k | LIPA | 0 |  |  | Withdrawn
38 | KeySpan Energy, Inc. | Far Rochaway Gen Ext. | 2000-02-01 | 79 |  |  |  |  | Far Rockaway | LIPA | 0 |  |  | Withdrawn
39 | KeySpan Energy, Inc. | E. F. Barrett Gen Ext | 2000-02-01 | 79 |  |  |  |  | Barrett | LIPA | 0 |  |  | Withdrawn
40 | KeySpan Energy, Inc. | Riverhead Gen Station | 2000-02-01 | 79 |  |  |  |  | Riverhead | LIPA | 0 |  |  | Withdrawn
41 | KeySpan Energy, Inc. | Southampton Gen Ext. | 2000-02-01 | 79 |  |  |  |  | Southampton | LIPA | 0 |  |  | Withdrawn
42 | PP&L Global, Inc. | Holbrook Energy | 2000-02-01 | 300 |  |  |  |  | Holbrook | LIPA | 0 |  |  | Withdrawn
43 | PP&L Global, Inc. | PPL Kings Park | 2000-02-01 | 300 |  |  |  |  | Pilgrim | LIPA | 0 |  |  | Withdrawn
44 | PP&L Global, Inc. | Ruland Energy | 2000-02-01 | 300 |  |  |  |  | Ruland Road | LIPA | 0 |  |  | Withdrawn
45 | PP&L Global, Inc. | Freeport Energy | 2000-02-01 | 100 |  |  |  |  | Freeport | LIPA | 0 |  |  | Withdrawn
46 | PP&L Global, Inc. | Brookhaven Energy | 2000-02-03 | 300 |  |  |  |  | Brookhaven | LIPA | 0 |  |  | Withdrawn
47 | GenPower, LLC | GenPower DC Tie-line | 2000-02-09 | 800 |  |  |  |  | West 49th Sreet | CONED | 0 |  |  | Withdrawn
48 | PP&L Global, Inc. | PPL Kings Park Ext. | 2000-02-10 | 300 |  |  |  |  | Pilgrim | LIPA | 0 |  |  | Withdrawn
49 | PP&L Global, Inc. | Brookhaven Energy Ext. | 2000-02-10 | 300 |  |  |  |  | Brookhaven | LIPA | 0 |  |  | Withdrawn
50 | AES Long Island, LLC | AES Smithtown Gen | 2000-02-10 | 510 |  |  |  |  | LIPA System | LIPA | 0 |  |  | Withdrawn
51 | KeySpan Energy, Inc. | Wading River Gen Ext. | 2000-02-15 | 150 |  |  |  |  | Wading River | LIPA | 0 |  |  | Withdrawn
52 | NIMO/Black River Power | Fort Drum Gen Exp. | 2000-03-06 | 50 |  |  |  |  | Fort Drum | NM-NG | 0 |  |  | Withdrawn
53 | TransEnergie US, Ltd | CT-Ruland, LI DC Tie | 2000-03-07 | 300 |  |  |  |  | Ruland Road | LIPA | 0 |  |  | Withdrawn
54 | TransEnergie US, Ltd | CT-Pilgrim, LI DC Tie | 2000-03-07 | 300 |  |  |  |  | Pilgrim | LIPA | 0 |  |  | Withdrawn
56 | 1st Rochdale Coop Group | Gotham Power/Brooklyn | 2000-03-17 | 79 |  |  |  |  | Kent Ave | CONED | 0 |  |  | Withdrawn
58 | Mirant | Lovett #3 Repowering | 2000-03-23 | 180 |  |  |  |  | Lovett | CONED | 0 |  |  | Withdrawn
59 | Mirant | Hillburn Unit #2 | 2000-03-23 | 79.9 |  |  |  |  | Hillburn | CONED | 0 |  |  | Withdrawn
60 | Mirant | Hillburn #2 Conversion | 2000-03-23 | 40 |  |  |  |  | Hillburn | CONED | 0 |  |  | Withdrawn
61 | GTM Energy, LLC | Greenpoint Energy Park | 2000-04-19 | 500 |  |  |  |  | Rainey-Farragut Lines | CONED | 0 |  |  | Withdrawn
62 | Project Orange Associates, LP | Project Orange | 2000-05-08 | 420 |  |  |  |  | Temple St. | NM-NG | 0 |  |  | Withdrawn
63 | Lewis Staley Associates, Inc. | LSA Station A | 2000-05-11 | 650 |  |  |  |  | Homer City-Stolle Rd Line | NYSEG | 0 |  |  | Withdrawn
64 | Lewis Staley Associates, Inc. | LSA Station B | 2000-05-12 | 600 |  |  |  |  | Dunkirk-Gardenville Line | NM-NG | 0 |  |  | Withdrawn
65 | Fortistar-Lockport Merchant | Lockport II Gen Station | 2000-05-15 | 79.9 |  | CT-NG | Niagara, NY | A | Harrison Station 115kV | NYSEG | 0 | 7/10/08 |  | Withdrawn
67 | Titan Development, LLC | Wallkill Energy | 2000-06-21 | 1080 |  |  |  |  | Coop Corn-Rock Tav Lines | NYPA | 0 |  |  | Withdrawn
68 | PP&L Global, Inc. | Ruland Energy Ext. | 2000-06-23 | 300 |  |  |  |  | Ruland Road | LIPA | 0 |  |  | Withdrawn
70 | Reliant Energy | Astoria Repowering-Phase 2 | 2000-08-18 | 173 |  | CT-NG | Queens, NY |  | Astoria 138kV | CONED | 0 | 8/9/06 |  | Withdrawn
71 | Mill Creek Wind Plant, LLC | Mill Creek Wind Plant | 2000-09-08 | 50 |  |  |  |  | Lowville | NM-NG | 0 |  |  | Withdrawn
72 | Fortistar Power Marketing, LLC | Island Gen. Station | 2000-09-08 | 79.9 |  |  |  |  | Fresh Kills | CONED | 0 |  |  | Withdrawn
73 | Fortistar Power Marketing, LLC | Island Gen. Station #2 | 2000-09-08 | 500 |  |  |  |  | Fresh Kills | CONED | 0 |  |  | Withdrawn
74 | FPL Energy, LLC | Oceanside Energy Center | 2000-10-10 | 330 |  |  |  |  | Barrett | LIPA | 0 |  |  | Withdrawn
75 | 1st Rochdale Coop Group | Gotham Power - Bronx II | 2000-10-17 | 79 |  |  |  |  | Hell Gate/Bruckner | CONED | 0 |  |  | Withdrawn
76 | Calpine Eastern Corporation | Waterford | 2000-10-30 | 530 |  | CT-NG | Saratoga, NY |  | NM-NG 230 or 115 kV | NM-NG | 0 | 3/06 |  | Withdrawn
77 | Titan Development, LLC | Dover Energy | 2000-11-17 | 1000 |  |  |  |  | Pl. Valley-Long Mt. Tie-Line | CONED | 0 |  |  | Withdrawn
78 | KeySpan Ravenswood | Ravenswood Repower Ph I | 2000-12-04 | 440 |  |  |  |  | Vernon | CONED | 0 |  |  | Withdrawn
86 | NRG/ Berrians I GT Power, LLC | Berrians GT Replacement | 2001-01-15 | 79.9 |  |  |  |  | Astoria | CONED | 0 |  |  | Withdrawn
87 | Titan Development, LLC | Buchanan Energy | 2001-02-26 | 500 |  |  |  |  | Buchanan | CONED | 0 |  |  | Withdrawn
88 | Titan Development, LLC | Halfmoon Energy | 2001-02-26 | 500 |  |  |  |  | Rotterdam-Bear Swamp line | NM-NG | 0 |  |  | Withdrawn
89A | Atlantic Energy, LLC | Neptune DC PJM-NYC | 2001-03-15 | 600 |  |  |  |  | W49th St | CONED | 0 |  |  | Withdrawn
89B | Atlantic Energy, LLC | Neptune DC PJM-NYC | 2001-03-15 | 600 |  |  |  |  | W49th St | CONED | 0 |  |  | Withdrawn
90 | Fortistar, LLC | Fortistar VP | 2001-03-20 | 79.9 |  | CT-NG | Richmond, NY | J | Fresh Kills 138kV | CONED | 0 | 5/27/09 |  | Withdrawn
91 | Fortistar, LLC | Fortistar VAN | 2001-03-20 | 79.9 |  | CT-NG | Richmond, NY | J | Goethals/Fresh Kills 138kV | CONED | 0 | 5/27/09 |  | Withdrawn
92 | Amerada Hess Corp. | Redhook Energy | 2001-05-01 | 79.9 |  |  |  |  | ConEd 138 kV (tbd) | CONED | 0 |  |  | Withdrawn
93 | In-City I, LLC | Cross Hudson Project | 2001-05-11 | 550 |  | CC-NG | New York, NY-NJ |  | W49th Street 345kV | CONED | 0 | 8/23/07 |  | Withdrawn
96 | Calpine Eastern Corporation | CPN 3rd Turbine, Inc. (JFK) | 2001-05-29 | 45 |  | CT-NG | Queens, NY | J | Jamaica 138kV | CONED | 0 | 7/10/08 |  | Withdrawn
97 | NYSEG Solutions | South Glens Falls Expansion | 2001-06-15 | 40 |  |  |  |  | Mohican-Butler#18 line | NM-NG | 0 |  |  | Withdrawn
98 | TransEnergie US Ltd. | PJM-New York City HVDC | 2001-06-22 | 990 |  |  |  |  | W49th St and/or Farragut | CONED | 0 |  |  | Withdrawn
100 | Titan Development, LLC | Blooming Grove Power | 2001-07-02 | 500 |  |  |  |  | Rock Tavern-Ramapo line | CONED | 0 |  |  | Withdrawn
101 | Northeast Utilities Service Co. | NU CT-LI HVDC Cable | 2001-07-13 | 660 |  |  |  |  | Shore Road | LIPA | 0 |  |  | Withdrawn
102 | Entergy Power Gen. Corp. | Indian Point Energy Center | 2001-07-23 | 400 |  | CT-NG | Westchester, NY |  | Buchanan 345kV | CONED | 0 |  |  | Withdrawn
103 | Pegasus Trans. Co., Ltd. | Niagara Reinforcement Inter. | 2001-08-15 | 1200 |  | DC | Oneida - NY, NY |  | Marcy,Edic,Porter - W49th St. | NYPA/NM/CE | 0 |  |  | Withdrawn
104 | PG&E/Liberty Gen. Co., LLC | Jupiter PJM-NYC Cable | 2001-08-24 | 1200 |  |  |  |  | W49th St or Farragut | CONED | 0 |  |  | Withdrawn
105 | Calpine Eastern Corporation | Titan Smith Street | 2001-10-05 | 79.9 |  | CT-NG | Kings, NY |  | Gowanus 138 or 345 kV | CONED | 0 | 3/06 |  | Withdrawn
106 | TransGas Energy, LLC | TransGas Energy | 2001-10-05 | 1100 |  | CC-NG | Kings, NY | J | E13St, Rainey, or Farragut-345kV | CONED | 0 | 3/1/12 |  | Withdrawn
108 | Sempra Generation | SE Long Island | 2001-11-29 | 575 |  | CT-NG | Suffolk, NY |  | Shoreham-Holbrook lines 138kV | LIPA | 0 |  |  | Withdrawn
109 | Calpine Eastern Corporation | Maspeth | 2002-01-25 | 79.9 |  |  |  |  | Vernon-Glendale line | CONED | 0 |  |  | Withdrawn
110 | PG&E/Liberty Gen. Co., LLC | Liberty Generation | 2002-02-04 | 400 |  | CT-NG | Richmond, NY-NJ |  | Goethals 345kV | CONED | 0 | 3/06 |  | Withdrawn
111 | River Hill Power Co., LLC | River Hill Project | 2002-02-05 | 290 |  | CT-NG | Chemung, NY-PA | C | Homer City-Watercure 345kV | NYSEG | 0 | 7/10/08 |  | Withdrawn
112 | TransEnergie US Ltd. | PJM-Rainey HVDC | 2002-04-09 | 660 |  | DC | Queens, NY-NJ |  | Rainey 345kV | CONED | 0 | 5/31/06 |  | Withdrawn
113 | Windfarm Prattsburgh, LLC | Prattsburgh Wind Park | 2002-04-22 | 55.5 |  | W | Yates, NY | C | Eelpot Rd-Flat St. 115kV | NYSEG | 0 | 2010-03-31 |  | Withdrawn
114 | Global Winds Harvest, Inc. | Cherry Valley Wind Park | 2002-04-22 | 40.5 |  |  |  |  | East Springfield | NYSEG | 0 |  |  | Withdrawn
116 | PG&E/Liberty Gen. Co., LLC | Liberty Gen Co, LLC | 2002-04-29 | 600 |  |  |  |  | Goethals | CONED | 0 |  |  | Withdrawn
117 | Chautauqua Windpower, LLC | Chautauqua Windpower | 2002-05-14 | 50 |  | W | Chautauqua, NY |  | Dunkirk-S. Ripley 230kV | NM-NG | 0 | 3/27/07 |  | Withdrawn
118 | Global Winds Harvest, Inc. | Prattsburgh Wind Park II | 2002-05-15 | 75 |  |  |  |  | Eelpot Rd-Flat St. line | NYSEG | 0 |  |  | Withdrawn
119 | ECOGEN, LLC | Prattsburgh Wind Farm | 2002-05-20 | 78.2 |  | W | Yates, NY | C | Eelpot Rd-Flat St. 115kV | NYSEG | 0 | 10/31/13 |  | Withdrawn
120 | ECOGEN, LLC | Springwater Wind Farm | 2002-05-20 | 79.5 |  |  |  |  | Eelpot Rd | NYSEG | 0 |  |  | Withdrawn
124 | Bay Energy, LLC | Bay Energy Project | 2002-07-01 | 79.9 |  | CT-NG | Kings, NY |  | Gowanus 138kV | CONED | 0 |  |  | Withdrawn
126 | TransEnergie US Ltd. | PJM-Newbridge Rd HVDC | 2002-09-10 | 350 |  | DC | Nassau, NY-NJ |  | Newbridge Road 138kV | LIPA | 0 | 5/31/06 |  | Withdrawn
127 | KeySpan Energy for LIPA | Northport-Norwalk Upgrade | 2002-09-19 | 150 |  |  |  |  | Northport | LIPA | 0 |  |  | Withdrawn
127A | Airtricity Munnsville Wind Farm, LLC | Munnsville | 2002-10-09 | 6 |  | W | Madison, NY | E | 46kV line | NYSEG | 0 | 1/31/14 |  | Withdrawn
130 | Electrotek Concepts, Inc. | Grace Corona Generation | 2003-01-14 | 79.9 |  |  |  |  | Corona | CONED | 0 |  |  | Withdrawn
137 | Conjunction, LLC | Empire Connection DC | 2003-06-16 | 2000 |  |  |  |  | N. Scotland/Leeds, ConEd | NM/CONED | 0 |  |  | Withdrawn
140 | National Grid | Leeds-PV Reconductoring | 2003-08-26 | N/A |  | AC | Greene-Dutchess, NY | G | Leeds/Athens-Pl. Valley 345kV | NM-NG | 0 | 7/10/08 |  | Withdrawn
141A | Atlantic Renewable Energy Corp. | Bishop | 2003-09-09 | 23.1 |  | W | Livingston, NY |  | Springwater 34.5kV line | NYSEG | 0 |  |  | Withdrawn
142 | EC&R Northeast, LLC | Steuben Wind | 2003-10-30 | 50 |  | W | Steuben, NY | C | Bennett-Palmiter 115kV line | NYSEG | 0 | 6/4/10 |  | Withdrawn
147 | NY Windpower, LLC | West Hill Windfarm | 2004-04-16 | 31.5 |  | W | Madison, NY | C | Oneida-Fenner 115kV | NM-NG | 0 | 8/31/12 |  | Withdrawn
148 | Trigen Nassau Gen Co., LLC | Trigen-Nassau | 2004-05-18 | 79.9 |  |  |  |  | Uniondale Substation | LIPA | 0 |  |  | Withdrawn
150 | Reunion Power, LLC | Cherry Valley Wind Power | 2004-06-17 | 70 |  | W | Otsego, NY | E | Marshville - Sharon 69kV | NM-NG | 0 | 2010-03-31 |  | Withdrawn
151 | Con Edison | West Side Switching Station | 2004-06-30 | N/A |  | AC | New York, NY | J | West 49th St & Farragut 345kV | CONED | 0 | 3/31/11 |  | Withdrawn
152 | Moresville Energy LLC | Moresville Energy Center | 2004-07-23 | 99 | 99 | W | Delaware, NY | E | Axtell Road-Grand Gorge 115kV | NYSEG | 0 | 6/30/11 |  | Withdrawn
154 | KeySpan Energy for LIPA | Holtsville-Brentwood-Pilgrim | 2004-08-19 | N/A | N/A | AC | Suffolk, NY | K | Holtsville & Pilgrim 138kV | LIPA | 0 | 2/28/17 |  | Withdrawn
155 | Invenergy NY, LLC | Canisteo Hills Windfarm | 2004-09-17 | 148.5 |  | W | Steuben, NY | C | Bennett-Bath 115kV | NYSEG | 0 | 3/1/12 |  | Withdrawn
157 | BP Alternative Energy NA, Inc. | Orion Energy NY I | 2004-10-12 | 100 | 100 | W | Herkimer, NY | E | Watkins Rd.-Inghams 115kV | NM-NG | 0 | 3/1/12 |  | Withdrawn
158 | Orion Energy, LLC | Orion Energy NY II | 2004-10-12 | 100 | 100 | W | Montgomery, NY |  | Inghams-Meco 115kV | NM-NG | 0 | 1/06 |  | Withdrawn
159 | Orion Energy, LLC | Orion Energy NY III | 2004-10-12 | 150 |  |  | Clinton, NY |  | TBD | NYSEG | 0 |  |  | Withdrawn
160 | Jericho Rise Wind Farm, LLC | Jericho Rise Wind Farm | 2004-10-12 | 79.2 | 79.2 | W | Franklin, NY | D | Willis 115 kV | NYPA | 0 | 4/30/11 |  | Withdrawn
162 | AES Somerset, LLC | Niagara Windpower | 2004-12-15 | 70 |  | W | Niagara, NY |  | Somerset Switch Yard | NYSEG | 0 | 8/05 |  | Withdrawn
163 | Clipper Windpower Dev. Co. Inc. | Paragon I Wind Generation | 2005-01-13 | 100 | 100 | W | Steuben, NY | C | Bath-Montour Falls 115kV | NYSEG | 0 | 8/19/08 |  | Withdrawn
164 | FPL Energy | Long Island Offshore Wind | 2005-01-28 | 140 | 140 | W | Suffolk, NY |  | Sterling Substation | LIPA | 0 | 2/26/08 |  | Withdrawn
165 | UPC Wind Management, LLC | Genesee Wind Farm | 2005-01-31 | 500 | 500 | W | Genesee, NY |  | Batavia Substation 115kV | NM-NG | 0 | 11/05 |  | Withdrawn
166 | Cape Vincent Wind Power, LLC | St. Lawrence Wind Farm | 2005-02-08 | 75.9 | 75.9 | W | Jefferson, NY | E | Rockledge Substation 115kV | NM-NG | 0 | 2/28/14 |  | Withdrawn
167 | AES New York Wind, LLC | St. Lawrence Wind Farm II | 2005-02-08 | 80 |  | W | Jefferson, NY |  | Lyme Substation | NM-NG | 0 | 6/05 |  | Withdrawn
168 | Dairy Hills Wind Farm, LLC | Dairy Hills Wind Farm | 2005-02-08 | 120 | 120 | W | Wyoming, NY | C | Stolle Rd.-Meyer 230kV | NYSEG | 0 | 3/1/12 |  | Withdrawn
169 | Alabama Ledge Wind Farm, LLC | Alabama Ledge Wind Farm | 2005-02-08 | 79.8 | 79.8 | W | Genesee, NY | B | Oakfield-Lockport 115kV | NM-NG | 0 | 6/1/12 |  | Withdrawn
170 | Machias Wind Farm, LLC | Machias Wind Farm | 2005-02-08 | 90 | 90 | W | Cattaraugus, NY |  | Homer Hill-Gardenville 115kV | NM-NG | 0 | 10/11/06 |  | Withdrawn
176 | Noble Environmental Power, LLC | Wethersfield Windfield 115kV | 2005-02-14 | 129 | 129 | W | Wyoming, NY |  | Arcade Substation 115kV | Village of Arcade | 0 | 7/18/06 |  | Withdrawn
178 | Noble Allegany Windpark, LLC | Allegany Windpark | 2005-02-14 | 100.5 | 100.5 | W | Cattaraugus, NY | A | Freedom Substation 115kV | Village of Arcade | 0 | 6/28/10 |  | Withdrawn
179 | Noble Environmental Power, LLC | Cherry Hill Windpark | 2005-02-14 | 102 | 102 | W | Franklin, NY | E | Nicholville-Malone 115kV | NYSEG | 0 | 2/5/09 |  | Withdrawn
180 | Invenergy Wind, LLC | Buffalo Rd. Wind Farm | 2005-02-23 | 165 | 165 | W | Wyoming, NY |  | Stolle Rd.-Meyer 230kV | NYSEG | 0 | 1/9/07 |  | Withdrawn
180A | Green Power | Cody Rd | 2005-03-17 | 10 | 10 | W | Madison, NY | C | Fenner - Cortland 115kV | NM-NG | 0 | 2/28/17 |  | Withdrawn
181 | Everpower Global | Cold Spring Wind | 2005-03-21 | 69.3 |  | W | Cattaraugus, NY |  | Falconer-Homer Hill 115kV | NM-NG | 0 | 9/05 |  | Withdrawn
183 | Invenergy Wind, LLC | Buffalo Rd. Wind Farm II | 2005-03-28 | 165 | 165 | W | Wyoming, NY |  | Batavia 115kV | NYSEG/NM-NG | 0 | 12/05 |  | Withdrawn
184 | Invenergy Wind, LLC | Ripley Hill | 2005-03-28 | 75.9 |  | W | Onondaga, NY |  | Town of Spafford | NYSEG/NM-NG | 0 | 8/05 |  | Withdrawn
186 | Jordanville Wind, LLC | Jordanville Wind | 2005-04-01 | 80 | 80 | W | Herkimer, NY | E | Porter-Rotterdam 230kV | NM-NG | 0 | 9/30/11 |  | Withdrawn
187 | North Slope Wind Farm, LLC | North Slope Wind | 2005-04-05 | 109.5 | 109.5 | W | Clinton, NY | D | Willis-Plattsburgh 230kV | NYPA | 0 | 2/5/09 |  | Withdrawn
188 | NY Windpower, LLC | Orangeville Wind | 2005-04-05 | 96 |  | W | Wyoming, NY |  | 115kV | NYSEG | 0 | 8/05 |  | Withdrawn
189 | Atlantic Wind, LLC | Horse Creek Wind | 2005-04-08 | 126 | 126 | W | Jefferson, NY | E | Coffeen St-Thousand Island 115kV | NM-NG | 0 | 4/30/14 |  | Withdrawn
190 | PPM Energy, Inc. | Mixer Road Wind | 2005-04-08 | 66 | 66 | W | Jefferson, NY |  | West Adams 115kV | NM-NG | 0 | 10/11/06 |  | Withdrawn
191 | New York Regional | New York Regional | 2005-05-13 | 1200 | 1200 | DC | Oneida-Orange NY | E, G | Edic - Rock Tavern | NM-NG/CH | 0 | 4/8/09 |  | Withdrawn
192 | Orion Energy, LLC | Orion Livingston | 2005-05-17 | 75 | 75 | W | Livingston, NY |  | Stolle Rd.-Meyer 230kV | NYSEG | 0 | 1/06 |  | Withdrawn
193 | Orion Energy, LLC | Orion Wyoming | 2005-05-17 | 60 | 60 | W | Wyoming, NY |  | South Perry 115kV | NYSEG | 0 | 1/9/07 |  | Withdrawn
194 | Calpine Energy Services | Bayonne | 2005-05-26 | 300 | 300 | ST-NG | New York, NY |  | World Trade Center 138kV | CONED | 0 | 2/06 |  | Withdrawn
195 | Brookfield Power US | Harbor Cable Project II | 2005-06-14 | 200 | 200 | DC | Richmond, NY - NJ | J | Goethal 345kV | CONED | 0 | 7/31/09 |  | Withdrawn
196 | Roaring Brook Windpower, LLC | Roaring Brook | 2005-07-01 | 79.9 | 79.8 | W | Lewis, NY |  | Adirondak-Porter 230kV | NM-NG | 0 | 7/10/06 |  | Withdrawn
197 | PPM Roaring Brook, LLC / PPM | Roaring Brook Wind | 2005-07-01 | 78 | 78 | W | Lewis, NY | E | Boonville-Lowville 115kV | NM-NG | 0 | 4/30/16 |  | Withdrawn
198 | Arkwright Summit Wind Farm, LLC | Arkwright Summit Wind Farm | 2005-07-21 | 79.8 | 79.8 | W | Chautauqua, NY | A | Dunkirk-Falconer 115kV | NM-NG | 0 | 9/30/13 |  | Withdrawn
200 | Cavallo Power | Linden Power I | 2005-08-16 | 845 | 915 | CC | NY, NY - Union, NJ |  | Goethal Substation | CONED | 0 | 2/06 |  | Withdrawn
201 | NRG Energy | Berrians GT | 2005-08-17 | 200 | 200 | CC-NG | Queens, NY | J | Astoria West Substation 138kV | CONED | 0 | 7/31/15 |  | Withdrawn
202 | Liberty Generating Co. | 130 MW Uprate | 2005-08-25 | 130 | 130 | CT-NG | NY, NY - Union, NJ |  | Goethal 345kV | CONED | 0 | 3/06 |  | Withdrawn
203 | GenWy Wind, LLC | GenWy Wind Farm | 2005-10-21 | 478.5 | 478.5 | W | Genesee, NY | A | Stolle Rd - Homer City 345kV | NYSEG | 0 | 2010-03-31 |  | Withdrawn
204 | Clipper Windpower Dev. Co. Inc. | Paragon II Wind Generation | 2005-10-27 | 150 | 150 | W | Steuben, NY | C | Avoca - Hillside 230kV | NYSEG | 0 | 8/19/08 |  | Withdrawn
204A | Duer's Patent Project, LLC | Beekmantown Windfarm | 2005-10-31 | 19.5 | 19.5 | W | Clinton, NY | D | Kents Falls - Sciota 115kV | NYSEG | 0 | 3/31/13 |  | Withdrawn
207 | Cape Vincent Wind Power, LLC | Cape Vincent | 2006-01-12 | 209.3 | 209.3 | W | Jefferson, NY | E | Rockledge Substation 115kV | NM-NG | 0 | 2/28/14 |  | Withdrawn
208 | CRC Development, LLC | Roundhouse Renewable | 2006-01-17 | 35 | 36 | ST-NG | Otsego, NY |  | City of Oneonta | NYSEG | 0 | 9/25/06 |  | Withdrawn
209 | SUEZ Energy Generating NA, Inc | Nassau Generating | 2006-02-10 | 88 | 100 | CT | Nassau, NY |  | Garden City Substation 138kV | LIPA | 0 | 7/10/07 |  | Withdrawn
210 | Canadian Niagara Power, Inc. | Fortran | 2006-03-14 | 150 | 150 | AC | Niagara, NY | A | Huntley Station 115kV | NM-NG | 0 | 2010-03-31 |  | Withdrawn
213 | Noble Environmental Power, LLC | Ellenburg II Windfield | 2006-04-03 | 21 | 21 | W | Clinton, NY | D | Willis-Plattsburgh WP-2 230kV | NYPA | 0 | 4/30/13 |  | Withdrawn
215 | Noble Burke Windpark, LLC | Noble Burke Windpark | 2006-04-03 | 120 | 120 | W | Franklin-Clinton, NY | D | Willis Substation 230kV | NYPA | 0 | 2/5/09 |  | Withdrawn
217 | AES Keystone Wind, LLC | Cherry Flats | 2006-06-06 | 90 | 90 | W | Tioga, PA | C | Homer City-Watercure 345kV | NYSEG | 0 | 12/22/08 |  | Withdrawn
218 | Gamesa Energy USA | Endless Mountain Wind | 2006-07-03 | 150 | 150 | W | Tioga - Bradford, PA |  | Homer City-Watercure 345kV | NYSEG | 0 | 7/27/06 |  | Withdrawn
219 | NRG Energy, Inc. | Huntley | 2006-07-12 | 752 | 752 | CC-C | Niagara, NY | A | Tonawanda | NM-NG | 0 | 12/22/08 |  | Withdrawn
220 | AES Keystone Wind, LLC | Armenia Mountain I | 2006-07-19 | 175 | 175 | W | Bradford, PA | C | Homer City-Watercure 345kV | NYSEG | 0 | 8/19/08 |  | Withdrawn
221 | AES Keystone Wind, LLC | Armenia Mountain II | 2006-07-19 | 75 | 75 | W | Bradford, PA | C | Homer City-Watercure 345kV | NYSEG | 0 | 4/8/09 |  | Withdrawn
222 | Ball Hill Windpark, LLC | Ball Hill Windpark | 2006-07-21 | 90 | 90 | W | Chautauqua, NY | A | Dunkirk-Gardenville 230kV | NM-NG | 0 | 11/30/13 |  | Withdrawn
223 | Noble Environmental Power, LLC | Arkwright Windpark | 2006-07-21 | 99 | 99 | W | Chautauqua, NY |  | Dunkirk-Falconer 115kV | NM-NG | 0 | 3/12/07 |  | Withdrawn
224 | NRG Energy, Inc. | Berrians GT II | 2006-08-23 | 50 | 90 | CC-NG | Queens , NY | J | Astoria West Substation 138kV | CONED | 0 | 7/31/15 |  | Withdrawn
224B | Casella Waste Systems | Chemung Landfill | 2006-09-05 | 6.4 | 6.4 | M | Chemung, NY | C | 115kV | NYSEG | 0 | 4/15/08 |  | Withdrawn
225A | Schenectady International, Inc. | SII Rotterdam Junction | 2006-09-08 | 9.3 | 9.3 | Wo | Rotterdam, NY | F | 69kV | NM-NG | 0 | 8/31/10 |  | Withdrawn
225B | Burrstone Energy | Faxton/ St. Luke | 2006-09-15 | 2.2 | 2.2 | NG | Herkimer, NY | E | TBD | NM-NG | 0 | 7/10/08 |  | Withdrawn
226 | Cavallo Power | Linden | 2006-09-08 | 1200 | 1200 | CC | NY, NY - Union, NJ |  | East 13th, West 49th | CONED | 0 | 11/14/06 |  | Withdrawn
227 | EC&R Northeast, LLC | Orleans Wind | 2006-09-28 | 120 | 120 | W | Orleans, NY | A | Shelby Substation - 115kV | NM-NG | 0 | 10/14/08 |  | Withdrawn
227A | Laidlaw Energy Group Inc. | Laidlaw Energy & Env. | 2006-10-30 | 7 | 7 | Wo | Cattaraugus, NY | A | 13.2kV | NM-NG | 0 | 5/31/13 |  | Withdrawn
228 | AES Bainbridge, LLC | Jennison | 2006-10-30 | 516 | 536 | C | Chenango, NY |  | TBD | NYSEG | 0 | 4/24/07 |  | Withdrawn
229 | AES Somerset 2, LLC | Somerset | 2006-11-01 | 687 | 706 | C | Niagara, NY |  | Somerset Substation 345kV | NYSEG | 0 | 3/27/07 |  | Withdrawn
230 | Cornell University | Cornell CHPP | 2006-11-02 | 30 | 30 | NG |  |  | Maple Ave. Substation 115kV |  | 0 | 11/21/06 |  | Withdrawn
231 | Seneca Energy II, LLC | Seneca | 2006-11-02 | 6.4 | 6.4 | M | Seneca, NY | C | Goulds Substation 34.5kV | NYSEG | 0 | 4/30/12 |  | Withdrawn
235 | Gamesa Energy USA, LLC | Canfield Wind | 2006-12-12 | 120 | 120 | W | Tioga - Bradford, PA |  | Homer City-Watercure 345kV | NYSEG | 0 | 10/16/07 |  | Withdrawn
236 | Gamesa Energy USA, LLC | Dean Wind | 2006-12-14 | 150 | 150 | W | Tioga - Schuyler, NY | C | Watercure-Oakdale 345kV | NYSEG | 0 | 4/30/11 |  | Withdrawn
237 | Allegany Wind, LLC | Allegany Wind | 2007-01-09 | 72.5 | 72.5 | W | Cattaraugus, NY | A | Homer Hill – Dugan Rd. 115kV | NM-NG | 0 | 2/28/15 |  | Withdrawn
238 | Tonawanda Creek Wind, LLC | Tonawanda Creek Wind | 2007-01-30 | 75 | 75 | W | Genesee, NY | A | Lockport – Batavia 115kV | NM-NG | 0 | 7/31/09 |  | Withdrawn
239 | Western Door Wind, LLC | Western Door Wind | 2007-01-30 | 100 | 100 | W | Yates, NY | C | Greenidge – Haley Rd. 115kV | NYSEG | 0 | 1/30/12 |  | Withdrawn
239A | Innovative Energy System, Inc. | Modern Innovative Plant | 2007-01-31 | 6.4 | 6.4 | M | Niagara, NY | A | Youngstown – Sanborn 34.5kV | NM-NG | 0 | 4/30/13 |  | Withdrawn
240 | Noble Environmental Power, LLC | Farmersville Windpark | 2007-02-26 | 100 | 100 | W | Cattaraugus, NY-PA | A | Stolle Rd - Farmer's Valley 345kV | NM-NG | 0 | 7/31/09 |  | Withdrawn
241 | Noble Chateaugay Windpark II, LLC | Chateaugay II Windpark | 2007-03-15 | 19.5 | 19.5 | W | Franklin, NY | D | Chateaugay Substation 34.5kV | NYSEG | 0 | 8/31/12 |  | Withdrawn
242 | RG&E | Brown's Race Uprate | 2007-04-09 | 6 | 6 | H | Monroe, NY |  | Brown's Race Substation | NYSEG | 0 | 6/5/07 |  | Withdrawn
243 | Astoria Energy, LLC | Astoria Uprate | 2007-04-12 | 100 | 230 | CC-NG | Queens, NY | J | Astoria East Substation 138kV | ConEd | 0 | 2010-03-31 |  | Withdrawn
244 | AES Bainbridge, LLC | Jennison | 2007-04-13 | 650 | 650 | C | Chenango, NY |  | Oakdale – Fraser 345kV | NYSEG | 0 | 3/20/08 |  | Withdrawn
246 | PPM Energy, Inc | Dutch Gap Wind | 2007-06-01 | 250 | 250 | W | Jefferson, NY | E | Indian River - Black Rive 115kV | NM-NG | 0 | 03/01/12 |  | Withdrawn
247 | RG&E | Russell Station | 2007-06-11 | 300 | 325 | CC-NG | Monroe, NY | B | Russell Station 115kV | RG&E | 0 | 4/30/12 |  | Withdrawn
248 | RG&E | Russell Station II | 2007-06-11 | 300 | 300 | C | Monroe, NY |  | Russell Station 115kV | NYSEG | 0 | 10/2/07 |  | Withdrawn
249 | Hess Corporation | Bayone Energy Center II | 2007-06-20 | 250 | 250 | D | Bayonne, NJ |  | Gowanus Substation 138kV | ConEd | 0 | 10/2/07 |  | Withdrawn
252 | Brookfield Power | Manhattan Cable | 2007-08-01 | 350 | 350 | DC | New York, NY | J | World Trade Center 138 kV | ConEd | 0 | 7/10/08 |  | Withdrawn
253 | Marble River, LLC | Marble River SPS | 2007-08-13 | TBD | TBD | AC | Clinton, NY | D | Moses-Willis-Plattsburgh 230kV | NYPA | 0 | 6/30/12 |  | Withdrawn
254 | Ripley-Westfield Wind LLC | Ripley-Westfield Wind | 2007-08-14 | 124.2 | 124.2 | W | Chautauqua, NY | A | Ripley - Dunkirk 230kV | NM-NG | 0 | 3/1/12 |  | Withdrawn
255 | In-City, LLC | Cross Hudson | 2007-08-23 | 550 | 550 | CC-NG | New York, NY-NJ | J | W49th Street 345kV | ConEd | 0 | 7/1/08 |  | Withdrawn
256 | Niagara Shore Winds, LLC | Niagara Shore Wind | 2007-09-04 | 70.5 | 70.5 | W | Niagara, NY | A | Somerset Switch Yard 345kV | NYSEG | 0 | 3/31/10 |  | Withdrawn
257 | RG&E | Brown's Race Uprate | 2007-09-12 | 2 | 2 | H | Monroe, NY | B | Beebee Station 34kV | RG&E | 0 | 3/31/11 |  | Withdrawn
258 | Babcock & Brown, LP | Ripley-Westfield Wind II | 2007-09-24 | 124.8 | 124.8 | W | Chautauqua, NY |  | Ripley - Dunkirk 230kV | NM-NG | 0 | 10/16/07 |  | Withdrawn
259 | Delaware County Electric | Delaware County Landfill | 2007-09-24 | 1 | 1 | M | Delaware, NY |  | TBD | NYSEG | 0 | 1/29/08 |  | Withdrawn
261 | Astoria Generating Company | South Pier Improvement | 2007-10-02 | 105 | 108 | CT-NG | Kings, NY | J | Gowanus 138kV | ConEd | 0 | 3/1/12 |  | Withdrawn
262 | RP Wind NY, LLC | Schoharie Highlands | 2007-10-05 | 70 | 70 | W | Schoharie, NY | F | 69kV | NM-NG | 0 | 5/12/09 |  | Withdrawn
264 | RG&E | Seth Green | 2007-10-23 | 2.8 | 2.8 | H | Monroe, NY | B | 11kV | RG&E | 0 | 3/31/14 |  | Withdrawn
266 | NRG Energy, Inc. | Berrians GT III | 2007-11-28 | 250 | 290 | CC-NG | Queens, NY | J | Astoria Annex 345kV | NYPA | 0 | 6/30/15 |  | Withdrawn
265 | CityGreen Transmission | CityGreen | 2007-11-16 | 1100 | 1100 | DC | Wsch'r/Bkln/Qns, NY | H, J | Millwood - Farragut/Rainey 345kV | ConEd | 0 | 2010-03-31 |  | Withdrawn
267 | Winergy Power, LLC | Winergy NYC Wind Farm | 2007-11-30 | 600 | 600 | W | New York, NY | J | Gowanus Substation 345kV | ConEd | 0 | 7/31/12 |  | Withdrawn
268 | NRG Energy, Inc. | Arthur Kill | 2007-12-07 | 800 | 800 | CC | New York, NY | J | Gowanus Substation | ConEd | 0 | 7/10/08 |  | Withdrawn
269 | WM Renewable Energy, LLC | Madison County Landfill | 2007-12-10 | 2 | 2 | M | Madison, NY |  | Canastota | NM-NG | 0 | 1/29/08 |  | Withdrawn
270 | Wind Development Contract Co LLC | Hounsfield Wind | 2007-12-13 | 244.8 | 244.8 | W | Jefferson, NY | E | Fitzpatrick - Edic 345kV | NYPA | 0 | 7/31/16 |  | Withdrawn
271 | State Line Wind Power LLC | State Line Wind | 2007-12-20 | 124.8 | 124.8 | W | Chautauqua, NY | A | South Ripley - Dunkirk 230kV | NM-NG | 0 | 10/31/11 |  | Withdrawn
272 | NYPA | Benchmark Generator | 2007-12-20 | 900 | 1080 | CT-ST | Queens, NY | J | Astoria 345kV | NYPA | 0 | 4/8/09 |  | Withdrawn
273 | Winergy Power, LLC | Winergy Long Island Wind | 2007-12-21 | 299 | 299 | W | Suffolk, NY | K | Sterling Substation | LIPA | 0 | 7/10/08 |  | Withdrawn
274 | In City I, LLC | PSEG Fossil Bergen Unit 2 | 2008-01-23 | 100 | 100 | CC-NG | New York, NY-NJ | J | W49th Street 345kV | ConEd | 0 | 7/10/08 |  | Withdrawn
275 | Shell Wind Energy Inc. | Cayuga County Wind | 2008-01-24 | 120 | 120 | W | Cayuga, NY | C | Milliken - Wright Ave. 115kV | NYSEG | 0 | 4/8/09 |  | Withdrawn
277 | UniStar Nuclear Energy | Nine Mile Point Station Unit #3 | 2008-02-04 | 1640 | 1660 | NU | Oswego, NY | C | Scriba Substation 345kV | NM-NG | 0 | 12/22/09 |  | Withdrawn
278 | Riverbank Power Corporation | Riverbank Power A | 2008-02-20 | 1000 | 1000 | PS | Niagara, NY | A | Niagara - Rochester 345kV | NYPA | 0 | 6/24/09 |  | Withdrawn
279 | Riverbank Power Corporation | Riverbank Power D1 | 2008-02-20 | 1000 | 1000 | PS | St. Lawrence, NY | E | Massena 765kV | NYPA | 0 | 2010-03-31 |  | Withdrawn
280 | Riverbank Power Corporation | Riverbank Power D2 | 2008-02-20 | 1000 | 1000 | H | St. Lawrence, NY | E | Massena 765kV | NYPA | 0 | 10/14/08 |  | Withdrawn
281 | Riverbank Power Corporation | Riverbank Power G | 2008-02-20 | 1000 | 1000 | PS | Rockland, NY | G | West Haverstraw 345kV | ConEd/O&R | 0 | 11/30/10 |  | Withdrawn
282 | Concord Wind Power LLC | Concord Wind | 2008-02-28 | 101.2 | 101.2 | W | Chautauqua, NY | A | Dunkirk - South Ripley 230kV | NM-NG | 0 | 5/31/11 |  | Withdrawn
283 | Riverbank Power Corporation | Riverbank Power J | 2008-03-03 | 1000 | 1000 | H | Queens, NY | J | Poletti Substation 345kV | NYPA | 0 | 4/15/08 |  | Withdrawn
285 | Machias Wind Farm, LLC | Machias I | 2008-03-27 | 79.2 | 79.2 | W | Cattaraugus, NY | A | Gardenville - Homer Hill 115kV | NM-NG | 0 | 6/30/12 |  | Withdrawn
286 | Machias Wind Farm, LLC | Machias II | 2008-03-27 | 199.5 | 199.5 | W | Cattaraugus, NY | A | 345kV | NYSEG | 0 | 4/8/09 |  | Withdrawn
287 | Horizon Wind Energy, LLC | Pomfret | 2008-03-27 | 73.5 | 73.5 | W | Chautauqua, NY | A | Dunkirk - Falconer 115kV | NM-NG | 0 | 9/30/10 |  | Withdrawn
288 | Chateaugay River Wind Farm, LLC | Chateaugay River | 2008-03-31 | 120 | 120 | W | Franklin, NY | E | Willis Substation 230kV | NYPA | 0 | 2/5/09 |  | Withdrawn
290 | National Grid | Paradise | 2008-04-03 | N/A | N/A | AC | Niagara, NY | A | Paradise Station 115kV | NM-NG | 0 | 3/31/11 |  | Withdrawn
291 | Long Island Cable, LLC | LI Cable - Phase 1 | 2008-04-14 | 440 | 440 | W | Suffolk, NY | K | Ruland Road 138kV | LIPA | 0 | 7/31/12 |  | Withdrawn
292 | Long Island Cable, LLC | LI Cable - Phase 2a | 2008-04-14 | 220 | 220 | W | Suffolk, NY | K | Ruland Road 138kV | LIPA | 0 | 7/31/12 |  | Withdrawn
293 | Long Island Cable, LLC | LI Cable - Phase 2b | 2008-04-14 | 280 | 280 | W | Suffolk, NY | K | Ruland Road 138kV | LIPA | 0 | 12/22/08 |  | Withdrawn
295 | CCH Holdings Group, LLC | Cross Hudson II | 2008-05-06 | 800 | 800 | AC | New York, NY-NJ | J | West 49th St. Substation 345kV | ConEd | 0 | 6/1/12 |  | Withdrawn
296 | Noble Environmental Power, LLC | Harrigan Hill Wind | 2008-05-12 | 100.5 | 100.5 | W | Clinton-Ellenburg, NY | D | Lyon Mt - Willis 115kV | NYSEG | 0 | 7/31/09 |  | Withdrawn
297 | Ashford Wind Farm, LLC | Ashford Wind | 2008-05-16 | 19.9 | 19.9 | W | Cattaraugus, NY | A | Otto-West Valley 34.5kV | NM-NG | 0 | 2010-03-31 |  | Withdrawn
298 | TCI Renewable, LLC | Leicester Wind | 2008-05-22 | 57 | 57 | W | Livingston, NY | A | Highbank - Mortimer 115kV | NYSEG | 0 | 8/31/10 |  | Withdrawn
299 | Erie Boulevard Hydropower | Great Bend | 2008-06-03 | 14.4 | 14.4 | H | Jefferson, NY | E | Deferiet 115 kV substation | NM-NG | 0 | 4/8/09 |  | Withdrawn
300 | Auburn Public Power Agency | Auburn Sewage Treatment | 2008-06-26 | 3 | 3 |  | Onondaga, NY | C | Auburn, NY | NYSEG | 0 | 2008-10-14 |  | Withdrawn
301 | Hamlin Wind, LLC | Hamlin Wind Farm | 2008-07-15 | 80 | 80 | W | Monroe, NY | A | West Hamlin 115kV | NM-NG | 0 | 2010-03-31 |  | Withdrawn
302 | Barre Wind, LLC | Barre Wind Farm | 2008-07-15 | 120 | 120 | W | Orleans, NY | A | Lockport - Mortimer 115 KV | NM-NG | 0 | 2008-12-22 |  | Withdrawn
303 | Invenergy Thermal Devel., LLC | Tioga County Energy | 2008-07-17 | 620 | 700 | CT | Tioga, NY | C | Oakdale - Watercure 345kV | NYSEG | 0 | 2009-04-08 |  | Withdrawn
304 | Transmission Developers Inc. | Clay HVDC | 2008-07-18 | 2000 | 2000 | DC | New York, NY | J | Clay to Farragut 345kV | NM-NG/ConEd | 0 | 2008-08-28 |  | Withdrawn
305 | TDI-USA Holdings Corporation | Champlain Hudson Power Express | 2008-07-18 | 1000 | 1000 | DC | Quebec - NY, NY | J | Astoria Annex Substation 345kV | NYPA | 0 | 1/31/17 |  | Withdrawn
306 | Transmission Developers Inc. | Clay HVDC | 2008-07-18 | 2000 | 2000 | DC | Onondaga/New York, NY | C, J | Clay 345kV - Sherman Creek 138 kV | NM-NG/ConEd | 0 | 11/30/11 |  | Withdrawn
307 | New York Wire, LLC | New York Wire-Phase 1 | 2008-07-29 | 550 | 550 | DC | NJ - Kings, NY | J | Gowanus Substation 345kV | ConEd | 0 | 7/31/12 |  | Withdrawn
309 | AP Dutchess Properties Inc. | Wingdale Energy Center | 2008-09-11 | 650 | 650 | CC-NG | Dutchess, NY | G | Pleasant Valley - Long Mt. | ConEd | 0 | 5/12/09 |  | Withdrawn
310 | Cricket Valley Energy Center, LLC | Cricket Valley Energy Center | 2008-09-22 | 1019.9 | 1136 | CC-NG | Dutchess, NY | G | Pleasant Valley - Long Mt. 345kV | ConEd | 0 | 12/31/14 |  | Withdrawn
311 | New York State Electric & Gas | Concord Casino | 2008-09-24 | 48 | 48 | L | Sullivan, NY | E | Coopers Corner - Rock Hill | NYSEG | 0 | 4/30/13 |  | Withdrawn
312 | RP Wind NY, LLC | Gateway Wind Energy | 2008-09-25 | 79.2 | 79.2 | W | Schenectady, NY | F | Princetown - Rotterdam | NM-NG | 0 | 4/8/09 |  | Withdrawn
313 | Atlantic Wind, LLC | Stone Church Wind | 2008-09-30 | 150 | 150 | W | St. Lawrence, NY | E | Mc Intyre Substation 115 kV | NM-NG | 0 | 3/31/11 |  | Withdrawn
314 | Riverbank Power Corporation | Oswego | 2008-10-07 | 1000 | 1000 | PS | Oswego, NY | C | Oswego complex 345kV | NM-NG | 0 | 6/24/09 |  | Withdrawn
315 | CRC Renewables, LLC | Onondaga Renewables | 2008-10-23 | 47 | 47 | Wo | Onondaga, NY | C | Geres Lock 115kV | NM-NG | 0 | 1/30/12 |  | Withdrawn
316 | State Line Wind Power, LLC | State Line Wind II | 2008-10-31 | 124.8 | 124.8 | W | Chautauqua, NY | A | Dunkirk - South Ripley 230kV | NM-NG | 0 | 10/28/09 |  | Withdrawn
319 | AES Energy Storage, LLC | Cayuga Energy Storage | 2008-12-03 | 20 | 20 | ES | Onondaga, NY | C | Milliken 115kV | NYSEG | 0 | 6/1/12 |  | Withdrawn
320 | AES Energy Storage, LLC | Somerset Energy Storage | 2008-12-03 | 20 | 20 | ES | Niagara, NY | A | Somerset 69kV | NYSEG | 0 | 6/1/12 |  | Withdrawn
321 | Monroe County | Monroe County Landfill | 2009-01-02 | 6.4 | 6.4 | M | Monroe, NY | B | Sanford Rd. | NM-NG | 0 | 9/30/09 |  | Withdrawn
322 | Rolling Upland Wind Farm, LLC | Rolling Upland Wind | 2009-01-13 | 59.9 | 59.9 | W | Madison, NY | E | County Line - Brothertown 115kV | NYSEG | 0 | 8/31/14 |  | Withdrawn
323 | Riverbank Power Corporation | Verplanck | 2009-01-23 | 1000 | 1000 | PS | Westchester, NY | H | Indian Point 345kV | ConEd/O&R | 0 | 6/24/09 |  | Withdrawn
324 | Belltown Biogas, LLC | Belltown Bio | 2009-03-06 | 2 | 2 | M | Cayuga, NY | C | King Ferry | NYSEG | 0 | 4/8/09 |  | Withdrawn
325 | Synergy Biogas, LKc | Synergy Bio | 2009-03-06 | 2 | 2 | M | Wyoming, NY | A | Wyoming | NM-NG | 0 | 4/8/09 |  | Withdrawn
327 | Con Edison | Offshore Wind | 2009-03-20 | 700 | 700 | W | NY - Suffolk, NY | J, K | Far Rockaway 69kV | LIPA | 0 | 6/30/11 |  | Withdrawn
328 | Steuben Rural | Steuben County Landfill | 2009-03-23 | 4.8 | 4.8 | M | Steuben, NY | C | Quarry - Bath 34.5 | NYSEG | 0 | 5/27/09 |  | Withdrawn
329 | Horizon Wind Energy, LLC | Madison Wind Expansion | 2009-03-23 | 8.25 | 8.25 | W | Madison, NY | E | County Line - Brothertown 115kV | NYSEG | 0 | 5/27/09 |  | Withdrawn
332 | FitzPatrick Nuclear Station | FitzPatrick Nuclear Uprate | 2009-05-01 | 112 | 112 | NU | Oswego, NY | C | FitzPatrick Substation | NYPA | 0 | 6/24/09 |  | Withdrawn
334 | Atlantic Wind, LLC | Sangerfield Wind | 2009-05-28 | 46 | 46 | W | Onieda, NY | E | TBD | NM-NG/NYSEG | 0 | 7/31/09 |  | Withdrawn
335 | NextEra Energy Resources, LLC | Cold Creek Spring Wind | 2009-06-09 | 150.7 | 150.7 | W | Cattaraugus, NY | A | Carrs Corners - Salamanca 115kV | NM-NG | 0 | 8/31/12 |  | Withdrawn
336 | Enfield Energy, LLC | Black Oak Wind | 2009-06-29 | 50 | 50 | W | Thompkins, NY | C | Black Oak Rd 115kV | NYSEG | 0 | 6/30/12 |  | Withdrawn
341 | Covanta Energy | Hempstead Expansion | 2009-09-02 | 37 | 39 | ST-SW | Nassau, NY | K | Hempstead 138kV | LIPA | 0 | 8/31/10 |  | Withdrawn
343 | Champlain Wind Link, LLC | Champlain Wind Link I | 2009-09-29 | 600 | 600 | AC | Clinton, NY - VT | D | Plattsburgh - New Haven, VT 230kV | NYPA | 0 | 7/31/12 |  | Withdrawn
344 | Champlain Wind Link, LLC | Champlain Wind Link II | 2009-09-29 | 600 | 600 | AC | Clinton, NY - VT | D | Plattsburgh - New Haven, VT 345kV | NYPA | 0 | 4/30/12 |  | Withdrawn
345 | St. Elizabeth Medical Center | St. Elizabeth Medical Center | 2009-11-02 | 2.3 | 2.3 | NG | Herkimer, NY | E |  | NM-NG | 0 | 11/30/09 |  | Withdrawn
346 | Beacon Power | Scotia Industrial Park | 2009-11-24 | 20 | 20 | F | Schenectady, NY | F | Spier - Rotterdam | NM-NG | 0 | 8/31/12 |  | Withdrawn
347 | Franklin Wind Farm, LLC | Franklin Wind | 2009-12-02 | 50.4 | 50.4 | W | Delaware, NY | E | Oakdale - Delhi 115kV | NYSEG | 0 | 1/31/19 |  | Withdrawn
348 | Casella Waste Systems | Hyland Landfill | 2009-12-02 | 0.8 | 0.8 | M | Allegany, NY | B | Station 249 | RG&E | 0 | 4/30/10 |  | Withdrawn
350 | Lake Erie Wind, LLC | Lake Erie Wind | 2010-02-16 | 810 | 810 | W | Chautauqua, NY | A | Dunkirk - Gardenville 230kV | NM-NG | 0 | 1/30/12 |  | Withdrawn
351 | Linden VFT, LLC | Linden VFT Uprate | 2010-03-02 | 15 | 15 | AC | Richmond, NY-NJ | J | Goethals 345kV | CONED | 0 | 2/28/13 |  | Withdrawn
352 | WM Renewable Energy | Oneida-Herkimer Landfill | 2010-04-08 | 3.2 | 3.2 | M | Oneida, NY | E |  |  | 0 | 6/4/10 |  | Withdrawn
354 | Atlantic Wind, LLC | North Ridge Wind | 2010-05-13 | 100 | 100 | W | St. Lawrence, NY | E | Nicholville - Parishville 115kV | NM-NG | 0 | 1/31/15 |  | Withdrawn
356 | Pattern Renewables | Hounsfield Wind | 2010-09-07 | 249.4 | 249.4 | W | Jefferson, NY | E | Oswego Substation 345kV | NYPA | 0 | 11/30/10 |  | Withdrawn
358 | West Point Partners, LLC | West Point Transmission | 2010-09-13 | 1000 | 1000 | DC | Greene, Westchester, NY | F, H | Leeds - Buchanan North 345kV | NM-NG/ConEd | 0 | 9/30/19 |  | Withdrawn
357 | West Point Partners, LLC | NY Power Pathway | 2010-09-10 | 1000 | 1000 | DC | Albany, Westchester, NY | F, H | New Scotland - Buchanan South 345kV | NM-NG/Coned | 0 | 2/28/13 |  | Withdrawn
359 | National Grid | Verizon - Project Oasis | 2010-12-20 | 75 | 75 | L | Niagara, NY | A | Somerset - Kintigh 345kV | NYSEG | 0 | 2/28/11 |  | Withdrawn
360 | NextEra Energy Resources, LLC | Watkins Glen Wind | 2010-12-22 | 122.4 | 122.4 | W | Schuyler, NY | C | Bath - Montour Falls 115 kV | NYSEG | 0 | 5/31/15 |  | Withdrawn
362 | Monticello Hills Wind, LLC | Monticello Hills Wind | 2011-03-07 | 19.8 | 19.8 | W | Otsego, NY | E | W. Winfield - Richfield Spring 46kV | NYSEG | 0 | 4/30/17 |  | Withdrawn
364 | Bruce Hill Wind, LLC | Bruce Hill Wind | 2011-05-04 | 18 | 18 | W | Delaware, NY | E | Axtell Road Substation 115 kV | NYSEG | 0 | 9/30/12 |  | Withdrawn
365 | Transmission Developers Inc. | Champlain Hudson SPS | 2011-07-15 | TBD | TBD | AC | Queens, NY | J | Astoria and Farragut Subsations | ConEd/NYPA | 0 | 12/31/12 |  | Withdrawn
366 | NextEra Energy Resources, LLC | Watkins Glen East | 2011-08-02 | 150.6 | 150.6 | W | Schuyler, NY | C | Montour Falls Substation | NYSEG | 0 | 10/31/12 |  | Withdrawn
367 | Orange & Rockland | North Rockland Transformer | 2011-09-14 | N/A | N/A | AC | Rockland, NY | G | Line Y94 345kV | ConEd | 0 | 7/31/18 |  | Withdrawn
369 | Clover Leaf Power, LLC | Clover Leaf Hollers Ave | 2011-10-24 | 173.9 | 192.75 | CT | Bronx, NY | J | E 179th St. Subsation 138kV | ConEd | 0 | 12/31/13 |  | Withdrawn
370 | Smokey Avenue Wind, LLC | Smokey Avenue Wind | 2011-10-28 | 18 | 18 | W | Otsego, NY | F | Worcester - Schenevus 23kV | NM-NG | 0 | 1/31/14 |  | Withdrawn
371 | South Mountain Wind, LLC | South Mountain Wind | 2011-10-31 | 18 | 18 | W | Delaware, NY | E | River Rd Substation 46kV | NYSEG | 0 | 9/30/19 |  | Withdrawn
374 | CPV Valley, LLC | CPV Valley II | 2012-02-21 | 820 | 820 | CC-D | Wawayanda, NY | G | Rock Tavern-Coopers Corners 345kV | NYPA | 0 | 9/30/15 |  | Withdrawn
376 | Ridgeline Energy, LLC | Troups Creek Wind | 2012-03-07 | 32 | 32 | W | Steuben, NY | C | Troupsburg Substation | NYSEG | 0 | 4/30/12 |  | Withdrawn
376A | Atlantic Development, LLC | Atlantice Development | 2012-03-15 | N/A | N/A | W | N/A | N/A | N/A | N/A | 0 | 7/31/09 |  | Withdrawn
377 | Monroe County | Monroe County Mill Seat | 2012-03-16 | 3.2 | 3.2 | M | Monroe, NY | B | Sanford Rd. 34.5kV | NM-NG | 0 | 4/30/16 |  | Withdrawn
379 | Seneca Energy II, LLC | Seneca II Expansion | 2012-04-24 | 6.4 | 6.4 | M | Seneca, NY | C | Seneca - Waterloo 34.5kV | NYSEG | 0 | 5/31/13 |  | Withdrawn
381 | Clipper Wind Power Development | Paragon Wind | 2012-05-15 | 79.9 | 79.9 | W | Steuben-Schuyler, NY | C | Stony Ridge - Hillside 230kV | NYSEG | 0 | 10/31/12 |  | Withdrawn
382 | Astoria Generating Co. | South Pier Improvement | 2012-05-30 | 91.2 | 95.5 | CT-NG | Kings, NY | J | Gowanus Substation 138kV | ConEd | 0 | 3/31/18 |  | Withdrawn
383 | NRG Energy, Inc. | Bowline Gen. Station Unit #3 | 2012-05-30 | 775 | 814 | CC-NG | Rockland, NY | G | Ladentown Substation 345kV | O&R | 0 | 9/30/19 |  | Withdrawn
384 | National Grid | Knickerbocker Pleasant Valley | 2012-06-15 | TBD | TBD | AC | Columbia-Dutchess, NY | F, G | Knickerbocker - P. Valley 345kV | NM-NG/ConEd | 0 | 5/31/16 |  | Withdrawn
385 | National Grid | Hudson Valley Reinforcement | 2012-06-15 | TBD | TBD | AC | Alb.-Col.-Dutch., NY | F, G | N. Scotland-Leeds-P. Valley 345kV | NM-NG/ConEd | 0 | 2/28/15 |  | Withdrawn
388 | Enel Green Power North America | Dexter Solar | 2012-07-24 | 17 | 17 | S | Jefferson, NY | E | Dexter Stubstation | NM-NG | 0 | 9/30/12 |  | Withdrawn
389 | GUSC Energy, Inc. | Griffiss Technology Park | 2012-08-14 | 0.9 | 0.9 | ST | Oneida, NY | E | Boonville - Rome 115kV | NM-NG | 0 | 9/30/12 |  | Withdrawn
391 | North America Transmission, LLC | Edic - Fraser #2 | 2012-09-21 | TBD | TBD | AC | Oneida-Delaware, NY | E | Edic - Fraser 345kV | NM-NG/NYSEG | 0 | 1/31/16 |  | Withdrawn
392 | Exelon Corporation | Scriba-Volney | 2012-10-05 | TBD | TBD | AC | Oswego, NY | C | Scriba - Volney 345kV | NM-NG/NYSEG | 0 | 5/31/16 |  | Withdrawn
398 | Black Oak Wind Farm, LLC | Black Oak Wind | 2013-01-10 | 12.5 | 12.5 | W | Tompkins, NY | C | Montour - Coddington 115kV | NYSEG | 0 | 8/31/17 |  | Withdrawn
399 | American Electric Power | Mohawk Valley HVDC | 2013-02-27 | 1000 | 1000 | DC | Oneida-Bronx, NY | E, J | Marcy - Mott Haven 345kV | NYPA/ConEd | 0 | 6/30/13 |  | Withdrawn
400 | East Coast Power LLC | Linden Cogen Uprate | 2013-03-04 | 208 | 204 | CT-NG | Linden, NJ-NY,NY | J | Linden Cogen 345kV | ConEd | 0 | 10/31/15 |  | Withdrawn
401 | Caithness Long Island II, LLC | Caithness Long Island II | 2013-03-22 | 599 | 632 | CC-D | Suffolk, NY | K | Sills Road Substation 138kV | LIPA | 0 | 9/30/19 |  | Withdrawn
402 | NextEra Energy Transmission | Marcy - PV 345 | 2013-05-17 | TBD | TBD | AC | Oneida-Dutchess, NY | E-G | Marcy - P. Valley 345kV | NM-NG/NYPA/ ConEd | 0 | 2/28/15 |  | Withdrawn
404 | NextEra Energy Transmission | Princetown - Rotterdam 230 | 2013-06-04 | TBD | TBD | AC | Schenectady, NY | F | Princetown - Rotterdam 230kV | NM-NG | 0 | 5/31/16 |  | Withdrawn
405 | NextEra Energy Transmission | Oakdale - Fraser 345 | 2013-06-21 | TBD | TBD | AC | Broome-Delaware, NY | C, E | Oakdale - Fraser 345kV | NYSEG | 0 | 12/31/15 |  | Withdrawn
406 | NextEra Energy Transmission | Marcy - KB - PV 345 | 2013-06-21 | TBD | TBD | AC | Oneida-Dutchess, NY | E-G | Marcy - P. Valley 345kV | NM-NG/NYPA/ ConEd | 0 | 2/28/15 |  | Withdrawn
407 | National Grid | Edic-N.Scotland-Leed-PV | 2013-07-01 | TBD | TBD | AC | Oneida-Dutchess, NY | E-G | Edic - Pleasant Valley 345kV | NM-NG | 0 | 2/28/15 |  | Withdrawn
408 | National Grid | Edic-Princetown-N.Scotland-Leeds-PV | 2013-07-01 | TBD | TBD | AC | Oneida-Dutchess, NY | E, G | Edic - Pleasant Valley 345kV | NM-NG | 0 | 2/28/15 |  | Withdrawn
409 | National Grid | Edic-Knickerbocker-PV | 2013-07-01 | TBD | TBD | AC | Oneida-Dutchess, NY | E, G | Edic - Pleasant Valley 345kV | NM-NG | 0 | 2/28/15 |  | Withdrawn
410 | National Grid | Edic-Princetown-Knickerbocker-PV | 2013-07-01 | TBD | TBD | AC | Oneida-Dutchess, NY | E, G | Edic - Pleasant Valley 345kV | NM-NG | 0 | 2/28/15 |  | Withdrawn
411 | BCDC Transmission LLC | BCDC Transmission | 2013-07-01 | 400 | 400 | AC | NJ - New York, NY | J | NJ - Farragut Substation 345kV | ConEd | 0 | 12/31/13 |  | Withdrawn
412 | New York State Electric & Gas | Oakdale - Fraser 345 | 2013-08-20 | N/A | N/A | AC | Broome-Delaware, NY | C, E | Oakdale - Fraser 345kV | NYSEG | 0 | 7/31/16 |  | Withdrawn
413 | National Grid | Edic-Prince.-N.Scotland-Knick.-PV | 2013-08-21 | TBD | TBD | AC | Oneida-Dutchess, NY | E, G | Edic - Pleasant Valley 345kV | NM-NG | 0 | 2/28/15 |  | Withdrawn
414 | North America Transmission, LLC | Segment B Enhanced | 2013-09-05 | N/A | N/A | AC | Albany-Dutchess, NY | F, G | New Scotland - P. Valley 345kV | NM-NG/ConEd/ O&R/CHGE | 0 | 4/30/19 |  | Withdrawn
415 | Iberdrola USA | Connect New York | 2013-09-06 | 1000 | 1000 | DC | Albany-Dutchess, NY | F, G | New Scotland - Hurley Ave 345kV | NM-NG/Cen Hud | 0 | 10/31/14 |  | Withdrawn
416 | NextEra Energy Transmission | Marcy - KB - PV 345 (2) | 2013-09-09 | TBD | TBD | AC | Oneida-Dutchess, NY | E, G | Marcy - P. Valley 345kV | NM-NG/NYPA/ ConEd | 0 | 2/28/15 |  | Withdrawn
417 | NextEra Energy Transmission | Marcy - KB - PV 345 (3) | 2013-09-09 | TBD | TBD | AC | Oneida-Dutchess, NY | E, G | Marcy - P. Valley 345kV | NM-NG/NYPA/ ConEd | 0 | 5/31/16 |  | Withdrawn
418 | NextEra Energy Transmission | Marcy - NS - PV 345 | 2013-09-09 | TBD | TBD | AC | Oneida-Dutchess, NY | E, G | Marcy - P. Valley 345kV | NM-NG/NYPA/ ConEd | 0 | 3/31/15 |  | Withdrawn
419 | NextEra Energy Transmission | Marcy - NS - KB - PV 345 | 2013-09-16 | TBD | TBD | AC | Oneida-Dutchess, NY | E, G | Marcy - P. Valley 345kV | NM-NG/NYPA/ ConEd | 0 | 5/31/16 |  | Withdrawn
420 | NextEra Energy Transmission | Marcy - KB - PV 345 (4) | 2013-09-16 | TBD | TBD | AC | Oneida-Dutchess, NY | E, G | Marcy - P. Valley 345kV | NM-NG/NYPA/ ConEd | 0 | 2/28/15 |  | Withdrawn
423 | Rochester Gas & Electric | University of Rochester | 2013-11-17 | 25 | 25 | L | Monroe, NY | B | Station 251 | NYSEG | 0 | 7/31/14 |  | Withdrawn
424 | Boundless Energy NE, LLC | Leeds Path West | 2013-11-26 | N/A | N/A | AC | Greene-Westchester, NY | G-J | Leeds - Millwood 345kV | NM-NG/NYPA/ Cen Hud/ConEd/NYSEG | 0 | 2/28/17 |  | Withdrawn
425 | NextEra Energy Resources, LLC | Brookfield Wind Energy | 2013-12-11 | 100.3 | 100.3 | W | Chenango, Madison, NY | E | Chadwicks - Yahnundadis 115kV | NM-NG/NYSEG | 0 | 5/31/15 |  | Withdrawn
426 | North America Transmission, LLC | NS-Knickerbocker-PV | 2013-12-11 | TBD | TBD | AC | Albany-Dutchess, NY | F-G | New Scotland - P. Valley 345kV | NM-NG/ConEd | 0 | 2/28/14 |  | Withdrawn
427 | Island Park Energy Center, LLC | Island Park Energy Center CCPP | 2014-01-24 | 268 | 295 | CT-NG | Nassau, NY | K | Barrett Power Station 138kV | LIPA | 0 | 2/28/17 |  | Withdrawn
428 | Island Park Energy Center, LLC | Island Park Energy Center SCPP | 2014-01-24 | 262 | 252 | CT-NG | Nassau, NY | K | Barrett Power Station 138kV | LIPA | 0 | 2/28/17 |  | Withdrawn
433 | East Hampton Solar Farm, LLC | East Hampton - Phase 1 | 2014-04-21 | 20 | 20 | S | Suffolk, NY | K | Amagansett Substation 69KV | LIPA | 0 | 5/31/14 |  | Withdrawn
434 | East Hampton Solar Farm 2, LLC | East Hampton - Phase 2 | 2014-04-21 | 20 | 20 | S | Suffolk, NY | K | Amagansett Substation 69KV | LIPA | 0 | 5/31/14 |  | Withdrawn
435 | East Hampton Solar Farm 2, LLC | East Hampton - Phase 3 | 2014-04-21 | 20 | 20 | S | Suffolk, NY | K | Amagansett Substation 69KV | LIPA | 0 | 5/31/14 |  | Withdrawn
436 | East Hampton Solar Farm 2, LLC | Riverhead - Phase 1 | 2014-04-21 | 20 | 20 | S | Suffolk, NY | K | Edwards Substation 69KV | LIPA | 0 | 5/31/14 |  | Withdrawn
437 | East Hampton Solar Farm 2, LLC | Riverhead - Phase 2 | 2014-04-21 | 20 | 20 | S | Suffolk, NY | K | Edwards Substation 69KV | LIPA | 0 | 5/31/14 |  | Withdrawn
438 | East Hampton Solar Farm 2, LLC | Riverhead - Phase 3 | 2014-04-21 | 20 | 20 | S | Suffolk, NY | K | Edwards Substation 69KV | LIPA | 0 | 5/31/14 |  | Withdrawn
439 | Boston Energy Trading | East Garden City-Valley Stream | 2014-05-09 | TBD | TBD | AC | Nassau, NY | K | E. Garden City-Valley Stream 138kV | LIPA | 0 | 4/30/16 |  | Withdrawn
440 | Erie Power, LLC | Erie Power | 2014-06-02 | 79.4 | 88 | CC-NG | Chautauqua, NY | A | South Ripley Substation 230kV | NM-NG | 0 | 2/28/18 |  | Withdrawn
443 | Manorville Solar, LLC | Manorville Solar | 2014-06-09 | 16 | 16 | S | Suffolk, NY | K | Riverhead - Eastport 69kV | LIPA | 0 | 4/30/15 |  | Withdrawn
441 | East Hampton Solar Farm, LLC | East Hampton Solar | 2014-06-09 | 60 | 60 | S | Suffolk, NY | K | Buell Substation 69kV | LIPA | 0 | 1/31/15 |  | Withdrawn
442 | Riverhead Solar Farm, LLC | Riverhead Solar | 2014-06-09 | 24 | 24 | S | Suffolk, NY | K | Edwards Substation 138kV | LIPA | 0 | 5/31/15 |  | Withdrawn
446 | Solar Alliance Freedom, Inc. | Jockey Hill Solar | 2014-07-21 | 2 | 2 | S | Ulster, NY | G | Hurley Substation 345kV | CenHud | 0 | 9/30/14 |  | Withdrawn
447 | FTS Devco LLC | East Hampton Expansion | 2014-07-25 | 20 | 20 | S | Suffolk, NY | K | Amagansett Substation 69kV | LIPA | 0 | 1/31/15 |  | Withdrawn
448 | Alps Interconnector, LLC | Alps HVDC | 2014-08-12 | 600 | 600 | DC | NE-Rensselaer, NY | F | Alps Substation 345kV | NM-NG | 0 | 11/30/18 |  | Withdrawn
450 | Stacy Solar Center, LLC | Stacy Solar | 2014-08-20 | 20 | 20 | S | Greene, NY | G | Coxsackie Substation 69kV | CenHud | 0 | 2/28/15 |  | Withdrawn
451 | Shortsville Solar Center, LLC | Shortsville Solar | 2014-08-20 | 20 | 20 | S | Ontario, NY | B | Substation #168 34.5kV | NYSEG | 0 | 10/31/14 |  | Withdrawn
452 | Taconic Solar Center, LLC | Taconic Solar | 2014-08-20 | 10 | 10 | S | Columbia, NY | F | Craryville Substation 34.5kV | NYSEG | 0 | 10/31/14 |  | Withdrawn
453 | Blue Hill Solar Center, LLC | Blue Hill Solar | 2014-08-20 | 20 | 20 | S | Columbia, NY | F | Blue Stores Substation 115kV | NM-NG | 0 | 10/31/14 |  | Withdrawn
454 | Sabin Solar Center, LLC | Sabin Solar | 2014-08-20 | 20 | 20 | S | Herkimer, NY | E | Salisbury Substation 115kV | NM-NG | 0 | 10/31/14 |  | Withdrawn
455 | Roseway Solar, LLC | Roseway Solar | 2014-08-21 | 19.9 | 19.9 | S | Sullivan, NY | E | 34.5kV | NYSEG | 0 | 2/28/15 |  | Withdrawn
456 | ESA Solar NY, LLC | Woodhull Solar | 2014-09-09 | 0.7 | 0.7 | S | Steuben, NY | C | Woodhull Substation | NYSEG | 0 | 7/31/15 |  | Withdrawn
457 | RES America Developments Inc. | Bellmont Wind | 2014-09-22 | 19.8 | 19.8 | W |  |  | Brainardsville, NY | NYSEG | 0 | 12/31/14 |  | Withdrawn
459 | ESA Solar NY, LLC | Warsaw Solar | 2014-11-05 | 2 | 2 | S | Wyoming, NY | B | Wethersfield Substation 115kV | NYSEG | 0 | 12/31/14 |  | Withdrawn
460 | Dryden Solar, LLC | Dryden Solar | 2014-11-10 | 5 | 5 | S | Tompkins, NY | C |  | NYSEG | 0 | 12/31/14 |  | Withdrawn
463 | Long Island Clean Energy Project LLC | 62 Weeks Rd. Fuel Cell | 2014-12-05 | 19.9 | 19.9 |  | Suffolk, NY | K | 69kV | LIPA | 0 | 1/31/15 |  | Withdrawn
464 | Long Island Clean Energy Project LLC | Pulaski Rd. Fuel Cell | 2014-12-05 | 19.9 | 19.9 |  | Suffolk, NY | K | 138kV | LIPA | 0 | 1/31/15 |  | Withdrawn
469 | NextEra Energy Transmission | Edic-PV 345 | 2015-01-06 | TBD | TBD | AC | Oneida-Dutchess, NY | E, G | Edic - Pleasant Valley 345kV | NM-NG/ConEd | 0 | 5/31/15 |  | Withdrawn
470 | NextEra Energy Transmission | Knickerbocker 115 | 2015-01-06 | TBD | TBD | AC | Columbia-Rensselaer, NY | F | Greenbush - Churchtown 115kV | NM-NG/NYSEG/ CHGE | 0 | 5/31/16 |  | Withdrawn
471 | NextEra Energy Transmission | Marcy-Princetown 345 | 2015-01-06 | TBD | TBD | AC | Oneida-Albany, NY | E, F | Marcy - Princetown 345kV | NM-NG/NYPA/ ConEd | 0 | 5/31/16 |  | Withdrawn
472 | NextEra Energy Transmission | Knickerbocker 345 | 2015-01-06 | TBD | TBD | AC | Rensselaer-Dutchess, NY | F | Knickerbocker - P. Valley 345kV | NM-NG/ConEd | 0 | 5/31/16 |  | Withdrawn
473 | Calverton Solar LLC | Calverton Solar | 2015-01-21 | 10 | 10 | S | Suffolk, NY | K | Riverhead - Wildwood 69kV | LIPA | 0 | 2/28/19 |  | Withdrawn
475 | OneEnergy Development, LLC | Windy Hill Solar | 2015-02-02 | 20 | 20 | W | Washington, NY | F | Battenkill Substation 115kV | NM-NG | 0 | 7/31/15 |  | Withdrawn
476 | New York State Electric & Gas | Edic-PV, Oakdale-Fraser | 2015-02-12 | N/A | N/A | AC | Oneida-Delaware, NY | E | Edic-PV, Oakdale-Fraser 345kV | NM-NG/NYSEG | 0 | 7/31/16 |  | Withdrawn
478 | Central Hudson Gas & Electric | Hurley Ave PARs | 2015-02-17 | TBD | TBD | AC | Dutchess, NY | G | Hurley Ave 345kV | CHGE/NM-NG/NYSEG | 0 | 3/31/16 |  | Withdrawn
479 | Central Hudson Gas & Electric | Edic-NS, Hurley PARs | 2015-02-17 | TBD | TBD | AC | Oneida-Dutchess, NY | E-G | Edic-NS, Hurley Ave 345kV | CHGE/NM-NG/NYSEG/NYPA | 0 | 3/31/16 |  | Withdrawn
480 | National Grid | Edic-NS, Knickerbocker-PV | 2015-02-20 | TBD | TBD | AC | Oneida-Dutchess, NY | E-G | Edic-NS, Knickerbocker-PV 345kV | NM-NG/ConEd | 0 | 5/31/16 |  | Withdrawn
481 | National Grid | Leeds - Pleasant Valley | 2015-02-20 | TBD | TBD | AC | Greene-Dutchess, NY | G | Leeds - P. Valley 345kV | NM-NG/ConEd | 0 | 12/31/15 |  | Withdrawn
482 | National Grid | Edic-NS, NS-Leeds-PV | 2015-02-20 | TBD | TBD | AC | Oneida-Dutchess, NY | E, G | Edic-NS, NS-Leeds-PV 345kV | NM-NG/ConEd | 0 | 12/31/15 |  | Withdrawn
483 | National Grid | NS-Leeds, Leeds-PV | 2015-02-20 | TBD | TBD | AC | Albany-Dutchess, NY | F, G | NS-Leeds, Leeds-PV 345kV | NM-NG/ConEd | 0 | 12/31/15 |  | Withdrawn
484 | National Grid | Edic-NS, NS-Leeds, Leeds-PV | 2015-02-20 | TBD | TBD | AC | Oneida-Dutchess, NY | E, G | Edic-NS, NS-Leeds, Leeds-PV 345kV | NM-NG/ConEd | 0 | 12/31/15 |  | Withdrawn
485 | National Grid | Knickerbocker-PV | 2015-03-04 | TBD | TBD | AC | Columbia-Dutchess, NY | F, G | Knickerbocker - P. Valley 345kV | NM-NG/ConEd | 0 | 5/31/16 |  | Withdrawn
486 | LI Energy Storage System | Buell Battery Storage | 2015-03-09 | 20 | 20 | ES | Suffolk, NY | K | East Hampton Substation 69kV | LIPA | 0 | 10/31/15 |  | Withdrawn
488 | LI Energy Storage System | Glenwood Battery Storage | 2015-03-09 | 20 | 20 | ES | Suffolk, NY | K | Glenwood Substation 69kV | LIPA | 0 | 4/30/17 |  | Withdrawn
489 | LI Energy Storage System | Southampton Battery Storage | 2015-03-09 | 20 | 20 | ES | Suffolk, NY | K | Southampton 69kV | LIPA | 0 | 10/31/15 |  | Withdrawn
491 | Yaphank Fuel Cell Park, LLC | Yaphank Fuel Cell Park | 2015-03-23 | 19.6 | 19.6 | ES | Suffolk, NY | K | Yaphank Substation 69kV | LIPA | 0 | 7/31/15 |  | Withdrawn
492 | Setauket Fuel Cell Park, LLC | Setauket Fuel Cell Park | 2015-03-23 | 19.6 | 19.6 | FC | Suffolk, NY | K | Terryville Substation 69kV | LIPA | 0 | 9/30/16 |  | Withdrawn
493 | EPCAL Fuel Cell Park, LLC | EPCAL Fuel Cell Park | 2015-03-30 | 19.6 | 19.6 | FC | Suffolk, NY | K | Riverhead 69 kV | LIPA | 0 | 1/31/16 |  | Withdrawn
494 | Alabama Ledge Wind Farm LLC | Alabama Ledge Wind | 2015-03-31 | 79.8 | 79.8 | W | Genesee, NY | B | Lockport - Oakfield 115kV | NM-NG | 0 | 9/30/19 |  | Withdrawn
499 | Sharon Solar LLC | Sharon Solar | 2015-05-07 | 19.6 | 19.6 | S | Schoharie, NY | F | Sharon Substation 69kV | NM-NG | 0 | 10/31/15 |  | Withdrawn
500 | Regeneron Solar LLC | Regeneron Solar | 2015-05-12 | 2 | 2 | S | Rensselaer, NY | F | East Greenbush, NY | NM-NG | 0 | 8/31/15 |  | Withdrawn
501 | Regeneron Solar LLC | Mariaville 2 Solar | 2015-05-12 | 2 | 2 | S | Schenectady, NY | F | Mariaville, NY | NM-NG | 0 | 8/31/15 |  | Withdrawn
502 | Lincoln Park DG LLC | Lincoln Park | 2015-05-22 | 18.3 | 18.3 |  | Dutchess, NY | F | Lincoln Park Substation | CHGE | 0 | 6/30/15 |  | Withdrawn
503 | East Kingstson DG LLC | East Kingston | 2015-05-22 | 18.3 | 18.3 |  | Dutchess, NY | F | East Kingston Substation | CHGE | 0 | 6/30/15 |  | Withdrawn
504 | NY DG Holding LLC | Saugerties | 2015-05-22 | 18.3 | 18.3 |  | Dutchess, NY | F | Saugerties Substation | CHGE | 0 | 6/30/15 |  | Withdrawn
505A | Central Hudson | Hurley Ave & Saugerties | 2015-06-05 | TBD | TBD | AC | Greene-Ulster, NY | G | Hurley Ave & Saugerties 69kV | CHGE | 0 | 10/31/15 |  | Withdrawn
507 | Erie Boulevard Hydropower, LP | Glens Falls Hydro | 2015-07-02 | 14.8 | 14.8 | H | Washington, NY | F | Henry St. - Glens Falls 34.5kV | NM-NG | 0 | 12/31/16 |  | Withdrawn
508 | Blue Circle DG LLC | Blue Circle | 2015-07-17 | 18.2 | 18.2 | FC | Greene, NY | G | LaFarge - PV 115 kV | NM-NG | 0 | 2/29/16 |  | Withdrawn
509 | North Catskill DG LLC | North Catskill | 2015-07-17 | 18.2 | 18.2 |  | Greene, NY | G | North Catskill Substation | CHGE | 0 | 8/31/15 |  | Withdrawn
511 | AG Energy, LP | Ogdensburg | 2015-09-04 | 79 | 90.1 | CC-NG | St. Lawrence, NY | E | North Ogdensburg Substation | NM-NG | 8 | 9/30/19 |  | Withdrawn
512 | Northbrook Lyons Falls | Lyons Fills Mill Hydro | 2015-09-11 | 2.5 | 2.5 | H | Lewis, NY | E | Taylorville- Boonville 115 kV | NM-NG | 0 | 6/30/19 |  | Withdrawn
514 | RES Americas Developments Inc. | Empire Wind | 2015-10-01 | 120 | 120 | W | Rensselaer, NY | F | Stephentown - Greenbush 115kV | NM-NG | 0 | 7/31/18 |  | Withdrawn
515 | North Bergen Liberty Generation Center LLC | Liberty Generation | 2015-10-07 | 1000 | 1000 | CC-NG | New York, NY | J | W49th St 345kV | ConEd | 0 | 1/31/18 |  | Withdrawn
522 | NYC Energy LLC | NYC Energy | 2015-12-16 | 79.9 | 79.9 | ES | New York, NY | J | Hudson Avenue East 138kV | ConEd | 0 | 11/30/19 |  | Withdrawn
525 | New York Power Authority | Western NY Energy Link | 2015-12-18 | N/A | N/A | AC | Niagara, NY | A | Niagara - Stolle - Gardenville | NYPA/NYSEG | 0 | 2/28/18 |  | Withdrawn
527 | Atlantic Wind, LLC | Horse Creek Wind | 2015-12-23 | 250 | 250 | W | Jefferson, NY | E | Indian River 115kV | NM-NG | 0 | 7/31/17 |  | Withdrawn
528 | National Grid | Moderate Power Transfer | 2015-12-30 | N/A | N/A | AC | Niagara-Erie, NY | A | Niagara, Erie, Stolle, Gardenville | NM-NG | 0 | 9/30/17 |  | Withdrawn
529 | National Grid | High Power Transfer | 2015-12-30 | N/A | N/A | AC | Niagara-Erie, NY | A | Niagara, Erie, Stolle, Gardenville | NM-NG | 0 | 9/30/17 |  | Withdrawn
530 | NextEra Energy Transmission New York, Inc. | Empire State Line | 2016-01-04 | N/A | N/A | AC | Niagara-Erie, NY | A | Dysinger - Stolle 345kV | NYPA/NYSEG | 0 | 9/30/19 |  | Withdrawn
532 | Invenergy Wind Development LLC | Allegany Wind | 2016-02-01 | 100 | 100 | W | Allegany, NY | B | Freedom Substation | Village of Arcade | 0 | 8/31/19 |  | Withdrawn
533 | Delano Management LLC | Empire Interconnection | 2016-02-03 | 275 | 275 | DC | Nassau, NY | K | Far Rockaway Substation 69kV | LIPA | 0 | 11/30/17 |  | Withdrawn
534 | OneEnergy Development, LLC | Great Valley Solar | 2016-02-03 | 20 | 20 | S | Washington, NY | F | Battenkill 34.5kV Substation | NM-NG | 0 | 7/31/19 |  | Withdrawn
536 | Empire Interconnection LLC | Glenwood | 2016-04-19 | 275 | 275 | AC | Suffolk, NY | K | Glenwood/Far Rockaway Station 69kV | LIPA | 0 | 11/30/17 |  | Withdrawn
537 | NextEra Energy Transmission New York, Inc. | Segment A | 2016-04-25 | N/A | N/A | AC | Oneida-Albany NY | E, F | Edic - New Scotland 345kV | NM-NG/NYPA | 0 | 9/30/19 |  | Withdrawn
538 | NextEra Energy Transmission New York, Inc. | Segment B | 2016-04-25 | N/A | N/A | AC | Albany-Dutchess, NY | F, G | Greenbush - PV 345kV | NM-NG/NYSEG/ CHGE/ConEd | 0 | 9/30/19 |  | Withdrawn
539 | NextEra Energy Transmission New York, Inc. | Segment B Alt | 2016-04-25 | N/A | N/A | AC | Albany-Dutchess, NY | F, G | Greenbush - PV 345kV | NM-NG/NYSEG/ CHGE/ConEd | 0 | 9/30/19 |  | Withdrawn
542 | National Grid | Segment A Edic-New Scotland | 2016-05-04 | N/A | N/A | AC | Oneida-Albany NY | E, F | Edic - New Scotland 345kV | NM-NG | 0 | 9/30/19 |  | Withdrawn
544 | Invenergy Wind Development LLC | Alle Catt Wind | 2016-05-04 | 100.5 | 100.5 | W | Cattaraugus, NY | A | Freedom Substation 115kV | Village of Arcade | 0 | 8/31/17 |  | Withdrawn
547 | North America Transmission, LLC | Dysinger-Stolle | 2016-05-25 | N/A | N/A | AC | Niagara-Erie, NY | A | Dysinger - Stolle 345kV | NYPA/NYSEG/ NM-NG | 0 | 4/30/19 |  | Withdrawn
548 | North America Transmission, LLC | Dysinger-Stolle-Gardenville | 2016-05-25 | N/A | N/A | AC | Niagara-Erie, NY | A | Dysinger - Gardenville 345kV | NYPA/NYSEG/ NM-NG | 0 | 10/31/17 |  | Withdrawn
549 | North America Transmission, LLC | Niagara-Dysinger-Stolle-Gardenville | 2016-05-25 | N/A | N/A | AC | Niagara-Erie, NY | A | Niagara - Gardenville 345kV | NYPA/NYSEG/ NM-NG | 0 | 10/31/17 |  | Withdrawn
550 | North America Transmission, LLC | Dysinger-Stolle-Gardenville II | 2016-06-02 | N/A | N/A | AC | Niagara-Erie, NY | A | Dysinger - Gardenville 345kV | NYPA/NYSEG/ NM-NG | 0 | 10/31/17 |  | Withdrawn
551 | OneEnergy Development, LLC | Caprock Solar | 2016-06-24 | 20 | 20 | S | Monroe, NY | B | South Union - Sweden 115kV | NM-NG | 0 | 8/31/17 |  | Withdrawn
552 | OneEnergy Development, LLC | Flotilla Solar | 2016-06-24 | 20 | 20 | S | Monroe, NY | B | Brockport - Hamlin 115kV | NM-NG | 0 | 8/31/17 |  | Withdrawn
553 | OneEnergy Development, LLC | Caspian Solar | 2016-06-24 | 20 | 20 | S | Monroe, NY | B | Sweden - South Union 115kV | NM-NG | 0 | 8/31/16 |  | Withdrawn
554 | Lookheed Martin | Lockheed Matin MST Syracuse | 2016-06-27 | [5 empty] | Lockheed Martin switch 13.8kV | NM-NG | 0 | 7/31/16 |  | Withdrawn
555 | North America Transmission, LLC | Segment A Base | 2016-07-06 | N/A | N/A | AC | Oneida-Albany NY | E, F | Edic - New Scotland 345kV | NM-NG | 0 | 4/30/19 |  | Withdrawn
557 | North America Transmission, LLC | Segment A Enhanced | 2016-07-06 | N/A | N/A | AC | Oneida-Albany NY | E, F | Edic - New Scotland 345kV | NM-NG | 0 | 4/30/19 |  | Withdrawn
558 | North America Transmission, LLC | Segment A 765 | 2016-07-06 | N/A | N/A | AC | Oneida-Albany NY | E, F | Edic - New Scotland 345kV | NM-NG/ NYPA | 0 | 4/30/19 |  | Withdrawn
559 | North America Transmission, LLC | Segment B Base | 2016-07-06 | N/A | N/A | AC | Oneida-Albany NY | E, F | Knickerbocker - PV 345kV | NM-NG/O&R CHGE/ConEd | 0 | 4/30/19 |  | Withdrawn
562 | OneEnergy Development, LLC | Hidden Meadow Solar | 2016-07-22 | 20 | 20 | S | Columbia-Dutchess, NY | F, G | Milan - Churchtown 115kV | NM-NG | 0 | 3/31/17 |  | Withdrawn
563 | Double Lock Solar, LLC | Double Lock Solar | 2016-07-25 | 20 | 20 | S | Herkimer, NY | E | St. Johnsville - Marshville 115kV | NM-NG | 0 | 7/31/19 |  | Withdrawn
567 | Tribes Hill Solar, LLC | Tribes Hill Solar | 2016-08-10 | 20 | 20 | S | Mongomery, NY | F | Ephrata - Florida 69KV | NM-NG | 0 | 6/30/18 |  | Withdrawn
568 | Turkey Hollow Solar, LLC | Turkey Hollow Solar | 2016-08-16 | 20 | 20 | S | Delaware, NY | F | Grand Gorge - Axtell Road 115kV | NYSEG | 0 | 1/31/18 |  | Withdrawn
569 | Hecate Energy, LLC | Greene County | 2016-08-17 | 50 | 50 | S | Greene, NY | G |  | CHGE | 0 | 9/30/16 |  | Withdrawn
578 | Sharon Solar LLC | Sharon Solar | 2016-09-20 | 20 | 20 | S | Schoharie, NY | F | Sharon Substation 69kV | NM-NG | 0 | 6/30/17 |  | Withdrawn
582 | Sunny Knoll Solar LLC | Sunny Knoll Solar | 2016-10-18 | 20 | 20 | S | Schoharie, NY | F | Cobleskill - Schoharie 69kV | NM-NG | 0 | 5/31/19 |  | Withdrawn
585 | Caledonia Solar LLC | Caledonia I Solar | 2016-11-07 | 20 | 20 | S | Livingston, NY | A | Golah - South Perry 69kV | NM-NG | 0 | 6/30/18 |  | Withdrawn
587 | Fork Valley Solar LLC | Fork Valley Solar | 2016-11-08 | 20 | 20 | S | Steuben, NY | C | Eelpot Rd 345.5kV Substation | NYSEG | 0 | 7/31/18 |  | Withdrawn
588 | Exelon Transmission Co., LLC | Niagara Transmission Expansion | 2016-11-15 | N/A | N/A | AC | Niagara-Erie, NY | A | Niagara - Gardenville | NYPA/NYSEG/ NM-NG | 0 | 9/30/17 |  | Withdrawn
593 | OneEnergy Development, LLC | Raceway Solar | 2016-12-28 | 20 | 20 | S | Rensselaer, NY | F | Cobb Hill Substation | NYSEG | 0 | 4/30/17 |  | Withdrawn
599 | LeRoy, LLC | LeRoy Solar | 2017-01-11 | 20 | 20 | S | Genesee, NY | B | LeRoy Substation 115kV | NGrid | 0 | 4/30/17 |  | Withdrawn
600 | Conti Enterprises, Inc. | Darby Solar | 2017-01-12 | 20 | 20 | S | Washington, NY | G | Mechanicville - Schaghticoke 34.5kV | NM-NG | 0 | 4/30/19 |  | Withdrawn
601 | HP Hood LLC | Hood Cogen | 2017-01-20 | 4 | 4 | CT-NG | Madison, NY | C | Oneida - Fenner 115kV | NGrid | 0 | 12/31/18 |  | Withdrawn
602 | Cypress Creek Renewables | Keesog Solar | 2017-01-30 | 50 | 50 | S | Franklin, NY | D | Moses - Willis 230kV | NYPA | 0 | 5/31/17 |  | Withdrawn
603 | Hecate Energy Riverhead, LLC | Riverhead | 2017-02-03 | 7.5 | 7.5 | S | Suffolk, NY | K | Wildwood - Riverhead 69kV | LIPA | 0 | 5/31/18 |  | Withdrawn
604 | Hecate Energy Columbia County 1, LLC | Columbia County 1 | 2017-02-07 | 20 | 20 | S | Columbia, NY | G | Craryville Substation 34.5kV | NYSEG | 0 | 7/31/17 |  | Withdrawn
605 | Hecate Energy Columbia County 2, LLC | Columbia County 2 | 2017-02-07 | 20 | 20 | S | Columbia, NY | G | Craryville Substation 34.5kV | NYSEG | 0 | 7/31/17 |  | Withdrawn
606 | Hecate Energy Craryville 3, LLC | Columbia County 3 | 2017-02-07 | 10 | 10 | S | Columbia, NY | G | Craryville Substation 34.5kV | NYSEG | 0 | 7/31/17 |  | Withdrawn
607 | Empire State Connector Corporation | Empire State Connector II | 2017-02-08 | 1000 | 1000 | DC | Oneida-New York, NY | E, J | Marcy - Astoria 345kV | NYPA/NM-NG/ ConEd | 0 | 3/31/17 |  | Withdrawn
608 | ITC New York Development, LLC | Segment A | 2017-02-08 | N/A | N/A | AC | Oneida-Albany NY | E, F | Edic - New Scotland 345kV | NM-NG | 0 | 4/30/19 |  | Withdrawn
609 | ITC New York Development, LLC | Segment B | 2017-02-08 | N/A | N/A | AC | Oneida-Albany NY | E, F | Knickerbocker - PV 345kV | NM-NG/NYSEG/ CHGE/ConEd | 0 | 4/30/19 |  | Withdrawn
610 | Woodruff Solar, LLC | Woodruff Solar | 2017-02-10 | 20 | 20 | S | Livingston, NY | A | Golah - N. Lakeville 34.5KV | NM-NG | 0 | 6/30/19 |  | Withdrawn
611 | Badra Solar, LLC | Badra Solar | 2017-02-10 | 20 | 20 | S | Franklin, NY | D | Nicholville - Malone 115kV | NM-NG | 0 | 3/31/17 |  | Withdrawn
613 | OneEnergy Development, LLC | Sugar Maple Solar | 2017-02-17 | 20 | 20 | S | Herkimer, NY | E | Trenton Falls - Poland 46kV | NM-NG | 0 | 6/30/19 |  | Withdrawn
614 | Sabertooth Solar, LLC | Sabertooth Solar | 2017-02-22 | 20 | 20 | S | Cortland, NY | B | Willett - Lapeer 115kV | NYSEG | 0 | 6/30/17 |  | Withdrawn
615 | West Point Partners, LLC | West Point II HVDC | 2017-03-02 | 1000 | 1000 | DC | Albany, Westchester, NY | F, H | New Scotland - Buchanan South 345kV | NM-NG/ConEd | 0 | 2/28/19 |  | Withdrawn
616 | Heelstone Development, LLC | Mohawk Solar | 2017-03-23 | 20 | 20 | S | Herkimer, NY | E | Watkins Rd - Ilion 115kV | NM-NG | 0 | 4/30/19 |  | Withdrawn
622 | Geronimo Solar Energy, LLC | Alcoa Solar | 2017-03-27 | 20 | 20 | S | St. Lawrence, NY | E | 13.8kV | NM-NG | 0 | 6/30/17 |  | Withdrawn
623 | Conti Enterprises, Inc. | Puckett Solar | 2017-04-05 | 20 | 20 | S | Chenango, NY | C | Chenango Forks 34.5kV Substation | NYSEG | 0 | 6/30/17 |  | Withdrawn
625 | Whitehart Solar, LLC | Whitehart Solar | 2017-04-13 | 20 | 20 | S | Sullivan, NY | E | Hyatt Rd.- Border City 115kV | NYSEG | 0 | 9/30/18 |  | Withdrawn
626 | KCE NY 1, LLC | KCE NY 1 | 2017-04-14 | 20 | 20 |  | Saratoga, NY | F | Luther Forest 34.5kV Substation | NM-NG | 0 | 6/30/17 |  | Withdrawn
627 | OneEnergy Development, LLC | Southtown 2 Solar | 2017-04-17 | 20 | 20 | S |  |  | North Angola 34.5kV Substation | NM-NG | 0 | 6/30/17 |  | Withdrawn
628 | OneEnergy Development, LLC | Slingshot 2 Solar | 2017-04-17 | 20 | 20 | S | Steuben, NY | C | Hammondsport 34.5 kV Substation | NYSEG | 0 | 8/31/17 |  | Withdrawn
630 | Cayuga Operating Co. | Cayuga Solar | 2017-04-27 | 20 | 20 | S | Lansing, NY | C | Milliken 34.5 Substation | NYSEG | 0 | 1/31/18 |  | Withdrawn
633 | Conti Enterprises, Inc. | Janis Solar | 2017-05-15 | 20 | 20 | S |  | B | Willet - Tarbell 34.5 kV | NYSEG | 0 | 6/30/17 |  | Withdrawn
634 | Champagne Storage, LLC | Champagne Storage | 2017-05-18 | 20 | 20 | ES | Madison, NY | E | Oneida - Cortland 115kV | NM-NG | 0 | 1/31/18 |  | Withdrawn
635 | Rising Solar, LLC | Rising Solar | 2017-06-14 | 20 | 20 | S | Orange, NY | G | Sugarloaf - Wisner 69kV | O&R | 0 | 12/31/18 |  | Withdrawn
636 | Daybreak Solar, LLC | Daybreak Solar | 2017-06-15 | 25 | 25 | S | Ulster, NY | G | East Walden Substation 69kV | CHGE | 0 | 1/31/19 |  | Withdrawn
639 | Owego Solar LLC | Owego Solar | 2017-07-19 | 20 | 20 | S | Tioga, NY | C | South Owego - Stagecoach 115kV | NYSEG | 0 | 11/30/17 |  | Withdrawn
640 | Granada Solar, LLC | Grissom Solar | 2017-07-19 | 20 | 20 | S | Fulton, NY | F | Vail Mills Substation 69kV | NM-NG | 0 | 11/30/17 |  | Withdrawn
641 | AVANGRID | Oakdale - Lafayette | 2017-07-24 | N/A | N/A | AC | Broome-Onondaga, NY | C | Oakdale - Lafayette | NM-NG/NYSEG | 0 | 9/30/19 |  | Withdrawn
642 | AVANGRID | Jennison - Edic | 2017-07-24 | N/A | N/A | AC | Chenango - Oneida, NY | E | Jennison - Edic | NM-NG/NYSEG | 0 | 9/30/19 |  | Withdrawn
643 | AVANGRID | Multiple Areas | 2017-07-24 | N/A | N/A | AC | Steuben - Otsego, NY | C, E | Transmission Reinforcements | NM-NG/NYSEG | 0 | 9/30/19 |  | Withdrawn
645 | Oya Solar NY LP | Manny Corner Solar | 2017-08-01 | 20 | 20 | S | Montgomery, NY | F | Meco - Rotterdam 115kV | NM-NG | 0 | 3/31/18 |  | Withdrawn
646 | Oya Solar NY LP | Shaw Solar | 2017-08-01 | 20 | 20 | S | Jefferson, NY | E | Thousand Island 115kV | NM-NG | 0 | 12/31/17 |  | Withdrawn
647 | Oya Solar NY LP | Robinson Solar | 2017-08-01 | 20 | 20 | S | Jefferson, NY | E | Thousand Island 115kV | NM-NG | 0 | 3/31/18 |  | Withdrawn
648 | Oya Solar NY LP | Black Creek Solar | 2017-08-01 | 20 | 20 | S | Jefferson, NY | E | Thousand Island - Coffeen 115kV | NM-NG | 0 | 12/31/17 |  | Withdrawn
651 | Yaphank Fuel Cell Park, LLC | Yaphank Solid Waste Management | 2017-08-04 | 7.4 | 7.4 | FC | Suffolk, NY | K | W. Yaphank - North Bellport 69kV | LIPA | 0 | 10/31/18 |  | Withdrawn
652 | Somerset Operating Company LLC | Somerset Solar | 2017-08-04 | 19.9 | 19.9 | S | Monroe, NY | B | Kintigh Switchyard 69kV | NYSEG | 0 | 2/2818 |  | Withdrawn
653 | Plattsburgh Solar, LLC | Moffitt Solar | 2017-08-07 | 20 | 20 | S | Clinton, NY | D | Northend - Woodruff Pond 46kV | NYSEG | 0 | 9/30/18 |  | Withdrawn
655 | Admiral Wind LLC | Admiral Wind LLC | 2017-08-11 | 20 | 20 | W | Madison, NY | C | Fenner - Oneida 115kV | NM-NG | 0 | 11/30/19 |  | Withdrawn
657 | Mistral Wind LLC | Mistral Wind LLC | 2017-08-11 | 20 | 20 | W | Genesee, NY | B | Lockport - Batavia 115kV | NM-NG | 0 | 11/30/19 |  | Withdrawn
656 | Taku Wind LLC | Taku Wind | 2017-08-11 | 20 | 20 | W | Genesee, NY | A | Akron - Attica 34.5kV | NM-NG | 0 | 1/31/18 |  | Withdrawn
658 | CVE North America, Inc. | Volney Solar Park | 2017-08-29 | 19.8 | 19.8 | S | Fulton, NY | F | South Oswego - Clay 115kV | NM-NG | 0 | 1/31/18 |  | Withdrawn
659 | Solar Liberty Energy Systems, Inc. | Westwood Rd | 2017-09-19 | 10.1 | 11.3 | S | Erie, NY | A | Erie St - Alden 34.5kV | NYSEG | 0 | 3/31/18 |  | Withdrawn
660 | Solar Liberty Energy Systems, Inc. | Liberty Dr | 2017-09-07 | 7.4 | 7.4 | S | Niagara Falls, NY | A | Packard - Erie St 115 kV | NM-NG | 0 | 3/31/18 |  | Withdrawn
661 | Solar Liberty Energy Systems, Inc. | Eden Evans Rd | 2017-09-07 | 18 | 18 | S | Angola, NY | A | Shelton - Angola 34.5kV | NM-NG | 0 | 3/31/18 |  | Withdrawn
662 | EDP Renewables North America LLC | Coldwater Solar | 2017-09-07 | 80 | 80 | S | Chautauqua, NY | A | Dunkirk - Gardenville 115kV | NM-NG | 0 | 4/30/19 |  | Withdrawn
663 | Solar Liberty Energy Systems, Inc. | Main St | 2017-09-08 | 10.8 | 10.8 | S | York, NY | A | Golah - South Perry 69 kV | NM-NG/NYSEG | 0 | 3/31/18 |  | Withdrawn
664 | South Cooper Solar LLC | South Cooper Solar | 2017-09-14 | 20 | 20 | S | Hinsdale, NY | A | Five Mile - Gardenville 115 kV | NM-NG | 0 | 5/31/18 |  | Withdrawn
665 | Forest Glen Solar LLC | Forest Glen Solar | 2017-09-14 | 20 | 20 | S | Allegany, NY | A | Five Mile - Homer Hill 115kV | NM-NG | 0 | 3/31/18 |  | Withdrawn
672 | LS Power Development, LLC | Helix Ravenswood I | 2017-10-06 | 30.2 | 30.2 | CT-NG | New York, NY | J | Rainey Substation 345kV | ConEd | 0 | 9/30/18 |  | Withdrawn
673 | LS Power Development, LLC | Helix Ravenswood II | 2017-10-06 | 72.4 | 72.4 | CT-NG | New York, NY | J | Rainey Substation 345kV | ConEd | 0 | 9/30/18 |  | Withdrawn
674 | Helix Ravenswood, LLC | Vernon Battery Storage I | 2017-10-24 | 10 | 10 | ES | Queens, NY | J | Vernon Substation | ConEd | 0 | 8/31/18 |  | Withdrawn
675 | Helix Ravenswood, LLC | Vernon Battery Storage II | 2017-10-24 | 10 | 10 | ES | Queens, NY | J | Vernon Substation | ConEd | 0 | 8/31/18 |  | Withdrawn
676 | Granada Solar, LLC | Regan Solar | 2017-10-25 | 20 | 20 | S | Guilford, NY | C | Guilford 46kV | NYSEG | 0 | 3/31/18 |  | Withdrawn
677 | Granada Solar, LLC | Grange Solar | 2017-10-25 | 20 | 20 | S | Nanticoke, NY | C | Vincent Cors 34.5kV | NYSEG | 0 | 1/31/18 |  | Withdrawn
681 | Granada Solar, LLC | Magruder Solar | 2018-01-02 | 20 | 20 | S | Gardiner, NY | G | Modena - Galeville 115kV | CHGE | 0 | 2/28/18 |  | Withdrawn
685 | sPower Development Company, LLC | EPCAL 1 | 2018-01-19 | 20 | 20 | S | Suffolk, NY | K | Riverhead - Brookhaven 138kV | LIPA | 0 | 4/30/18 |  | Withdrawn
687 | sPower Development Company, LLC | EPCAL 2 | 2018-01-29 | 150 | 150 | S | Suffolk, NY | K | Edwards - Brookhaven 69kV | LIPA | 0 | 6/30/18 |  | Withdrawn
688 | EDF Renewable Development Inc. | East Walden Solar | 2018-02-02 | 20 | 20 | S | Orange, NY | G | East Waldon Sutbation | CHGE | 0 | 3/31/18 |  | Withdrawn
689 | EDF Renewable Development Inc. | Goshen Solar | 2018-02-02 | 20 | 20 | S | Orange, NY | G | Huntley Station 115kV | O&R | 0 | 3/31/18 |  | Withdrawn
690 | EDF Renewable Development Inc. | Slate Hill 1 Solar | 2018-02-02 | 20 | 20 | S | Orange, NY | G | Shoemaker - Westtown | O&R | 0 | 3/31/18 |  | Withdrawn
691 | EDF Renewable Development Inc. | Slate Hill 2 Solar | 2018-02-02 | 20 | 20 | S | Orange, NY | G | Shoemaker - Westtown | O&R | 0 | 3/31/18 |  | Withdrawn
692 | Consolidated Edison Company of New York, Inc. | Astoria Storage on Demand | 2018-02-07 | 15 | 15 | ES | Queens, NY | J | North Queens Substation | ConEd | 0 | 3/31/18 |  | Withdrawn
705 | Oya Solar NY, LP | Chaumont Solar | 2018-04-10 | 160 | 160 | S | Sullivan, NY | G | Thousand Island - Coffeen 115kV | NM-NG | 0 | 7/31/18 |  | Withdrawn
707 | PSEG Power New York LLC | Bethlehem Battery | 2018-05-04 | 10 | 10 | ES | Albany, NY | F | Albany Substation 115kV | NM-NG | 0 | 11/30/18 |  | Withdrawn
708 | PSEG Power New York LLC | Bethlehem Solar | 2018-05-04 | 1 | 1 | S | Albany, NY | F | 13.2kV Substation | NM-NG | 0 | 6/30/18 |  | Withdrawn
711 | Somerset Solar Development LLC | Somerset Solar | 2018-05-31 | 19.9 | 19.9 | S | Monroe, NY | B | Kintigh Substation 345 kV | NYSEG | 0 | 10/31/18 |  | Withdrawn
712 | Cayuga Solar LLC | Cayuga Solar | 2018-05-31 | 19.9 | 19.9 | S | Tomkins, NY | C | Milliken Substation 34.5kV | NYSEG | 0 | 11/30/18 |  | Withdrawn
714 | EDF Renewables Development, Inc. | Edora C Solar Energy Center | 2018-06-01 | 20 | 20 | S | Orange, NY | G | Shoemaker-Westtown 69kV | O&R | 0 | 7/31/19 |  | Withdrawn
723 | Lyonsdale Biomass, LLC | Lyonsdale Solar | 2018-06-08 | 19.9 | 19.9 | S | Lewis, NY | E | Lyonsdale Substation 115kV | NM-NG | 0 | 4/30/19 |  | Withdrawn
724 | Brewster Solar, LLC | Brewster Solar | 2018-06-08 | 24.98 | 24.98 | S | Putnam, NY | G | Pawling - Croton Falls 115kV | NYSEG | 0 | 11/30/18 |  | Withdrawn
725 | York Solar, LLC | York Solar | 2018-06-08 | 24.9 | 24.9 | S | Livingston, NY | A | Line #863 - 69kV | NM-NG | 0 | 11/30/18 |  | Withdrawn
726 | Niagara Falls Solar, LLC | Niagara Falls Solar | 2018-06-08 | 24.9 | 24.9 | S | Niagara, NY | A | Line #181 - 115kV | NM-NG | 0 | 9/30/18 |  | Withdrawn
727 | Alden Solar, LLC | Alden Solar | 2018-06-11 | 24.9 | 24.9 | S | Erie, NY | A | Cold Springs - Pulteny 34.5kV | NYSEG | 0 | 9/30/18 |  | Withdrawn
728 | EDF Renewables Development, Inc. | Champlain Solar | 2018-06-11 | 20 | 20 | S | Clinton, NY | E | Mason Corners-Sciota Flatrock 115kV | NYSEG | 0 | 7/31/18 |  | Withdrawn
729 | EDF Renewables Development, Inc. | Quiet Meadows Solar | 2018-06-11 | 20 | 20 | S | Oneida, NY | E | Oneida - Oneida Energy 115kV | NM-NG | 0 | 8/31/18 |  | Withdrawn
732 | Machias Solar, LLC | Machias Solar | 2018-06-11 | 20 | 20 | S | Cattaraugus, NY | A | Fivemile - Gardenville 115kV | NM-NG | 0 | 12/31/18 |  | Withdrawn
733 | Arcade Solar, LLC | Arcade Solar | 2018-06-11 | 19.9 | 19.9 | S | Wyoming, NY | A | Arcade - Bliss 115kv | Village of Arcade | 0 | 11/30/18 |  | Withdrawn
736 | Empire State Solar, LLC | Meads Hill Solar | 2018-06-12 | 20 | 20 | S | Schuyler, NY | C | Montour Falls - Greenidge 115kV | NYSEG | 0 | 11/30/18 |  | Withdrawn
739 | Hecate Energy Cody Road LLC | Cody Road | 2018-06-12 | 19.92 | 19.92 | W | Madison, NY | C | Fenner - Cortland 115kV | NM-NG | 0 | 7/31/19 |  | Withdrawn
743 | Invenergy Solar Development North America LLC | Hornell Solar | 2018-07-16 | 20 | 20 | S | Steuben, NY | C | Bennett 34.5kV | NYSEG | 0 | 10/31/19 |  | Withdrawn
747 | White Creek Solar LLC | White Creek Solar | 2018-07-30 | 100 | 100 | S | Livingston, NY | A | Jones - Mortimer 115kV | NM-NG | 0 | 10/31/18 |  | Withdrawn
749 | KCE NY 11 LLC | KCE NY 11 | 2018-08-10 | 20 | 20 | ES | Orange, NY | G | Coldenham Substation 115kV | CHGE | 0 | 2/28/19 |  | Withdrawn
750 | Calpine Mid Atlantic Development, LLC | Bethpage Storage | 2018-08-14 | 50 | 50 | ES | Nassau, NY | K | Grumman Substation 69kV | LIPA | 0 | 5/31/19 |  | Withdrawn
752 | Granada Solar, LLC (Conti) | Goldenrod Solar | 2018-08-15 | 90 | 90 | S | Herkimer, NY | E | Meco - Rotterdam 115 kV | NM-NG | 0 | 10/31/18 |  | Withdrawn
753 | Granada Solar, LLC (Conti) | Blue Star Solar | 2018-08-15 | 100 | 100 | S | Washington, NY | F | Mohican - Luther Forest 115kV | NM-NG | 0 | 10/31/18 |  | Withdrawn
757 | Granada Solar, LLC | Monarda Solar | 2018-08-29 | 20 | 20 | S | Herkimer, NY | E | Meco - Rotterdam 115 kV | NM-NG | 0 | 12/31/18 |  | Withdrawn
761 | Invenergy Solar Development LLC | Athens Energy Center | 2018-09-17 | 100 | 100 | - | Greene County, NY | G | New Scotland - North Catskill 115kV | NM-NG | 0 | 10/31/18 |  | Withdrawn
771 | Mistral Wind LLC | Mistral Wind Alternative | 2018-10-10 | 20 | 20 | W | Genesee, NY | B | N. Akron - Attica 34.5 kV | NM-NG | 0 | 9/30/19 |  | Withdrawn
772 | Hollyhock Solar, LLC | Hollyhock Solar | 2018-10-15 | 20 | 20 | S | Albany, NY | F | Leeds - New Scotland 115kV | NM-NG | 0 | 12/31/18 |  | Withdrawn
773 | Charboneau Solar, LLC | Charboneau Solar | 2018-10-15 | 20 | 20 | S | Essex, NY | F | Ticonderoga - Hague Road 115kV | NM-NG | 0 | 4/30/19 |  | Withdrawn
793 | esVolta, LP | Ladybug Energy Storage | 2019-02-06 | 75 | 75 | ES | Westchester, NY | I | Sprainbrook Substation | ConEd | 0 | 7/31/19 |  | Withdrawn
794 | esVolta, LP | Bluebird Energy Storage | 2019-02-06 | 40 | 40 | ES | Westchester, NY | I | Dunwoodie Substation | ConEd | 0 | 7/31/19 |  | Withdrawn
795 | esVolta, LP | Appleseed Energy Storage | 2019-02-06 | 50 | 50 | ES | Greene, NY | G | Leeds Substation | NM-NG | 0 | 7/31/19 |  | Withdrawn
817 | Quogue Energy Storage, LLC | Quogue Energy Storage | 2019-04-12 | 19.95 | 19.95 | ES | Suffolk, NY | K | Quogue Substation 69kV | LIPA | 0 | 6/30/19 |  | Withdrawn
818 | Setauket Energy Storage, LLC | Port Jeff 1-Terryville Energy Storage | 2019-04-15 | 19.95 | 19.95 | ES | Suffolk, NY | K | Port Jefferson - Terryville 69kV | LIPA | 0 | 6/30/19 |  | Withdrawn
819 | Setauket Energy Storage, LLC | Port Jeff 2-Terryville Energy Storage | 2019-04-15 | 19.95 | 19.95 | ES | Suffolk, NY | K | Port Jefferson - Terryville 69kV | LIPA | 0 | 6/30/19 |  | Withdrawn
820 | Setauket Energy Storage, LLC | Port Jeff 2-Stony Brook Energy Storage | 2019-04-15 | 19.95 | 19.95 | ES | Suffolk, NY | K | Port Jefferson - Stony Brook 69kV | LIPA | 0 | 6/30/19 |  | Withdrawn
821 | Setauket Energy Storage, LLC | Port Jeff -Mt. Sinai Energy Storage | 2019-04-15 | 19.95 | 19.95 | ES | Suffolk, NY | K | Port Jefferson - Mt. Sinai 69kV | LIPA | 0 | 6/30/19 |  | Withdrawn
829 | NRG Arthur Kill Storage LLC | Arthur Kill Energy Storage 2 | 2019-04-24 | 60 | 60 | ES | Richmond, NY | J | Arthur Kill 138kV | ConEd | 0 | 9/30/19 |  | Withdrawn
838 | NRG Astoria Storage LLC | Astoria Energy Storage 3 | 2019-05-09 | 20 | 20 | ES | Queens, NY | J | Astoria East 138kV Substation | ConEd | 0 | 8/31/19 |  | Withdrawn
839 | NRG Astoria Storage LLC | Astoria Energy Storage 4 | 2019-05-09 | 20 | 20 | ES | Queens, NY | J | Astoria West 138kV Substation | ConEd | 0 | 8/31/19 |  | Withdrawn
854 | Boralex US Development, LLC | NY16 Energy Storage | 2019-05-24 | 4 | 4 | ES | Washington, NY | F | Battenkill - Mohican 115kV | NM-NG | 0 | 9/30/19 |  | Withdrawn
856 | Boralex US Development, LLC | NY13 Energy Storage | 2019-05-24 | 4 | 4 | ES | Washington, NY | F | Battenkill - Mohican 115kV | NM-NG | 0 | 9/30/19 |  | Withdrawn
884 | Dimension NY 1 LLC | Blooming Farm LLC | 2019-06-12 | 10.234 | 10.234 | ES | Orange, NY | G | Blooming Grove Substation 69kV | O&R | 0 | 9/30/19 |  | Withdrawn
886 | Empire State Land Holdings, LLC | Turin Highlands Solar | 2019-06-12 | 20 | 20 | S | Oneida, NY | E | Taylorville - Boonville 115kV | NM-NG | 0 | 7/31/19 |  | Withdrawn
889 | Energy Storage Resources, LLC | Peconic River II | 2019-06-20 | [7 empty] | 0 | 9/30/19 |  | Withdrawn
890 | Energy Storage Resources, LLC | Queen City | 2019-06-20 | [7 empty] | 0 | 9/30/19 |  | Withdrawn
891 | Energy Storage Resources, LLC | Meredith Woods | 2019-06-24 | [7 empty] | 0 | 9/30/19 |  | Withdrawn
896 | Sky Solar Inc. | Hornell Center 16 BESS | 2019-07-18 | [7 empty] | 0 | 10/31/19 |  | Withdrawn
897 | Mitsubishi Hitachi Power Systems Americas, Inc. | Bluejay Solar | 2019-08-01 | 5 | 5 | S |  |  |  | NYSEG | 0 | 10/31/19 |  | Withdrawn