## Interconnection Queue
Queue Pos. | Developer/Interconnection Customer | Project Name | Date of IR | SP (MW) | WP (MW) | Record Type | Type/ Fuel | Energy Storage Capability | Minimum_Duration Full Discharge | County | State | NYISO Zone | Points of Interconnection | Utility | Affected Transmission Owner (ATO) | Project Status # | Last Updated Date | Availability of Studies | IA Tender Date | CY/FS Complete Date | Proposed In-Service/Initial Backfeed Date | Proposed Sync Date | Proposed COD
0276 | Homer Solar Energy Center LLC | Homer Solar Energy Center | 2008-01-30 | 90 | 90 | Large Facility | S |  |  | Cortland | NY | C | Cortland - Fenner 115kV | NM-NG |  | 11 | 2026-05-31 | FES, SRIS, FS | 2021-02-08 | 2021-02-08 | 04-2028 | 04-2028 | 06-2028
0495 | Mohawk Solar LLC | Mohawk Solar | 2015-04-02 | 90.5 | 90.5 | Large Facility | S |  |  | Montgomery | NY | F | St. Johnsville - Marshville 115kV | NM-NG |  | 11 | 2025-09-30 | FES, SRIS, FS | 2021-02-08 | 2021-02-08 | 06/2027 | 10/2027 | 11/2027
0519 | Canisteo Wind Energy LLC | Canisteo Wind | 2015-11-02 | 290.7 | 290.7 | Large Facility | W |  |  | Steuben | NY | C | Bennett 115kV | NYSEG |  | 11 | 2025-03-31 | FES, SRIS, FS | 2021-02-08 | 2021-02-08 | 02-2028 | 02-2028 | 05-2028
0522 | NYC Energy LLC | NYC Energy | 2015-12-16 | 79.9 | 79.9 | Large Facility | ES | 319.6 | 4 | Kings | NY | J | Hudson Avenue East 138kV | ConEd |  | 12 | 2026-06-30 | FES, SRIS, FS | 2024-05-15 | 2024-12-16 | 05-2027 | 05-2027 | 06-2027
0535 | Riverhead Solar 2, LLC | Riverhead Solar 2 | 2016-02-23 | 36 | 36 | Large Facility | S |  |  | Suffolk | NY | K | Edwards 138kV | LIPA |  | 11 | 2024-09-30 | FES, SRIS, FS | 2021-02-08 | 2021-02-08 | 09-2027 | 12-2027 | 01-2028
0564 | Rock District Solar, LLC | Rock District Solar | 2016-07-25 | 20 | 20 | Small Generation | S |  |  | Schoharie | NY | F | Sharon - Cobleskill 69kV | NM-NG |  | 11 | 2026-06-30 | SIS, FS | 2020-07-10 | 2020-06-03 | 01-2027 | 12-2026 | 02-2027
0571 | Heritage Wind, LLC | Heritage Wind | 2016-09-01 | 126 | 126 | Large Facility | W |  |  | Genesee | NY | B | Lockport - Mortimer 115kV | NM-NG |  | 11 | 2025-09-30 | FES, SRIS, FS | 2023-01-11 | 2023-01-11 | 05-2027 | 08-2027 | 10-2027
0572 | Hecate Energy Greene 1 LLC | Greene County 1 | 2016-09-06 | 20 | 20 | Small Generation | S |  |  | Greene | NY | G | Coxsackie - North Catskill 69kV | CHG&E |  | 11 | 2025-05-31 | SIS, FS | 2020-02-18 | 2020-01-24 | 05-2027 | 04-2027 | 06-2027
0573 | Hecate Energy Greene 2 LLC | Greene County 2 | 2016-09-06 | 10 | 10 | Small Generation | S |  |  | Greene | NY | G | Coxsackie 13.8kV | CHG&E |  | 11 | 2025-05-31 | SIS, FS | 2020-02-18 | 2020-01-24 | 05-2027 | 04-2027 | 06-2027
0575 | Little Pond Solar, LLC | Little Pond Solar | 2016-09-16 | 20 | 20 | Small Generation | S |  |  | Orange | NY | G | Mongaup - Shoemaker 69kV | O&R |  | 11 | 2026-06-30 | FES, SIS, FS | 2021-01-29 | 2020-12-16 | 07-2027 | 04-2026 | 09-2027
0581 | SunEast Hills Solar LLC | Hills Solar | 2025-11-26 | 20 | 20 | Small Generation | S |  |  | Herkimer | NY | E | Fairfield - Inghams 115kV | NM-NG |  | 11 | 2026-06-30 | FES, SIS, FS | 2020-04-07 | 2020-02-11 | 01-2028 | 12-2027 | 04-2028
0584 | Dog Corners Solar NY LLC | Dog Corners Solar | 2025-11-25 | 20 | 20 | Small Generation | S |  |  | Cayuga | NY | C | Aurora 34.5kV | NYSEG |  | 12 | 2026-06-30 | SIS, FS | 2019-06-21 | 2019-05-08 | 08-2026 | 09-2026 | 01-2027
0586 | Watkins Road Solar NY LLC | Watkins Rd Solar | 2016-11-08 | 20 | 20 | Small Generation | S |  |  | Herkimer | NY | E | Watkins Rd - Ilion 115kV | NM-NG |  | 12 | 2026-06-30 | SIS, FS | 2020-02-18 | 2019-11-25 | 12-2026 | 11-2026 | 02-2027
0590 | Scipio Solar NY LLC | Scipio Solar | 2016-12-02 | 18 | 18 | Small Generation | S |  |  | Cayuga | NY | C | Scipio 34.5kV | NYSEG |  | 12 | 2026-06-30 | SIS, FS | 2019-05-22 | 2019-03-21 | 06-2027 | 06-2027 | 09-2027
0596 | Alle-Catt Wind Energy LLC | Alle Catt II Wind | 2017-01-04 | 339.1 | 339.1 | Large Facility | W |  |  | Cattaraugus | NY | A | Stolle Rd - Five Mile Rd 345kV | NM-NG |  | 12 | 2026-05-31 | SRIS, FS | 2021-02-08 | 2021-02-08 | 09-2026 | 09-2026 | 12-2026
0617 | Watkins Glen Solar Energy Center, LLC | Watkins Glen Solar | 2017-03-27 | 50 | 50 | Large Facility | S |  |  | Schuyler | NY | C | Bath - Montour Falls 115kV | NYSEG |  | 11 | 2025-01-31 | SRIS, FS | 2020-12-04 | 2021-02-08 | 03-2028 | 04/2028 | 04-2028
0620 | Gateway Solar Energy Center, LLC | Gateway Solar Energy Center | 2017-03-27 | 180 | 180 | Large Facility | S |  |  | St. Lawrence | NY | D | Massena - Moses 230kV | NYPA |  | 11 | 2025-02-28 | FES, SRIS, FS | 2021-02-08 | 2021-02-08 | 02-2028 | 02-2028 | 04-2028
0637 | Flint Mine Solar LLC | Flint Mine Solar | 2017-06-29 | 100 | 100 | Large Facility | S |  |  | Greene | NY | G | LaFarge - Pleasant Valley 115kV, Feura Bush - North Catskill 115kV | NM-NG |  | 11 | 2026-06-30 | FES, SRIS, FS | 2021-02-08 | 2021-02-08 | 12-2027 | 12-2027 | 04-2028
0644 | Hecate Energy Columbia County 1, LLC | Columbia County 1 | 2017-07-26 | 60 | 60 | Large Facility | S |  |  | Columbia | NY | F | Craryville 115kV | NYSEG |  | 11 | 2024-06-30 | FES, SRIS, FS | 2021-02-08 | 2021-02-08 | 12-2026 | 12-2026 | 2-2027
0670 | SunEast Skyline Solar LLC | SunEast Skyline Solar LLC | 2017-09-21 | 20 | 20 | Small Generation | S |  |  | Westmoreland | NY | E | Campus Rd - Clinton 46kV | NM-NG |  | 11 | 2023-07-31 | FES, SIS, FS | 2020-08-13 | 2020-07-31 | 11/2027 | 10/2027 | 4/2028
0683 | KCE NY 2, LLC | KCE NY 2 | 2018-01-18 | 200 | 200 | Large Facility | ES | 800 | 4 | Montgomery | NY | G | Coldenham 115kV | CHG&E |  | 11 | 2026-06-30 | SRIS, FS | 2021-03-16 | 2021-02-08 | 05-2027 | 05-2027 | 06-2027
0704 | Bear Ridge Solar, LLC | Bear Ridge Solar | 2018-03-20 | 100 | 100 | Large Facility | S |  |  | Niagara | NY | A | Mountain- Lockport 115kV | NM-NG |  | 11 | 2025-02-28 | SRIS, FS | 2021-02-08 | 2021-02-08 | 12-2027 | 04-2028 | 04-2028
0710 | Horseshoe Solar Energy LLC | Horseshoe Solar | 2018-05-29 | 180 | 180 | Large Facility | S |  |  | Livingston | NY | B | Golah 115kV | NM-NG |  | 11 | 2025-10-31 | FES, FS | 2023-01-11 | 2023-01-11 | 02-2028 | 02-2028 | 05-2028
0716 | Moraine Solar Energy Center, LLC | Moraine Solar Energy Center | 2018-06-04 | 93.5 | 93.5 | Large Facility | S |  |  | Allegany | NY | C | Moraine 115kV | NYSEG |  | 11 | 2025-10-31 | FES, SRIS, FS | 2025-01-14 | 2024-12-16 | 08-2028 | 08-2028 | 09-2028
0720 | Trelina Solar Energy Center, LLC | Trelina Solar Energy Center | 2018-06-07 | 79.8 | 79.8 | Large Facility | S |  |  | Seneca | NY | C | Border City - Station 168 115 KV | NYSEG |  | 11 | 2025-01-31 | SRIS, FS | 2021-02-08 | 2021-02-08 | 04-2028 | 03-2028 | 04-2028
0721 | Excelsior Energy Center, LLC | Excelsior Energy Center | 2018-06-07 | 280 | 280 | Large Facility | S |  |  | Genesee | NY | B | Dysinger - N. Rochester 345kV | NYPA |  | 12 | 2026-05-31 | SRIS, FS | 2021-01-22 | 2021-02-08 | 09-2026 | 09-2026 | 11-2026
0734 | ELP Ticonderoga Solar LLC | Ticonderoga Solar | 2018-06-12 | 20 | 20 | Small Generation | S |  |  | Essex | NY | F | Ticonderoga 115kV - Republic Line 2 | NM-NG |  | 11 | 2026-01-31 | FES, SIS, FS | 2021-03-18 | 2021-07-31 | 11-2026 | 02-2025 | 12-2026
0737 | Empire Offshore Wind LLC | Empire Wind 1 | 2018-06-12 | 816 | 816 | Large Facility | OSW |  |  | Kings | NY | J | Gowanus 345kV | ConEd |  | 12 | 2026-06-30 | SRIS, FS | 2021-02-08 | 2021-02-08 | 08-2026 | 10-2026 | 09-2027
0766 | Sunrise Wind LLC | Sunrise Wind | 2018-09-28 | 880 | 880 | Large Facility | OSW |  |  | Suffolk | NY | K | Holbrook 138kV & West Bus 138kV | LIPA |  | 12 | 2026-06-30 | SRIS, FS | 2023-01-11 | 2023-01-11 | 06-2025 | 10-2026 | 10-2027
0774 | Tracy Solar Energy Center, LLC | Tracy Solar Energy Center | 2018-10-18 | 119 | 119 | Large Facility | S |  |  | Jefferson | NY | E | Thousand Island - Lyme 115kV | NM-NG |  | 11 | 2025-12-31 | SRIS, FS |  | 2024-12-16 | 08-2028 | 08-2028 | 12-2028
0777 | White Creek Solar, LLC | White Creek Solar | 2018-11-01 | 135 | 135 | Large Facility | S |  |  | Livingston | NY | B | Sta 82 - Sta 128 115kV | RG&E |  | 11 | 2025-10-31 | SRIS, FS | 2024-06-28 | 2024-12-16 | 04-2028 | 05-2028 | 06-2028
0783 | ConnectGen Chautauqua County LLC | South Ripley Solar and BESS | 2018-12-07 | 270 | 270 | Large Facility | CR | 80 | 4 | Chautauqua | NY | A | South Ripley Substation 230kV | NM-NG |  | 11 | 2026-06-30 | FES, SRIS, FS | 2023-01-11 | 2023-01-11 | 07-2027 | 07-2027 | 12-2027
0800 | Rich Road Solar Energy Center, LLC | Rich Road Solar Energy Center | 2019-02-20 | 240 | 240 | Large Facility | CR |  | 4 | St. Lawrence | NY | E | Moses - Adirondack 230 kV Line #2 (MA2) | NYPA |  | 10 | 2025-01-31 | FES, SRIS, FS |  | 2024-12-16 | 10-2027 | 10-2027 | 04-2028
0801 | Prattsburgh Wind, LLC | Prattsburgh Wind Farm | 2019-02-21 | 147 | 147 | Large Facility | W |  |  | Steuben | NY | C | Stoney Ridge - Canadaigua 230kV | NYSEG |  | 11 | 2026-06-30 | SRIS, FS | 2023-01-11 | 2023-01-11 | 06-2027 | 06-2027 | 09-2027
0804 | KCE NY 10, LLC | KCE NY 10 | 2019-03-22 | 20 | 20 | Small Generation | ES | 80 | 4 | Erie | NY | A | Erie Substation 34.5kV | NYSEG |  | 11 | 2026-01-31 | FES, SIS, FS | 2022-10-20 | 2022-04-28 | 08-2026 | 08-2026 | 10-2026
0805 | Oxbow Hill Solar, LLC | Oxbow Hill Solar | 2019-03-22 | 140 | 140 | Large Facility | S |  |  | Madison | NY | C | Fenner 115kV Substation | NM-NG |  | 10 | 2026-07-31 | FES, FS | 2023-02-09 | 2023-01-11 | 03-2029 | 06-2029 | 06-2029
0811 | Hecate Energy Cider Solar LLC | Cider Solar | 2019-04-03 | 500 | 500 | Large Facility | S |  |  | Genesee | NY | B | Dysinger - New Rochester 345kV | NYPA | NextEra | 12 | 2026-06-30 | SRIS, FS | 2023-01-11 | 2023-01-11 | 05-2026 | 05-2026 | 01-2027
0815 | Bayonne Energy Center III, LLC | Bayonne Energy Center III | 2019-04-05 | 49.8 | 49.8 | Large Facility | ES | 199.2 | 4 | Kings | NY | J | Gowanus 345kV | ConEd |  | 12 | 2026-05-31 | SRIS, FS | 2023-04-25 | 2023-01-11 | 05-2027 | 06-2027 | 07-2027
0827 | Lighthouse Arthur Kill, LLC | Arthur Kill Energy Storage 1 | 2019-04-22 | 15 | 15 | Small Generation | ES | 60 | 4 | Richmond | NY | J | Fresh Kills 13.8kV | ConEd |  | 12 | 2026-02-28 | FS | 2022-07-07 | 2022-01-20 | 04-2026 | 04-2026 | 12-2026
0828 | Valley Solar NY LLC | Valley Solar | 2019-04-24 | 20 | 20 | Small Generation | S |  |  | Tioga | NY | C | Owego 34.5kV Substation | NYSEG |  | 12 | 2026-06-30 | SIS, FS | 2021-01-22 | 2020-11-03 | 01-2027 | 01-2027 | 01-2027
0832 | Hawthorn Solar, LLC | CS Hawthorn Solar | 2019-05-06 | 20 | 20 | Small Generation | S |  |  | Rensselaer | NY | F | North Troy - Hoosick 115kV | NM-NG |  | 11 | 2026-04-30 | FES, FS | 2022-07-13 | 2022-06-27 | 01-2027 | 02-2027 | 03-2027
0833 | Dolan Solar, LLC | Dolan Solar | 2019-05-06 | 20 | 20 | Small Generation | S |  |  | Washington | NY | F | Battenkill - Mohican 115kV | NM-NG |  | 11 | 2026-04-30 | SIS, FS | 2021-04-13 | 2021-03-01 | 08-2027 | 09-2027 | 09-2027
0834 | Eastern Generation, LLC | Luyster Creek Energy Storage 2 | 2019-05-07 | 79 | 79 | Large Facility | ES | 316 | 4 | Queens | NY | J | Astoria West 138kV | ConEd |  | 10 | 2026-06-30 | SRIS, FS |  | 2024-12-16 | 02-2028 | 03-2027 | 04-2028
0835 | Eastern Generation, LLC | Luyster Creek Energy Storage 1 | 2019-05-07 | 56.3 | 57.3 | Large Facility | ES | 225 | 4 | Queens | NY | J | Astoria West 138kV | ConEd |  | 11 | 2026-06-30 | SRIS, FS | 2023-02-22 | 2023-01-11 | 02-2028 | 03-2028 | 04-2028
0843 | Greens Corners Solar LLC | NY37 Solar | 2025-12-02 | 20 | 20 | Small Generation | S |  |  | Jefferson | NY | E | Coffeen - West Adams 115kV Substation | NM-NG |  | 11 | 2026-08-31 | SIS, FS | 2023-05-17 | 2023-04-04 | 07-2028 | 07-2028 | 09-2028
0863 | Highbanks Solar LLC | Highbanks Solar | 2019-05-29 | 12.5 | 12.5 | Small Generation | S |  |  | Livingston | NY | B | S158 High banks 34.5 kV | RG&E |  | 10 | 2026-06-30 | SIS, FS | 2022-10-17 | 2022-08-05 | 08-2029 | 08-2029 | 09-2029
0864 | Greens Corners Solar LLC | NY38 Solar | 2019-05-29 | 120 | 120 | Large Facility | S |  |  | Jefferson | NY | E | Coffeen - West Adams 115kV | NM-NG |  | 11 | 2026-02-28 | SRIS, FS | 2023-01-11 | 2023-01-11 | 02-2028 | 02-2028 | 04-2028
0865 | Flat Hill Solar NY LLC | Flat Hill Solar | 2019-05-31 | 20 | 20 | Small Generation | S |  |  | Herkimer | NY | E | Inghams-Valley 46kV Line 27 | NM-NG |  | 12 | 2026-06-30 | SIS, FS | 2022-09-15 | 2022-08-19 | 06-2027 | 05-2027 | 08-2027
0880 | Brookside Solar, LLC | Brookside Solar | 2019-06-10 | 100 | 100 | Large Facility | S |  |  | Franklin | NY | D | Chateaugay - Willis 115kV | NYSEG |  | 11 | 2026-01-31 | SRIS, FS |  | 2024-12-16 | 12-2027 | 12-2027 | 12-2027
0882 | Riverside Solar, LLC | Riverside Solar | 2019-06-10 | 100 | 100 | Large Facility | S |  |  | Jefferson | NY | E | Lyme Substation 115kV | NM-NG |  | 10 | 2025-01-31 | FES, SRIS, FS | 2025-03-18 | 2024-12-16 | 09-2027 | 09-2027 | 12-2027
0883 | Garnet Energy Center, LLC | Garnet Energy Center | 2019-06-11 | 200 | 200 | Large Facility | S |  |  | Cayuga | NY | B | Pannell - Clay 345kV | NYPA |  | 11 | 2025-02-28 | FS | 2023-01-11 | 2023-01-11 | 11-2027 | 11-2027 | 04-2028
0885 | Grassy Knoll Solar NY LLC | Grassy Knoll Solar | 2019-06-12 | 20 | 20 | Small Generation | S |  |  | Herkimer | NY | E | Watkins Rd - Inghams 115kV | NM-NG |  | 11 | 2026-06-30 | SIS, FS | 2022-09-15 | 2022-08-15 | 01-2028 | 02-2028 | 05-2028
0899 | Sithe/Independence Power Partners, LP | Scriba-Volney Series Reactor | 2019-08-02 | N/A | N/A | Transmission Interconnection | AC |  |  | Oswego | NY | C | Volney - Scriba 345 kV | NM-NG |  | 11 | 2025-05-31 | SIS |  |  | 11-2026 | N/A | N/A
0907 | Harlem River ESS, LLC | Harlem River Yard | 2019-09-04 | 79.9 | 79.9 | Large Facility | ES | 319.6 | 4 | Queens | NY | J | Hell Gate 138kV | NYPA |  | 10 | 2025-02-28 | SRIS, FS | 2023-02-10 | 2023-01-11 | 11-2027 | 11-2027 | 01-2028
0930 | Eastern Generation, LLC | Luyster Creek Energy Storage 3 | 2019-10-25 | 15 | 15 | Small Generation | ES | 60 | 4 | Queens | NY | J | North Queens 27kV | ConEd |  | 10 | 2025-03-31 | SIS, FS |  | 2024-04-16 | 01-2027 | 01-2027 | 03-2027
0931 | East River ESS, LLC | Astoria Energy Storage | 2019-10-28 | 100 | 100 | Large Facility | ES | 400 | 4 | Queens | NY | J | Astoria West 138kV | ConEd |  | 12 | 2026-08-31 | SRIS, FS | 2023-01-11 | 2023-01-11 | 05-2026 | 06-2026 | 10-2026
0932 | Hatchery Solar LLC | Hatchery Solar | 2019-10-29 | 20 | 20 | Small Generation | S |  |  | Livingston | NY | B | Caledonia - Golah 34.5 kV | NM-NG |  | 11 | 2026-03-31 | SIS, FS | 2025-01-07 | 2024-10-10 | 12-2028 | 11-2028 | 01-2029
0950 | Hemlock Ridge Solar LLC | Hemlock Ridge Solar | 2019-11-21 | 200 | 200 | Large Facility | S |  |  | Orleans | NY | B | Lockport - Mortimer 115kV | NM-NG |  | 11 | 2025-08-31 | SRIS, FS | 2024-08-20 | 2024-12-16 | 03-2028 | 03-2028 | 04-2028
0953 | Sugar Maple Solar, LLC | Sugar Maple Solar | 2019-12-05 | 125 | 125 | Large Facility | S |  |  | Lewis | NY | E | North Carthage - Taylorville #8 and Black River - Taylorville #2 115kV | NM-NG |  | 10 | 2025-01-31 | SRIS, FS |  | 2024-12-16 | 09-2027 | 09-2027 | 12-2027
0956 | Holtsville Energy Storage, LLC | Holtsville 138kV Energy Storage | 2019-12-10 | 110 | 110 | Large Facility | ES | 2380 | 8 | Suffolk | NY | K | West Bus 138 kV | LIPA |  | 11 | 2026-06-30 | SRIS, FS | 2023-01-11 | 2023-01-11 | 02-2028 | 03-2028 | 05-2028
0967 | KCE NY 5 LLC | KCE NY 5 | 2019-12-27 | 94 | 94 | Large Facility | ES | 376 | 4 | Ulster | NY | G | Ohioville 115 kV | CHG&E |  | 10 | 2026-08-31 | SRIS, FS |  | 2024-12-16 | 08-2029 | 08-2029 | 01-2030
0971 | East Setauket Energy Storage, LLC | East Setauket Energy Storage | 2020-01-10 | 125 | 125 | Large Facility | ES | 2383.6 | 8 | Suffolk | NY | K | Holbrook - Miller Place 138kV | LIPA |  | 10 | 2025-02-28 | FS | 2024-03-06 | 2025-02-11 | 02-2027 | 03-2027 | 04-2027
0987 | Sunrise Wind LLC | Sunrise Wind II | 2020-01-29 | 44 | 44 | Large Facility | OSW |  |  | Suffolk | NY | K | Holbrook 138kV | LIPA |  | 12 | 2026-06-30 | FS | 2023-01-11 | 2023-01-11 | 06-2025 | 10-2026 | 10-2027
0995 | Alabama Solar Park LLC | Alabama Solar Park LLC | 2020-02-27 | 130 | 130 | Large Facility | S |  |  | Genesee | NY | B | Lockport - Batavia 115kV (Line#112) | NM-NG |  | 10 | 2025-01-31 | FS |  | 2024-12-16 | 07-2028 | 07-2028 | 10-2028
1000 | Flat Stone Solar NY LLC | Flat Stone Solar | 2020-03-18 | 20 | 20 | Small Generation | S |  |  | Oneida | NY | E | Oneida - Rome 115kV | NM-NG |  | 10 | 2026-06-30 | SIS, FS | 2024-05-21 | 2024-03-14 | 02-2028 | 03-2028 | 05-2028
1003 | Clear View Solar LLC | Clear View Solar | 2020-04-06 | 20 | 20 | Small Generation | S |  |  | Steuben | NY | C | Eelpot Road 34.5 kV | NYSEG |  | 11 | 2026-09-30 | SIS, FS | 2022-09-06 | 2022-07-08 | 07-2026 | 06-2026 | 08-2026
1007 | NYC Energy | NYC Energy LLC - Phase 2 | 2020-04-22 | 220.1 | 220.1 | Large Facility | ES | 880.4 | 4 | Kings | NY | J | Hudson Ave 138 kV | ConEd |  | 12 | 2026-06-30 | SRIS, FS |  | 2024-12-16 | 05-2027 | 05-2027 | 06-2027
1009 | Yellow Barn Solar, LLC | Yellow Barn Solar | 2020-04-30 | 160 | 160 | Large Facility | S |  |  | Tompkins | NY | C | Milliken - Etna 115 kV line #975 | NYSEG |  | 11 | 2026-08-31 | SRIS, FS | 2025-02-18 | 2024-12-16 | 10-2028 | 10-2028 | 11-2028
1015 | Somers Solar, LLC | Somers Solar, LLC | 2020-05-05 | 20 | 20 | Small Generation | S |  |  | Washington | NY | F | Mohican - Battenkill 115kV | NM-NG |  | 11 | 2026-01-31 | FS | 2024-02-20 | 2024-01-20 | 11-2027 | 09-2027 | 12-2027
1031 | ConnectGen Montgomery County LLC | Mill Point Solar | 2020-06-18 | 250 | 250 | Large Facility | CR | 700 | 4 | Montgomery | NY | E | Marcy - New Scotland 345kV | NM-NG |  | 10 | 2026-06-30 | SRIS, FS | 2025-02-21 | 2024-12-16 | 07-2028 | 07-2028 | 12-2028
1079 | Somerset Solar, LLC | Somerset Solar | 2020-08-18 | 125 | 125 | Large Facility | S |  |  | Niagara | NY | A | Kintigh 345 kV | NYSEG |  | 11 | 2025-08-31 | SRIS, FS | 2024-07-05 | 2024-12-16 | 05-2028 | 05-2028 | 06-2028
1080 | Mineral Basin Solar Power, LLC | Mineral Basin Solar Power | 2020-08-21 | 401.6 | 401.6 | Large Facility | S |  |  | Clearfield | PA | C | Homer City - Mainesburg 345KV | NYSEG |  | 10 | 2026-06-30 | SRIS, FS |  | 2024-12-16 | 03-2029 | 03-2029 | 12-2029
1113 | Caithness LI Energy Storage, LLC | CLIES 20 MW | 2020-11-18 | 20 | 20 | Small Generation | ES | 120 | 6 | Suffolk | NY | K | Sills Road 138 kV | LIPA |  | 10 | 2025-03-31 | SIS, FS | 2025-01-07 | 2024-06-21 | 12-2027 | 10-2027 | 12-2027
1117 | Caithness LI Energy Storage, LLC | CLIES 70MW | 2020-11-25 | 70 | 70 | Large Facility | ES | 420 | 6 | Suffolk | NY | K | Sills Road 138kV | LIPA |  | 10 | 2025-03-31 | SRIS, FS | 2025-05-05 | 2025-02-11 | 12-2027 | 12-2027 | 12-2027
1122 | East Fishkill Storage 1, LLC | East Fishkill | 2020-12-11 | 205 | 205 | Large Facility | ES | 800 | 4 | Dutchess | NY | G | Shenandoah 115kV | CHG&E |  | 11 | 2025-10-31 | SRIS, FS | 2025-01-22 | 2024-12-16 | 05-2029 | 06-2029 | 12-2029
1123 | KCE NY 29, LLC | KCE NY 29 | 2020-12-14 | 79 | 79 | Large Facility | ES | 600 | 4 | Suffolk | NY | K | Kings 138 kV | LIPA |  | 10 | 2026-03-31 | FS |  | 2024-12-16 | 06-2028 | 07-2028 | 08-2028
1130 | Hoffman Falls Wind LLC | Hoffman Falls Wind | 2021-01-27 | 72 | 72 | Large Facility | W |  |  | Madison | NY | C | Cortland - Fenner 115kV Line #3 | NM-NG |  | 11 | 2026-06-30 | FS | 2025-03-05 | 2024-12-16 | 02-2029 | 02-2029 | 04-2029
1148 | Agricola Wind LLC | Agricola Wind | 2021-03-10 | 97 | 97 | Large Facility | W |  |  | Cayuga | NY | C | Milliken to Wright Ave 115 kV line #973 | NYSEG |  | 11 | 2026-08-31 | SRIS, FS | 2025-03-05 | 2024-12-16 | 03-2029 | 02-2029 | 04-2029
1151 | York Run Solar, LLC | York Run Solar | 2021-03-18 | 90 | 90 | Large Facility | S |  |  | Chautauqua | NY | A | Falconer - Warren 115 kV line #171 | NM-NG |  | 11 | 2026-06-30 | SRIS, FS | 2025-02-19 | 2024-12-16 | 8-2028 | 07-2028 | 9-2028
1166 | BR Project 1 LLC | BR Benson Mines Solar | 2021-05-07 | 12.1 | 12.1 | Small Generation | S |  |  | St. Lawrence | NY | E | Brown's Falls to Newton Falls #22 34.5kV Line | NM-NG |  | 11 | 2025-12-31 | SIS, FS | 2025-03-17 | 2024-10-10 | 10-2027 | 10-2027 | 12-2027
1183 | Fort Covington Solar LLC | NY125A - Fort Covington Solar | 2021-05-20 | 250 | 250 | Large Facility | S |  |  | Franklin | NY | D | Moses-Willis 230 kV (MW1) | NYPA |  | 11 | 2025-09-30 | SRIS, FS | 2025-04-15 | 2024-12-16 | 05-2028 | 05-2028 | 07-2028
1184 | Two Rivers Solar Farm, LLC | NY125B - Two Rivers Solar | 2021-05-20 | 200 | 200 | Large Facility | S |  |  | St-Lawrence | NY | D | Moses-Willis 230kV (MW2) | NYPA |  | 11 | 2025-01-31 | SRIS, FS | 2025-04-15 | 2024-12-16 | 07-2028 | 07-2028 | 09-2028
1188 | North Seneca Solar Project | North Seneca Solar Project, LLC | 2021-05-27 | 90 | 90 | Large Facility | S |  |  | Seneca | NY | C | Hooks Road - Elbridge 115kV line#7 | NM-NG |  | 10 | 2025-01-31 | SRIS, FS | 2025-03-17 | 2024-12-16 | 06-2027 | 06-2027 | 09-2027
1237 | Sugar Maple Energy Storage, LLC | Sugar Maple Energy Storage | 2021-08-24 | 20 | 20 | Small Generation | ES | 80 | 4 | Jefferson | NY | E | North Carthage-Taylorville #8 and Black River-Taylorville #2 115 kV lines | NM-NG |  | 10 | 2026-07-31 | SIS | 2025-02-05 |  | 06-2028 | 09-2028 | 12-2028
1255 | Holtsville Brookhaven Battery Storage LLC | Holtsville Brookhaven Battery Storage | 2021-09-22 | 79.9 | 79.9 | Large Facility | ES | 159.8 | 2 | Suffolk | NY | K | Line 69-849 from West Yaphank to North Bellport | LIPA |  | 10 | 2026-01-31 | SRIS | 2025-04-16 |  | 08-2027 | 09-2027 | 10-2027
1257 | Edwards Calverton Battery Storage LLC | Edwards Calverton Battery Storage | 2021-09-22 | 60 | 60 | Large Facility | ES | 120 | 2 | Suffolk | NY | K | Edwards Avenue Substation at 138 kV | LIPA |  | 10 | 2026-01-31 | SRIS, FS | 2025-04-03 | 2025-02-11 | 09-2027 | 10-2027 | 11-2027
1289 | New York Power Authority / New York Transco LLC. | Propel NY Energy - Alternate Solution 5 | 2021-10-11 | N/A | N/A | Transmission Interconnection | AC |  |  | Nassau, Queens, Bronx, Westchester | NY | I; J; K | Sprain Brook 345 kV; Tremont 345 kV; East Garden City 345 kV; Barrett 138 kV; East Garden City 138 kV; Shore Road 138 kV; Syosset 138 kV; Ruland Rd 138 kV | LIPA, ConEd, NYPA |  | 9 | 2025-06-30 | SIS |  |  | 06/29-06/30
1308 | New York Power Authority | Richmond Spoke | 2021-12-02 | N/A | N/A | Transmission Interconnection | AC |  |  | Richmond | NY | J | Goethals - Gowanus 345 kV | ConEd |  | 6 | 2022-07-31 | SIS |  |  | 12-2030
1329 | ELP Granby Solar II LLC | ELP Granby Solar II | 2022-02-11 | 20 | 20 | Small Generation | CR |  |  | Oswego | NY | C | Curtis Street - Teall 115 kV | NM-NG |  | 11 | 2026-06-30 | FES, SIS, FS | 2025-01-28 | 2024-10-07 | 06-2028 | 04-2028 | 06-2028
1365 | Queensboro Development, LLC | Queensboro Renewable Express Circuit A | 2022-04-15 | N/A | N/A | Transmission Interconnection | DC |  |  | Queens | NY | J | Rainey 345 kV substation and Vernon 138 kV substation | ConEd |  | 6 | 2022-07-31 | SIS |  |  | 04-2029
1366 | Queensboro Development, LLC | Queensboro Renewable Express Circuit B | 2022-04-15 | N/A | N/A | Transmission Interconnection | DC |  |  | Queens | NY | J | Rainey 345 kV substation and Vernon 138 kV substation | ConEd |  | 6 | 2024-03-31 | SIS |  |  | 04-2029
1555 | North Bergen Liberty Generating LLC | Liberty Green Line | 2023-05-12 | N/A | N/A | Transmission Interconnection | AC |  |  | New York County | NY | J | Con Edison W 49th St 345kV Substation | ConEd, PJM |  | 4 | 2026-03-31 | FES |  |  | 01-2029
1667 | Consolidated Edison Company of New York | Designated Public Policy Project Rainey Breaker Replacement | 2024-01-12 | N/A | N/A | Transmission Interconnection | AC |  |  | New York | NY | J | Rainey 345kV Substation | ConEd |  | 7 | 2024-07-31 |  |  |  | 05-2030
1671 | NYSEG | Meyer Substation Rebuild and South Perry Substation Rebuild | 2024-02-02 | N/A | N/A | Transmission Expansion | AC |  |  | Wyoming/Livingston | NY | C | Meyer 115kV, 34.5, 230kV South Perry 115kV, 34.5kV, 69kV | NYSEG | RG&E | 5 | 2026-04-30 |  |  |  | 12-2030
1672 | National Grid | Ames Road Station | 2024-02-05 | N/A | N/A | Transmission Expansion | AC |  |  | Montgomery | NY | E,F | 345kV Edic Princetown 351 345kV Edic Princetwon 352 115kV Saint Johnsville Mashville 11 115kV Clinton Marshville 12 | NM-NG, LS Power | NYPA | 5 | 2025-08-31 |  |  |  | 01-2028
| Number of new projects during August |  | 33
| Number of new projects year to date |  | 58
| Number withdrawn during August |  | 1
| Number withdrawn year to date |  | 21
NOTES: | ● The column labeled 'SP' refers to the maximum summer megawatt electrical output. The column labeled 'WP' refers to the maximum winter megawatt electrical output.
● Type / Fuel Key: ST=Steam Turbine, CT=Combustion Turbine, CC, CS= Steam Turbine & Combustion Turbine, H=Hydro, PS=Pumped Storage, W=Wind, OSW= Off-Shore Wind, NU=Nuclear, NG=Natural Gas, M=Methane, SW=Solid Waste, S=Solar, Wo=Wood, F=Flywheel ES=Energy Storage, O=Oil, C=Coal, D=Dual Fuel, AC,
DC, L=Load, FC=Fuel Cell,CW=CSR - ES + Wind, CR=CSR - ES + Solar
● The column labeled 'M' refers to the zone
● Project Status # Key: 1=Scoping Meeting Pending, 2=FES Pending, 3=FES in Progress,3A=FES Approved/Performed, 4=SRIS/SIS Pending, 5=SRIS/SIS in Progress,5P=SRIS Commenced, Stopped and Pending Adoption of IP, 6=SRIS/SIS Approved, 7=FS Pending, 8=Rejected Cost Allocation/Next FS Pending, 9=FS in Progress, 10=Accepted Cost Allocation/IA in Progress,
11=IA Completed, 12=Under Construction, 13=In Service for Test, 14=In Service Commercial, 0=Withdrawn, 15=Partial In-Service, P=Pending Adoption of IP Compliance with Order 2023
● Availability of Studies Key: None=Not Available, FES=Feasibility Study Available, SRIS=System Reliability Impact Study Available, FS=Facilities Study and/or ATRA Available
● CY Completion/SGIA Tender refers to the Attachment X milestone used to apply the 4-year COD limitation.
● Proposed In-Service Dates, Proposed Initial Synchronization Dates and Commercial Operation Dates (COD) are shown in format Year/Qualifier, where Qualifier may indicate the month, season, or quarter.
DPS/State - SIR Interconnection Queue (for Projects not subject to the NYISO process):
http://www3.dps.ny.gov/W/PSCWeb.nsf/All/286D2C179E9A5A8385257FBF003F1F7E?OpenDocument

## Cluster Projects
Queue Pos. | Interconnection Customer Name | Project Name | Date of IR | SP (MW) | WP (MW) | Project Type | Type/ Fuel | Energy Storage Capability | Minimum_Duration Full Discharge | County | State | NYISO Zone | Points of Interconnection | Utility | Affected Transmission Owner (ATO) | Project Status # | Last Updated Date | Availability of Studies | IA Tender Date | Proposed In-Service/Initial Backfeed Date | Proposed Sync Date | Proposed COD
C24-003 | Vineyard Mid-Atlantic LLC | Vineyard Mid-Atlantic West | 2024-08-01 | 1321 | 1321 | A proposed new Generating Facility | OSW |  |  | Nassu | NY | K | East Garden City 345kV | NYPA | LIPA, Transco | 7 | 2025-11-30 |  |  | 01-2031 | 08-2031 | 03-2032
C24-004 | Palladium Storage LLC | Palladium Storage | 2024-08-01 | 140 | 140 | A proposed new Generating Facility | ES | 560 | 4 | Bronx | NY | J | Hell Gate Annex 138KV Substation | NYPA | ConEd | 7 | 2026-03-31 |  |  | 06-2028 | 07-2028 | 08-2028
C24-005 | Blue Spruce Storage LLC | Blue Spruce Storage | 2024-08-01 | 300 | 300 | A proposed new Generating Facility | ES | 1200 | 4 | Bronx | NY | J | Mott Haven 138KV Bus | ConEd |  | 7 | 2025-11-30 |  |  | 12-2028 | 12-2028 | 12-2028
C24-008 | KCE NY 30, LLC | KCE NY 30 | 2024-08-01 | 50 | 50 | A proposed new Generating Facility | ES | 200 | 4 | Suffolk | NY | K | West Babylon 69 kV | LIPA |  | 7 | 2026-05-31 |  |  | 05-2028 | 09-2028 | 10-2028
C24-010 | KCE NY 21, LLC | KCE NY 21 | 2024-08-01 | 60 | 60 | A proposed new Generating Facility | ES | 240 | 4 | Suffolk | NY | K | Pulaski 69kV Substation | LIPA |  | 7 | 2026-05-31 |  |  | 09-2029 | 10-2029 | 12-2029
C24-013 | Battery Park Storage LLC | Battery Park Storage | 2024-08-01 | 190 | 190 | A proposed new Generating Facility | ES | 760 | 4 | Brooklyn | NY | J | Greenwood 138KV | ConEd |  | 7 | 2026-03-31 |  |  | 06-2028 | 07-2028 | 08-2028
C24-021 | Bluepoint Wind LLC | Bluepoint Wind 1 | 2024-08-01 | 1310 | 1310 | A proposed new Generating Facility | OSW |  |  | Kings | NY | J | Brooklyn Clean Energy Hub 345kV Substation | CONED |  | 7 | 2025-08-31 |  |  | 01-2033 | 07-2033 | 12-2033
C24-032 | BayWa r.e Projects LLC. | Oakdale Battery Storage LLC | 2024-08-01 | 150 | 150 | A proposed new Generating Facility | ES | 600 | 4 | Broome | NY | C | Oakdale 115 kV | NYSEG |  | 7 | 2026-06-30 |  |  | 03-2030 | 04-2030 | 08-2030
C24-033 | KCE NY 31, LLC | KCE NY 31 | 2024-08-01 | 50 | 50 | A proposed new Generating Facility | ES | 200 | 4 | Suffolk | NY | K | Shoreham 138kV | LIPA |  | 7 | 2026-05-31 |  |  | 05-2027 | 09-2027 | 12-2027
C24-042 | Liberty Renewables Inc. | Hoffman Falls Wind 2 | 2024-08-01 | 29.8 | 29.8 | A material modification to a proposed or existing facility | W |  |  | Madison | NY | C | Fenner - Shippy Rd Line 3 115 kV | NM-NG |  | 7 | 2026-01-31 |  |  | 2-2029 | 2-2029 | 4-2029
C24-047 | BayWa r.e Projects LLC. | Lincoln Park DG, LLC | 2024-08-01 | 150 | 150 | A proposed new Generating Facility | ES | 600 | 4 | Ulster | NY | G | Lincoln Park - East Kingston 115 kV | CHGE |  | 7 | 2026-06-30 |  |  | 07-2030 | 08-2030 | 12-2030
C24-048 | BPP NY Lansing BESS I LLC | BPP NY Lansing BESS I | 2024-08-01 | 200 | 200 | A proposed new Generating Facility | ES | 800 | 4 | Tompkins | NY | C | Milliken 115kV (aka Cayuga 115kV) | NYSEG |  | 7 | 2026-04-30 |  |  | 05-2028 | 06-2028 | 07-2028
C24-052-001 | Liberty Renewables Inc. | Hemlock Hollow Wind | 2024-08-01 | 95 | 95 | A proposed new Generating Facility | W |  |  | Cattaraugus | NY | A | Dugan - Homer Hill 115kV, Line #155 | NM-NG |  | 7 | 2026-02-28 |  |  | 07-2029 | 08-2029 | 09-2029
C24-060 | TransGrid Energy LLC | Gemma Energy Storage | 2024-08-01 | 200 | 200 | A proposed new Generating Facility | ES | 800 | 4 | Steuben | NY | C | Stony Ridge 230kV | NYSEG |  | 7 | 2026-06-30 |  |  | 06-2027 | 06-2027 | 12-2027
C24-061 | TransGrid Energy LLC | Daphne Energy Storage | 2024-08-01 | 75 | 75 | A proposed new Generating Facility | ES | 300 | 4 | Suffolk County & Mastic City | NY | K | Moriches 69kV | LIPA |  | 7 | 2026-06-30 |  |  | 06-2027 | 06-2027 | 12-2027
C24-062 | TransGrid Energy LLC | Highbush Energy Storage | 2024-08-01 | 200 | 200 | A proposed new Generating Facility | ES | 800 | 4 | Dutchess | NY | G | Manchester 115 kV | CHGE |  | 7 | 2026-06-30 |  |  | 06-2027 | 06-2027 | 12-2027
C24-064 | EDF Renewables Development, Inc. | Fraser Energy Storage | 2024-08-01 | 135 | 135 | A proposed new Generating Facility | ES | 540 | 4 | Delaware | NY | E | Fraser substation 115 kV | NYSEG |  | 7 | 2026-02-28 |  |  | 09-2028 | 07-2029 | 11-2029
C24-066 | TransGrid Energy LLC | Coral Energy Storage | 2024-08-01 | 100 | 100 | A proposed new Generating Facility | ES | 400 | 4 | Chemung | NY | C | Yawger 115kV Substation | NYSEG |  | 7 | 2026-06-30 |  |  | 06-2027 | 06-2027 | 12-2027
C24-072 | GCI Eastwater, LLC | Eastwater Energy Storage | 2024-08-02 | 100 | 100 | A proposed new Generating Facility | ES | 400 | 4 | Monroe | NY | B | Station 82 - Station 121 Line 23 115kV | NM-NG | RG&E | 7 | 2026-01-31 |  |  | 02-2027 | 03-2027 | 06-2027
C24-074 | Lighthouse Battery, LLC | Lighthouse Energy Storage | 2024-08-02 | 250 | 250 | A proposed new Generating Facility | ES | 1000 | 4 | Chautauqua | NY | A | Gardenville - Dunkirk Line 74 230 kV | NM-NG |  | 7 | 2026-07-31 |  |  | 02-2027 | 03-2027 | 06-2027
C24-079 | Maple Harvest Wind | Maple Harvest Wind | 2024-08-08 | 162 | 162 | A proposed new Generating Facility | W |  |  | Onondaga | NY | C | Tilden-Cortland Line 18. | NM-NG |  | 7 | 2026-02-28 |  |  | 10-2028 | 11-2028 | 12-2028
C24-081 | The New York Power Authority | Port Morris Energy Storage | 2024-08-08 | 130 | 130 | A material modification to a proposed or existing facility | ES | 520 | 4 | Bronx | NY | J | Hell Gate Annex 138kV | NYPA | ConEd | 7 | 2025-03-31 |  |  | 10-2028 | 10-2028 | 12-2028
C24-085 | Terra-Gen Development Company, LLC | Arch 4 | 2024-08-09 | 150 | 150 | A proposed new Generating Facility | ES | 600 | 4 | Orange | NY | G | Rock Tavern 345kV Substation | CHGE | Transco, O&R, NYPA | 7 | 2026-03-31 |  |  | 10-2028 | 10-2028 | 12-2028
C24-088 | Terra-Gen Development Company, LLC | Arch 3 | 2024-08-09 | 100 | 100 | A proposed new Generating Facility | ES | 480 | 4 | Orange | NY | G | Rock Tavern 345kV Substation | CHGE | Transco, O&R | 7 | 2026-03-31 |  |  | 10-2028 | 10-2028 | 12-2028
C24-093 | Terra-Gen Development Company, LLC | Alcazar 1 | 2024-08-22 | 100 | 100 | A proposed new Generating Facility | ES | 400 | 4 | Ulster | NY | G | Hurley 345kV Substation | CHGE |  | 7 | 2026-03-31 |  |  | 10-2028 | 10-2028 | 12-2028
C24-094 | Terra-Gen Development Company, LLC | Alcazar 2 | 2024-08-22 | 150 | 150 | A proposed new Generating Facility | ES | 600 | 4 | Ulster | NY | G | Hurley 345kV Substation | CHGE |  | 7 | 2026-03-31 |  |  | 10-2028 | 10-2028 | 12-2028
C24-097 | RWE Solar Development, LLC | Basecamp BESS | 2024-08-26 | 170 | 170 | A proposed new Generating Facility | ES | 680 | 4 | Chautauqua | NY | A | Laona Station 115kV | NM-NG |  | 7 | 2026-06-30 |  |  | 09-2028 | 10-2028 | 02-2029
C24-098 | RWE Solar Development, LLC | Farmhouse BESS | 2024-08-26 | 150 | 150 | A proposed new Generating Facility | ES | 600 | 4 | Orange | NY | G | Roseton 345 kV Substation | CHGE | NYPA | 7 | 2026-06-30 |  |  | 01-2029 | 02-2029 | 06-2029
C24-104 | ACE DevCo NC, LLC | Horseblock Energy Storage | 2024-08-27 | 100 | 100 | A proposed new Generating Facility | ES | 400 | 4 | Suffolk | NY | K | West Yaphank 69kV Substation | LIPA |  | 7 | 2025-12-31 |  |  | 03-2028 | 04-2028 | 06-2028
C24-108 | Little Salmon Solar LLC | NY125C - Little Salmon Solar | 2024-08-29 | 200 | 200 | A proposed new Generating Facility | S |  |  | Franklin | NY | D | 345kV Line HW1 Haverstock - WIllis | NYPA |  | 7 | 2026-04-30 |  |  | 11-2028 | 11-2028 | 12-2028
C24-111 | Fort Edward Solar LLC | Fort Edward Solar Farm (NY53) | 2024-08-29 | 100 | 100 | A proposed new Generating Facility | S |  |  | Washington | NY | F | Mohican to Battenkill 115 kV Line #15 | NM-NG |  | 7 | 2026-07-31 |  |  | 11-2027 | 11-2027 | 12-2027
C24-125 | RWE Solar Development, LLC | Town Line Solar Phase II | 2024-09-05 | 60 | 60 | A proposed Co-located Storage Resource (CSR) | CR | 0 | 0 | Sullivan | NY | E | Coopers Corner to Middletown Tap 345 kV Line | NYPA | NYSEG, O&R | 7 | 2026-06-30 |  |  | 12-2029 | 01-2030 | 05-2030
C24-129 | MN8 Energy Development Company LLC | Buffalo Road Energy Storage | 2024-09-05 | 100 | 100 | A proposed new Generating Facility | ES | 200 | 2 | Niagara | NY | A | Dupont to Packard 115 kV Line #184 | NM-NG |  | 7 | 2026-07-31 |  |  | 08-2028 | 09-2028 | 12-2028
C24-130 | Lighthouse Bethlehem, LLC | Elevate Bethlehem | 2024-09-05 | 120 | 120 | A proposed new Generating Facility | ES | 1200 | 10 | Albany | NY | F | Albany Steam 115 kV Substation | NM-NG |  | 7 | 2025-11-30 |  |  | 03-2028 | 04-2028 | 06-2028
C24-131 | Lighthouse Arthur Kill II, LLC | Elevate Arthur Kill II | 2024-09-05 | 180 | 180 | A proposed new Generating Facility | ES | 1800 | 10 | Richmond | NY | J | Fresh Kills 345 kV substation | ConEd |  | 7 | 2025-11-30 |  |  | 03-2028 | 04-2028 | 06-2028
C24-135 | Cayuga Lake Solar, LLC | Cayuga Solar | 2024-09-06 | 60 | 60 | A proposed new Generating Facility | S |  |  | Tompkins | NY | C | Milliken 115 kV Substation | NYSEG |  | 7 | 2025-12-31 |  |  | 09-2028 | 10-2028 | 12-2028
C24-138 | Marathon Power | Marathon BESS | 2024-09-06 | 135 | 135 | A proposed new Generating Facility | ES | 540 | 4 | Suffolk | NY | K | Greenlawn 138kV | LIPA |  | 7 | 2026-08-31 |  |  | 12-2027 | 12-2027 | 02-2028
C24-139 | Emeren US, LLC | Valcour Storage | 2024-09-09 | 150 | 150 | A proposed new Generating Facility | ES | 600 | 4 | Clinton | NY | D | Patnode 230 kV substation | NYPA |  | 7 | 2026-08-31 |  |  | 10-2028 | 11-2028 | 12-2028
C24-148 | Emeren US, LLC | Willard Storage | 2024-09-10 | 300 | 300 | A proposed new Generating Facility | ES | 1200 | 4 | Rensselaer | NY | F | Eastover 115kV | NM-NG |  | 7 | 2026-08-31 |  |  | 6-2029 | 9-2029 | 12-2029
C24-154 | Sandlot Energy LLC | Sandlot IFB | 2024-09-11 | 50 | 50 | A proposed new Generating Facility | ES | 500 | 10 | Suffolk | NY | K | Deposit - Indian Head 69 kV Line | LIPA |  | 7 | 2026-08-31 |  |  | 12-2027 | 12-2027 | 02-2028
C24-162 | Calpine Mid-Atlantic Development, LLC | Ramadi Utility Storage | 2024-09-13 | 140 | 140 | A proposed new Generating Facility | ES | 560 | 4 | Suffolk | NY | K | William Floyd to West Yaphank 69kV | LIPA |  | 7 | 2025-12-31 |  |  | 09-2027 | 01-2028 | 04-2028
C24-163 | BGTF NY BESS Holdings LLC | Porter Energy Storage | 2024-09-15 | 50 | 50 | A proposed new Generating Facility | ES | 200 | 4 | Essex | NY | F | Hague Road to Ticonderoga 115 kV line 4 | NM-NG |  | 7 | 2026-08-31 |  |  | 10-2028 | 11-2028 | 12-2028
C24-165 | KCE NY 38, LLC | KCE NY 38 | 2024-09-16 | 250 | 250 | A proposed new Generating Facility | ES | 1000 | 4 | Columbia | NY | F | Churchtown 115 kV Substation | Transco |  | 7 | 2026-05-31 |  |  | 09-2029 | 10-2029 | 12-2029
C24-167 | KCE NY 37, LLC | KCE NY 37 | 2024-09-16 | 150 | 150 | A proposed new Generating Facility | ES | 600 | 4 | Suffolk | NY | K | Sills Rd - Brookhaven 138 kV line | LIPA |  | 7 | 2026-05-31 |  |  | 09-2029 | 10-2029 | 12-2029
C24-173 | KCE NY 34, LLC | KCE NY 34 | 2024-09-17 | 100 | 100 | A proposed new Generating Facility | ES | 400 | 4 | Ulster | NY | G | Saugerties 69 kV | CHGE |  | 7 | 2026-05-31 |  |  | 09-2029 | 10-2029 | 12-2029
C24-175 | RWE Solar Development, LLC | Stargazer I | 2024-09-17 | 325 | 325 | A proposed Co-located Storage Resource (CSR) | CR | 340 | 4 | McKean | PA | A | Homer City to Pierce Brook 345 kV Line | NYSEG |  | 7 | 2026-06-30 |  |  | 01-2029 | 02-2029 | 07-2029
C24-176 | RWE Solar Development, LLC | Stargazer II | 2024-09-17 | 325 | 325 | A proposed Co-located Storage Resource (CSR) | CR | 340 | 4 | McKean | PA | A | Homer City to Pierce Brook 345 kV Line | NYSEG |  | 7 | 2026-06-30 |  |  | 01-2029 | 02-2029 | 07-2029
C24-178 | Astoria Generating Company, L.P. | Gowanus Energy Storage | 2024-09-17 | 150 | 150 | A proposed new Generating Facility | ES | 1500 | 10 | Kings | NY | J | Gowanus 138kV Substation | ConEd |  | 7 | 2026-08-31 |  |  | 03-2028 | 04-2028 | 06-2028
C24-182 | Southern Tier Energy Center, LLC | Southern Tier Energy Center | 2024-09-17 | 200 | 200 | A proposed new Generating Facility | ES | 800 | 4.0 | Tioga | NY | C | Oakdale 130755 - Watercure 130757 345 kV line | NYSEG |  | 7 | 2026-07-31 |  |  | 10-2029 | 11-2029 | 12-2029
C24-183 | East Setauket Energy Storage, LLC | East Setauket Storage II | 2024-09-17 | 248 | 248 | A material modification to a proposed or existing facility | ES | 992 | 4 | Suffolk | NY | K | Holbrook - North Shore Beach 138kV | LIPA |  | 7 | 2026-01-31 |  |  | 09-2029 | 10-2029 | 12-2029
C24-189 | NY North Country, LLC | North Country Wind | 2024-09-18 | 380 | 380 | A proposed new Generating Facility | W |  |  | Franklin and Clinton | NY | D | Willis 230kV substation | NYPA |  | 7 | 2026-03-31 |  |  | 11-2028 | 12-2028 | 06-2029
C24-190 | NY North Country, LLC | North Country Wind II | 2024-09-18 | 380 | 380 | A proposed new Generating Facility | W |  |  | Franklin and Clinton | NY | D | Willis-Haverstock 345kV HW1 | NYPA |  | 7 | 2026-03-31 |  |  | 11-2028 | 12-2028 | 06-2029
C24-202 | Brusselville Solar, LLC | Brusselville Solar Energy Center | 2024-09-19 | 170 | 170 | A proposed Co-located Storage Resource (CSR) | CR | 80 | 4 | Genesee | NY | B | Dysinger-New Rochester 345kV Line (DH2) | NYPA | NYSEG,RG&E | 7 | 2026-07-31 |  |  | 10-2030 | 11-2030 | 12-2030
C24-205 | NEER Interconnection Holdings, LLC | Wheelhouse Energy Storage | 2024-09-19 | 200 | 200 | A proposed new Generating Facility | ES | 800 | 4.0 | Schoharie | NY | F | Edic - Princetown Line #352 | NYPA | NM-NG | 7 | 2026-07-31 |  |  | 10-2030 | 11-2030 | 12-2030
C24-207 | NextEra Energy Resources Interconnection Holdings, LLC | Trelina Energy Storage | 2024-09-19 | 120 | 120 | A proposed new Generating Facility | ES | 480 | 4.0 | Seneca, Ontario | NY | C | Border City to Station 168 115 kV | NYSEG | NM-NG, RG&E | 7 | 2026-07-31 |  |  | 10-2030 | 11-2030 | 12-2030
C24-217 | Bay Breeze Solar, LLC | Bay Breeze solar | 2024-09-20 | 150 | 150 | A proposed new Generating Facility | S |  |  | Jefferson | NY | E | North Watertown (Lyme Junction)-Lyme Line 13 115 kV | NM-NG |  | 7 | 2026-01-31 |  |  | 09-2029 | 10-2029 | 12-2029
C24-224 | ACE DevCo NC, LLC | Cohocton | 2024-09-20 | 130 | 130 | A proposed Co-located Storage Resource (CSR) | CR | 400 | 4 | Steuben | NY | C | Bath - Spencer Hill (Howard) 115 kV | NYSEG |  | 7 | 2025-12-31 |  |  | 07-2029 | 08-2029 | 10-2029
C24-225 | Goldenrod Wind LLC | Goldenrod Wind | 2024-09-20 | 39 | 39 | A proposed new Generating Facility | W |  |  | Chautauqua | NY | A | Moon Road-Hartfield 115kV Line159 | NM-NG |  | 7 | 2026-06-30 |  |  | 06-2029 | 09-2029 | 12-2029
C24-230 | Dewdrop Wind LLC | Dewdrop Wind | 2024-09-21 | 62 | 62 | A proposed new Generating Facility | W |  |  | Chautauqua | NY | A | South Ripley Substation -Dunkirk Substation 230kV | NM-NG |  | 7 | 2026-06-30 |  |  | 06-2029 | 09-2029 | 12-2029
C24-233 | Shallow Seam Energy Storage, LLC | Shallow Seam BESS | 2024-09-22 | 400 | 400 | A proposed new Generating Facility | ES | 1600 | 4 | Clearfield | PA | C | Homer City - Mainesburg 345kV Line (L47) | NYSEG |  | 7 | 2025-11-30 |  |  | 09-2028 | 12-2028 | 03-2029
C24-238 | Zenobe Americas Inc. | Zenobe Burns LLC | 2024-09-23 | 100 | 100 | A proposed new Generating Facility | ES | 400 | 4 | Allegany | NY | C | Moraine Rd 115kV Substation | NYSEG |  | 7 | 2026-06-30 |  |  | 12-2027 | 04-2028 | 07-2028
C24-253 | Nexamp Solar LLC | Troy Heights Energy Storage | 2024-09-23 | 40 | 40 | A proposed new Generating Facility | ES | 160 | 4 | Tompkins | NY | C | Coddington Substation 34.5 kV | NYSEG |  | 7 | 2026-08-31 |  |  | 08-2028 | 09-2028 | 12-2028
C24-281 | the New York Power Authority | Brentwood Energy Storage | 2024-09-25 | 49.1 | 49.1 | A material modification to a proposed or existing facility | ES | 196.4 | 4 | Suffolk | NY | K | Brentwood 69 kV Substation | LIPA |  | 7 | 2025-03-31 |  |  | 06-2028 | 07-2028 | 08-2028
C24-283 | Resilient New York Storage, LLC by Hanwha Energy USA Holdings Corporation | Resilient New York Energy Storage | 2024-09-25 | 349 | 349 | A proposed new Generating Facility | ES | 1396 | 4 | Richmond | NY | J | Goethals 345 kV | ConEd |  | 7 | 2026-03-31 |  |  | 11-2028 | 11-2028 | 12-2028
C24-284 | Prologis Energy LLC | South Bronx Energy Storage | 2024-09-25 | 100 | 100 | A proposed new Generating Facility | ES | 400 | 4 | Bronx | NY | J | Hell Gate 138 kV Substation | NYPA | ConEd | 7 | 2026-06-30 |  |  | 07-2030 | 08-2030 | 12-2030
C24-293 | Oswego Clean Energy Holdings | Oswego Clean Energy | 2024-09-27 | 24.9 | 24.9 | A proposed new Generating Facility | S |  |  | Oswego | NY | C | Oswego 115 kV Substation | NM-NG |  | 7 | 2026-04-30 |  |  | 11-2026 | 12-2026 | 12-2026
C24-300 | Kimberlite Solar Power, LLC | Kimberlite Solar | 2024-09-30 | 175 | 175 | A proposed new Generating Facility | S |  |  | Clearfield | PA | C | Homer City - Mainesburg 345kV Line (L47) | NYSEG |  | 7 | 2025-02-28 |  |  | 09-2028 | 12-2028 | 03-2029
C24-301 | Moonlight Flats Solar Power, LLC | Moonlight Flats Solar | 2024-09-30 | 250 | 250 | A proposed new Generating Facility | S |  |  | Clearfield | PA | C | Homer City 345 kV to Mainesburg 345 kV L47 | NYSEG |  | 7 | 2025-02-28 |  |  | 09-2028 | 12-2028 | 03-2029
C24-304-004 | Chateauguay River, LLC | NY Chateaugay 0 Willis Rd Storage | 2024-10-01 | 150 | 150 | A proposed new Generating Facility | ES | 600 | 4 | Franklin | NY | D | Willis 230kV substation | NYPA |  | 7 | 2026-04-30 |  |  | 02-2028 | 03-2028 | 04-2028
C24-317 | BGTF NY BESS Holdings LLC | Leo Energy Storage | 2024-10-03 | 75 | 75 | A proposed new Generating Facility | ES | 300 | 4 | Clinton | NY | D | Lyon Mountain 115 kV Substation | NYSEG | NYPA | 7 | 2026-08-31 |  |  | 10-2028 | 11-2028 | 12-2028
C24-318 | Nexamp Solar LLC | Sherburne Storage | 2024-10-04 | 40 | 40 | A proposed new Generating Facility | ES | 160 | 4 | Chenango | NY | E | County Line 46 kV Substation | NYSEG |  | 7 | 2026-08-31 |  |  | 08-2028 | 09-2028 | 12-2028
C24-321 | Jericho Solar Park LLC | Jericho Solar | 2024-10-07 | 100 | 100 | A proposed new Generating Facility | S |  |  | Franklin | NY | D | NYPA's Willis Sub @115kV | NYPA |  | 7 | 2026-08-31 |  |  | 05-2029 | 07-2029 | 10-2029
C24-324 | Origis Development LLC | Overlook Storage | 2024-10-08 | 199 | 199 | A proposed new Generating Facility | ES | 796 | 4 | Dutchess | NY | G | Pleasant Valley - Todd Hill 115 kV | CHGE |  | 7 | 2026-01-31 |  |  | 09-2028 | 10-2028 | 12-2028
C24-326 | Origis Development LLC | Lockport Storage | 2024-10-08 | 180 | 180 | A proposed new Generating Facility | ES | 720 | 4 | Niagara | NY | A | Robinson Road 230 kV | NYSEG |  | 7 | 2026-01-31 |  |  | 09-2028 | 10-2028 | 12-2028
C24-331 | the New York Power Authority | Hell Gate Energy Storage | 2024-10-09 | 90 | 90 | A material modification to a proposed or existing facility | ES | 360 | 4 | Bronx | NY | J | Hell Gate 138kV | NYPA | ConEd | 7 | 2025-03-31 |  |  | 10-2028 | 10-2028 | 12-2028
C24-333 | the New York Power Authority | Pouch Energy Storage System | 2024-10-09 | 47.1 | 47.1 | A material modification to a proposed or existing facility | ES | 188.4 | 4 | Kings | NY | J | Fox Hills 138kV Substation | ConEd |  | 7 | 2025-03-31 |  |  | 10-2028 | 10-2028 | 12-2028
C24-336 | ConnectGen Montgomery County LLC | Mill Point Solar II | 2024-10-10 | 100 | 100 | A proposed Co-located Storage Resource (CSR) | CR |  |  | Montgomery | NY | E | Marcy - New Scotland 345kV, Line 18 | NM-NG | NYPA | 7 | 2026-06-30 |  |  | 4-2029 | 5-2029 | 8-2029
C24-337 | Terra-Gen Development Company, LLC | Aria Storage 1 | 2024-10-10 | 100 | 100 | A proposed new Generating Facility | ES | 400 | 4 | Dutchess | NY | H | East Fishkill 345 kV substation | ConEd |  | 7 | 2026-03-31 |  |  | 10-2028 | 10-2028 | 12-2028
C24-338 | Terra-Gen Development Company, LLC | Aria Storage 2 | 2024-10-10 | 150 | 150 | A proposed new Generating Facility | ES | 600 | 4 | Dutchess | NY | H | East Fishkill 345 kV | ConEd |  | 7 | 2026-03-31 |  |  | 10-2028 | 12-2028 | 12-2028
C24-341 | Origis Development LLC | Marlboro Storage | 2024-10-10 | 100 | 100 | A proposed new Generating Facility | ES | 400 | 4 | Ulster | NY | G | Marlboro 115kV Substation | CHGE |  | 7 | 2026-01-31 |  |  | 09-2028 | 10-2028 | 12-2028
C24-352 | Sawhall Energy Storage LLC | Swiss Valley Energy Storage | 2024-10-15 | 300 | 300 | A proposed new Generating Facility | ES | 1200 | 4 | Wyoming | NY | C | Wethersfield 230 kV Substation | NYSEG |  | 7 | 2026-03-31 |  |  | 09-2029 | 10-2029 | 12-2029
C24-358 | Hambletonian Energy Storage LLC | Sugar Loaf Energy Storage I | 2024-10-15 | 300 | 300 | A proposed new Generating Facility | ES | 1200 | 4 | Orange | NY | G | Sugarloaf 138 kV Substation | O&R | Transco | 7 | 2026-03-31 |  |  | 09-2029 | 10-2029 | 12-2029
C24-362 | RWE Solar Development, LLC | Amsterdam Solar | 2024-10-15 | 150 | 150 | A proposed new Generating Facility | S |  |  | Montgomery | NY | E | Edic - Gordon Road 345 kV, Line 14 | NM-NG | NYPA, LSpower | 7 | 2026-06-30 |  |  | 05-2028 | 06-2028 | 07-2028
C24-363 | RWE Solar Development, LLC | Town Line Solar CSR Phase I | 2024-10-15 | 240 | 240 | A proposed Co-located Storage Resource (CSR) | CR | 400 | 4 | Sullivan | NY | E | Coopers Corner to Middletown Tap 345 kV Line | NYPA | NYSEG, O&R | 7 | 2026-06-30 |  |  | 12-2029 | 01-2030 | 05-2030
C24-364 | RWE Solar Development, LLC | Erie Canal BESS | 2024-10-15 | 230 | 230 | A proposed new Generating Facility | ES | 920 | 4 | Niagara | NY | A | Robinson Road 115 kV | NYSEG |  | 7 | 2026-07-31 |  |  | 09-2028 | 10-2028 | 02-2029
C24-366 | Azalea Wind LLC | Azalea Wind 1 | 2024-10-15 | 50 | 50 | A proposed new Generating Facility | W |  |  | Schuyler | NY | C | Montour Falls to Coddington Road 115kV | NYSEG |  | 7 | 2025-02-28 |  |  | 06-2029 | 09-2029 | 12-2029
C24-370 | Azalea Wind LLC | Azalea Wind 2 | 2024-10-15 | 50 | 50 | A material modification to a proposed or existing facility | W |  |  | Schuyler | NY | C | Montour Falls to Coddington Road 115kV | NYSEG |  | 7 | 2026-06-30 |  |  | 06-2029 | 09-2029 | 12-2029
CR24-1002 | National Grid Generation, LLC | West Babylon Internal Combustion (IC), Unit 4 | 2024-09-27 |  |  | CRIS Only Request | O |  |  | Suffolk | NY | K | West Babylon 13.8 kV | LIPA |  | 7 | 2025-02-28 |  |  |  |  | I/S
CR24-1003 | GB II New York LLC | Bethlehem Energy Center Uprate | 2024-10-04 |  |  | CRIS Only Request | NG |  |  | Albany | NY | F | Albany Steam 115 kV | NM-NG |  | 7 | 2026-04-30 |  |  | 06-2026 | 06-2026 | 06-2026
CR24-1004 | Arthur Kill Power LLC | Arthur Kill Unit 2 Uprate | 2024-10-04 |  |  | CRIS Only Request | NG |  |  | Richmond | NY | J | Freshkills 138kV | ConEd |  | 7 | 2026-04-30 |  |  |  |  | I/S
C26-0001 | Evergreen Ridge Power, LLC | EVERGREEN RIDGE POWER | 2026-07-31 | 624 | 641 | A proposed new Generating Facility | CC |  |  | TIOGA | PA | C | Mainesburg 345 kV to Homer City 345 kV Circuit ID -1 | NYSEG |  | 1 | 2026-08-31 |  |  | 01-2031 | 04-2031 | 02-2032
C26-0002 | Roma Storage LLC | Roma Storage | 2026-07-31 | 300 | 300 | A proposed new Generating Facility | ES | 1200 | 4 | Queens | NY | J | Astoria East 138 kV | ConEd |  | 1 | 2026-08-31 |  |  | 06-2031 | 09-2031 | 12-2031
C26-0003 | Terra-Gen Development Company, LLC | Alcazar 1 | 2026-07-31 | 100 | 100 | A proposed new Generating Facility | ES | 400 | 4 | Ulster | NY | G | Hurley 345kV Substation | CHG&E |  | 1 | 2026-08-31 |  |  | 10-2028 | 10-2028 | 12-2028
C26-0004 | KCE NY 21, LLC | KCE NY 21 | 2026-07-31 | 60 | 60 | A proposed new Generating Facility | ES | 240 | 4 | Suffolk | NY | K | Pulaski 69kV Substation | LIPA |  | 1 | 2026-08-31 |  |  | 09-2029 | 10-2029 | 12-2029
C26-0005 | Good Ole 77 Energy LLC | Seventy Seven Wind | 2026-07-31 | 199 | 199 | A proposed new Generating Facility | W |  |  | Wyoming | NY | C | High Sheldon 230 kV | NYSEG |  | 1 | 2026-08-31 |  |  | 05-2032 | 08-2032 | 11-2032
C26-0006 | Terra-Gen Development Company, LLC | Alcazar 2 | 2026-07-31 | 150 | 150 | A proposed new Generating Facility | ES | 600 | 4 | Ulster | NY | G | Hurley 345kV Substation | CHG&E |  | 1 | 2026-08-31 |  |  | 10-2028 | 10-2028 | 12-2028
C26-0008 | KCE NY 34, LLC | KCE NY 34 | 2026-07-31 | 100 | 100 | A proposed new Generating Facility | ES | 400 | 4 | Ulster | NY | G | Saugerties 69 kV | CHG&E |  | 1 | 2026-08-31 |  |  | 09-2029 | 10-2029 | 12-2029
C26-0010 | Terra-Gen Development Company, LLC | Alcazar 4 | 2026-07-31 | 79 | 79 | A proposed new Generating Facility | ES | 316 | 4 | Dutchess | NY | G | Hurley Avenue 115 kV Substation | CHG&E |  | 1 | 2026-08-31 |  |  | 04-2030 | 04-2030 | 09-2030
C26-0011 | NY North Country, LLC | North Country Wind | 2026-07-31 | 380 | 380 | A proposed new Generating Facility | W |  |  | Franklin and Clinton | NY | D | Willis 230kV substation | NYPA |  | 1 | 2026-08-31 |  |  | 11-2028 | 12-2028 | 06-2029
C26-0012 | NY North Country, LLC | North Country Wind II | 2026-07-31 | 380 | 380 | A proposed new Generating Facility | W |  |  | Franklin and Clinton | NY | D | Willis-Haverstock 345kV HW1 | NYPA |  | 1 | 2026-08-31 |  |  | 11-2028 | 12-2028 | 06-2029
C26-0013 | Terra-Gen Development Company, LLC | Alcazar 3 | 2026-07-31 | 250 | 250 | A proposed new Generating Facility | ES | 1000 | 4 | Dutchess | NY | G | Hurley Avenue 345 kV Substation | CHG&E |  | 1 | 2026-08-31 |  |  | 04-2030 | 04-2030 | 09-2030
C26-0014 | Rolling Hills Wind, LLC | Rolling Hills Wind | 2026-07-31 | 185 | 185 | A proposed new Generating Facility | W |  |  | Herkimer | NY | F | Edic-Princetown 345 kV ckt 352 | NYPA | NM-NG | 1 | 2026-08-31 |  |  | 04-2030 | 04-2030 | 09-2030
C26-0015 | Terra-Gen Development Company, LLC | Aria Storage 3 | 2026-07-31 | 150 | 150 | A proposed new Generating Facility | ES | 600 | 4 | Dutchess | NY | H | East Fishkill 115 kV | CHG&E | CONED | 1 | 2026-08-31 |  |  | 04-2030 | 04-2030 | 09-2030
C26-0016 | Terra-Gen Development Company, LLC | Arch 5 | 2026-07-31 | 250 | 250 | A proposed new Generating Facility | ES | 1000 | 4 | Orange | NY | G | Rock Tavern 345 kV Substation | CHG&E | NYPA, O&R, ConEd | 1 | 2026-08-31 |  |  | 04-2030 | 04-2030 | 09-2030
C26-0017 | ACE DevCo NC, LLC | North Watertown BESS | 2026-07-31 | 200 | 200 | A proposed new Generating Facility | ES | 800 | 4 | Jefferson | NY | E | 115 kV North Watertown Substation | NM-NG |  | 1 | 2026-08-31 |  |  | 07-2029 | 08-2029 | 10-2029
C26-0018 | Canal Solar, LLC | Rolling Hills Solar | 2026-08-05 | 185 | 185 | A proposed new Generating Facility | S |  |  | Herkimer | NY | F | Edic-Princetown 345 kV ckt 352 | NYPA | NM-NG | 1 | 2026-08-31 |  |  | 04-2030 | 04-2030 | 09-2030
C26-0019 | WEB Addison Solar LLC | WEB Addison Solar | 2026-08-05 | 96 | 96 | A proposed new Generating Facility | S |  |  | Steuben | NY | C | NYSEG Stony Ridge - Sullivan Park 115 kV line | NYSEG |  | 1 | 2026-09-30 |  |  | 10-2030 | 11-2030 | 12-2030
C26-0020 | Brookside Forest Energy Storage LLC | Brookside Forest | 2026-08-10 | 300 | 300 | A proposed new Generating Facility | ES | 1200 | 4 | Lowville | NY | E | 115kV Waters Road Station | NM-NG |  | 1 | 2026-08-31 |  |  | 03-2030 | 06-2030 | 09-2030
C26-0021 | ACE DevCo NC, LLC | Blue Mountain BESS | 2026-08-11 | 100 | 100 | A proposed new Generating Facility | ES | 400 | 4 | Ulster | NY | G | Saugerties - Hurley 69 kV | CHG&E |  | 1 | 2026-09-30 |  |  | 09-2029 | 10-2029 | 12-2029
C26-0022 | Terra-Gen Development Company, LLC | Clay Energy Storage 1 | 2026-08-13 | 250 | 250 | A proposed new Generating Facility | ES | 1000 | 4 | Onondaga | NY | C | Clay 345 kV Substation | NM-NG | NYPA | 1 | 2026-08-31 |  |  | 04-2030 | 04-2030 | 12-2030
C26-0023 | Terra-Gen Development Company, LLC | Clay Energy Storage 2 | 2026-08-13 | 150 | 150 | A proposed new Generating Facility | ES | 600 | 4 | Onondaga | NY | C | CLAY 115kV Substation | NM-NG |  | 1 | 2026-08-31 |  |  | 04-2030 | 04-2030 | 04-2030
C26-0024 | ACE DevCo NC, LLC | Cohocton | 2026-08-13 | 130 | 130 | A proposed Co-located Storage Resource (CSR) | CR | 400 | 4 | Steuben | NY | C | Bath - Spencer Hill (Howard) 115 kV | NYSEG |  | 1 | 2025-08-31 |  |  | 07-2029 | 08-2029 | 10-2029
C26-0025 | ACE DevCo NC, LLC | Riptide Storage | 2026-08-14 | 200 | 200 | A proposed new Generating Facility | ES | 800 | 4 | Suffolk | NY | K | POI is Edwards Avenue 138 kV Substation via existing position for Riverhead Solar Farm/Q535 Riverhead Solar 2 Projects | LIPA |  | 1 | 2026-08-31 |  |  | 09-2029 | 10-2029 | 12-2029
C26-0026 | Fort Edward Solar LLC | Fort Edward Solar Farm (NY53) | 2026-08-17 | 100 | 100 | A proposed new Generating Facility | S |  |  | Washington | NY | F | Mohican to Battenkill 115 kV Line #15 | NM-NG |  | 1 | 2026-08-31 |  |  | 11-2027 | 11-2027 | 12-2027
C26-0030 | Bay Breeze Solar, LLC | Bay Breeze solar | 2026-08-25 | 150 | 150 | A proposed new Generating Facility | S |  |  | Jefferson | NY | E | North Watertown (Lyme Junction)-Lyme Line 13 115 kV | NM-NG |  | 1 | 2026-09-30 |  |  | 09-2029 | 10-2029 | 12-2029
NOTES: | ● The column labeled 'SP' refers to the maximum summer megawatt electrical output. The column labeled 'WP' refers to the maximum winter megawatt electrical output.
● Type / Fuel Key: ST=Steam Turbine, CT=Combustion Turbine, CC, CS= Steam Turbine & Combustion Turbine, H=Hydro, PS=Pumped Storage, W, OSW= Off-Shore Wind, NU=Nuclear, NG=Natural Gas, M=Methane, SW=Solid Waste, S, Wo=Wood, F=Flywheel ES, O=Oil, C=Coal, D=Dual Fuel, AC,
DC, L=Load, FC=Fuel Cell,CW=CSR - ES + Wind, CR=CSR - ES + Solar
● The column labeled 'Z' refers to the zone
● Project Status # Key: 1C = IR Validated/ Scoping Meeting Pending, 2C = Customer Engagement Window, 3C = Phase 1 Entry Decision Period, 4C = Phase 1 Study, 5C = Phase 2 Entry Decision Period, 6C = Phase 2 Study, 7C = Final Decision Period, 10C = Accepted Cost Allocation/ IA in Progress, 11C = IA Completed, 12C = Under Construction, 13C = In Service for Test, 14C = In Service Commercial, 15C =Partially In-Service/ Partially under construction
● Proposed In-Service Dates, Proposed Initial Synchronization Dates and Commercial Operation Dates (COD) are shown in format Year/Qualifier, where Qualifier may indicate the month, season, or quarter.

## Load Projects
Queue Number | Developer Name | Project: Project Name | IR Submission Date | Peak MW load | End-Use | Record Type Name | Type/Fuel | County | State | NYISO Zone | Points of Interconnection | CTO/Utility | Affected Transmission Owner (ATO) | Project Status # | SIS Bundle | Last Updated Date | Availability of Studies | IA Tender Date | FS Completion Date | Proposed Initial Backfeed Date
205 | National Grid | Luther Forest | 2005-11-02 | 40 |  | Load Interconnection | L | Saratoga | NY | F | Round Lake 115kV | NM-NG |  | 14 |  | 2013-03-31 | SIS |  |  | I/S
849 | Somerset Operating Company, LLC | Somerset Load | 2019-05-21 | 250 |  | Load Interconnection | L | Niagara | NY | A | Kintigh 345kV | NYSEG |  | 14 |  | 2022-07-31 | SIS, FS |  |  | I/S
1446 | Air Products and Chemicals Inc | Massena Green Hydrogen | 2022-10-05 | 110 |  | Load Interconnection | L | St Lawrence | NY | E | Haverstock - Adirondack 345 kV line 1 | NYPA |  | 0 |  | 2025-03-31
1465 | Digihost Technologies, Inc. | Digihost load | 2022-11-14 | 50.2 |  | Load Interconnection | L | Niagara | NY | A | Walck Rd. 115kV | NM-NG |  | 14 |  | 1900-01-13 | N/A |  |  | I/S
0290A | Green Island Power Authority | Green Island Power | 2008-04-07 | 20 |  | Load Interconnection | L | Albany | NY | F | Maplewood - Johnson Rd 115kV | NM-NG |  | 14 |  | 2011-11-30 | SIS |  |  | I/S
0311 | NY State Electric & Gas | Concord Casino | 2008-09-24 | 48 |  | Load Interconnection | L | Sullivan | NY | E | Coopers Corner - Rock Hill | NYSEG |  | 0 |  | 2013-04-30
0359 | National Grid | Verizon - Project Oasis | 2010-12-20 | 75 |  | Load Interconnection | L | Niagara | NY | A | Somerset - Kintigh 345kV | NYSEG |  | 0 |  | 2011-02-28
0423 | Rochester Gas & Electric | University of Rochester | 2013-11-17 | 25 |  | Load Interconnection | L | Monroe | NY | B | Station 251 | NYSEG |  | 0 |  | 2014-07-31
0580 | Genesee County Economic Devel. | WNY STAMP | 2016-09-27 | 300 | DAT | Load Interconnection | L | Genesee | NY | B | Kintigh/Niagara - New Rochester 345kV | NYPA |  | 12 | N/A | 2025-03-31 | SIS |  |  | 11-2026
0776 | Greenidge Generation LLC | Greenidge Load | 2018-10-22 | 60 | DAT-CM | Load Interconnection | L | Yates | NY | C | Greenidge 115kV | NYSEG |  | 7 | N/A | 2026-03-31 | SIS |  |  | 04-2030
0850 | Cayuga Operating Company, LLC | Cayuga Load | 2019-05-21 | 50 | DAT-CM | Load Interconnection | L | Cayuga | NY | C | Milliken 115kV | NYSEG |  | 7 | N/A | 2024-04-30 | SIS |  |  | 12-2026
0909 | PetaWatt Holdings, Inc. | Massena Load | 2019-09-18 | 200 |  | Load Interconnection | L | St. Lawrence | NY | E | Dennison 115kV substation | NM-NG |  | 0 |  | 2026-07-31 |  |  |  | 07-2026
0979 | North Country Data Center | North Country Data Center | 2020-01-22 | 435 | DAT-CM | Load Interconnection | L | St. Lawrence | NY | D | Reynolds 115kV | NYPA |  | 12 | N/A | 2026-07-31 | SIS |  |  | 01-2026
1213 | ZeroC Data Centers, LLC | St Lawrence Data and Agricultural Center | 2021-06-28 | 200 | DAT-CM | Load Interconnection | L | St. Lawrence | NY | D | Dennison 115kV substation | NM-NG |  | 10 | N/A | 2026-07-31 | SIS |  |  | 08-2025
1315 | Sabey Data Center Properties, LLC | SDC St. Lawrence | 2021-12-20 | 120 | DAT | Load Interconnection | L | St. Lawrence | NY | D | Moses-Reynolds MRG-1 and Moses-Reynolds MRG-2 at 115kV | NYPA |  | 8 | N/A | 2026-07-31 | SIS |  |  | 11-2026
1484 | GCEDC | 580 STAMP load increase | 2022-12-02 | 300 | DAT | Load Interconnection | L | Genesee | NY | B | 115 kv STAMP substation | NM-NG |  | 12 | N/A | 2026-07-31 | SIS |  |  | 05-2028
1521 | Iroquois Gas Transmission System | IGTS Wright EMD Compressor | 2023-02-14 | 14.38 |  | Load Interconnection | L | Schoharie | NY | F | Rotterdam - New Scotland #13 115kV line | NM-NG |  | 0 |  | 2026-07-31 |  |  |  | 02-2030
1522 | Iroquois Gas Transmission System | GTS Dover EMD Compressor | 2023-02-15 | 16.5 |  | Load Interconnection | L | Dutchess | NY | G | Pleasant Valley - Cricket Valley 345kV | ConEd |  | 0 |  | 2024-07-31 |  |  |  | 01-2027
1536 | Micron New York Semiconductor Manufacturing LLC | White Pine Phase 1 | 2023-03-11 | 480 | M-CH | Load Interconnection | L | Onondaga | NY | C | Clay 345 kV Substation | NM-NG |  | 12 | N/A | 2025-04-30 | SIS |  |  | 06-2025
1627 | Micron New York Semiconductor Manufacturing LLC | Micron Fab 2 | 2023-10-31 | 576 | M-CH | Load Interconnection | L | Onondaga | NY | C | National Grid Clay 345 kV Substation | NM-NG |  | 9 | N/A | 2026-07-31 | SIS |  |  | 12-2027
1633 | Robert Delcalzo | Suffern Quarry Data Center | 2023-11-13 | 200 |  | Load Interconnection | L | Rockland | NY | G | There is a 135kv line abutting our property. We will be building a substation. We currently connect to the Hillburn Area Station. | O&R |  | 0 |  | 2025-05-31 |  |  |  | 10-2026
1646 | P&M Brick LLC | POWI Project | 2023-11-30 | 50 | M-IN | Load Interconnection | L | Albany | NY | F | New Scotland to Knickerbocker 345kV line | NM-NG | NY Transco, LSPNY, CHGE | 6 | N/A | 2026-07-31 | SIS |  |  | 01-2026
1670 | Lake Mariner Data LLC | Lake Mariner Data II | 2024-01-23 | 250 | DAT-AI | Load Interconnection | L | Niagara | NY | A | Kintigh 345kV Substation | NYSEG |  | 6 | N/A | 2026-07-31 | SIS |  |  | 02-2027
1681 | Niagara Falls Redevelopment LLC | Niagara Digital Campus | 2024-04-09 | 140 | DAT | Load Interconnection | L | Niagara | NY | A | Adams to Packard 115kV lines 187 and 188 | NM-NG |  | 9 | N/A | 2026-07-31 | SIS |  |  | 01-2027
1682 | Equity Suffern Developers, LLC | Hudson Valley Data Center | 2024-04-24 | 50 |  | Load Interconnection | L | Rockland | NY | G | Line 60 138kV - Ramapo to Tallman | O&R |  | 0 |  | 2026-08-31 |  |  |  | 09-2028
1683 | Cayuga Operating Company, LLC | Cayuga Compute | 2024-04-24 | 88 | DAT | Load Interconnection | L | Tompkins | NY | C | Milliken substation 115kV | NYSEG |  | 6 | N/A | 2026-08-31 | SIS |  |  | 01-2027
1713 | Project Sycamore - Orangeburg | Project Sycamore Orangeburg | 2024-06-19 | 22.3 | DAT | Load Interconnection | L | Rockland | NY | G | Oak Street 138kV | O&R |  | 10 | 25-1 | 2025-12-31 | SIS |  |  | 10-2029
1714 | Robert Delcalzo | Hudson Valley Data Center | 2024-07-02 | 50 | DAT | Load Interconnection | L | Rockland | NY | G | Line 60 138KV - Ramp to Tallman | O&R |  | 10 | 25-1 | 2025-12-31 | SIS |  |  | 01-2027
1715 | Jerry Martin | 1547 CSR - Orangeburg LLC | 2024-07-02 | 30 | DAT | Load Interconnection | L | Rockland | NJ | G | 138kV Line 703 between Corporate Drive and Harings Corner | O&R |  | 10 | 25-1 | 2025-12-31 | SIS |  |  | 03-2027
1716 | DataBank Holdings, LLC | Orangeburg Expansion Phase 2 | 2024-08-05 | 30 |  | Load Interconnection | L | Orange | NY | G | Oak St 38kV substation | O&R |  | 0 |  | 2025-12-31 |  |  |  | 03-2027
1717 | Holtec Decommissioning International (HDI) | Proposed Datacenters at 450 Broadway, Buchanan, NY, 10511 | 2024-08-07 | 200 | DAT | Load Interconnection | L | Westchester | NY | H | Buchanan 138kV Substation | ConEd |  | 6 | N/A | 2025-12-31 |  |  |  | 03-2027
1719 | ZeroC Data Centers, LLC | New York State Artificial Intelligence Data Center | 2024-09-18 | 300 |  | Load Interconnection | L | St. Lawrence | NY | D | Dennison 115kV substation | NM-NG |  | 0 |  | 2025-12-31 |  |  |  | 06-2028
1721 | WF Industrial XII LLC | Brookhaven Logistics Center | 2024-10-28 | 176.6 | DAT | Load Interconnection | L | Suffolk | NY | K | 138-872 Holbrook to Sills Rd | LIPA |  | 9 | N/A | 2025-12-31 | SIS |  |  | 12-2027
1723 | Olean Digital LLC | Olean Digital Data Center | 2024-11-07 | 300 |  | Load Interconnection | L | Cattaraugus | NY | A | Homer Hill 115kV Substation | NM-NG |  | 0 |  | 2025-12-31 |  |  |  | 12-2028
1724 | Alcoa | Alcoa East Energy Allocation Project | 2024-12-09 | 200 |  | Load Interconnection | L | St. Lawrence | NY | D | Haverstock - Willis 345kV lines HW1 & HW2 | NYPA |  | 0 |  | 2026-04-30 |  |  |  | 07-2027
1725 | Greenidge Generation, LLC | Greenidge 200 MW Data Center Project | 2024-12-20 | 200 | DAT | Load Interconnection | L | Yates | NY | C | New York State Electric & Gas (NYSEG) - Greenidge 115 kV Substation | NYSEG | National Grid | 5 | 25-2 | 2026-06-30 |  |  |  | 05-2028
1726 | Riverview Innovation & Technology Campus, Inc. | Data & Technology Campus | 2025-01-31 | 300 | DAT | Load Interconnection | L | Erie | NY | A | Huntley - Packard 230kV line 78 | NM-NG | NYSEG | 5 | 25-2 | 2026-06-30 |  |  |  | 12-2027
1728 | Arconic Corporation | Arsenal Data Site 250 | 2025-03-07 | 233 | DAT-AI | Load Interconnection | L | St Lawrence | NY | E | Haverstock to Adirondak 345kV line HA-1 | NYPA | National Grid | 5 | 25-2 | 2026-06-30 |  |  |  | 10-2028
1729 | Arconic Corporation | Arsenal Data Site 500 | 2025-03-07 | 233 | DAT-AI | Load Interconnection | L | St Lawrence | NY | E | Haverstock to Adirondak 345kV line HA-1 | NYPA | National Grid | 5 | 25-2 | 2026-04-30 |  |  |  | 08-2028
1730 | Arconic Corporation | Arsenal Data Site 1000 | 2025-03-07 | 467 | DAT-AI | Load Interconnection | L | St Lawrence | NY | E | Haverstock to Adirondak 345kV line HA-1 | NYPA | National Grid | 5 | 25-2 | 2026-06-30 |  |  |  | 05-2027
1731 | ZeroC Data Centers, LLC | New York State Artificial Intelligence Data Center | 2025-03-14 | 300 | DAT-AI | Load Interconnection | L | St. Lawrence | NY | E | Haverstock-Adirondack 345kV transmission line HA-2 | NYPA | National Grid | 5 | 25-2 | 2026-04-30 |  |  |  | 12-2029
1732 | TeraWulf Brookings LLC | Wulf Compute Data Center II | 2025-03-29 | 250 | DAT-AI | Load Interconnection | L | Niagara | NY | A | Kintigh 345kV sub-station | NYSEG | NYPA, NM-NG | 5 | 25-2 | 2026-01-31 |  |  |  | 07-2030
1733 | Cayuga Operating Company, LLC | Cayuga Data | 2025-03-29 | 162 | DAT-AI | Load Interconnection | L | Tompkins | NY | C | Milliken 115kV Substation | NYSEG | National Grid | 5 | 25-2 | 2026-01-31 |  |  |  | 12-2027
1735 | Turin Management LLC | Remington Factory Redevelopment | 2025-05-02 | 100 | DAT | Load Interconnection | L | Herkimer | NY | E | Ilion Municipal 115kV substation | IMEU | NYPA ,National Grid | 5 | 26-1 | 2026-08-31 |  |  |  | 02-2029
1736 | Ranalli SuperDC LLC | Ranalli SuperDC | 2025-05-07 | 270 | DAT | Load Interconnection | L | Onondaga | NY | C | Clay to Pannell ckts PC-1 and PC-2 | NYPA | NM-NG, NYSEG/RGE | 5 | 25-3 | 2026-06-30 |  |  |  | 06-2027
1737 | Griffiss Utility Services Corporation | Griffiss Park Triangle Development | 2025-06-03 | 66 | M-CG | Load Interconnection | L | Oneida | NY | E | Gulf to Rome 115kV line | NM-NG |  | 5 | 25-3 | 2026-06-30 |  |  |  | 06-2027
1738 | Donovan Drive Holdings LLC | 1 Gig Data Center East Fishkill, NY | 2025-07-17 | 1000 | DAT | Load Interconnection | L | Dutchess | NY | H | East Fishkill to Wood Street 345 kV lines (38 and 39) | CONED | NYSEG, Central Hudson | 5 | 26-2 | 2026-06-30 |  |  |  | 10-2026
1739 | Brookhaven Science Associates on behalf of US Department of Energy | Brookhaven National Laboratory Electron Ion Collider Project | 2025-07-30 | 120 |  | Load Interconnection | L | Suffolk | NY | K | LIPA existing 69 kV / 13.8 kV substation (PSEG Fifth Ave substation) | LIPA |  | 0 |  | 2026-07-31 |  |  |  | 06-2027
1740 | Turin Management LLC | Incremental Load Request for Remington Factory Redevelopment | 2025-08-29 | 400 | DAT | Load Interconnection | L | Herkimer | NY | E | Line 1: 345KV from EDIC to Fraser. Line 2: 345 KV from Marcy to Coopers Corners | NYPA | National Grid, NYSEG, Transco, IMEU | 5 | 26-1 | 2026-06-30 |  |  |  | 07-2027
1741 | North East Data LLC | North East Data LLC Data Center | 2025-08-29 | 500 | DAT | Load Interconnection | L | Niagara | NY | A | 230kV lines 77 and 78 | NM-NG |  | 4 |  | 2026-08-31 |  |  |  | 12-2029
1742 | St. Lawrence Infrastructure, LLC | St. Lawrence Infrastructure 1 | 2025-09-02 | 860 | DAT-AI | Load Interconnection | L | St. Lawrence | NY | E | NYPA HA-2, 345kV Transmission Line | NYPA |  | 4 | 26-4 | 2026-05-31 |  |  |  | 01-2030
1743 | St. Lawrence Infrastructure, LLC | St. Lawrence Infrastructure 2 | 2025-09-02 | 1935 | DAT-AI | Load Interconnection | L | St. Lawrence | NY | D | NYPA's 230kV Moses Massena 1 (MMS-1) and 230kV Moses Massena 2 (MMS-2) | NYPA |  | 4 | 26-4 | 2026-01-31 |  |  |  | 12-2028
1744 | Brookhaven Logistics Center, LLC | Brookhaven Data Center | 2025-09-05 | 300 |  | Load Interconnection | L | Suffolk | NY | K | LIPA 138kV line circuit, between Caithness Long Island Energy Center Substation and Brookhaven Substation. Coordinates: 40°49'05.8"N 72°55'45.4"W. | LIPA |  | 0 |  | 2026-01-31 |  |  |  | 01-2029
1745 | American Data Center Partners LLC | Pontoon Bridge Road Data Center | 2025-10-09 | 250 | DAT | Load Interconnection | L | St Lawrence | NY | E | Haverstock-Adirondack 345kV transmission lines | NYPA |  | 4 | 26-4 | 2026-03-31 |  |  |  | 06-2028
1746 | Onondaga County Department of Water Environment Protection | OOWWTP Expansion Program | 2025-10-15 | 50 | O | Load Interconnection | L | Onondaga | NY | C | National Grid's 115kV lines: Clay-Teall LN#11 and Clay-Woodard LN#17 | National Grid | NYPA | 5 | 26-3 | 2026-06-30 |  |  |  | 01-2028
1747 | GLOBE DH LLC | Globe Digital Holdings - 1 | 2025-10-17 | 192 | DAT-AI | Load Interconnection | L | Niagara | NY | A | Beck Packard 76 230kV | National Grid |  | 4 |  | 2026-06-30 |  |  |  | 10-2028
1748 | GLOBE DH LLC | GLOBE DH 2 | 2025-10-17 | 192 | DAT-AI | Load Interconnection | L | NIAGARA FALLS | NY | A | Beck Packard 76 230kV | National Grid |  | 4 | [5 empty] | 01-2027
1749 | GLOBE DH LLC | Globe DH 3 | 2025-10-17 | 192 | DAT-AI | Load Interconnection | L | niagara falls | NY | A | Niagara Packard 77 230kV | National Grid | NYPA | 4 |  | 2026-06-30 |  |  |  | 03-2029
1750 | Advance Albany County Alliance | Al Tech Steel Site | 2025-10-21 | 60 | RD | Load Interconnection | L | Albany | NY | F | Maplewood Menands 18 | NM-NG |  | 4 |  | 2026-06-30 |  |  |  | 02-2029
1751 | North Country Data Center LLC | Massena Development LLC Power Allocation | 2025-10-21 | 200 | DAT | Load Interconnection | L | St; Lawrence | NY | D | NYPA - HW1 and HW2 (345kV) Lines - at Haverstock Substation | NYPA |  | 4 | 26-4 | 2026-07-31 |  |  |  | 03-2027
1752 | The Agency | Broome County Tech Park | 2025-10-30 | 250 | RD | Load Interconnection | L | Broome | NY | C | 345 kV POI via a loop on the existing Oakdale-Fraser Line 32. The interconnection substation will have a ring bus configuration. | NYSEG | NGRID, NYPA | 5 | 26-3 | 2026-09-30 |  |  |  | 07-2037
1753 | New York State Office of General Services | New York State Dept. of Health Lab (Harriman Campus, Albany NY) | 2025-11-04 | 87 | RD | Load Interconnection | L | Albany | NY | F | Woodlawn-State Campus #12 115kV feeder, and Menands-State Campus #15-115kV feeder. | National Grid |  | 4 |  | 2026-05-31 |  |  |  | 01-2030
1754 | EKG Group LLC | Kenwood Tech Center | 2025-11-11 | 180 | DAT | Load Interconnection | L | Albany | NY | F | Albany?Bethlehem 115 kV Line #18 | National Grid |  | 4 |  | 2026-01-31 |  |  |  | 12-2028
1755 | Research Foundation of SUNY | Site Master Plan Expansion Phase I | 2025-12-18 | 45 | RD | Load Interconnection | L | Albany | NY | F | Patroon Creek and McKnownville | National Grid |  | 4 |  | 2026-01-31 |  |  |  | 01-2029
1756 | Research Foundation of SUNY | Site Master Plan Expansion Phase II | 2025-12-18 | 90 |  | Load Interconnection | L | Albany | NY | F | Patroon Creek and McKnownville | National Grid |  | 0 |  | 2026-01-31
1757 | NY-Route 9W LLC | NY-Route 9W Load Center | 2026-01-07 | 1000 |  | Load Interconnection | L | Greene | NY | F | Leeds 345kV substation | National Grid |  | 0 |  | 2026-01-31
1758 | GE Vernova | GE Vernova 2690 Balltown Road High Yard Upgrade | 2026-01-29 | 20 | RD | Load Interconnection | L | Schenectady | NY | F | Rosa Road - General Electric R&D National Grid #14 | National Grid |  | 4 |  | 2026-03-31 |  |  |  | 06-2028
1759 | Robert Grant | Saratoga Expansion | 2026-03-25 | 40 | M-CG | Load Interconnection | L | Saratoga | NY | F | Adjacent to existing 34.5kV service, a new 115kV substation will be built. | National Grid |  | 4 |  | 2026-06-30 |  |  |  | 01-2028
1760 | iPark East Fishkill LLC | iPark 84 Data Center Interconnection | 2026-03-25 | 150 | DAT | Load Interconnection | L | Dutchess | NY | G | New 115kV line from CHG&E East Fishkill Substation | Central Hudson |  | 5 | 26-2 | 2026-06-30 |  |  |  | 10-2028
1761 | URI TALY | NYISO Load Interconnection Process - Data Center Inquiry | 2026-04-12 | 150 | DAT | Load Interconnection | L | Horseheads | NY | C | Broad Street 34.5 kV Line 93 | NYSEG |  | 1 | [5 empty] | 01-2027
1762 | Highwall Energy, LLC | Highwall Data Center | 2026-05-12 | 400 | DAT | Load Interconnection | L | Clearfield | PA | C | same POI of Q#1080 (Mineral Basin Solar), connects to NYSEG's L47 line | NYSEG |  | 4 |  | 2026-06-30 |  |  |  | 03-2029
1763 | Patriot Forge PA, LLC | Patriot Forge | 2026-05-29 | 350 | DAT | Load Interconnection | L | Tioga | PA | C | Tap on the NYSEG 345 kV Line 47 (Homer City -Mainesburg 345 kV) | NYSEG |  | 4 |  | 2026-06-30 |  |  |  | 02-2029
1764 | Titan Mining Corporation | Kilbourne Graphite Concentrator Plant | 2026-07-16 | 15 |  | Load Interconnection | L | ST LAWRENCE | NY | E | ZINCO 115 | National Grid |  | 1 |  | 2026-07-31 |  |  |  | 03-2027
1765 | Eldo Varghese | Micron Fab 3 | 2026-08-28 | 606 |  | Load Interconnection | L | Onondaga | New York | C | National Grid - Clay Substation | National Grid |  | 1 |  | 2026-09-30 |  |  |  | 07-2037
End-Use Key
DAT Data Center
AI AI Data center
CM Cryptocurrency mining data center
M Manufacturing
CH Microchip fabrication
CG Consumable Goods
IN Industrial Goods
RD Research and Development
HP Hydrogen Production
O Other
NOTES:
● Project status # Key:0=Withdrawn, 1=Scoping Meeting Pending, 2=FES Pending, 3=FES in Progress,3A=FES Approved/Performed, 4=SRIS/SIS Pending, 5=SRIS/SIS in Progress, 5P=SRIS Commenced, Stopped and Pending Adoption of IP, 6=SRIS/SIS Approved, 7=FS Pending, 8=Rejected Cost Allocation/Next FS Pending, 9=FS in Progress, 10=Accepted Cost Allocation/IA in Progress,
11=IA Completed, 12=Under Construction, 13=In Service for Test, 14=In Service Commercial, 0=Withdrawn, 15=Partial In-Service, P=Pending Adoption of IP Compliance with Order 2023
● Availability of Studies Key: None=Not Available, FES=Feasibility Study Available, SRIS=System Reliability Impact Study Available, FS=Facilities Study and/or ATRA Available
● Proposed In-Service Dates, Proposed Initial Synchronization Dates and Commercial Operation Dates (COD) are shown in format Year/Qualifier, where Qualifier may indicate the month, season, or quarter.
● The column labeled "SIS Bundle" refers to the groupings of load projects being studied in the same post project SIS case (bundle), as described in the SIS scope. The SIS code is in the following format, "XX-Y", where "XX" is the year the SIS scope was approved, and "Y" is a serial number within the given year.

## Load Project Tracking
Load Project Tracking Summary (by NYISO Zone and Requested MW)
MW By Status |  | A | B | C | D | E | F | G | H | I | J | K | NYCA
- | Withdrawn (not included in NYCA total) | 375 | 25 | 0 | 500 | 358 | 1104.38 | 296.5 | 0 | 0 | 0 | 420 | 3078.88
1 | Scoping Meeting Pending | 0 | 0 | 756 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 771
4 | SIS Pending | 1076 | 0 | 750 | 2135 | 1110 | 432 | 0 | 0 | 0 | 0 | 0 | 5503
5 | SIS In-Progress | 550 | 0 | 932 | 0 | 1799 | 0 | 150 | 1000 | 0 | 0 | 0 | 4431
6 | SIS Approved | 250 | 0 | 88 | 0 | 0 | 50 | 0 | 200 | 0 | 0 | 0 | 588
7 | FS Pending | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110
9 | FS In-Progress | 140 | 0 | 576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176.6 | 892.6
10 | Accepted Cost Allocation IA in Progress | 0 | 0 | 0 | 200 | 0 | 0 | 102.3 | 0 | 0 | 0 | 0 | 302.3
12 | Under Construction | 0 | 600 | 480 | 435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1515
I/S | In-service | 300.2 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 360.2
| Total | 2016 | 600 | 3692 | 2770 | 2924 | 482 | 252.3 | 1200 | 0 | 0 | 176.6 | 14473.1
MW By End-Use |  | A | B | C | D | E | F | G | H | I | J | K | NYCA
DAT | Data Center (general) | 940 | 600 | 1458 | 320 | 750 | 180 | 252.3 | 1200 | 0 | 0 | 176.6 | 5876.9
DAT-AI | AI Datacenter | 1076 | 0 | 162 | 1935 | 2093 | 0 | 0 | 0 | 0 | 0 | 0 | 5266
DAT-CM | Cryptocurrency mining | 0 | 0 | 110 | 635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 745
M | Manufacturing (general) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
M-CH | Microchip fabrication | 0 | 0 | 1056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056
M-CG | Consumable Goods | 0 | 0 | 0 | 0 | 66 | 40 | 0 | 0 | 0 | 0 | 0 | 106
M-IN | Industrial Goods | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 50
RD | Research and Development | 0 | 0 | 250 | 0 | 0 | 212 | 0 | 0 | 0 | 0 | 0 | 462
HP | Hydrogen Production | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
O | Other | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50
| Total | 2016 | 600 | 3086 | 2890 | 2909 | 482 | 252.3 | 1200 | 0 | 0 | 176.6 | 13611.9
Note total excludes withdrawn and in-service load projects
MW By IR Submission Date |  | A | B | C | D | E | F | G | H | I | J | K | NYCA | Running Total
44196 | 2020 and earlier | 0 | 300 | 110 | 435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 845 | 845
44561 | 2021 | 0 | 0 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320 | 1165
44926 | 2022 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 1465
45291 | 2023 | 0 | 0 | 1056 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 1106 | 2571
45657 | 2024 | 390 | 0 | 288 | 0 | 0 | 0 | 102.3 | 200 | 0 | 0 | 176.6 | 1156.9 | 3727.9
46022 | 2025 | 1626 | 0 | 732 | 2135 | 2909 | 372 | 0 | 1000 | 0 | 0 | 0 | 8774 | 12501.9
46387 | 2026 | 0 | 0 | 1506 | 0 | 15 | 60 | 150 | 0 | 0 | 0 | 0 | 1731 | 14232.9
| Total | 2016 | 600 | 3692 | 2890 | 2924 | 482 | 252.3 | 1200 | 0 | 0 | 176.6 | 14232.9
*Note total excludes withdrawn and in-service load projects

## Affected System Studies
Queue Pos. | Developer/Interconnection Customer | Project Name | Date of IR | SP (MW) | WP (MW) | Type/ Fuel | County | State | Zone | Points of Interconnection | Utility | Affected Transmission Owner (ATO) | NYISO Status | Last Updated Date | Availability of Studies | IA Tender Date | CY/FS Complete Date | Proposed In-Service/Initial Backfeed Date | Proposed Sync Date | Proposed COD
A01-703 | Parkway Generation Operating LLC | Bergen 230kV | 2025-09-26 | 35.61 | 35.61 | NG | Bergen | NJ |  | Bergen 230kV | PJM |  | 5 | 2025-09-30 |  |  |  | 2027-05-21
A01-715 | Parkway Generation Operating LLC | Linden 230kV | 2025-09-26 | 127.17 | 127.17 | NG | Union | NJ |  | Linden 230kV | PJM |  | 5 | 2025-09-30 |  |  |  | 2029-05-31
A01-722 | Parkway Generation Operating LLC | Linden 230kV | 2025-09-26 | 130.4 | 130.4 | NG | Union | NJ |  | Linden 230kV | PJM |  | 5 | 2025-09-30 |  |  |  | 2030-05-31
A02-002 | Homer City Generation, L.P. | Homer City 230 kV | 2026-07-08 | 1400 | 1400 | NG | Indiana | PA |  | Homer City 230 kV | PJM |  | 4 | 2026-07-31
A02-003 | Homer City Generation, L.P. | Homer City 345 kV | 2026-07-08 | 3000 | 3000 | NG | Indiana | PA |  | Homer City 345 kV | PJM |  | 4 | 2026-07-31
1718 | Seven Creek Energy, LLC | Erie East BESS | 2024-09-10 |  |  | AC | Erie | PA |  | Erie East 230kV (First Energy, Erie PA) | PJM |  | 0 | 2026-05-31
1720 | Elk Run Storage LLC | Elk Run Storage | 2024-10-16 |  |  | AC | Tioga | PA |  | Mainesburg 115 kV Substation | PJM |  | 0 | 2025-01-31
1722 | Treebeard BESS Project Co LLC | Treebeard BESS | 2024-10-29 |  |  | AC | New Milford | CT |  | 115 kV line 1555 between Rocky River and Bulls Bridge substations | ISO-NE |  | 0 | 2025-05-31
1734 | Mid-Atlantic Interstate Transmission, LLC | Fairbanks Run Mod Sub | 2025-04-09 |  |  | AC | Warren | PA |  | Tapping the National Grid Falconer to MAIT Warren line on the Pennsylvania side of the line. | PJM |  | 0 | 2025-08-31
A01-005 | Franklin Energy, LLC | East Towanda-South Troy 115 kV II | 2025-09-26 | 20 | 20 | S | Bradford | PA |  | East Towanda-South Troy 115 kV II | PJM |  | 0 | 2025-10-31
A01-102 | Clark Run Solar LLC | Seward-Glory 115 kV | 2025-09-26 | 100 | 100 | S | Indiana | PA |  | Seward-Glory 115 kV | PJM |  | 0 | 2025-12-31
A01-206 | Agnes Solar, LLC | Tennessee Gas-East Towanda 115 kV | 2025-09-26 | 48 | 48 | S | Bradford | PA |  | Tennessee Gas-East Towanda 115 kV | PJM |  | 0 | 2025-12-31
A01-220 | Franklin Energy, LLC | East Towanda-South Troy 115 kV | 2025-09-26 | 31 | 31 | S | Bradford | PA |  | East Towanda-South Troy 115 kV | PJM |  | 0 | 2025-10-31
A01-221 | Franklin Energy, LLC | South Troy - North Towanda 34.5 kV | 2025-09-26 | 20 | 20 | S | Bradford | PA |  | South Troy - North Towanda 34.5 kV | PJM |  | 0 | 2025-10-31
A01-268 | Clark Run Solar LLC | Seward-Glory 115 kV II | 2025-09-26 | 0 | 0 | ES | Indiana | PA |  | Seward-Glory 115 kV II | PJM |  | 0 | 2025-12-31
A01-327 | Agnes Solar, LLC | Tennessee Gas-East Towanda 115 kV | 2025-09-26 | 10 | 10 | S | Bradford | PA |  | Tennessee Gas-East Towanda 115 kV | PJM |  | 0 | 2025-12-31
A01-358 | McKean County Solar, LLC | Pierce Brook-Lewis Run 230kV | 2025-09-26 | 20 | 20 | ES | McKean | PA |  | Pierce Brook-Lewis Run 230kV | PJM |  | 0 | 2025-12-31
A01-357 | McKean County Solar, LLC | Pierce Brook-Lewis Run 230kV | 2025-09-26 | 20 | 20 | S | McKean | PA |  | Pierce Brook-Lewis Run 230kV | PJM |  | 0 | 2025-12-31
A01-359 | McKean County Solar, LLC | Pierce Brook - Lewis Run 230 kV | 2025-09-26 | 20 | 20 | S | McKean | PA |  | Pierce Brook - Lewis Run 230 kV | PJM |  | 0 | 2025-12-31
A01-360 | McKean County Solar, LLC | Pierce Brook - Lewis Run 230 kV | 2025-09-26 | 20 | 20 | ES | McKean | PA |  | Pierce Brook - Lewis Run 230 kV | PJM |  | 0 | 2025-12-31
A01-456 | McKean County Solar, LLC | Pierce Brook-Lewis Run 230 kV | 2025-09-26 | 80 | 80 | S | McKean | PA |  | Pierce Brook-Lewis Run 230 kV | PJM |  | 0 | 2025-12-31
A01-457 | McKean County Solar, LLC | Pierce Brook - Lewis Run 230 kV | 2025-09-26 | 80 | 80 | S | McKean | PA |  | Pierce Brook - Lewis Run 230 kV | PJM |  | 0 | 2025-12-31
A01-439 | Field Brook Solar LLC | Oxbow 34.5 kV | 2025-09-26 | 9.8 | 9.8 | S | Wyoming | PA |  | Oxbow 34.5 kV | PJM |  | 0 | 2025-10-31
A01-587 | RWE Solar Development, LLC | Farmers Valley – Ridgeway 115 kV | 2025-09-26 | 200 | 200 | S | McKean | PA |  | Farmers Valley – Ridgeway 115 kV | PJM |  | 0 | 2025-12-31
A01-588 | RWE Solar Development, LLC | Lewis Run - Pierce Brook 230 kV | 2025-09-26 | 240 | 240 | S | McKean | PA |  | Lewis Run - Pierce Brook 230 kV | PJM |  | 0 | 2025-12-31
A01-589 | RWE Solar Development, LLC | Lewis Run - Pierce Brook 230 kV | 2025-09-26 | 170 | 170 | ES | McKean | PA |  | Lewis Run - Pierce Brook 230 kV | PJM |  | 0 | 2025-12-31
A01-720 | Hamilton Liberty LLC | East Towanda 230 kV | 2025-09-26 | 0 | 0 | NG | Bradford | PA |  | East Towanda 230 kV | PJM |  | 0 | 2025-12-31
A01-356 | Robin Solar LLC | South Troy - Canton 34.5 kV | 2025-09-26 | 20 | 20 | S | Bradford | PA |  | South Troy - Canton 34.5 kV | PJM |  | 0 | 2026-03-31
NOTES:
● Project Status # Key: 4=Affected System Study Pending, 5=Affected System Study in Progress,5P=SRIS Commenced, Stopped and Pending Adoption of IP, 6=SRIS/SIS Approved, 7=FS Pending, 8=Rejected Cost Allocation/Next FS Pending, 9=FS in Progress, 10=Accepted Cost Allocation/IA in Progress,

## Withdrawn
Queue Pos. | Owner/Developer | Project Name | Date of IR | SP (MW) | WP (MW) | Type/ Fuel | County | State | Z | Interconnection Point | Utility | S | Last Update
0005 | Sithe Energies | Torne Valley Station | 1999-01-28 | 860 |  |  |  | NY |  | Ramapo | CONED | 0
0006 | Sunset Energy Fleet LLC | Sunset Energy Fleet | 1999-02-17 | 520 |  |  |  | NY |  | Gowanus | CONED | 0
0007 | American National Power | Ramapo Energy | 1999-02-23 | 1100 |  |  |  | NY |  | Ramapo | CONED | 0
0008 | Columbia Electric Corp. | Grassy Point | 1999-02-23 | 1100 |  |  |  | NY |  | West Haverstraw | CONED | 0
0009 | Millennium Power Gen Co. LLC | Millennium 1 | 1999-02-23 | 160 |  |  |  | NY |  | Hell Gate/Bruckner | CONED | 0
0010 | Millennium Power Gen Co. LLC | Millennium 2 | 1999-02-23 | 320 |  |  |  | NY |  | Hell Gate/Bruckner | CONED | 0
0012 | East Coast Power, LLC | East Coast Power Linden | 1999-03-25 | 70 |  | ST | Richmond-NJ | NY | J | Goethals 345kV | CONED | 0 | 2008-07-10
0013 | East Coast Power, LLC | Linden 7 | 1999-03-25 | 100 |  | ST | Richmond-NJ | NY | J | Goethals 345kV | CONED | 0 | 2008-07-10
0014 | East Coast Power, LLC | Linden Plant Improvement | 1999-03-25 | 20 |  | ST | Richmond-NJ | NY | J | Goethals 345kV | CONED | 0 | 2008-07-10
0015 | AEP Resources Service Corp. | CT-LI AC Tie-line | 1999-04-13 | 600 |  |  |  | NY |  | Shoreham, Long Island | LIPA | 0
0016 | Oak Point Property, LLC | Oak Point Yard | 1999-04-15 | 500 |  | CC | Bronx | NY | J | Hell Gate/Bruckner 138kV | CONED | 0 | 2008-07-10
0019 | NYC Energy LLC | NYC Energy LLC | 1999-05-07 | 79.9 |  | CT | Kings | NY | J | Kent Ave 138kV | CONED | 0 | 2010-09-30
0020 | KeySpan Energy, Inc. | Spagnoli Road CC Unit | 1999-05-17 | 250 |  | CC | Suffolk | NY | K | Spagnoli Road 138kV | LIPA | 0 | 2012-03-01
0021 | KeySpan Energy, Inc. | Shoreham Gen Station | 1999-05-17 | 250 |  |  |  | NY |  | Shoreham | LIPA | 0
0022 | Calpine Eastern Corporation | Wawayanda Energy Center | 1999-06-10 | 500 |  | CC | Orange | NY |  | Coop Corn-Rock Tav Lines 345kV | NYPA | 0 | 2006-06-26
0023 | Calpine Eastern Corporation | Sullivan County Power Project | 1999-06-25 | 1080 |  | CC | Sullivan | NY |  | Coop Corn-Rock Tav Lines 345kV | NYPA | 0 | 2006-03-31
0024 | Reliant Energy | Astoria Repowering-Phase 1 | 1999-07-13 | 367 |  | CC | Queens | NY |  | Astoria 138kV | CONED | 0 | 2006-08-09
0026 | Twin Tier Power, LLC | Twin Tier Power | 1999-08-20 | 520 |  |  |  | NY |  | Watercure-Oakdale 31 Line | NYSEG | 0
0027 | ENRON | Far Rockaway Barge | 1999-09-08 | 60 |  |  |  | NY |  | Far Rockaway | LIPA | 0
0028 | KeySpan Energy, Inc. | Spagnoli Road GT Unit | 1999-09-08 | 79.9 |  |  |  | NY |  | Spagnoli Road | LIPA | 0
0029 | Mirant | Bowline Point Unit 3 | 1999-10-13 | 750 |  | CC | Rockland | NY |  | W. Haverstraw 345kV | CONED | 0 | 2006-07-10
0030 | Sithe Energies | Heritage Station | 1999-10-29 | 800 |  |  |  | NY |  | Independence (Oswego) | NM-NG | 0
0031 | SCS Energy, LLC | Astoria Energy - Phase 2 | 1999-11-16 | 500 |  | NG | Queens | NY | J | Astoria 138kV | CONED | 0 | 2023-05-31
0032 | American National Power | Brookhaven Energy | 1999-11-22 | 580 |  | CC | Suffolk | NY |  | Holbrook-Brookhaven 138kV | LIPA | 0
0033 | Glenville Energy Park, LLC | Glenville Energy Park | 1999-11-30 | 540 |  | CC | Schenectady | NY | F | Rotterdam 230kV | NM-NG | 0 | 2008-07-10
0034 | York Research Corp. | North First Street | 2000-01-11 | 500 |  |  |  | NY |  | Con Ed System | CONED | 0
0035 | Gotham Power Zerega, LLC | Gotham Power - Bronx I | 2000-01-12 | 79.9 |  | CT | Bronx | NY | J | Parkchester/Tremont 138kV | CONED | 0 | 2008-07-10
0036 | Boundless Energy, LLC | Project Neptune DC NB-NYC | 2000-01-21 | 1200 |  | DC | Kings | NY | J | Farragut 345kV | CONED | 0 | 2008-07-10
0037 | Caithness Energy, LLC | Kitchen | 2000-01-28 | 750 |  |  |  | NY |  | Riverh'd-Brookh'n-Holb'k | LIPA | 0
0038 | KeySpan Energy, Inc. | Far Rochaway Gen Ext. | 2000-02-01 | 79 |  |  |  | NY |  | Far Rockaway | LIPA | 0
0039 | KeySpan Energy, Inc. | E. F. Barrett Gen Ext | 2000-02-01 | 79 |  |  |  | NY |  | Barrett | LIPA | 0
0040 | KeySpan Energy, Inc. | Riverhead Gen Station | 2000-02-01 | 79 |  |  |  | NY |  | Riverhead | LIPA | 0
0041 | KeySpan Energy, Inc. | Southampton Gen Ext. | 2000-02-01 | 79 |  |  |  | NY |  | Southampton | LIPA | 0
0042 | PP&L Global, Inc. | Holbrook Energy | 2000-02-01 | 300 |  |  |  | NY |  | Holbrook | LIPA | 0
0043 | PP&L Global, Inc. | PPL Kings Park | 2000-02-01 | 300 |  |  |  | NY |  | Pilgrim | LIPA | 0
0044 | PP&L Global, Inc. | Ruland Energy | 2000-02-01 | 300 |  |  |  | NY |  | Ruland Road | LIPA | 0
0045 | PP&L Global, Inc. | Freeport Energy | 2000-02-01 | 100 |  |  |  | NY |  | Freeport | LIPA | 0
0046 | PP&L Global, Inc. | Brookhaven Energy | 2000-02-03 | 300 |  |  |  | NY |  | Brookhaven | LIPA | 0
0047 | GenPower, LLC | GenPower DC Tie-line | 2000-02-09 | 800 |  |  |  | NY |  | West 49th Sreet | CONED | 0
0048 | PP&L Global, Inc. | PPL Kings Park Ext. | 2000-02-10 | 300 |  |  |  | NY |  | Pilgrim | LIPA | 0
0049 | PP&L Global, Inc. | Brookhaven Energy Ext. | 2000-02-10 | 300 |  |  |  | NY |  | Brookhaven | LIPA | 0
0050 | AES Long Island, LLC | AES Smithtown Gen | 2000-02-10 | 510 |  |  |  | NY |  | LIPA System | LIPA | 0
0051 | KeySpan Energy, Inc. | Wading River Gen Ext. | 2000-02-15 | 150 |  |  |  | NY |  | Wading River | LIPA | 0
0052 | NIMO/Black River Power | Fort Drum Gen Exp. | 2000-03-06 | 50 |  |  |  | NY |  | Fort Drum | NM-NG | 0
0053 | TransEnergie US, Ltd | CT-Ruland, LI DC Tie | 2000-03-07 | 300 |  |  |  | NY |  | Ruland Road | LIPA | 0
0054 | TransEnergie US, Ltd | CT-Pilgrim, LI DC Tie | 2000-03-07 | 300 |  |  |  | NY |  | Pilgrim | LIPA | 0
0056 | 1st Rochdale Coop Group | Gotham Power/Brooklyn | 2000-03-17 | 79 |  |  |  | NY |  | Kent Ave | CONED | 0
0057 | Flat Rock Windpower, LLC | Flat Rock Windpower | 2000-03-21 | 100 |  | W |  | NY |  | Lowville-Boonville | NM-NG | 0
0058 | Mirant | Lovett #3 Repowering | 2000-03-23 | 180 |  |  |  | NY |  | Lovett | CONED | 0
0059 | Mirant | Hillburn Unit #2 | 2000-03-23 | 79.9 |  |  |  | NY |  | Hillburn | CONED | 0
0060 | Mirant | Hillburn #2 Conversion | 2000-03-23 | 40 |  |  |  | NY |  | Hillburn | CONED | 0
0061 | GTM Energy, LLC | Greenpoint Energy Park | 2000-04-19 | 500 |  |  |  | NY |  | Rainey-Farragut Lines | CONED | 0
0062 | Project Orange Associates, LP | Project Orange | 2000-05-08 | 420 |  |  |  | NY |  | Temple St. | NM-NG | 0
0063 | Lewis Staley Associates, Inc. | LSA Station A | 2000-05-11 | 650 |  |  |  | NY |  | Homer City-Stolle Rd Line | NYSEG | 0
0064 | Lewis Staley Associates, Inc. | LSA Station B | 2000-05-12 | 600 |  |  |  | NY |  | Dunkirk-Gardenville Line | NM-NG | 0
0065 | Fortistar-Lockport Merchant | Lockport II Gen Station | 2000-05-15 | 79.9 |  | CT | Niagara | NY | A | Harrison Station 115kV | NYSEG | 0 | 2008-07-10
0067 | Titan Development, LLC | Wallkill Energy | 2000-06-21 | 1080 |  |  |  | NY |  | Coop Corn-Rock Tav Lines | NYPA | 0
0068 | PP&L Global, Inc. | Ruland Energy Ext. | 2000-06-23 | 300 |  |  |  | NY |  | Ruland Road | LIPA | 0
0070 | Reliant Energy | Astoria Repowering-Phase 2 | 2000-08-18 | 173 |  | CT | Queens | NY |  | Astoria 138kV | CONED | 0 | 2006-08-09
0071 | Mill Creek Wind Plant, LLC | Mill Creek Wind Plant | 2000-09-08 | 50 |  |  |  | NY |  | Lowville | NM-NG | 0
0072 | Fortistar Power Marketing, LLC | Island Gen. Station | 2000-09-08 | 79.9 |  |  |  | NY |  | Fresh Kills | CONED | 0
0073 | Fortistar Power Marketing, LLC | Island Gen. Station #2 | 2000-09-08 | 500 |  |  |  | NY |  | Fresh Kills | CONED | 0
0074 | FPL Energy, LLC | Oceanside Energy Center | 2000-10-10 | 330 |  |  |  | NY |  | Barrett | LIPA | 0
0075 | 1st Rochdale Coop Group | Gotham Power - Bronx II | 2000-10-17 | 79 |  |  |  | NY |  | Hell Gate/Bruckner | CONED | 0
0076 | Calpine Eastern Corporation | Waterford | 2000-10-30 | 530 |  | CT | Saratoga | NY |  | NM-NG 230 or 115 kV | NM-NG | 0 | 2019-03-06
0077 | Titan Development, LLC | Dover Energy | 2000-11-17 | 1000 |  |  |  | NY |  | Pl. Valley-Long Mt. Tie-Line | CONED | 0
0078 | KeySpan Ravenswood | Ravenswood Repower Ph I | 2000-12-04 | 440 |  |  |  | NY |  | Vernon | CONED | 0
0086 | NRG/ Berrians I GT Power, LLC | Berrians GT Replacement | 2001-01-15 | 79.9 |  |  |  | NY |  | Astoria | CONED | 0
0087 | Titan Development, LLC | Buchanan Energy | 2001-02-26 | 500 |  |  |  | NY |  | Buchanan | CONED | 0
0088 | Titan Development, LLC | Halfmoon Energy | 2001-02-26 | 500 |  |  |  | NY |  | Rotterdam-Bear Swamp line | NM-NG | 0
0089A | Atlantic Energy, LLC | Neptune DC PJM-NYC | 2001-03-15 | 600 |  |  |  | NY |  | W49th St | CONED | 0
0089B | Atlantic Energy, LLC | Neptune DC PJM-NYC | 2001-03-15 | 600 |  |  |  | NY |  | W49th St | CONED | 0
0090 | Fortistar, LLC | Fortistar VP | 2001-03-20 | 79.9 |  | CT | Richmond | NY | J | Fresh Kills 138kV | CONED | 0 | 2009-05-27
0091 | Fortistar, LLC | Fortistar VAN | 2001-03-20 | 79.9 |  | CT | Richmond | NY | J | Goethals/Fresh Kills 138kV | CONED | 0 | 2009-05-27
0092 | Amerada Hess Corp. | Redhook Energy | 2001-05-01 | 79.9 |  |  |  | NY |  | ConEd 138 kV (tbd) | CONED | 0
0093 | In-City I, LLC | Cross Hudson Project | 2001-05-11 | 550 |  | CC | NY | NY |  | W49th Street 345kV | CONED | 0 | 2007-08-23
0096 | Calpine Eastern Corporation | CPN 3rd Turbine, Inc. (JFK) | 2001-05-29 | 45 |  | CT | Queens | NY | J | Jamaica 138kV | CONED | 0 | 2008-07-10
0097 | NYSEG Solutions | South Glens Falls Expansion | 2001-06-15 | 40 |  |  |  | NY |  | Mohican-Butler#18 line | NM-NG | 0
0098 | TransEnergie US Ltd. | PJM-NY City HVDC | 2001-06-22 | 990 |  |  |  | NY |  | W49th St and/or Farragut | CONED | 0
0100 | Titan Development, LLC | Blooming Grove Power | 2001-07-02 | 500 |  |  |  | NY |  | Rock Tavern-Ramapo line | CONED | 0
0101 | Northeast Utilities Service Co. | NU CT-LI HVDC Cable | 2001-07-13 | 660 |  |  |  | NY |  | Shore Road | LIPA | 0
0102 | Entergy Power Gen. Corp. | Indian Point Energy Center | 2001-07-23 | 400 |  | CT | Westchester | NY |  | Buchanan 345kV | CONED | 0
0103 | Pegasus Trans. Co., Ltd. | Niagara Reinforcement Inter. | 2001-08-15 | 1200 |  | DC | Oneida-NY | NY |  | Marcy,Edic,Porter - W49th St. | NYPA/NM/CE | 0
0104 | PG&E/Liberty Gen. Co., LLC | Jupiter PJM-NYC Cable | 2001-08-24 | 1200 |  |  |  | NY |  | W49th St or Farragut | CONED | 0
0105 | Calpine Eastern Corporation | Titan Smith Street | 2001-10-05 | 79.9 |  | CT | Kings | NY |  | Gowanus 138 or 345 kV | CONED | 0 | 2019-03-06
0106 | TransGas Energy, LLC | TransGas Energy | 2001-10-05 | 1100 |  | CC | Kings | NY | J | E13St, Rainey, or Farragut-345kV | CONED | 0 | 2012-03-01
0108 | Sempra Generation | SE Long Island | 2001-11-29 | 575 |  | CT | Suffolk | NY |  | Shoreham-Holbrook lines 138kV | LIPA | 0
0109 | Calpine Eastern Corporation | Maspeth | 2002-01-25 | 79.9 |  |  |  | NY |  | Vernon-Glendale line | CONED | 0
0110 | PG&E/Liberty Gen. Co., LLC | Liberty Generation | 2002-02-04 | 400 |  | CT | Richmond-NJ | NY |  | Goethals 345kV | CONED | 0 | 2019-03-06
0111 | River Hill Power Co., LLC | River Hill Project | 2002-02-05 | 290 |  | CT | Chemung-PA | NY | C | Homer City-Watercure 345kV | NYSEG | 0 | 2008-07-10
0112 | TransEnergie US Ltd. | PJM-Rainey HVDC | 2002-04-09 | 660 |  | DC | Queens-NJ | NY |  | Rainey 345kV | CONED | 0 | 2006-05-31
0113 | Windfarm Prattsburgh, LLC | Prattsburgh Wind Park | 2002-04-22 | 55.5 |  | W | Yates | NY | C | Eelpot Rd-Flat St. 115kV | NYSEG | 0 | 2010-03-31
0114 | Global Winds Harvest, Inc. | Cherry Valley Wind Park | 2002-04-22 | 40.5 |  |  |  | NY |  | East Springfield | NYSEG | 0
0116 | PG&E/Liberty Gen. Co., LLC | Liberty Gen Co, LLC | 2002-04-29 | 600 |  |  |  | NY |  | Goethals | CONED | 0
0117 | Chautauqua Windpower, LLC | Chautauqua Windpower | 2002-05-14 | 50 |  | W | Chautauqua | NY |  | Dunkirk-S. Ripley 230kV | NM-NG | 0 | 2007-03-27
0118 | Global Winds Harvest, Inc. | Prattsburgh Wind Park II | 2002-05-15 | 75 |  |  |  | NY |  | Eelpot Rd-Flat St. line | NYSEG | 0
0119 | ECOGEN, LLC | Prattsburgh Wind Farm | 2002-05-20 | 78.2 |  | W | Yates | NY | C | Eelpot Rd-Flat St. 115kV | NYSEG | 0 | 2013-10-31
0120 | ECOGEN, LLC | Springwater Wind Farm | 2002-05-20 | 79.5 |  |  |  | NY |  | Eelpot Rd | NYSEG | 0
0124 | Bay Energy, LLC | Bay Energy Project | 2002-07-01 | 79.9 |  | CT | Kings | NY |  | Gowanus 138kV | CONED | 0
0126 | TransEnergie US Ltd. | PJM-Newbridge Rd HVDC | 2002-09-10 | 350 |  | DC |  | NY |  | Newbridge Road 138kV | LIPA | 0 | 2006-05-31
0127 | KeySpan Energy for LIPA | Northport-Norwalk Upgrade | 2002-09-19 | 150 |  |  |  | NY |  | Northport | LIPA | 0
0127A | Airtricity Munnsville Wind Farm, LLC | Munnsville - Phase 2 | 2002-10-09 | 5.5 |  | W | Madison | NY | E | 46kV line | NYSEG | 0 | 2023-05-31
0128 | Flat Rock Wind Power, LLC | Flat Rock Wind Power 230 kV | 2002-11-20 | 240 |  | W |  | NY |  | Adirondack-Porter line | NM-NG | 0
0129 | Conjunction, LLC | Empire Connection | 2002-12-10 | 2000 |  | DC |  | NY |  | New Scotland / ConEd | NM-NG/CONED | 0
0130 | Electrotek Concepts, Inc. | Grace Corona Generation | 2003-01-14 | 79.9 |  |  |  | NY |  | Corona | CONED | 0
0131 | Green Power Energy, LLC | Cody Road Wind Farm | 2003-03-05 | 10.5 |  | W |  | NY |  | Oneida-Cortland line | NM-NG | 0
0132 | Airtricity Developments, LLC | Munnsville Windpower | 2003-05-11 | 40 |  | W |  | NY |  | NYSEG Ckt 806 | NYSEG | 0
0134 | TransEnergie US Ltd. | PJM-Barrett HVDC | 2003-05-21 | 650 |  |  |  | NY |  | Barrett 138 kV | LIPA | 0
0137 | Conjunction, LLC | Empire Connection DC | 2003-06-16 | 2000 |  |  |  | NY |  | N. Scotland/Leeds, ConEd | NM/CONED | 0
0140 | National Grid | Leeds-PV Reconductoring | 2003-08-26 | N/A |  | AC | Greene-Dutchess | NY | G | Leeds/Athens-Pl. Valley 345kV | NM-NG | 0 | 2008-07-10
0141A | Atlantic Renewable Energy Corp. | Bishop | 2003-09-09 | 23.1 |  | W | Livingston | NY |  | Springwater 34.5kV line | NYSEG | 0
0142 | EC&R Northeast, LLC | Steuben Wind | 2003-10-30 | 50 |  | W | Steuben | NY | C | Bennett-Palmiter 115kV line | NYSEG | 0 | 2010-06-04
0147 | NY Windpower, LLC | West Hill Windfarm | 2004-04-16 | 31.5 |  | W | Madison | NY | C | Oneida-Fenner 115kV | NM-NG | 0 | 2012-08-31
0148 | Trigen Nassau Gen Co., LLC | Trigen-Nassau | 2004-05-18 | 79.9 |  |  |  | NY |  | Uniondale Substation | LIPA | 0
0150 | Reunion Power, LLC | Cherry Valley Wind Power | 2004-06-17 | 70 |  | W | Ostego | NY | E | Marshville - Sharon 69kV | NM-NG | 0 | 2010-03-31
0151 | Con Edison | West Side Switching Station | 2004-06-30 | N/A |  | AC | NY | NY | J | West 49th St & Farragut 345kV | CONED | 0 | 2011-03-31
0152 | Moresville Energy LLC | Moresville Energy Center | 2004-07-23 | 99 | 99 | W | Delaware | NY | E | Axtell Road-Grand Gorge 115kV | NYSEG | 0 | 2011-06-30
0154 | KeySpan Energy for LIPA | Holtsville-Brentwood-Pilgrim | 2004-08-19 | N/A | N/A | AC | Suffolk | NY | K | Holtsville & Pilgrim 138kV | LIPA | 0 | 2017-02-28
0155 | Invenergy NY, LLC | Canisteo Hills Windfarm | 2004-09-17 | 148.5 |  | W | Steuben | NY | C | Bennett-Bath 115kV | NYSEG | 0 | 2012-03-01
0157 | BP Alternative Energy NA, Inc. | Orion Energy NY I | 2004-10-12 | 100 | 100 | W | Herkimer | NY | E | Watkins Rd.-Inghams 115kV | NM-NG | 0 | 2012-03-01
0158 | Orion Energy, LLC | Orion Energy NY II | 2004-10-12 | 100 | 100 | W | Montgomery | NY |  | Inghams-Meco 115kV | NM-NG | 0 | 2019-01-06
0159 | Orion Energy, LLC | Orion Energy NY III | 2004-10-12 | 150 |  |  | Clinton | NY |  | TBD | NYSEG | 0
0160 | Jericho Rise Wind Farm, LLC | Jericho Rise Wind Farm | 2004-10-12 | 79.2 | 79.2 | W | Franklin | NY | D | Willis 115 kV | NYPA | 0 | 2011-04-30
0162 | AES Somerset, LLC | Niagara Windpower | 2004-12-15 | 70 |  | W | Niagara | NY |  | Somerset Switch Yard | NYSEG | 0 | 2019-08-05
0163 | Clipper Windpower Dev. Co. Inc. | Paragon I Wind Generation | 2005-01-13 | 100 | 100 | W | Steuben | NY | C | Bath-Montour Falls 115kV | NYSEG | 0 | 2008-08-19
0164 | FPL Energy | Long Island Offshore Wind | 2005-01-28 | 140 | 140 | W | Suffolk | NY |  | Sterling Substation | LIPA | 0 | 2008-02-26
0165 | UPC Wind Management, LLC | Genesee Wind Farm | 2005-01-31 | 500 | 500 | W | Genesee | NY |  | Batavia Substation 115kV | NM-NG | 0 | 2019-11-05
0166 | Cape Vincent Wind Power, LLC | St. Lawrence Wind Farm | 2005-02-08 | 75.9 | 75.9 | W | Jefferson | NY | E | Rockledge Substation 115kV | NM-NG | 0 | 2014-02-28
0167 | AES NY Wind, LLC | St. Lawrence Wind Farm II | 2005-02-08 | 80 |  | W | Jefferson | NY |  | Lyme Substation | NM-NG | 0 | 2019-06-05
0168 | Dairy Hills Wind Farm, LLC | Dairy Hills Wind Farm | 2005-02-08 | 120 | 120 | W | Wyoming | NY | C | Stolle Rd.-Meyer 230kV | NYSEG | 0 | 2012-03-01
0169 | Alabama Ledge Wind Farm, LLC | Alabama Ledge Wind Farm | 2005-02-08 | 79.8 | 79.8 | W | Genesee | NY | B | Oakfield-Lockport 115kV | NM-NG | 0 | 2012-06-01
0170 | Machias Wind Farm, LLC | Machias Wind Farm | 2005-02-08 | 90 | 90 | W | Cattaraugus | NY |  | Homer Hill-Gardenville 115kV | NM-NG | 0 | 2006-10-11
0176 | Noble Environmental Power, LLC | Wethersfield Windfield 115kV | 2005-02-14 | 129 | 129 | W | Wyoming | NY |  | Arcade Substation 115kV | Village of Arcade | 0 | 2006-07-18
0178 | Noble Allegany Windpark, LLC | Allegany Windpark | 2005-02-14 | 100.5 | 100.5 | W | Cattaraugus | NY | A | Freedom Substation 115kV | Village of Arcade | 0 | 2010-06-28
0179 | Noble Environmental Power, LLC | Cherry Hill Windpark | 2005-02-14 | 102 | 102 | W | Franklin | NY | E | Nicholville-Malone 115kV | NYSEG | 0 | 2009-02-05
0180 | Invenergy Wind, LLC | Buffalo Rd. Wind Farm | 2005-02-23 | 165 | 165 | W | Wyoming | NY |  | Stolle Rd.-Meyer 230kV | NYSEG | 0 | 2007-01-09
0180A | Green Power | Cody Rd | 2005-03-17 | 10 | 10 | W | Madison | NY | C | Fenner - Cortland 115kV | NM-NG | 0 | 2017-02-28
0181 | Everpower Global | Cold Spring Wind | 2005-03-21 | 69.3 |  | W | Cattaraugus | NY |  | Falconer-Homer Hill 115kV | NM-NG | 0 | 2019-09-05
0183 | Invenergy Wind, LLC | Buffalo Rd. Wind Farm II | 2005-03-28 | 165 | 165 | W | Wyoming | NY |  | Batavia 115kV | NYSEG/NM-NG | 0 | 2019-12-05
0184 | Invenergy Wind, LLC | Ripley Hill | 2005-03-28 | 75.9 |  | W | Onondaga | NY |  | Town of Spafford | NYSEG/NM-NG | 0 | 2019-08-05
0186 | Jordanville Wind, LLC | Jordanville Wind | 2005-04-01 | 80 | 80 | W | Herkimer | NY | E | Porter-Rotterdam 230kV | NM-NG | 0 | 2011-09-30
0187 | North Slope Wind Farm, LLC | North Slope Wind | 2005-04-05 | 109.5 | 109.5 | W | Clinton | NY | D | Willis-Plattsburgh 230kV | NYPA | 0 | 2009-02-05
0188 | NY Windpower, LLC | Orangeville Wind | 2005-04-05 | 96 |  | W | Wyoming | NY |  | 115kV | NYSEG | 0 | 2019-08-05
0189 | Atlantic Wind, LLC | Horse Creek Wind | 2005-04-08 | 126 | 126 | W | Jefferson | NY | E | Coffeen St-Thousand Island 115kV | NM-NG | 0 | 2014-04-30
0190 | PPM Energy, Inc. | Mixer Road Wind | 2005-04-08 | 66 | 66 | W | Jefferson | NY |  | West Adams 115kV | NM-NG | 0 | 2006-10-11
0191 | NY Regional | NY Regional | 2005-05-13 | 1200 | 1200 | DC | Oneida-Orange | NY | E, G | Edic - Rock Tavern | NM-NG/CH | 0 | 2009-04-08
0192 | Orion Energy, LLC | Orion Livingston | 2005-05-17 | 75 | 75 | W | Livingston | NY |  | Stolle Rd.-Meyer 230kV | NYSEG | 0 | 2019-01-06
0193 | Orion Energy, LLC | Orion Wyoming | 2005-05-17 | 60 | 60 | W | Wyoming | NY |  | South Perry 115kV | NYSEG | 0 | 2007-01-09
0194 | Calpine Energy Services | Bayonne | 2005-05-26 | 300 | 300 | ST | NY | NY |  | World Trade Center 138kV | CONED | 0 | 2019-02-06
0195 | Brookfield Power US | Harbor Cable Project II | 2005-06-14 | 200 | 200 | DC | Richmond | NY | J | Goethal 345kV | CONED | 0 | 2009-07-31
0196 | Roaring Brook Windpower, LLC | Roaring Brook | 2005-07-01 | 79.9 | 79.8 | W | Lewis | NY |  | Adirondak-Porter 230kV | NM-NG | 0 | 2006-07-10
0197 | PPM Roaring Brook, LLC / PPM | Roaring Brook Wind | 2005-07-01 | 78 | 78 | W | Lewis | NY | E | Boonville-Lowville 115kV | NM-NG | 0 | 2016-04-30
0198 | Arkwright Summit Wind Farm, LLC | Arkwright Summit Wind Farm | 2005-07-21 | 79.8 | 79.8 | W | Chautauqua | NY | A | Dunkirk-Falconer 115kV | NM-NG | 0 | 2013-09-30
0200 | Cavallo Power | Linden Power I | 2005-08-16 | 845 | 915 | CC | NY-NJ | NY |  | Goethal Substation | CONED | 0 | 2019-02-06
0201 | NRG Energy | Berrians GT | 2005-08-17 | 200 | 200 | CC | Queens | NY | J | Astoria West Substation 138kV | CONED | 0 | 2015-07-31
0202 | Liberty Generating Co. | 130 MW Uprate | 2005-08-25 | 130 | 130 | CT | NY-NJ | NY |  | Goethal 345kV | CONED | 0 | 2019-03-06
0203 | GenWy Wind, LLC | GenWy Wind Farm | 2005-10-21 | 478.5 | 478.5 | W | Genesee | NY | A | Stolle Rd - Homer City 345kV | NYSEG | 0 | 2010-03-31
0204 | Clipper Windpower Dev. Co. Inc. | Paragon II Wind Generation | 2005-10-27 | 150 | 150 | W | Steuben | NY | C | Avoca - Hillside 230kV | NYSEG | 0 | 2008-08-19
0204A | Duer's Patent Project, LLC | Beekmantown Windfarm | 2005-10-31 | 19.5 | 19.5 | W | Clinton | NY | D | Kents Falls - Sciota 115kV | NYSEG | 0 | 2013-03-31
0207 | Cape Vincent Wind Power, LLC | Cape Vincent | 2006-01-12 | 209.3 | 209.3 | W | Jefferson | NY | E | Rockledge Substation 115kV | NM-NG | 0 | 2014-02-28
0208 | CRC Development, LLC | Roundhouse Renewable | 2006-01-17 | 35 | 36 | ST | Otsego | NY |  | City of Oneonta | NYSEG | 0 | 2006-09-25
0209 | SUEZ Energy Generating NA, Inc | Nassau Generating | 2006-02-10 | 88 | 100 | CT | Nassau | NY |  | Garden City Substation 138kV | LIPA | 0 | 2007-07-10
0210 | Canadian Niagara Power, Inc. | Fortran | 2006-03-14 | 150 | 150 | AC | Niagara | NY | A | Huntley Station 115kV | NM-NG | 0 | 2010-03-31
0213 | Noble Environmental Power, LLC | Ellenburg II Windfield | 2006-04-03 | 21 | 21 | W | Clinton | NY | D | Willis-Plattsburgh WP-2 230kV | NYPA | 0 | 2013-04-30
0215 | Noble Burke Windpark, LLC | Noble Burke Windpark | 2006-04-03 | 120 | 120 | W | Franklin-Clinton | NY | D | Willis Substation 230kV | NYPA | 0 | 2009-02-05
0217 | AES Keystone Wind, LLC | Cherry Flats | 2006-06-06 | 90 | 90 | W | Tioga | PA | C | Homer City-Watercure 345kV | NYSEG | 0 | 2008-12-22
0218 | Gamesa Energy USA | Endless Mountain Wind | 2006-07-03 | 150 | 150 | W | Tioga - Bradford | PA |  | Homer City-Watercure 345kV | NYSEG | 0 | 2006-07-27
0219 | NRG Energy, Inc. | Huntley | 2006-07-12 | 752 | 752 | CC | Niagara | NY | A | Tonawanda | NM-NG | 0 | 2008-12-22
0220 | AES Keystone Wind, LLC | Armenia Mountain I | 2006-07-19 | 175 | 175 | W | Bradford | PA | C | Homer City-Watercure 345kV | NYSEG | 0 | 2008-08-19
0221 | AES Keystone Wind, LLC | Armenia Mountain II | 2006-07-19 | 75 | 75 | W | Bradford | PA | C | Homer City-Watercure 345kV | NYSEG | 0 | 2009-04-08
0222 | Ball Hill Windpark, LLC | Ball Hill Windpark | 2006-07-21 | 90 | 90 | W | Chautauqua | NY | A | Dunkirk-Gardenville 230kV | NM-NG | 0 | 2013-11-30
0223 | Noble Environmental Power, LLC | Arkwright Windpark | 2006-07-21 | 99 | 99 | W | Chautauqua | NY |  | Dunkirk-Falconer 115kV | NM-NG | 0 | 2007-03-12
0224 | NRG Energy, Inc. | Berrians GT II | 2006-08-23 | 50 | 90 | CC | Queens | NY | J | Astoria West Substation 138kV | CONED | 0 | 2015-07-31
0224B | Casella Waste Systems | Chemung Landfill | 2006-09-05 | 6.4 | 6.4 | M | Chemung | NY | C | 115kV | NYSEG | 0 | 2008-04-15
0225A | Schenectady International, Inc. | SII Rotterdam Junction | 2006-09-08 | 9.3 | 9.3 | Wo | Rotterdam | NY | F | 69kV | NM-NG | 0 | 2010-08-31
0225B | Burrstone Energy | Faxton/ St. Luke | 2006-09-15 | 2.2 | 2.2 | NG | Herkimer | NY | E | TBD | NM-NG | 0 | 2008-07-10
0226 | Cavallo Power | Linden | 2006-09-08 | 1200 | 1200 | CC | NY-NJ | NY |  | East 13th, West 49th | CONED | 0 | 2006-11-14
0227 | EC&R Northeast, LLC | Orleans Wind | 2006-09-28 | 120 | 120 | W | Orleans | NY | A | Shelby Substation - 115kV | NM-NG | 0 | 2008-10-14
0227A | Laidlaw Energy Group Inc. | Laidlaw Energy & Env. | 2006-10-30 | 7 | 7 | Wo | Cattaraugus | NY | A | 13.2kV | NM-NG | 0 | 2013-05-31
0228 | AES Bainbridge, LLC | Jennison | 2006-10-30 | 516 | 536 | C | Chenango | NY |  | TBD | NYSEG | 0 | 2007-04-24
0229 | AES Somerset 2, LLC | Somerset | 2006-11-01 | 687 | 706 | C | Niagara | NY |  | Somerset Substation 345kV | NYSEG | 0 | 2007-03-27
0230 | Cornell University | Cornell CHPP | 2006-11-02 | 30 | 30 | NG |  | NY |  | Maple Ave. Substation 115kV |  | 0 | 2006-11-21
0231 | Seneca Energy II, LLC | Seneca | 2006-11-02 | 6.4 | 6.4 | M | Seneca | NY | C | Goulds Substation 34.5kV | NYSEG | 0 | 2012-04-30
0235 | Gamesa Energy USA, LLC | Canfield Wind | 2006-12-12 | 120 | 120 | W | Tioga - Bradford | PA |  | Homer City-Watercure 345kV | NYSEG | 0 | 2007-10-16
0236 | Gamesa Energy USA, LLC | Dean Wind | 2006-12-14 | 150 | 150 | W | Tioga - Schuyler | NY | C | Watercure-Oakdale 345kV | NYSEG | 0 | 2011-04-30
0237 | Allegany Wind, LLC | Allegany Wind | 2007-01-09 | 72.5 | 72.5 | W | Cattaraugus | NY | A | Homer Hill Ð Dugan Rd. 115kV | NM-NG | 0 | 2015-02-28
0238 | Tonawanda Creek Wind, LLC | Tonawanda Creek Wind | 2007-01-30 | 75 | 75 | W | Genesee | NY | A | Lockport Ð Batavia 115kV | NM-NG | 0 | 2009-07-31
0239 | Western Door Wind, LLC | Western Door Wind | 2007-01-30 | 100 | 100 | W | Yates | NY | C | Greenidge Ð Haley Rd. 115kV | NYSEG | 0 | 2012-01-30
0239A | Innovative Energy System, Inc. | Modern Innovative Plant | 2007-01-31 | 6.4 | 6.4 | M | Niagara | NY | A | Youngstown Ð Sanborn 34.5kV | NM-NG | 0 | 2013-04-30
0240 | Noble Environmental Power, LLC | Farmersville Windpark | 2007-02-26 | 100 | 100 | W | Cattaraugus-PA | NY | A | Stolle Rd - Farmer's Valley 345kV | NM-NG | 0 | 2009-07-31
0241 | Noble Chateaugay Windpark II, LLC | Chateaugay II Windpark | 2007-03-15 | 19.5 | 19.5 | W | Franklin | NY | D | Chateaugay Substation 34.5kV | NYSEG | 0 | 2012-08-31
0242 | RG&E | Brown's Race Uprate | 2007-04-09 | 6 | 6 | H | Monroe | NY |  | Brown's Race Substation | NYSEG | 0 | 2007-06-05
0243 | Astoria Energy, LLC | Astoria Uprate | 2007-04-12 | 100 | 230 | CC | Queens | NY | J | Astoria East Substation 138kV | ConEd | 0 | 2010-03-31
0244 | AES Bainbridge, LLC | Jennison | 2007-04-13 | 650 | 650 | C | Chenango | NY |  | Oakdale Ð Fraser 345kV | NYSEG | 0 | 2008-03-20
0246 | PPM Energy, Inc | Dutch Gap Wind | 2007-06-01 | 250 | 250 | W | Jefferson | NY | E | Indian River - Black Rive 115kV | NM-NG | 0 | 2012-03-01
0247 | RG&E | Russell Station | 2007-06-11 | 300 | 325 | CC | Monroe | NY | B | Russell Station 115kV | RG&E | 0 | 2012-04-30
0248 | RG&E | Russell Station II | 2007-06-11 | 300 | 300 | C | Monroe | NY |  | Russell Station 115kV | NYSEG | 0 | 2007-10-02
0249 | Hess Corporation | Bayone Energy Center II | 2007-06-20 | 250 | 250 | D | Bayonne | NJ |  | Gowanus Substation 138kV | ConEd | 0 | 2007-10-02
0252 | Brookfield Power | Manhattan Cable | 2007-08-01 | 350 | 350 | DC | NY | NY | J | World Trade Center 138 kV | ConEd | 0 | 2008-07-10
0253 | Marble River, LLC | Marble River SPS | 2007-08-13 | TBD | TBD | AC | Clinton | NY | D | Moses-Willis-Plattsburgh 230kV | NYPA | 0 | 2012-06-30
0254 | Ripley-Westfield Wind LLC | Ripley-Westfield Wind | 2007-08-14 | 124.2 | 124.2 | W | Cahatauqua | NY | A | Ripley - Dunkirk 230kV | NM-NG | 0 | 2012-03-01
0255 | In-City, LLC | Cross Hudson | 2007-08-23 | 550 | 550 | CC | NY-NJ | NY | J | W49th Street 345kV | ConEd | 0 | 2008-07-01
0256 | Niagara Shore Winds, LLC | Niagara Shore Wind | 2007-09-04 | 70.5 | 70.5 | W | Niagara | NY | A | Somerset Switch Yard 345kV | NYSEG | 0 | 2010-03-31
0257 | RG&E | Brown's Race Uprate | 2007-09-12 | 2 | 2 | H | Monroe | NY | B | Beebee Station 34kV | RG&E | 0 | 2011-03-31
0258 | Babcock & Brown, LP | Ripley-Westfield Wind II | 2007-09-24 | 124.8 | 124.8 | W | Chautauqua | NY |  | Ripley - Dunkirk 230kV | NM-NG | 0 | 2007-10-16
0259 | Delaware County Electric | Delaware County Landfill | 2007-09-24 | 1 | 1 | M | Delaware | NY |  | TBD | NYSEG | 0 | 2008-01-29
0261 | Astoria Generating Company | South Pier Improvement | 2007-10-02 | 105 | 108 | CT | Kings | NY | J | Gowanus 138kV | ConEd | 0 | 2012-03-01
0262 | RP Wind NY, LLC | Schoharie Highlands | 2007-10-05 | 70 | 70 | W | Schoharie | NY | F | 69kV | NM-NG | 0 | 2009-05-12
0264 | RG&E | Seth Green | 2007-10-23 | 2.8 | 2.8 | H | Monroe | NY | B | 11kV | RG&E | 0 | 2014-03-31
0265 | CityGreen Transmission | CityGreen | 2007-11-16 | 1100 | 1100 | DC | Westchester-Queens | NY | H, J | Millwood - Farragut/Rainey 345kV | ConEd | 0 | 2010-03-31
0266 | NRG Energy, Inc. | Berrians GT III | 2007-11-28 | 250 | 290 | CC | Queens | NY | J | Astoria Annex 345kV | NYPA | 0 | 2015-06-30
0267 | Winergy Power, LLC | Winergy NYC Wind Farm | 2007-11-30 | 600 | 600 | W | NY | NY | J | Gowanus Substation 345kV | ConEd | 0 | 2012-07-31
0268 | NRG Energy, Inc. | Arthur Kill | 2007-12-07 | 800 | 800 | CC | NY | NY | J | Gowanus Substation | ConEd | 0 | 2008-07-10
0269 | WM Renewable Energy, LLC | Madison County Landfill | 2007-12-10 | 2 | 2 | M | Madison | NY |  | Canastota | NM-NG | 0 | 2008-01-29
0270 | Wind Development Contract Co LLC | Hounsfield Wind | 2007-12-13 | 244.8 | 244.8 | W | Jefferson | NY | E | Fitzpatrick - Edic 345kV | NYPA | 0 | 2016-07-31
0271 | State Line Wind Power LLC | State Line Wind | 2007-12-20 | 124.8 | 124.8 | W | Chautauqua | NY | A | South Ripley - Dunkirk 230kV | NM-NG | 0 | 2011-10-31
0272 | NYPA | Benchmark Generator | 2007-12-20 | 900 | 1080 | CT | Queens | NY | J | Astoria 345kV | NYPA | 0 | 2009-04-08
0273 | Winergy Power, LLC | Winergy Long Island Wind | 2007-12-21 | 299 | 299 | W | Suffolk | NY | K | Sterling Substation | LIPA | 0 | 2008-07-10
0274 | In City I, LLC | PSEG Fossil Bergen Unit 2 | 2008-01-23 | 100 | 100 | CC | NY-NJ | NY | J | W49th Street 345kV | ConEd | 0 | 2008-07-10
0275 | Shell Wind Energy Inc. | Cayuga County Wind | 2008-01-24 | 120 | 120 | W | Cayuga | NY | C | Milliken - Wright Ave. 115kV | NYSEG | 0 | 2009-04-08
0277 | UniStar Nuclear Energy | Nine Mile Point Station Unit #3 | 2008-02-04 | 1640 | 1660 | NU | Oswego | NY | C | Scriba Substation 345kV | NM-NG | 0 | 2009-12-22
0278 | Riverbank Power Corporation | Riverbank Power A | 2008-02-20 | 1000 | 1000 | PS | Niagara | NY | A | Niagara - Rochester 345kV | NYPA | 0 | 2009-06-24
0279 | Riverbank Power Corporation | Riverbank Power D1 | 2008-02-20 | 1000 | 1000 | PS | St. Lawrence | NY | E | Massena 765kV | NYPA | 0 | 2010-03-31
0280 | Riverbank Power Corporation | Riverbank Power D2 | 2008-02-20 | 1000 | 1000 | H | St. Lawrence | NY | E | Massena 765kV | NYPA | 0 | 2008-10-14
0281 | Riverbank Power Corporation | Riverbank Power G | 2008-02-20 | 1000 | 1000 | PS | Rockland | NY | G | West Haverstraw 345kV | ConEd/O&R | 0 | 2010-11-30
0282 | Concord Wind Power LLC | Concord Wind | 2008-02-28 | 101.2 | 101.2 | W | Chautauqua | NY | A | Dunkirk - South Ripley 230kV | NM-NG | 0 | 2011-05-31
0283 | Riverbank Power Corporation | Riverbank Power J | 2008-03-03 | 1000 | 1000 | H | Queens | NY | J | Poletti Substation 345kV | NYPA | 0 | 2008-04-15
0285 | Machias Wind Farm, LLC | Machias I | 2008-03-27 | 79.2 | 79.2 | W | Cattaraugus | NY | A | Gardenville - Homer Hill 115kV | NM-NG | 0 | 2012-06-30
0286 | Machias Wind Farm, LLC | Machias II | 2008-03-27 | 199.5 | 199.5 | W | Cattaraugus | NY | A | 345kV | NYSEG | 0 | 2009-04-08
0287 | Horizon Wind Energy, LLC | Pomfret | 2008-03-27 | 73.5 | 73.5 | W | Chautauqua | NY | A | Dunkirk - Falconer 115kV | NM-NG | 0 | 2010-09-30
0288 | Chateaugay River Wind Farm, LLC | Chateaugay River | 2008-03-31 | 120 | 120 | W | Franklin | NY | E | Willis Substation 230kV | NYPA | 0 | 2009-02-05
0290 | National Grid | Paradise | 2008-04-03 | N/A | N/A | AC | Niagara | NY | A | Paradise Station 115kV | NM-NG | 0 | 2011-03-31
0291 | Long Island Cable, LLC | LI Cable - Phase 1 | 2008-04-14 | 440 | 440 | W | Suffolk | NY | K | Ruland Road 138kV | LIPA | 0 | 2012-07-31
0292 | Long Island Cable, LLC | LI Cable - Phase 2a | 2008-04-14 | 220 | 220 | W | Suffolk | NY | K | Ruland Road 138kV | LIPA | 0 | 2012-07-31
0293 | Long Island Cable, LLC | LI Cable - Phase 2b | 2008-04-14 | 280 | 280 | W | Suffolk | NY | K | Ruland Road 138kV | LIPA | 0 | 2008-12-22
0295 | CCH Holdings Group, LLC | Cross Hudson II | 2008-05-06 | 800 | 800 | AC | NY-NJ | NY | J | West 49th St. Substation 345kV | ConEd | 0 | 2012-06-01
0296 | Noble Environmental Power, LLC | Harrigan Hill Wind | 2008-05-12 | 100.5 | 100.5 | W | Clinton-Ellenburg | NY | D | Lyon Mt - Willis 115kV | NYSEG | 0 | 2009-07-31
0297 | Ashford Wind Farm, LLC | Ashford Wind | 2008-05-16 | 19.9 | 19.9 | W | Cattaraugus | NY | A | Otto-West Valley 34.5kV | NM-NG | 0 | 2010-03-31
0298 | TCI Renewable, LLC | Leicester Wind | 2008-05-22 | 57 | 57 | W | Livingston | NY | A | Highbank - Mortimer 115kV | NYSEG | 0 | 2010-08-31
0299 | Erie Boulevard Hydropower | Great Bend | 2008-06-03 | 14.4 | 14.4 | H | Jefferson | NY | E | Deferiet 115 kV substation | NM-NG | 0 | 2009-04-08
0300 | Auburn Public Power Agency | Auburn Sewage Treatment | 2008-06-26 | 3 | 3 |  | Onondaga | NY | C | Auburn, NY | NYSEG | 0 | 2008-10-14
0301 | Hamlin Wind, LLC | Hamlin Wind Farm | 2008-07-15 | 80 | 80 | W | Monroe | NY | A | West Hamlin 115kV | NM-NG | 0 | 2010-03-31
0302 | Barre Wind, LLC | Barre Wind Farm | 2008-07-15 | 120 | 120 | W | Orleans | NY | A | Lockport - Mortimer 115 KV | NM-NG | 0 | 2008-12-22
0303 | Invenergy Thermal Devel., LLC | Tioga County Energy | 2008-07-17 | 620 | 700 | CT | Tioga | NY | C | Oakdale - Watercure 345kV | NYSEG | 0 | 2009-04-08
0304 | Transmission Developers Inc. | Clay HVDC | 2008-07-18 | 2000 | 2000 | DC | NY | NY | J | Clay to Farragut 345kV | NM-NG/ConEd | 0 | 2008-08-28
0305 | TDI-USA Holdings Corporation | Champlain Hudson Power Express | 2008-07-18 | 1000 | 1000 | DC | Quebec - NY | NY | J | Astoria Annex Substation 345kV | NYPA | 0 | 2017-01-31
0306 | Transmission Developers Inc. | Clay HVDC | 2008-07-18 | 2000 | 2000 | DC | Onondaga/NY | NY | C, J | Clay 345kV - Sherman Creek 138 kV | NM-NG/ConEd | 0 | 2011-11-30
0307 | NY Wire, LLC | NY Wire-Phase 1 | 2008-07-29 | 550 | 550 | DC | NJ-Kings | NY | J | Gowanus Substation 345kV | ConEd | 0 | 2012-07-31
0309 | AP Dutchess Properties Inc. | Wingdale Energy Center | 2008-09-11 | 650 | 650 | CC | Dutchess | NY | G | Pleasant Valley - Long Mt. | ConEd | 0 | 2009-05-12
0310 | Cricket Valley Energy Center, LLC | Cricket Valley Energy Center | 2008-09-22 | 1019.9 | 1136 | CC | Dutchess | NY | G | Pleasant Valley - Long Mt. 345kV | ConEd | 0 | 2014-12-31
0312 | RP Wind NY, LLC | Gateway Wind Energy | 2008-09-25 | 79.2 | 79.2 | W | Schenectady | NY | F | Princetown - Rotterdam | NM-NG | 0 | 2009-04-08
0313 | Atlantic Wind, LLC | Stone Church Wind | 2008-09-30 | 150 | 150 | W | St. Lawrence | NY | E | Mc Intyre Substation 115 kV | NM-NG | 0 | 2011-03-31
0314 | Riverbank Power Corporation | Oswego | 2008-10-07 | 1000 | 1000 | PS | Oswego | NY | C | Oswego complex 345kV | NM-NG | 0 | 2009-06-24
0315 | CRC Renewables, LLC | Onondaga Renewables | 2008-10-23 | 47 | 47 | Wo | Onondaga | NY | C | Geres Lock 115kV | NM-NG | 0 | 2012-01-30
0316 | State Line Wind Power, LLC | State Line Wind II | 2008-10-31 | 124.8 | 124.8 | W | Chautauqua | NY | A | Dunkirk - South Ripley 230kV | NM-NG | 0 | 2009-10-28
0317 | CityGreen Transmission Inc. | CityGreen AC | 2008-11-05 | 1100 | 1100 | AC | Wsch'r/Bkln/Qns | NY | H, J | Millwood 345kV - Farragut/Rainey | ConEd | 0 | 9/30/09
0319 | AES Energy Storage, LLC | Cayuga Energy Storage | 2008-12-03 | 20 | 20 | ES | Onondaga | NY | C | Milliken 115kV | NYSEG | 0 | 2012-06-01
0320 | AES Energy Storage, LLC | Somerset Energy Storage | 2008-12-03 | 20 | 20 | ES | Niagara | NY | A | Somerset 69kV | NYSEG | 0 | 2012-06-01
0321 | Monroe County | Monroe County Landfill | 2009-01-02 | 6.4 | 6.4 | M | Monroe | NY | B | Sanford Rd. | NM-NG | 0 | 2009-09-30
0322 | Rolling Upland Wind Farm, LLC | Rolling Upland Wind | 2009-01-13 | 59.9 | 59.9 | W | Madison | NY | E | County Line - Brothertown 115kV | NYSEG | 0 | 2014-08-31
0323 | Riverbank Power Corporation | Verplanck | 2009-01-23 | 1000 | 1000 | PS | Westchester | NY | H | Indian Point 345kV | ConEd/O&R | 0 | 2009-06-24
0324 | Belltown Biogas, LLC | Belltown Bio | 2009-03-06 | 2 | 2 | M | Cayuga | NY | C | King Ferry | NYSEG | 0 | 2009-04-08
0325 | Synergy Biogas, LKc | Synergy Bio | 2009-03-06 | 2 | 2 | M | Wyoming | NY | A | Wyoming | NM-NG | 0 | 2009-04-08
0327 | Con Edison | Offshore Wind | 2009-03-20 | 700 | 700 | W | NY-Suffolk | NY | J, K | Far Rockaway 69kV | LIPA | 0 | 2011-06-30
0328 | Steuben Rural | Steuben County Landfill | 2009-03-23 | 4.8 | 4.8 | M | Steuben | NY | C | Quarry - Bath 34.5 | NYSEG | 0 | 2009-05-27
0329 | Horizon Wind Energy, LLC | Madison Wind Expansion | 2009-03-23 | 8.3 | 8.3 | W | Madison | NY | E | County Line - Brothertown 115kV | NYSEG | 0 | 2009-05-27
0332 | FitzPatrick Nuclear Station | FitzPatrick Nuclear Uprate | 2009-05-01 | 112 | 112 | NU | Oswego | NY | C | FitzPatrick Substation | NYPA | 0 | 2009-06-24
0334 | Atlantic Wind, LLC | Sangerfield Wind | 2009-05-28 | 46 | 46 | W | Onieda | NY | E | TBD | NM-NG/NYSEG | 0 | 2009-07-31
0335 | NextEra Energy Resources, LLC | Cold Creek Spring Wind | 2009-06-09 | 150.7 | 150.7 | W | Cattaraugus | NY | A | Carrs Corners - Salamanca 115kV | NM-NG | 0 | 2012-08-31
0336 | Enfield Energy, LLC | Black Oak Wind | 2009-06-29 | 50 | 50 | W | Thompkins | NY | C | Black Oak Rd 115kV | NYSEG | 0 | 2012-06-30
0338 | RG&E | Brown's Race II | 2009-08-11 | 6.3 | 6.3 | H | Monroe | NY | B | Station 137 11kV | RG&E | 0 | 2019-12-31
0341 | Covanta Energy | Hempstead Expansion | 2009-09-02 | 37 | 39 | ST | Nassau | NY | K | Hempstead 138kV | LIPA | 0 | 2010-08-31
0343 | Champlain Wind Link, LLC | Champlain Wind Link I | 2009-09-29 | 600 | 600 | AC | Clinton | NY | D | Plattsburgh - New Haven, VT 230kV | NYPA | 0 | 2012-07-31
0344 | Champlain Wind Link, LLC | Champlain Wind Link II | 2009-09-29 | 600 | 600 | AC | Clinton | NY | D | Plattsburgh - New Haven, VT 345kV | NYPA | 0 | 2012-04-30
0345 | St. Elizabeth Medical Center | St. Elizabeth Medical Center | 2009-11-02 | 2.3 | 2.3 | NG | Herkimer | NY | E |  | NM-NG | 0 | 2009-11-30
0346 | Beacon Power | Scotia Industrial Park | 2009-11-24 | 20 | 20 | F | Schenectady | NY | F | Spier - Rotterdam | NM-NG | 0 | 2012-08-31
0347 | Franklin Wind Farm, LLC | Franklin Wind | 2009-12-02 | 50.4 | 50.4 | W | Delaware | NY | E | Oakdale - Delhi 115kV | NYSEG | 0 | 2019-01-31
0348 | Casella Waste Systems | Hyland Landfill | 2009-12-02 | 0.8 | 0.8 | M | Allegany | NY | B | Station 249 | RG&E | 0 | 2010-04-30
0349 | Taylor Biomass Energy-Montgomery, LLC | Taylor Biomass | 2009-12-30 | 19 | 22.5 | SW | Orange | NY | G | Maybrook - Rock Tavern 69kV | CHGE | 0 | 2021-06-30
0350 | Lake Erie Wind, LLC | Lake Erie Wind | 2010-02-16 | 810 | 810 | W | Chautauqua | NY | A | Dunkirk - Gardenville 230kV | NM-NG | 0 | 2012-01-30
0351 | Linden VFT, LLC | Linden VFT Uprate | 2010-03-02 | 15 | 15 | AC | Richmond | NY | J | Goethals 345kV | CONED | 0 | 2013-02-28
0352 | WM Renewable Energy | Oneida-Herkimer Landfill | 2010-04-08 | 3.2 | 3.2 | M | Oneida | NY | E |  |  | 0 | 2010-06-04
0354 | Atlantic Wind, LLC | North Ridge Wind | 2010-05-13 | 100 | 100 | W | St. Lawrence | NY | E | Nicholville - Parishville 115kV | NM-NG | 0 | 2015-01-31
0356 | Pattern Renewables | Hounsfield Wind | 2010-09-07 | 249.4 | 249.4 | W | Jefferson | NY | E | Oswego Substation 345kV | NYPA | 0 | 2010-11-30
0357 | West Point Partners, LLC | NY Power Pathway | 2010-09-10 | 1000 | 1000 | DC | Albany-Westchester | NY | F, H | New Scotland - Buchanan South 345kV | NM-NG/Coned | 0 | 2013-02-28
0358 | West Point Partners, LLC | West Point Transmission | 2010-09-13 | 1000 | 1000 | DC | Greene, Westchester | NY | F, H | Leeds - Buchanan North 345kV | NM-NG/ConEd | 0 | 2018-01-31
0360 | NextEra Energy Resources, LLC | Watkins Glen Wind | 2010-12-22 | 122.4 | 122.4 | W | Schuyler | NY | C | Bath - Montour Falls 115 kV | NYSEG | 0 | 2015-05-31
0361 | US PowerGen Co. | Luyster Creek Energy | 2011-02-15 | 401 | 444 | D | Queens | NY | J | Astoria West Substation 138kV | CONED | 0 | 2020-02-29
0362 | Monticello Hills Wind, LLC | Monticello Hills Wind | 2011-03-07 | 19.8 | 19.8 | W | Ostego | NY | E | W. Winfield - Richfield Spring 46kV | NYSEG | 0 | 2017-04-30
0363 | Anbaric Development Partners, LLC | Poseidon Offshore | 2011-04-27 | 500 | 500 | W | NY - Suffolk | NY | K | Ruland Rd. 138kV | LIPA | 0 | 2020-07-31
0364 | Bruce Hill Wind, LLC | Bruce Hill Wind | 2011-05-04 | 18 | 18 | W | Delaware | NY | E | Axtell Road Substation 115 kV | NYSEG | 0 | 2012-09-30
0365 | Transmission Developers Inc. | Champlain Hudson SPS | 2011-07-15 | TBD | TBD | AC | Queens | NY | J | Astoria and Farragut Subsations | ConEd/NYPA | 0 | 2012-12-31
0366 | NextEra Energy Resources, LLC | Watkins Glen East | 2011-08-02 | 150.6 | 150.6 | W | Schuyler | NY | C | Montour Falls Substation | NYSEG | 0 | 2012-10-31
0367 | Orange & Rockland | North Rockland Transformer | 2011-09-14 | N/A | N/A | AC | Rockland | NY | G | Line Y94 345kV | ConEd | 0 | 2018-07-31
0369 | Clover Leaf Power, LLC | Clover Leaf Hollers Ave | 2011-10-24 | 173.9 | 192.8 | CT | Bronx | NY | J | E 179th St. Subsation 138kV | ConEd | 0 | 2013-12-31
0370 | Smokey Avenue Wind, LLC | Smokey Avenue Wind | 2011-10-28 | 18 | 18 | W | Otsego | NY | F | Worcester - Schenevus 23kV | NM-NG | 0 | 2014-01-31
0371 | South Mountain Wind, LLC | South Mountain Wind | 2011-10-31 | 18 | 18 | W | Delaware | NY | E | River Rd Substation 46kV | NYSEG | 0 | 2018-01-31
0372 | Dry Lots Wind, LLC | Dry Lots Wind | 2011-10-31 | 33 | 33 | W | Herkimer | NY | E | Schuyler - Whitesboro 46kV | NM-NG | 0 | 2021-02-28
0374 | CPV Valley, LLC | CPV Valley II | 2012-02-21 | 820 | 820 | CC | Wawayanda | NY | G | Rock Tavern-Coopers Corners 345kV | NYPA | 0 | 2015-09-30
0376 | Ridgeline Energy, LLC | Troups Creek Wind | 2012-03-07 | 32 | 32 | W | Steuben | NY | C | Troupsburg Substation | NYSEG | 0 | 2012-04-30
0376A | Atlantic Development, LLC | Atlantice Development | 2012-03-15 | N/A | N/A | W | N/A | NY | N/A | N/A | N/A | 0 | 2009-07-31
0377 | Monroe County | Monroe County Mill Seat | 2012-03-16 | 3.2 | 3.2 | M | Monroe | NY | B | Sanford Rd. 34.5kV | NM-NG | 0 | 2016-04-30
0379 | Seneca Energy II, LLC | Seneca II Expansion | 2012-04-24 | 6.4 | 6.4 | M | Seneca | NY | C | Seneca - Waterloo 34.5kV | NYSEG | 0 | 2013-05-31
0381 | Clipper Wind Power Development | Paragon Wind | 2012-05-15 | 79.9 | 79.9 | W | Steuben-Schuyler | NY | C | Stony Ridge - Hillside 230kV | NYSEG | 0 | 2012-10-31
0382 | Astoria Generating Co. | South Pier Improvement | 2012-05-30 | 91.2 | 95.5 | CT | Kings | NY | J | Gowanus Substation 138kV | ConEd | 0 | 2018-03-31
0383 | NRG Energy, Inc. | Bowline Gen. Station Unit #3 | 2012-05-30 | 775 | 814 | CC | Rockland | NY | G | Ladentown Substation 345kV | O&R | 0 | 2019-07-31
0384 | National Grid | Knickerbocker Pleasant Valley | 2012-06-15 | TBD | TBD | AC | Columbia-Dutchess | NY | F, G | Knickerbocker - P. Valley 345kV | NM-NG/ConEd | 0 | 2016-05-31
0385 | National Grid | Hudson Valley Reinforcement | 2012-06-15 | TBD | TBD | AC | Alb.-Col.-Dutch. | NY | F, G | N. Scotland-Leeds-P. Valley 345kV | NM-NG/ConEd | 0 | 2015-02-28
0386 | Vermont Green Line Devco, LLC | Grand Isle Intertie | 2012-06-28 | 400 | 400 | DC | Clinton | NY | D | Plattsburgh 230kV-New Haven, VT 345kV | NYPA | 0 | 2022-10-31
0388 | Enel Green Power North America | Dexter Solar | 2012-07-24 | 17 | 17 | S | Jefferson | NY | E | Dexter Stubstation | NM-NG | 0 | 2012-09-30
0389 | GUSC Energy, Inc. | Griffiss Technology Park | 2012-08-14 | 0.9 | 0.9 | ST | Oneida | NY | E | Boonville - Rome 115kV | NM-NG | 0 | 2012-09-30
0391 | North America Transmission, LLC | Edic - Fraser #2 | 2012-09-21 | TBD | TBD | AC | Oneida-Delaware | NY | E | Edic - Fraser 345kV | NM-NG/NYSEG | 0 | 2016-01-31
0392 | Exelon Corporation | Scriba-Volney | 2012-10-05 | TBD | TBD | AC | Oswego | NY | C | Scriba - Volney 345kV | NM-NG/NYSEG | 0 | 2016-05-31
0393 | NRG Berrians East Development, LLC | Berrians East Replacement | 2012-10-16 | 94.2 | 57 | D | Queens | NY | J | Astoria East 138kV Substation | CONED | 0 | 2023-01-31
0398 | Black Oak Wind Farm, LLC | Black Oak Wind | 2013-01-10 | 12.5 | 12.5 | W | Thompkins | NY | C | Montour - Coddington 115kV | NYSEG | 0 | 2017-08-31
0399 | American Electric Power | Mohawk Valley HVDC | 2013-02-27 | 1000 | 1000 | DC | Oneida-Bronx | NY | E, J | Marcy - Mott Haven 345kV | NYPA/ConEd | 0 | 2013-06-30
0400 | East Coast Power LLC | Linden Cogen Uprate | 2013-03-04 | 208 | 204 | CT | Linden | NJ | J | Linden Cogen 345kV | ConEd | 0 | 2015-10-31
0401 | Caithness Long Island II, LLC | Caithness Long Island II | 2013-03-22 | 599 | 632 | D | Suffolk | NY | K | Sills Road Substation 138kV | LIPA | 0 | 2018-09-30
0402 | NextEra Energy Transmission | Marcy - PV 345 | 2013-05-17 | TBD | TBD | AC | Oneida-Dutchess | NY | E-G | Marcy - P. Valley 345kV | NM-NG/NYPA/ ConEd | 0 | 2015-02-28
0404 | NextEra Energy Transmission | Princetown - Rotterdam 230 | 2013-06-04 | TBD | TBD | AC | Schenectady | NY | F | Princetown - Rotterdam 230kV | NM-NG | 0 | 2016-05-31
0405 | NextEra Energy Transmission | Oakdale - Fraser 345 | 2013-06-21 | TBD | TBD | AC | Broome-Delaware | NY | C, E | Oakdale - Fraser 345kV | NYSEG | 0 | 2015-12-31
0406 | NextEra Energy Transmission | Marcy - KB - PV 345 | 2013-06-21 | TBD | TBD | AC | Oneida-Dutchess | NY | E-G | Marcy - P. Valley 345kV | NM-NG/NYPA/ ConEd | 0 | 2015-02-28
0407 | National Grid | Edic-N.Scotland-Leed-PV | 2013-07-01 | TBD | TBD | AC | Oneida-Dutchess | NY | E-G | Edic - Pleasant Valley 345kV | NM-NG | 0 | 2015-02-28
0408 | National Grid | Edic-Princetown-N.Scotland-Leeds-PV | 2013-07-01 | TBD | TBD | AC | Oneida-Dutchess | NY | E, G | Edic - Pleasant Valley 345kV | NM-NG | 0 | 2015-02-28
0409 | National Grid | Edic-Knickerbocker-PV | 2013-07-01 | TBD | TBD | AC | Oneida-Dutchess | NY | E, G | Edic - Pleasant Valley 345kV | NM-NG | 0 | 2015-02-28
0410 | National Grid | Edic-Princetown-Knickerbocker-PV | 2013-07-01 | TBD | TBD | AC | Oneida-Dutchess | NY | E, G | Edic - Pleasant Valley 345kV | NM-NG | 0 | 2015-02-28
0411 | BCDC Transmission LLC | BCDC Transmission | 2013-07-01 | 400 | 400 | AC | NY | NY | J | NJ - Farragut Substation 345kV | ConEd | 0 | 2013-12-31
0412 | NY State Electric & Gas | Oakdale - Fraser 345 | 2013-08-20 | N/A | N/A | AC | Broome-Delaware | NY | C, E | Oakdale - Fraser 345kV | NYSEG | 0 | 2016-07-31
0413 | National Grid | Edic-Prince.-N.Scotland-Knick.-PV | 2013-08-21 | TBD | TBD | AC | Oneida-Dutchess | NY | E, G | Edic - Pleasant Valley 345kV | NM-NG | 0 | 2015-02-28
0414 | North America Transmission, LLC | Segment B Enhanced | 2013-09-05 | N/A | N/A | AC | Albany-Dutchess | NY | F, G | New Scotland - P. Valley 345kV | NM-NG/ConEd/ O&R/CHGE | 0 | 2019-04-30
0415 | Iberdrola USA | Connect NY | 2013-09-06 | 1000 | 1000 | DC | Albany-Dutchess | NY | F, G | New Scotland - Hurley Ave 345kV | NM-NG/Cen Hud | 0 | 2014-10-31
0416 | NextEra Energy Transmission | Marcy - KB - PV 345 (2) | 2013-09-09 | TBD | TBD | AC | Oneida-Dutchess | NY | E, G | Marcy - P. Valley 345kV | NM-NG/NYPA/ ConEd | 0 | 2015-02-28
0417 | NextEra Energy Transmission | Marcy - KB - PV 345 (3) | 2013-09-09 | TBD | TBD | AC | Oneida-Dutchess | NY | E, G | Marcy - P. Valley 345kV | NM-NG/NYPA/ ConEd | 0 | 2016-05-31
0418 | NextEra Energy Transmission | Marcy - NS - PV 345 | 2013-09-09 | TBD | TBD | AC | Oneida-Dutchess | NY | E, G | Marcy - P. Valley 345kV | NM-NG/NYPA/ ConEd | 0 | 2015-03-31
0419 | NextEra Energy Transmission | Marcy - NS - KB - PV 345 | 2013-09-16 | TBD | TBD | AC | Oneida-Dutchess | NY | E, G | Marcy - P. Valley 345kV | NM-NG/NYPA/ ConEd | 0 | 2016-05-31
0420 | NextEra Energy Transmission | Marcy - KB - PV 345 (4) | 2013-09-16 | TBD | TBD | AC | Oneida-Dutchess | NY | E, G | Marcy - P. Valley 345kV | NM-NG/NYPA/ ConEd | 0 | 2015-02-28
0424 | Boundless Energy NE, LLC | Leeds Path West | 2013-11-26 | N/A | N/A | AC | Greene-Westchester | NY | G-J | Leeds - Millwood 345kV | NM-NG/NYPA/ Cen Hud/ConEd/NYSEG | 0 | 2017-02-28
0425 | NextEra Energy Resources, LLC | Brookfield Wind Energy | 2013-12-11 | 100.3 | 100.3 | W | Chenango, Madison | NY | E | Chadwicks - Yahnundadis 115kV | NM-NG/NYSEG | 0 | 2015-05-31
0426 | North America Transmission, LLC | NS-Knickerbocker-PV | 2013-12-11 | TBD | TBD | AC | Albany-Dutchess | NY | F-G | New Scotland - P. Valley 345kV | NM-NG/ConEd | 0 | 2014-02-28
0427 | Island Park Energy Center, LLC | Island Park Energy Center CCPP | 2014-01-24 | 268 | 295 | CT | Nassau | NY | K | Barrett Power Station 138kV | LIPA | 0 | 2017-02-28
0428 | Island Park Energy Center, LLC | Island Park Energy Center SCPP | 2014-01-24 | 262 | 252 | CT | Nassau | NY | K | Barrett Power Station 138kV | LIPA | 0 | 2017-02-28
0433 | East Hampton Solar Farm, LLC | East Hampton - Phase 1 | 2014-04-21 | 20 | 20 | S | Suffolk | NY | K | Amagansett Substation 69KV | LIPA | 0 | 2014-05-31
0434 | East Hampton Solar Farm 2, LLC | East Hampton - Phase 2 | 2014-04-21 | 20 | 20 | S | Suffolk | NY | K | Amagansett Substation 69KV | LIPA | 0 | 2014-05-31
0435 | East Hampton Solar Farm 2, LLC | East Hampton - Phase 3 | 2014-04-21 | 20 | 20 | S | Suffolk | NY | K | Amagansett Substation 69KV | LIPA | 0 | 2014-05-31
0436 | East Hampton Solar Farm 2, LLC | Riverhead - Phase 1 | 2014-04-21 | 20 | 20 | S | Suffolk | NY | K | Edwards Substation 69KV | LIPA | 0 | 2014-05-31
0437 | East Hampton Solar Farm 2, LLC | Riverhead - Phase 2 | 2014-04-21 | 20 | 20 | S | Suffolk | NY | K | Edwards Substation 69KV | LIPA | 0 | 2014-05-31
0438 | East Hampton Solar Farm 2, LLC | Riverhead - Phase 3 | 2014-04-21 | 20 | 20 | S | Suffolk | NY | K | Edwards Substation 69KV | LIPA | 0 | 2014-05-31
0439 | Boston Energy Trading | East Garden City-Valley Stream | 2014-05-09 | TBD | TBD | AC | Nassau | NY | K | E. Garden City-Valley Stream 138kV | LIPA | 0 | 2016-04-30
0440 | Erie Power, LLC | Erie Power | 2014-06-02 | 79.4 | 88 | CC | Chautauqua | NY | A | South Ripley Substation 230kV | NM-NG | 0 | 2018-02-28
0441 | East Hampton Solar Farm, LLC | East Hampton Solar | 2014-06-09 | 60 | 60 | S | Suffolk | NY | K | Buell Substation 69kV | LIPA | 0 | 2015-01-31
0442 | Riverhead Solar Farm, LLC | Riverhead Solar | 2014-06-09 | 24 | 24 | S | Suffolk | NY | K | Edwards Substation 138kV | LIPA | 0 | 2015-05-31
0443 | Manorville Solar, LLC | Manorville Solar | 2014-06-09 | 16 | 16 | S | Suffolk | NY | K | Riverhead - Eastport 69kV | LIPA | 0 | 2015-04-30
0445 | Lighthouse Wind, LLC | Lighthouse Wind | 2014-06-30 | 201.3 | 201.3 | W | Niagara | NY | A | AES Somerset Substation 345kV | NYSEG | 0 | 2021-02-28
0446 | Solar Alliance Freedom, Inc. | Jockey Hill Solar | 2014-07-21 | 2 | 2 | S | Ulster | NY | G | Hurley Substation 345kV | CenHud | 0 | 2014-09-30
0447 | FTS Devco LLC | East Hampton Expansion | 2014-07-25 | 20 | 20 | S | Suffolk | NY | K | Amagansett Substation 69kV | LIPA | 0 | 2015-01-31
0448 | Alps Interconnector, LLC | Alps HVDC | 2014-08-12 | 600 | 600 | DC |  | NY | F | Alps Substation 345kV | NM-NG | 0 | 2018-11-30
0449 | Stockbridge Wind, LLC | Stockbridge Wind | 2014-08-13 | 72.6 | 72.6 | W | Madison | NY | C | Whitman - Oneida 115kV | NM-NG | 0 | 2021-02-28
0450 | Stacy Solar Center, LLC | Stacy Solar | 2014-08-20 | 20 | 20 | S | Greene | NY | G | Coxsackie Substation 69kV | CenHud | 0 | 2015-02-28
0451 | Shortsville Solar Center, LLC | Shortsville Solar | 2014-08-20 | 20 | 20 | S | Ontario | NY | B | Substation #168 34.5kV | NYSEG | 0 | 2014-10-31
0452 | Taconic Solar Center, LLC | Taconic Solar | 2014-08-20 | 10 | 10 | S | Columbia | NY | F | Craryville Substation 34.5kV | NYSEG | 0 | 2014-10-31
0453 | Blue Hill Solar Center, LLC | Blue Hill Solar | 2014-08-20 | 20 | 20 | S | Columbia | NY | F | Blue Stores Substation 115kV | NM-NG | 0 | 2014-10-31
0454 | Sabin Solar Center, LLC | Sabin Solar | 2014-08-20 | 20 | 20 | S | Herkimer | NY | E | Salisbury Substation 115kV | NM-NG | 0 | 2014-10-31
0455 | Roseway Solar, LLC | Roseway Solar | 2014-08-21 | 19.9 | 19.9 | S | Sullivan | NY | E | 34.5kV | NYSEG | 0 | 2015-02-28
0456 | ESA Solar NY, LLC | Woodhull Solar | 2014-09-09 | 0.7 | 0.7 | S | Steuben | NY | C | Woodhull Substation | NYSEG | 0 | 2015-07-31
0457 | RES America Developments Inc. | Bellmont Wind | 2014-09-22 | 19.8 | 19.8 | W |  | NY |  | Brainardsville, NY | NYSEG | 0 | 2014-12-31
0458 | TDI-USA Holdings, Inc. | CH Interconnection | 2014-10-24 | 1000 | 1000 | DC | Quebec-NY | NY | J | Astoria Annex Substation 345kV | NYPA | 0 | 2021-05-31
0459 | ESA Solar NY, LLC | Warsaw Solar | 2014-11-05 | 2 | 2 | S | Wyoming | NY | B | Wethersfield Substation 115kV | NYSEG | 0 | 2014-12-31
0460 | Dryden Solar, LLC | Dryden Solar | 2014-11-10 | 5 | 5 | S | Thompkins | NY | C |  | NYSEG | 0 | 2014-12-31
0463 | Long Island Clean Energy Project LLC | 62 Weeks Rd. Fuel Cell | 2014-12-05 | 19.9 | 19.9 |  | Suffolk | NY | K | 69kV | LIPA | 0 | 2015-01-31
0464 | Long Island Clean Energy Project LLC | Pulaski Rd. Fuel Cell | 2014-12-05 | 19.9 | 19.9 |  | Suffolk | NY | K | 138kV | LIPA | 0 | 2015-01-31
0465 | Hudson Transmission Partners | Hudson Transmission NY to PJM | 2014-12-15 | 675 | 675 | DC | NY | NY | J | W49th St 345kV - Bergen 230kV | ConEd | 0 | 2021-01-31
0466 | Atlantic Wind, LLC | Bone Run Wind | 2014-12-16 | 132 | 132 | W | Cattaraugus | NY | A | Falconer - Homer Hill 115kV | NM-NG | 0 | 2021-02-28
0468 | Apex Clean Energy LLC | Galloo Island Wind | 2014-12-30 | 110.4 | 110.4 | W | Oswego | NY | C | Hammermill - Wine Creek 115kV | NM-NG | 0 | 2021-02-28
0469 | NextEra Energy Transmission | Edic-PV 345 | 2015-01-06 | TBD | TBD | AC | Oneida-Dutchess | NY | E, G | Edic - Pleasant Valley 345kV | NM-NG/ConEd | 0 | 2015-05-31
0470 | NextEra Energy Transmission | Knickerbocker 115 | 2015-01-06 | TBD | TBD | AC | Columbia-Rensselaer | NY | F | Greenbush - Churchtown 115kV | NM-NG/NYSEG/ CHGE | 0 | 2016-05-31
0471 | NextEra Energy Transmission | Marcy-Princetown 345 | 2015-01-06 | TBD | TBD | AC | Oneida-Albany | NY | E, F | Marcy - Princetown 345kV | NM-NG/NYPA/ ConEd | 0 | 2016-05-31
0472 | NextEra Energy Transmission | Knickerbocker 345 | 2015-01-06 | TBD | TBD | AC | Rensselaer-Dutchess | NY | F | Knickerbocker - P. Valley 345kV | NM-NG/ConEd | 0 | 2016-05-31
0473 | Calverton Solar LLC | Calverton Solar | 2015-01-21 | 10 | 10 | S | Suffolk | NY | K | Riverhead - Wildwood 69kV | LIPA | 0 | 2019-02-28
0474 | EDP Renewables North America | North Slope Wind | 2015-01-30 | 200 | 200 | W | Franklin-Clinton | NY | D | Patnode 230kV | NYPA | 0 | 2021-02-28
0475 | OneEnergy Development, LLC | Windy Hill Solar | 2015-02-02 | 20 | 20 | W | Washington | NY | F | Battenkill Substation 115kV | NM-NG | 0 | 2015-07-31
0476 | NY State Electric & Gas | Edic-PV, Oakdale-Fraser | 2015-02-12 | N/A | N/A | AC | Oneida-Delaware | NY | E | Edic-PV, Oakdale-Fraser 345kV | NM-NG/NYSEG | 0 | 2016-07-31
0478 | Central Hudson Gas & Electric | Hurley Ave PARs | 2015-02-17 | TBD | TBD | AC | Dutchess | NY | G | Hurley Ave 345kV | CHGE/NM-NG/NYSEG | 0 | 2016-03-31
0479 | Central Hudson Gas & Electric | Edic-NS, Hurley PARs | 2015-02-17 | TBD | TBD | AC | Oneida-Dutchess | NY | E-G | Edic-NS, Hurley Ave 345kV | CHGE/NM-NG/NYSEG/NYPA | 0 | 2016-03-31
0480 | National Grid | Edic-NS, Knickerbocker-PV | 2015-02-20 | TBD | TBD | AC | Oneida-Dutchess | NY | E-G | Edic-NS, Knickerbocker-PV 345kV | NM-NG/ConEd | 0 | 2016-05-31
0481 | National Grid | Leeds - Pleasant Valley | 2015-02-20 | TBD | TBD | AC | Greene-Dutchess | NY | G | Leeds - P. Valley 345kV | NM-NG/ConEd | 0 | 2015-12-31
0482 | National Grid | Edic-NS, NS-Leeds-PV | 2015-02-20 | TBD | TBD | AC | Oneida-Dutchess | NY | E, G | Edic-NS, NS-Leeds-PV 345kV | NM-NG/ConEd | 0 | 2015-12-31
0483 | National Grid | NS-Leeds, Leeds-PV | 2015-02-20 | TBD | TBD | AC | Albany-Dutchess | NY | F, G | NS-Leeds, Leeds-PV 345kV | NM-NG/ConEd | 0 | 2015-12-31
0484 | National Grid | Edic-NS, NS-Leeds, Leeds-PV | 2015-02-20 | TBD | TBD | AC | Oneida-Dutchess | NY | E, G | Edic-NS, NS-Leeds, Leeds-PV 345kV | NM-NG/ConEd | 0 | 2015-12-31
0485 | National Grid | Knickerbocker-PV | 2015-03-04 | TBD | TBD | AC | Columbia-Dutchess | NY | F, G | Knickerbocker - P. Valley 345kV | NM-NG/ConEd | 0 | 2016-05-31
0486 | LI Energy Storage System | Buell Battery Storage | 2015-03-09 | 20 | 20 | ES | Suffolk | NY | K | East Hampton Substation 69kV | LIPA | 0 | 2015-10-31
0487 | LI Energy Storage System, LLC | Far Rockaway Battery Storage | 2015-03-09 | 20 | 20 | ES | Nassau | NY | K | Far Rockaway 69kV | LIPA | 0 | 2022-10-31
0488 | LI Energy Storage System | Glenwood Battery Storage | 2015-03-09 | 20 | 20 | ES | Suffolk | NY | K | Glenwood Substation 69kV | LIPA | 0 | 2017-04-30
0489 | LI Energy Storage System | Southampton Battery Storage | 2015-03-09 | 20 | 20 | ES | Suffolk | NY | K | Southampton 69kV | LIPA | 0 | 2015-10-31
0491 | Yaphank Fuel Cell Park, LLC | Yaphank Fuel Cell Park | 2015-03-23 | 19.6 | 19.6 | ES | Suffolk | NY | K | Yaphank Substation 69kV | LIPA | 0 | 2015-07-31
0492 | Setauket Fuel Cell Park, LLC | Setauket Fuel Cell Park | 2015-03-23 | 19.6 | 19.6 | FC | Suffolk | NY | K | Terryville Substation 69kV | LIPA | 0 | 2016-09-30
0493 | EPCAL Fuel Cell Park, LLC | EPCAL Fuel Cell Park | 2015-03-30 | 19.6 | 19.6 | FC | Suffolk | NY | K | Riverhead 69 kV | LIPA | 0 | 2016-01-31
0494 | Alabama Ledge Wind Farm LLC | Alabama Ledge Wind | 2015-03-31 | 79.8 | 79.8 | W | Genesee | NY | B | Lockport - Oakfield 115kV | NM-NG | 0 | 2020-01-31
0496 | Renovo Energy Center, LLC | Renovo Energy Center | 2015-04-13 | 480 | 504 | CC | Clinton | PA | C | Homer City - Mainsburg 345kV | NYSEG | 0 | 2021-02-28
0497 | Invenergy Wind Development LLC | Bull Run Wind | 2015-04-24 | 303.6 | 303.6 | W | Clinton | NY | D | Patnode 230kV | NYPA | 0 | 2023-01-31
0498 | ESC Tioga County Power, LLC | Tioga County Power | 2015-04-29 | 550 | 550 | CC | Tioga | PA | C | Homer City - Mainsburg 345kV | NYSEG | 0 | 2021-02-28
0499 | Sharon Solar LLC | Sharon Solar | 2015-05-07 | 19.6 | 19.6 | S | Schoharie | NY | F | Sharon Substation 69kV | NM-NG | 0 | 2015-10-31
0500 | Regeneron Solar LLC | Regeneron Solar | 2015-05-12 | 2 | 2 | S | Rensselaer | NY | F | East Greenbush, NY | NM-NG | 0 | 2015-08-31
0501 | Regeneron Solar LLC | Mariaville 2 Solar | 2015-05-12 | 2 | 2 | S | Schenectady | NY | F | Mariaville, NY | NM-NG | 0 | 2015-08-31
0502 | Lincoln Park DG LLC | Lincoln Park | 2015-05-22 | 18.3 | 18.3 |  | Dutchess | NY | F | Lincoln Park Substation | CHGE | 0 | 2015-06-30
0503 | East Kingstson DG LLC | East Kingston | 2015-05-22 | 18.3 | 18.3 |  | Dutchess | NY | F | East Kingston Substation | CHGE | 0 | 2015-06-30
0504 | NY DG Holding LLC | Saugerties | 2015-05-22 | 18.3 | 18.3 |  | Dutchess | NY | F | Saugerties Substation | CHGE | 0 | 2015-06-30
0505A | Central Hudson | Hurley Ave & Saugerties | 2015-06-05 | TBD | TBD | AC | Greene-Ulster | NY | G | Hurley Ave & Saugerties 69kV | CHGE | 0 | 2015-10-31
0506 | Empire State Connector Corp. | Empire State Connector | 2015-06-10 | 1000 | 1000 | DC | Onondaga | NY | E, J | Marcy - Gowanus 345kV | NYPA/ConEd | 0 | 2023-01-31
0507 | Erie Boulevard Hydropower, LP | Glens Falls Hydro | 2015-07-02 | 14.8 | 14.8 | H | Washington | NY | F | Henry St. - Glens Falls 34.5kV | NM-NG | 0 | 2016-12-31
0508 | Blue Circle DG LLC | Blue Circle | 2015-07-17 | 18.2 | 18.2 | FC | Greene | NY | G | LaFarge - PV 115 kV | NM-NG | 0 | 2016-02-29
0509 | North Catskill DG LLC | North Catskill | 2015-07-17 | 18.2 | 18.2 |  | Greene | NY | G | North Catskill Substation | CHGE | 0 | 2015-08-31
0511 | AG Energy, LP | Ogdensburg | 2015-09-04 | 79 | 90.1 | CC | St. Lawrence | NY | E | North Ogdensburg Substation | NM-NG | 0 | 2019-09-30
0512 | Northbrook Lyons Falls | Lyons Fills Mill Hydro | 2015-09-11 | 2.5 | 2.5 | H | Lewis | NY | E | Taylorville- Boonville 115 kV | NM-NG | 0 | 2019-06-30
0514 | RES Americas Developments Inc. | Empire Wind | 2015-10-01 | 120 | 120 | W | Rensselaer | NY | F | Stephentown - Greenbush 115kV | NM-NG | 0 | 2018-07-31
0515 | North Bergen Liberty Generation Center LLC | Liberty Generation | 2015-10-07 | 1000 | 1000 | CC | NY | NY | J | W49th St 345kV | ConEd | 0 | 2018-01-31
0516 | East Coast Power LLC | Linden Cogen Uprate | 2015-10-12 | 234.4 | 234.4 | CT | Union | NJ | J | Linden Cogen 345kV | ConEd | 0 | 2020-02-29
0518 | PPL Electric Utilities | Compass | 2015-10-27 | N/A | N/A | AC | Rockland | NY | G | Lackawanna - Ramapo 345kV | ConEd | 0 | 2021-05-31
0520 | EDP Renewables North America | Rolling Upland Wind | 2015-12-03 | 72.6 | 72.6 | W | Madison | NY | E | County Line - Brothertown 115kV | NYSEG | 0 | 2023-01-31
0521 | Bull Run Energy LLC | Bull Run II Wind | 2015-12-15 | 449 | 449 | W | Clinton | NY | D | Patnode-Duley, Ryan-Plattsburgh 230kV | NYPA | 0 | 2026-03-31
0523 | Dunkirk Power LLC | Dunkirk Unit 2 | 2015-12-17 | 75 | 75 | ST | Chautauqua | NY | A | Dunkirk 115kV | NM-NG | 0 | 2020-06-30
0524 | Dunkirk Power LLC | Dunkirk Unit 3 & 4 | 2015-12-17 | 370 | 370 | ST | Chautauqua | NY | A | Dunkirk 230kV | NM-NG | 0 | 2020-06-30
0525 | NY Power Authority | Western NY Energy Link | 2015-12-18 | N/A | N/A | AC | Niagara | NY | A | Niagara - Stolle - Gardenville | NYPA/NYSEG | 0 | 2018-02-28
0526 | Atlantic Wind, LLC | North Ridge Wind | 2015-12-23 | 100 | 100 | W | St. Lawrence | NY | D | Malone - Colton 115kV | NM-NG | 0 | 2023-01-31
0527 | Atlantic Wind, LLC | Horse Creek Wind | 2015-12-23 | 250 | 250 | W | Jefferson | NY | E | Indian River 115kV | NM-NG | 0 | 2017-07-31
0528 | National Grid | Moderate Power Transfer | 2015-12-30 | N/A | N/A | AC | Niagara-Erie | NY | A | Niagara, Erie, Stolle, Gardenville | NM-NG | 0 | 2017-09-30
0529 | National Grid | High Power Transfer | 2015-12-30 | N/A | N/A | AC | Niagara-Erie | NY | A | Niagara, Erie, Stolle, Gardenville | NM-NG | 0 | 2017-09-30
0530 | NextEra Energy Transmission NY, Inc. | Empire State Line | 2016-01-04 | N/A | N/A | AC | Niagara-Erie | NY | A | Dysinger - Stolle 345kV | NYPA/NYSEG | 0 | 2018-01-31
0532 | Invenergy Wind Development LLC | Allegany Wind | 2016-02-01 | 100 | 100 | W | Allegany | NY | B | Freedom Substation | Village of Arcade | 0 | 2019-03-31
0533 | Delano Management LLC | Empire Interconnection | 2016-02-03 | 275 | 275 | DC | Nassau | NY | K | Far Rockaway Substation 69kV | LIPA | 0 | 2017-11-30
0534 | OneEnergy Development, LLC | Great Valley Solar | 2016-02-03 | 20 | 20 | S | Washington | NY | F | Battenkill 34.5kV Substation | NM-NG | 0 | 2019-07-31
0536 | Empire Interconnection LLC | Glenwood | 2016-04-19 | 275 | 275 | AC | Suffolk | NY | K | Glenwood/Far Rockaway Station 69kV | LIPA | 0 | 2017-11-30
0537 | NextEra Energy Transmission NY, Inc. | Segment A | 2016-04-25 | N/A | N/A | AC | Oneida-Albany | NY | E, F | Edic - New Scotland 345kV | NM-NG/NYPA | 0 | 2018-01-31
0538 | NextEra Energy Transmission NY, Inc. | Segment B | 2016-04-25 | N/A | N/A | AC | Albany-Dutchess | NY | F, G | Greenbush - PV 345kV | NM-NG/NYSEG/ CHGE/ConEd | 0 | 2018-10-31
0539 | NextEra Energy Transmission NY, Inc. | Segment B Alt | 2016-04-25 | N/A | N/A | AC | Albany-Dutchess | NY | F, G | Greenbush - PV 345kV | NM-NG/NYSEG/ CHGE/ConEd | 0 | 2018-10-31
0540 | AVANGRID | Connect NY Edic - PV | 2016-04-28 | 1000 | 1000 | DC | Oneida-Dutchess | NY | E, G | Edic - PV 345kV | NM-NG/ ConEd | 0 | 2022-10-31
0541 | AVANGRID | Connect NY Edic - Ramapo | 2016-04-28 | 1000 | 1000 | DC | Oneida-Dutchess | NY | E, G | Edic - Ramapo 345kV | NM-NG/ ConEd | 0 | 2022-10-31
0542 | National Grid | Segment A Edic-New Scotland | 2016-05-04 | N/A | N/A | AC | Oneida-Albany | NY | E, F | Edic - New Scotland 345kV | NM-NG | 0 | 2018-01-31
0544 | Invenergy Wind Development LLC | Alle Catt Wind | 2016-05-04 | 100.5 | 100.5 | W | Cattaraugus | NY | A | Freedom Substation 115kV | Village of Arcade | 0 | 2017-08-31
0545 | Sky High Solar, LLC | Sky High Solar | 2016-05-16 | 20 | 20 | S | Onondaga | NY | C | Tilden -Tully Center 115kV | NM-NG | 0 | 2026-01-31
0547 | North America Transmission, LLC | Dysinger-Stolle | 2016-05-25 | N/A | N/A | AC | Niagara-Erie | NY | A | Dysinger - Stolle 345kV | NYPA/NYSEG/ NM-NG | 0 | 2019-04-30
0548 | North America Transmission, LLC | Dysinger-Stolle-Gardenville | 2016-05-25 | N/A | N/A | AC | Niagara-Erie | NY | A | Dysinger - Gardenville 345kV | NYPA/NYSEG/ NM-NG | 0 | 2017-10-31
0549 | North America Transmission, LLC | Niagara-Dysinger-Stolle-Gardenville | 2016-05-25 | N/A | N/A | AC | Niagara-Erie | NY | A | Niagara - Gardenville 345kV | NYPA/NYSEG/ NM-NG | 0 | 2017-10-31
0550 | North America Transmission, LLC | Dysinger-Stolle-Gardenville II | 2016-06-02 | N/A | N/A | AC | Niagara-Erie | NY | A | Dysinger - Gardenville 345kV | NYPA/NYSEG/ NM-NG | 0 | 2017-10-31
0551 | OneEnergy Development, LLC | Caprock Solar | 2016-06-24 | 20 | 20 | S | Monroe | NY | B | South Union - Sweden 115kV | NM-NG | 0 | 2017-08-31
0552 | OneEnergy Development, LLC | Flotilla Solar | 2016-06-24 | 20 | 20 | S | Monroe | NY | B | Brockport - Hamlin 115kV | NM-NG | 0 | 2017-08-31
0553 | OneEnergy Development, LLC | Caspian Solar | 2016-06-24 | 20 | 20 | S | Monroe | NY | B | Sweden - South Union 115kV | NM-NG | 0 | 2016-08-31
0554 | Lookheed Martin | Lockheed Matin MST Syracuse | 2016-06-27 |  |  |  |  | NY |  | Lockheed Martin switch 13.8kV | NM-NG | 0 | 2016-07-31
0555 | North America Transmission, LLC | Segment A Base | 2016-07-06 | N/A | N/A | AC | Oneida-Albany | NY | E, F | Edic - New Scotland 345kV | NM-NG | 0 | 2019-04-30
0557 | North America Transmission, LLC | Segment A Enhanced | 2016-07-06 | N/A | N/A | AC | Oneida-Albany | NY | E, F | Edic - New Scotland 345kV | NM-NG | 0 | 2019-04-30
0558 | North America Transmission, LLC | Segment A 765 | 2016-07-06 | N/A | N/A | AC | Oneida-Albany | NY | E, F | Edic - New Scotland 345kV | NM-NG/ NYPA | 0 | 2019-04-30
0559 | North America Transmission, LLC | Segment B Base | 2016-07-06 | N/A | N/A | AC | Oneida-Albany | NY | E, F | Knickerbocker - PV 345kV | NM-NG/O&R CHGE/ConEd | 0 | 2019-04-30
0560 | Deer River Wind, LLC | Deer River Wind | 2016-07-08 | 100 | 100 | W | Lewis | NY | E | Black River-Lighthouse Hill 115kV | NM-NG | 0 | 2024-12-31
0561 | Astoria Generating Company LP | Astoria Generating Unit 4 | 2016-07-18 | 385 | 385 | ST | NY | NY | J | Astoria West Substation 138 kV | ConEd | 0 | 2020-02-29
0562 | OneEnergy Development, LLC | Hidden Meadow Solar | 2016-07-22 | 20 | 20 | S | Columbia-Dutchess | NY | F, G | Milan - Churchtown 115kV | NM-NG | 0 | 2017-03-31
0563 | Double Lock Solar, LLC | Double Lock Solar | 2016-07-25 | 20 | 20 | S | Herkimer | NY | E | St. Johnsville - Marshville 115kV | NM-NG | 0 | 2019-07-31
0565 | Tayandenega Solar, LLC | Tayandenega Solar | 2016-07-25 | 20 | 20 | S | Montgomery | NY | F | St. Johnsville - Inghams 115kV | NM-NG | 0 | 2025-06-30
0567 | Tribes Hill Solar, LLC | Tribes Hill Solar | 2016-08-10 | 20 | 20 | S | Montgomery | NY | F | Ephrata - Florida 69KV | NM-NG | 0 | 2018-06-30
0568 | Turkey Hollow Solar, LLC | Turkey Hollow Solar | 2016-08-16 | 20 | 20 | S | Delaware | NY | F | Grand Gorge - Axtell Road 115kV | NYSEG | 0 | 2018-01-31
0569 | Hecate Energy, LLC | Greene County | 2016-08-17 | 50 | 50 | S | Greene | NY | G |  | CHGE | 0 | 2016-09-30
0574 | Atlantic Wind, LLC | Mad River Wind | 2016-09-16 | 450 | 450 | W | Jefferson-Oswego | NY | E | Volney - Marcy 345kV | NM-NG | 0 | 2023-01-31
0576 | Astoria Generating Company LP | Astoria Generating Unit 4 | 2016-09-16 | 385 | 385 | ST | NY | NY | J | Astoria East Substation 138kV | ConEd | 0 | 2020-02-29
0577 | Greene County Energy Properties, LLC | Greene County Energy | 2016-09-20 | 20 | 20 | S | Greene | NY | G | New Baltimore - Coxsackie 69 kV | CHG&E | 0 | 2024-05-31
0578 | Sharon Solar LLC | Sharon Solar | 2016-09-20 | 20 | 20 | S | Schoharie | NY | F | Sharon Substation 69kV | NM-NG | 0 | 2017-06-30
0582 | Sunny Knoll Solar LLC | Sunny Knoll Solar | 2016-10-18 | 20 | 20 | S | Schoharie | NY | F | Cobleskill - Schoharie 69kV | NM-NG | 0 | 2019-05-31
0585 | Caledonia Solar LLC | Caledonia I Solar | 2016-11-07 | 20 | 20 | S | Livingston | NY | A | Golah - South Perry 69kV | NM-NG | 0 | 2018-06-30
0587 | Fork Valley Solar LLC | Fork Valley Solar | 2016-11-08 | 20 | 20 | S | Steuben | NY | C | Eelpot Rd 345.5kV Substation | NYSEG | 0 | 2018-07-31
0588 | Exelon Transmission Co., LLC | Niagara Transmission Expansion | 2016-11-15 | N/A | N/A | AC | Niagara-Erie | NY | A | Niagara - Gardenville | NYPA/NYSEG/ NM-NG | 0 | 2017-09-30
0589 | Duke Energy Renewables Solar, LLC | North Country Solar | 2016-12-02 | 15 | 15 | S | Lewis | NY | E | Boonville 46kV | NM-NG | 0 | 2022-03-31
0591 | SunEast Highview Solar LLC | Highview Solar | 2016-12-02 | 20 | 20 | S | Wyoming | NY | C | South Perry 34.5kV | NYSEG | 0 | 2026-05-31
0592 | Niagara NY Solar LLC | Niagara Solar | 2016-12-02 | 20 | 20 | S | Wyoming | NY | A | Bennington 34.5kV | NYSEG | 0 | 2026-05-31
0595 | North Park Energy, LLC | SW Energy | 2016-12-29 | 100 | 100 | ES | Cattaraugus | NY | A | Five Mile Rd Substation 115kV | NM-NG | 0 | 2021-08-31
0597 | Hecate Energy Greene County 3 LLC | Greene County 3 | 2017-01-10 | 20.0 | 20.0 | S | Greene | NY | G | North Catskill - Coxsackie 69kV | CHG&E | 0 | 2024-05-31
0599 | LeRoy, LLC | LeRoy Solar | 2017-01-11 | 20 | 20 | S | Genesee | NY | B | LeRoy Substation 115kV | NGrid | 0 | 2017-04-30
0600 | Conti Enterprises, Inc. | Darby Solar | 2017-01-12 | 20 | 20 | S | Washington | NY | G | Mechanicville - Schaghticoke 34.5kV | NM-NG | 0 | 2019-04-30
0601 | HP Hood LLC | Hood Cogen | 2017-01-20 | 4 | 4 | CT | Madison | NY | C | Oneida - Fenner 115kV | NGrid | 0 | 2018-12-31
0602 | Cypress Creek Renewables | Keesog Solar | 2017-01-30 | 50 | 50 | S | Franklin | NY | D | Moses - Willis 230kV | NYPA | 0 | 2017-05-31
0603 | Hecate Energy Riverhead, LLC | Riverhead | 2017-02-03 | 7.5 | 7.5 | S | Suffolk | NY | K | Wildwood - Riverhead 69kV | LIPA | 0 | 2018-05-31
0604 | Hecate Energy Columbia County 1, LLC | Columbia County 1 | 2017-02-07 | 20 | 20 | S | Columbia | NY | G | Craryville Substation 34.5kV | NYSEG | 0 | 2017-07-31
0605 | Hecate Energy Columbia County 2, LLC | Columbia County 2 | 2017-02-07 | 20 | 20 | S | Columbia | NY | G | Craryville Substation 34.5kV | NYSEG | 0 | 2017-07-31
0606 | Hecate Energy Craryville 3, LLC | Columbia County 3 | 2017-02-07 | 10 | 10 | S | Columbia | NY | G | Craryville Substation 34.5kV | NYSEG | 0 | 2017-07-31
0607 | Empire State Connector Corporation | Empire State Connector II | 2017-02-08 | 1000 | 1000 | DC | Oneida-NY | NY | E, J | Marcy - Astoria 345kV | NYPA/NM-NG/ ConEd | 0 | 2017-03-31
0608 | ITC NY Development, LLC | Segment A | 2017-02-08 | N/A | N/A | AC | Oneida-Albany | NY | E, F | Edic - New Scotland 345kV | NM-NG | 0 | 2019-04-30
0609 | ITC NY Development, LLC | Segment B | 2017-02-08 | N/A | N/A | AC | Oneida-Albany | NY | E, F | Knickerbocker - PV 345kV | NM-NG/NYSEG/ CHGE/ConEd | 0 | 2019-04-30
0610 | Woodruff Solar, LLC | Woodruff Solar | 2017-02-10 | 20 | 20 | S | Livingston | NY | A | Golah - N. Lakeville 34.5KV | NM-NG | 0 | 2019-06-30
0611 | Badra Solar, LLC | Badra Solar | 2017-02-10 | 20 | 20 | S | Franklin | NY | D | Nicholville - Malone 115kV | NM-NG | 0 | 2017-03-31
0613 | OneEnergy Development, LLC | Sugar Maple Solar | 2017-02-17 | 20 | 20 | S | Herkimer | NY | E | Trenton Falls - Poland 46kV | NM-NG | 0 | 2019-06-30
0614 | Sabertooth Solar, LLC | Sabertooth Solar | 2017-02-22 | 20 | 20 | S | Cortland | NY | B | Willett - Lapeer 115kV | NYSEG | 0 | 2017-06-30
0615 | West Point Partners, LLC | West Point II HVDC | 2017-03-02 | 1000 | 1000 | DC | Albany-Westchester | NY | F, H | New Scotland - Buchanan South 345kV | NM-NG/ConEd | 0 | 2019-02-28
0616 | Heelstone Development, LLC | Mohawk Solar | 2017-03-23 | 20 | 20 | S | Herkimer | NY | E | Watkins Rd - Ilion 115kV | NM-NG | 0 | 2019-04-30
0621 | Blue Stone Solar Energy, LLC | Saugerties Solar | 2017-03-27 | 20 | 20 | S | Ulster | NY | G | Saugerties - Woodstock 69kV | CHGE | 0 | 2020-10-31
0622 | Geronimo Solar Energy, LLC | Alcoa Solar | 2017-03-27 | 20 | 20 | S | St. Lawrence | NY | E | 13.8kV | NM-NG | 0 | 2017-06-30
0623 | Conti Enterprises, Inc. | Puckett Solar | 2017-04-05 | 20 | 20 | S | Chenango | NY | C | Chenango Forks 34.5kV Substation | NYSEG | 0 | 2017-06-30
0624 | Franklin Solar, LLC | Franklin Solar | 2017-04-11 | 150 | 150 | S | Franklin | NY | D | Malone 115kV Substation | NM-NG | 0 | 2023-01-31
0625 | Whitehart Solar, LLC | Whitehart Solar | 2017-04-13 | 20 | 20 | S | Sullivan | NY | E | Hyatt Rd.- Border City 115kV | NYSEG | 0 | 2018-09-30
0626 | KCE NY 1, LLC | KCE NY 1 | 2017-04-14 | 20 | 20 |  | Saratoga | NY | F | Luther Forest 34.5kV Substation | NM-NG | 0 | 2017-06-30
0627 | OneEnergy Development, LLC | Southtown 2 Solar | 2017-04-17 | 20 | 20 | S |  | NY |  | North Angola 34.5kV Substation | NM-NG | 0 | 2017-06-30
0628 | OneEnergy Development, LLC | Slingshot 2 Solar | 2017-04-17 | 20 | 20 | S | Steuben | NY | C | Hammondsport 34.5 kV Substation | NYSEG | 0 | 2017-08-31
0629 | Silver Lake Solar, LLC | Silver Lake Solar | 2017-04-27 | 24.9 | 24.9 | S | Wyoming | NY |  | South Perry 34.5kV | NYSEG | 0 | 2023-08-31
0630 | Cayuga Operating Co. | Cayuga Solar | 2017-04-27 | 20 | 20 | S | Lansing | NY | C | Milliken 34.5 Substation | NYSEG | 0 | 2018-01-31
0632 | GridAmerica Holdings Inc. | Alps - Berkshire | 2017-05-04 | N/A | N/A | AC | Rensselaer | NY | F | Alps - Berkshire 345kV | NM-NG | 0 | 2022-10-31
0633 | Conti Enterprises, Inc. | Janis Solar | 2017-05-15 | 20 | 20 | S |  | NY | B | Willet - Tarbell 34.5 kV | NYSEG | 0 | 2017-06-30
0634 | Champagne Storage, LLC | Champagne Storage | 2017-05-18 | 20 | 20 | ES | Madison | NY | E | Oneida - Cortland 115kV | NM-NG | 0 | 2018-01-31
0635 | Rising Solar, LLC | Rising Solar | 2017-06-14 | 20 | 20 | S | Orange | NY | G | Sugarloaf - Wisner 69kV | O&R | 0 | 2018-12-31
0636 | Daybreak Solar, LLC | Daybreak Solar | 2017-06-15 | 25 | 25 | S | Ulster | NY | G | East Walden Substation 69kV | CHGE | 0 | 2019-01-31
0639 | Owego Solar LLC | Owego Solar | 2017-07-19 | 20 | 20 | S | Tioga | NY | C | South Owego - Stagecoach 115kV | NYSEG | 0 | 2017-11-30
0640 | Granada Solar, LLC | Grissom Solar | 2017-07-19 | 20 | 20 | S | Fulton | NY | F | Vail Mills Substation 69kV | NM-NG | 0 | 2017-11-30
0641 | AVANGRID | Oakdale - Lafayette | 2017-07-24 | N/A | N/A | AC | Broome-Onondaga | NY | C | Oakdale - Lafayette | NM-NG/NYSEG | 0 | 2019-10-04
0642 | AVANGRID | Jennison - Edic | 2017-07-24 | N/A | N/A | AC | Chenango - Oneida | NY | E | Jennison - Edic | NM-NG/NYSEG | 0 | 2019-10-04
0643 | AVANGRID | Multiple Areas | 2017-07-24 | N/A | N/A | AC | Steuben - Otsego | NY | C, E | Transmission Reinforcements | NM-NG/NYSEG | 0 | 2019-10-04
0645 | Oya Solar NY LP | Manny Corner Solar | 2017-08-01 | 20 | 20 | S | Montgomery | NY | F | Meco - Rotterdam 115kV | NM-NG | 0 | 2018-03-31
0646 | Oya Solar NY LP | Shaw Solar | 2017-08-01 | 20 | 20 | S | Jefferson | NY | E | Thousand Island 115kV | NM-NG | 0 | 2017-12-31
0647 | Oya Solar NY LP | Robinson Solar | 2017-08-01 | 20 | 20 | S | Jefferson | NY | E | Thousand Island 115kV | NM-NG | 0 | 2018-03-31
0648 | Oya Solar NY LP | Black Creek Solar | 2017-08-01 | 20 | 20 | S | Jefferson | NY | E | Thousand Island - Coffeen 115kV | NM-NG | 0 | 2017-12-31
0649 | CR Fuel Cell, LLC | Clare Rose | 2017-08-03 | 13.9 | 13.9 | FC | Suffolk | NY | K | William Floyd 69kV | LIPA | 0 | 2021-12-31
0650 | BRT Fuel Cell, LLC | Brookhaven Rail Terminal | 2017-08-03 | 18.5 | 18.5 | FC | Suffolk | NY | K | W. Yaphank - Yaphank 69kV | LIPA | 0 | 2021-12-31
0651 | Yaphank Fuel Cell Park, LLC | Yaphank Solid Waste Management | 2017-08-04 | 7.4 | 7.4 | FC | Suffolk | NY | K | W. Yaphank - North Bellport 69kV | LIPA | 0 | 2018-10-31
0652 | Somerset Operating Company LLC | Somerset Solar | 2017-08-04 | 19.9 | 19.9 | S | Monroe | NY | B | Kintigh Switchyard 69kV | NYSEG | 0 | 2018-02-01
0653 | Plattsburgh Solar, LLC | Moffitt Solar | 2017-08-07 | 20 | 20 | S | Clinton | NY | D | Northend - Woodruff Pond 46kV | NYSEG | 0 | 2018-09-30
0654 | Renovo Energy Center LLC | Renovo Energy Center | 8/11/2017 | N/A | N/A | AC | Clinton | PA | C | Homer City - Mainsburg 345kV | NYSEG | 0 | 2023-04-30
0655 | Admiral Wind LLC | Admiral Wind LLC | 2017-08-11 | 20 | 20 | W | Madison | NY | C | Fenner - Oneida 115kV | NM-NG | 0 | 2019-09-30
0656 | Taku Wind LLC | Taku Wind | 2017-08-11 | 20 | 20 | W | Genesee | NY | A | Akron - Attica 34.5kV | NM-NG | 0 | 2018-01-31
0657 | Mistral Wind LLC | Mistral Wind LLC | 2017-08-11 | 20 | 20 | W | Genesee | NY | B | Lockport - Batavia 115kV | NM-NG | 0 | 2018-11-30
0658 | CVE North America, Inc. | Volney Solar Park | 2017-08-29 | 19.8 | 19.8 | S | Fulton | NY | F | South Oswego - Clay 115kV | NM-NG | 0 | 2018-01-31
0659 | Solar Liberty Energy Systems, Inc. | Westwood Rd | 2017-09-19 | 10.1 | 11.3 | S | Erie | NY | A | Erie St - Alden 34.5kV | NYSEG | 0 | 2018-03-31
0660 | Solar Liberty Energy Systems, Inc. | Liberty Dr | 2017-09-07 | 7.4 | 7.4 | S | Niagara Falls | NY | A | Packard - Erie St 115 kV | NM-NG | 0 | 2018-03-31
0661 | Solar Liberty Energy Systems, Inc. | Eden Evans Rd | 2017-09-07 | 18 | 18 | S | Erie | NY | A | Shelton - Angola 34.5kV | NM-NG | 0 | 2018-03-31
0662 | EDP Renewables North America LLC | Coldwater Solar | 2017-09-07 | 80 | 80 | S | Chautauqua | NY | A | Dunkirk - Gardenville 115kV | NM-NG | 0 | 2019-04-30
0663 | Solar Liberty Energy Systems, Inc. | Main St | 2017-09-08 | 10.8 | 10.8 | S | York | NY | A | Golah - South Perry 69 kV | NM-NG/NYSEG | 0 | 2018-03-31
0664 | South Cooper Solar LLC | South Cooper Solar | 2017-09-14 | 20 | 20 | S | Cattaraugus | NY | A | Five Mile - Gardenville 115 kV | NM-NG | 0 | 2018-05-31
0665 | Forest Glen Solar LLC | Forest Glen Solar | 2017-09-14 | 20 | 20 | S | Allagany | NY | A | Five Mile - Homer Hill 115kV | NM-NG | 0 | 2018-03-31
0666 | Martin Rd Solar LLC | Martin Rd Solar | 2017-09-14 | 20.0 | 20.0 | Solar | Machias | NY | A | Arcade - Five Mile 115kV | NM-NG | 0 | 2024-04-30
0667 | Bakerstand Solar LLC | Bakerstand Solar | 2017-09-14 | 20 | 20 | Solar | Cattaraugus | NY | A | Machias - Maplehurst 34.5kV | NM-NG | 0 | 2024-04-30
0668 | North Bergen Liberty Generating, LLC | Liberty Generating Alternative | 2017-09-15 | 1171 | 1172 | CC | NY | NY | J | West 49th St 345kV | ConEd | 0 | 2023-05-31
0669 | SED NY Holdings LLC | Clay Solar | 2017-09-21 | 20 | 20 | S | Clay | NY | C | Clay - Lockheed 115kV | NM-NG | 0 | 2021-05-31
0671 | East Coast Power LLC | Linden Cogen Uprate | 2017-09-25 | 32 | 23 | CT | Union | NJ | J | Linden Cogen 345kV | ConEd | 0 | 2020-11-30
0672 | LS Power Development, LLC | Helix Ravenswood I | 2017-10-06 | 30.2 | 30.2 | CT | NY | NY | J | Rainey Substation 345kV | ConEd | 0 | 2018-09-30
0673 | LS Power Development, LLC | Helix Ravenswood II | 2017-10-06 | 72.4 | 72.4 | CT | NY | NY | J | Rainey Substation 345kV | ConEd | 0 | 2018-09-30
0674 | Helix Ravenswood, LLC | Vernon Battery Storage I | 2017-10-24 | 10 | 10 | ES | Queens | NY | J | Vernon Substation | ConEd | 0 | 2018-08-31
0675 | Helix Ravenswood, LLC | Vernon Battery Storage II | 2017-10-24 | 10 | 10 | ES | Queens | NY | J | Vernon Substation | ConEd | 0 | 2018-08-31
0676 | Granada Solar, LLC | Regan Solar | 2017-10-25 | 20 | 20 | S | Chenango | NY | C | Guilford 46kV | NYSEG | 0 | 2018-03-31
0677 | Granada Solar, LLC | Grange Solar | 2017-10-25 | 20 | 20 | S | Broome | NY | C | Vincent Cors 34.5kV | NYSEG | 0 | 2018-01-31
0679 | Anbaric Development Partners, LLC, NY OceanGrid, LLC | NY City Offshore Wind | 2017-11-07 | 1200 | 1200 | DC | Kings | NY | J | Gowanus 345kV | ConEd | 0 | 2024-05-31
0680 | Anbaric Development Partners, LLC | Juno Power Express | 2017-11-07 | 1200 | 1200 | DC | Suffolk | NY | K | Ruland Rd. 138kV | LIPA | 0 | 2024-11-30
0681 | Granada Solar, LLC | Magruder Solar | 2018-01-02 | 20 | 20 | S | Ulster | NY | G | Modena - Galeville 115kV | CHGE | 0 | 2018-02-28
0684 | ITC Lake Erie Connector, LLC | Lake Erie Connector | 2018-01-18 | N/A | N/A | AC | Chautauqua | NY | A | S. Ripley 230kV | NM-NG | 0 | 2022-08-31
0685 | sPower Development Company, LLC | EPCAL 1 | 2018-01-19 | 20 | 20 | S | Suffolk | NY | K | Riverhead - Brookhaven 138kV | LIPA | 0 | 2018-04-30
0686 | Invenergy Solar Development North America LLC | Bull Run Solar Energy Center | 2018-01-26 | 125 | 125 | S | Clinton | NY | D | Patnode-Duley, Ryan-Plattsburgh 230kV | NYPA | 0 | 2024-06-30
0687 | sPower Development Company, LLC | EPCAL 2 | 2018-01-29 | 150 | 150 | S | Suffolk | NY | K | Edwards - Brookhaven 69kV | LIPA | 0 | 2018-06-30
0688 | EDF Renewable Development Inc. | East Walden Solar | 2018-02-02 | 20 | 20 | S | Orange | NY | G | East Waldon Sutbation | CHGE | 0 | 2018-03-31
0689 | EDF Renewable Development Inc. | Goshen Solar | 2018-02-02 | 20 | 20 | S | Orange | NY | G | Huntley Station 115kV | O&R | 0 | 2018-03-31
0690 | EDF Renewable Development Inc. | Slate Hill 1 Solar | 2018-02-02 | 20 | 20 | S | Orange | NY | G | Shoemaker - Westtown | O&R | 0 | 2018-03-31
0691 | EDF Renewable Development Inc. | Slate Hill 2 Solar | 2018-02-02 | 20 | 20 | S | Orange | NY | G | Shoemaker - Westtown | O&R | 0 | 2018-03-31
0692 | Consolidated Edison Company of NY, Inc. | Astoria Storage on Demand | 2018-02-07 | 15 | 15 | ES | Queens | NY | J | North Queens Substation | ConEd | 0 | 2018-03-31
0693 | Renovo Energy Center, LLC | Renovo Energy Center Uprate | 2018-02-13 | 515 | 548 | CC | Clinton | PA | C | Homer City - Mainesburg 345kV | NYSEG | 0 | 2023-01-31
0694 | Sunset Hill Solar, LLC | Sunset Hill Solar | 2018-02-16 | 20 | 20 | S | Albany | NY | G | New Baltimore - Westerlo NW 69 kV | CHG&E | 0 | 2024-05-31
0697 | Helix Ravenswood, LLC | Ravenswood Energy Storage 1 | 2018-03-09 | 129 | 129 | ES | Queens | NY | J | Rainey - Farragut 345kV | ConEd | 0 | 2023-01-31
0698 | Helix Ravenswood, LLC | Ravenswood Energy Storage 2 | 2018-03-09 | 129 | 129 | ES | Queens | NY | J | Vernon-Rainey 138kV | ConEd | 0 | 2023-01-31
0699 | Helix Ravenswood, LLC | Ravenswood Gas | 2018-03-09 | 238.5 | 243.8 | CT | Queens | NY | J | Rainey - Farragut 345kV | ConEd | 0 | 2023-01-31
0700 | Robinson Grid, LLC | Robinson Grid | 2018-03-13 | 300 | 300 | ES | Kings | NY | J | Gowanus 345kV | ConEd | 0 | 2024-12-31
0702 | Anbaric Development Partners, LLC | Long Island Offshore AC | 2018-03-15 | 800 | 800 | W | Suffolk | NY | K | Ruland Rd. 138kV | LIPA | 0 | 2020-05-31
0703 | Anbaric Development Partners, LLC | NY City Offshore AC | 2018-03-15 | 800 | 800 | W | Kings | NY | J | Farragut 345kV | ConEd | 0 | 2020-05-31
0705 | Oya Solar NY, LP | Chaumont Solar | 2018-04-10 | 160 | 160 | S | Sullivan | NY | G | Thousand Island - Coffeen 115kV | NM-NG | 0 | 2018-07-31
0706 | High Bridge Wind, LLC | High Bridge Wind | 2018-04-25 | 100.8 | 100.8 | W | Chenango | NY | E | E. Norwich - Jennison 115kV | NYSEG | 0 | 2026-05-31
0707 | PSEG Power NY LLC | Bethlehem Battery | 2018-05-04 | 10 | 10 | ES | Albany | NY | F | Albany Substation 115kV | NM-NG | 0 | 2018-11-30
0708 | PSEG Power NY LLC | Bethlehem Solar | 2018-05-04 | 1 | 1 | S | Albany | NY | F | 13.2kV Substation | NM-NG | 0 | 2018-06-30
0709 | Alder Creek Solar, LLC | Alder Creek Solar | 2018-05-18 | 165 | 165 | S | Oneida | NY | E | Chases Lake - Porter 230kV | NM-NG | 0 | 2024-05-31
0711 | Somerset Solar Development LLC | Somerset Solar | 2018-05-31 | 19.9 | 19.9 | S | Monroe | NY | B | Kintigh Substation 345 kV | NYSEG | 0 | 2018-10-31
0712 | Cayuga Solar LLC | Cayuga Solar | 2018-05-31 | 19.9 | 19.9 | S | Thompkins | NY | C | Milliken Substation 34.5kV | NYSEG | 0 | 2018-11-30
0713 | EDF Renewables Development, Inc. | Edora B Solar Energy Center | 2018-06-01 | 20 | 20 | S | Orange | NY | G | Hartley Substation 69kV | O&R | 0 | 2020-05-31
0714 | EDF Renewables Development, Inc. | Edora C Solar Energy Center | 2018-06-01 | 20 | 20 | S | Orange | NY | G | Shoemaker-Westtown 69kV | O&R | 0 | 2019-07-31
0715 | EDF Renewables Development, Inc. | Suffragette Solar Energy Center | 2018-06-01 | 20 | 20 | S | Cayuga | NY | C | Hyatt Substation 34.5kV | NYSEG | 0 | 2021-05-31
0718 | Cortland Energy Center, LLC | Cortland Energy Center | 2018-06-07 | 50 | 50 | S | Cortland | NY | C | Cortland - SUNY 115 kV | NM-NG | 0 | 2023-01-31
0719 | East Light Energy Center, LLC | East Light Energy Center | 2018-06-07 | 40 | 40 | S | Montgomery | NY | F | Meco - Rotterdam 115 kV | NM-NG | 0 | 2023-01-31
0722 | SED NY Holdings LLC | Manchester Solar | 2018-06-07 | 20 | 20 | S | Ontario | NY | C | Station 168 34.5 kV line #704 | RG&E | 0 | 2021-02-28
0723 | Lyonsdale Biomass, LLC | Lyonsdale Solar | 2018-06-08 | 19.9 | 19.9 | S | Lewis | NY | E | Lyonsdale Substation 115kV | NM-NG | 0 | 2019-04-30
0724 | Brewster Solar, LLC | Brewster Solar | 2018-06-08 | 25 | 25 | S | Putnam | NY | G | Pawling - Croton Falls 115kV | NYSEG | 0 | 2018-11-30
0725 | York Solar, LLC | York Solar | 2018-06-08 | 24.9 | 24.9 | S | Livingston | NY | A | Line #863 - 69kV | NM-NG | 0 | 2018-11-30
0726 | Niagara Falls Solar, LLC | Niagara Falls Solar | 2018-06-08 | 24.9 | 24.9 | S | Niagara | NY | A | Line #181 - 115kV | NM-NG | 0 | 2018-09-30
0727 | Alden Solar, LLC | Alden Solar | 2018-06-11 | 24.9 | 24.9 | S | Erie | NY | A | Cold Springs - Pulteny 34.5kV | NYSEG | 0 | 2018-09-30
0728 | EDF Renewables Development, Inc. | Champlain Solar | 2018-06-11 | 20 | 20 | S | Clinton | NY | E | Mason Corners-Sciota Flatrock 115kV | NYSEG | 0 | 2018-07-31
0729 | EDF Renewables Development, Inc. | Quiet Meadows Solar | 2018-06-11 | 20 | 20 | S | Oneida | NY | E | Oneida - Oneida Energy 115kV | NM-NG | 0 | 2018-08-31
0732 | Machias Solar, LLC | Machias Solar | 2018-06-11 | 20 | 20 | S | Cattaraugus | NY | A | Fivemile - Gardenville 115kV | NM-NG | 0 | 2018-12-31
0733 | Arcade Solar, LLC | Arcade Solar | 2018-06-11 | 19.9 | 19.9 | S | Wyoming | NY | A | Arcade - Bliss 115kv | Village of Arcade | 0 | 2018-11-30
0736 | Empire State Solar, LLC | Meads Hill Solar | 2018-06-12 | 20 | 20 | S | Schuyler | NY | C | Montour Falls - Greenidge 115kV | NYSEG | 0 | 2018-11-30
0738 | Empire Offshore Wind LLC | El Melville | 2018-06-12 | 816 | 816 | W | Suffolk | NY | K | Ruland Rd. Substation 138kV | LIPA | 0 | 2023-01-31
0739 | Hecate Energy Cody Road LLC | Cody Road | 2018-06-12 | 19.9 | 19.9 | W | Madison | NY | C | Fenner - Cortland 115kV | NM-NG | 0 | 2019-07-31
0740 | Oakdale Battery Storage LLC | Oakdale Battery Storage | 2018-06-18 | 120 | 120 | ES | Broome | NY | C | Oakdale Substation 115kV | NYSEG | 0 | 2024-05-31
0741 | Bluestone Wind, LLC | Bluestone Battery Storage | 2018-07-02 | 10 | 10 | ES | Broome | NY | E | Afton - Stilesville 115kV | NYSEG | 0 | 2020-04-30
0742 | Consolidated Edison Co. of NY, Inc. | Astoria Storage on Demand | 2018-07-05 | 1.5 | 1.5 | ES | Queens | NY | J | North Queens 27kV | ConEd | 0 | 2022-01-31
0743 | Invenergy Solar Development North America LLC | Hornell Solar | 2018-07-16 | 20 | 20 | S | Steuben | NY | C | Bennett 34.5kV | NYSEG | 0 | 2019-10-31
0744 | Mitchell Energy Facility, LLC | Magruder BESS | 2018-07-18 | 20 | 20 | ES | Ulster | NY | G | East Walden - Modena 115kV | CHG&E | 0 | 2026-01-31
0745 | Energy Storage Resources, LLC | Huckleberry Ridge Energy | 2018-07-25 | 100 | 100 | ES | Orange | NY | G | Shoemaker-Westtown 69kV line #11 and Shoemaker to Deerpark 69 kV #14 | O&R | 0 | 2024-05-31
0746 | Peconic River Energy Storage LLC d/b/a North Street Energy Storage | North Street Energy Storage | 2018-07-30 | 150 | 150 | ES | Suffolk | NY | K | Brookhaven - Sills 138kV | LIPA | 0 | 2023-05-31
0747 | White Creek Solar LLC | White Creek Solar | 2018-07-30 | 100 | 100 | S | Livingston | NY | A | Jones - Mortimer 115kV | NM-NG | 0 | 2018-10-31
0749 | KCE NY 11 LLC | KCE NY 11 | 2018-08-10 | 20 | 20 | ES | Orange | NY | G | Coldenham Substation 115kV | CHGE | 0 | 2019-02-28
0750 | Calpine Mid Atlantic Development, LLC | Bethpage Storage | 2018-08-14 | 50 | 50 | ES | Nassau | NY | K | Grumman Substation 69kV | LIPA | 0 | 2019-05-31
0751 | Calpine Mid Atlantic Development, LLC | Stony Brook Storage | 2018-08-14 | 24 | 24 | ES | Suffolk | NY | K | 8LR substation 69kV | LIPA | 0 | 8/31/21
0752 | Granada Solar, LLC (Conti) | Goldenrod Solar | 2018-08-15 | 90 | 90 | S | Herkimer | NY | E | Meco - Rotterdam 115 kV | NM-NG | 0 | 2018-10-31
0753 | Granada Solar, LLC (Conti) | Blue Star Solar | 2018-08-15 | 100 | 100 | S | Washington | NY | F | Mohican - Luther Forest 115kV | NM-NG | 0 | 2018-10-31
0754 | Anbaric Development Partners, LLC | NY Ocean Grid - Canal | 2018-08-20 | 800 | 800 | W | Suffolk | NY | K | Canal Substation 138kV | LIPA | 0 | 2020-08-31
0755 | Anbaric Development Partners, LLC | NY Ocean Grid - Shoreham | 2018-08-20 | 800 | 800 | W | Suffolk | NY | K | Shoreham Substation 138kV | LIPA | 0 | 2020-07-31
0756 | Rising Solar, LLC | Rising Solar II | 2018-08-24 | 20 | 20 | S | Orange | NY | G | Sugarloaf Substation - 69kV | O&R | 0 | 2021-01-31
0757 | Granada Solar, LLC | Monarda Solar | 2018-08-29 | 20 | 20 | S | Herkimer | NY | E | Meco - Rotterdam 115 kV | NM-NG | 0 | 2018-12-31
0760 | NY Power Authority | Moses-Adirondack | 2018-09-07 | N/A | N/A | AC | St. Lawrence-Lewis | NY | D, E | Moses - Adirondack 230kV | NYPA | 0 | 3/31/21
0761 | Invenergy Solar Development LLC | Athens Energy Center | 2018-09-17 | 100 | 100 |  | Greene | NY | G | New Scotland - North Catskill 115kV | NM-NG | 0 | 2018-10-31
0762 | Invenergy Storage Development LLC | Riverhead Storage Energy Center | 2018-09-17 | 75 | 75 | ES | Suffolk | NY | K | Brookhaven - Edwards Ave 138kV | LIPA | 0 | 2020-03-31
0763 | Invenergy Solar Development LLC | Cicero Storage | 2018-09-25 | 10 | 10 | ES | Onondaga | NY | C | Pine Grove Substation 13.2kV | NM-NG | 0 | 2020-01-31
0764 | Bay State Wind LLC | NY Wind Canal | 2018-09-28 | 440 | 440 | W | Suffolk | NY | K | Canal Substation 138kV | LIPA | 0 | 2020-10-31
0765 | Bay State Wind LLC | NY Wind Brookhaven | 2018-09-28 | 880 | 880 | W | Suffolk | NY | K | Brookhaven 138kV | LIPA | 0 | 2020-12-31
0767 | Bay State Wind LLC | NY Wind Gowanus | 2018-09-28 | 1200 | 1200 | W | NY | NY | J | Gowanus Substation 345kV | ConEd | 0 | 8/31/21
0770 | KCE NY8 LLC | KCE NY 8a | 2018-10-09 | 20 | 20 | ES | Greene | NY | G | South Cairo 13.2kV | CHG&E | 0 | 2024-12-31
0771 | Mistral Wind LLC | Mistral Wind Alternative | 2018-10-10 | 20 | 20 | W | Genesee | NY | B | N. Akron - Attica 34.5 kV | NM-NG | 0 | 2020-01-31
0772 | Hollyhock Solar, LLC | Hollyhock Solar | 2018-10-15 | 20 | 20 | S | Albany | NY | F | Leeds - New Scotland 115kV | NM-NG | 0 | 2018-12-31
0773 | Charboneau Solar, LLC | Charboneau Solar | 2018-10-15 | 20 | 20 | S | Essex | NY | F | Ticonderoga - Hague Road 115kV | NM-NG | 0 | 2019-04-30
0778 | Astoria Generating Company LP | Gowanus Gas Turbine Facility Repowering | 2018-11-08 | 549 | 588 | CT | Kings | NY | J | Gowanus Substation 345kV | ConEd | 0 | 2023-01-31
0779 | Hecate Energy Gedney Hill LLC | Gedney Hill Solar | 2018-11-09 | 20 | 20 | S | Albany | NY | G | New Baltimore - Westerlo 69kV | CHG&E | 0 | 2024-05-31
0780 | Hecate Energy Johnstown LLC | Johnstown Solar | 2018-11-09 | 20 | 20 | S | Schenectady | NY |  | Stoner - Rotterdam 115kV | NM-NG | 0 | 2023-08-31
0782 | Invenergy Solar Development North America LLC | Hornell Storage | 2018-12-04 | 20 | 20 | ES | Steuben | NY | C | Bennett 34.5kV | NYSEG | 0 | 2020-04-30
0784 | High Bridge Wind, LLC | High Bridge Battery | 2018-12-11 | 5 | 5 | ES | Chenango | NY | E | E. Norwich - Jennison 115kV | NYSEG | 0 | 2024-06-30
0785 | ConnectGen Erie-Wyoming LLC | Erie-Wyoming County Solar | 2018-12-12 | 175 | 175 | CR | Wyoming | NY | C | Stolle Road - High Sheldon 230kV | NYSEG | 0 | 2024-12-31
0786 | Ravenswood Development, LLC | Ravenswood Energy Storage | 2018-12-20 | 187 | 187 | ES | Queens | NY | J | Rainey - Farragut 345kV | ConEd | 0 | 2021-12-31
0787 | Levy Grid, LLC | Levy Grid, LLC | 2018-12-20 | 150 | 150 | ES | Erie | NY | A | Gardenville Subsation 115kV | NM-NG | 0 | 2026-06-30
0788 | Atlantic Shores Offshore Wind Project 3, LLC | Atlantic Shores Offshore Wind 7 | 2019-01-14 | 880 | 880 | W | Nassau | NY | K | East Garden City 345kV Substation | NYPA | 0 | 2021-06-30
0789 | Atlantic Shores Offshore Wind Project 3, LLC | Atlantic Shores Offshore Wind 8 | 2019-01-14 | 880.0 | 880.0 | W | Kings | NY | J | Gowanus 345kV | ConEd | 0 | 2024-05-31
0790 | Atlantic Shores Offshore Wind Project 2, LLC | Atlantic Shores Offshore Wind 9 | 2019-01-14 | 880.0 | 880.0 | W | Richmond | NY | J | Fresh Kills 345kV | ConEd | 0 | 2024-05-31
0791 | Danskammer Energy LLC | Danskammer Energy Center | 2019-01-14 | 84.4 | 88.9 | CC | Orange | NY | G | Danskammer 115kV | CHGE | 0 | 2022-08-31
0792 | Anbaric Development Partners, LLC | Juno Power Express 2 | 2019-01-29 | 800.0 | 800.0 | DC | Suffolk | NY | K | Ruland Road 138kV | LIPA | 0 | 2024-05-31
0793 | esVolta, LP | Ladybug Energy Storage | 2019-02-06 | 75 | 75 | ES | Westchester | NY | I | Sprainbrook Substation | ConEd | 0 | 2019-07-31
0794 | esVolta, LP | Bluebird Energy Storage | 2019-02-06 | 40 | 40 | ES | Westchester | NY | I | Dunwoodie Substation | ConEd | 0 | 2019-07-31
0795 | esVolta, LP | Appleseed Energy Storage | 2019-02-06 | 50 | 50 | ES | Greene | NY | G | Leeds Substation | NM-NG | 0 | 2019-07-31
0802 | EDF Renewables Development, Inc. | Bunker Solar Energy Center | 2019-03-06 | 125 | 125 | ES | Franklin | NY | D | Willis - Lyon Mt 115kV | NYSEG | 0 | 2020-03-31
0803 | Yonkers Grid, LLC | Yonkers Grid, LLC | 2019-03-11 | 100 | 100 | ES | Westchester | NY | I | Dunwoodie - 138kV North Substation | ConEd | 0 | 2023-09-30
0806 | SED NY Holdings LLC | Limestone Solar | 2019-03-25 | 20.0 | 20.0 | S | Fulton | NY | F | Stoner - Rotterdam 115kV | NM-NG | 0 | 2024-05-31
0807 | SunEast Hilltop Solar LLC | Hilltop Solar | 2019-03-28 | 20 | 20 | S | Rensselaer | NY | F | Eastover - Schaghticoke 115kV | NM-NG | 0 | 2024-09-30
0808 | Barrett Ridge Energy, LLC | Barrett Ridge Energy | 2019-04-01 | 107 | 107 | ES | Orange | NY | G | Sugar Loaf - Vernon 115kV | CHGE | 0 | 2021-04-20
0809 | Seven Creek Energy, LLC | Seven Creek Energy | 2019-04-01 | 240 | 240 | ES | Chautauqua | NY | A | South Ripley Substation 230kV | NM-NG | 0 | 2021-04-20
0812 | Diamond Generating Corporation | CWW 200 Wind | 2019-04-03 | 200 | 200 | W | Erie | NY | A | Harbor Front 115kV | NM-NG | 0 | 2021-03-31
0813 | Diamond Generating Corporation | CWW 300 Wind | 2019-04-03 | 300 | 300 | W | Erie | NY | A | Harbor Front 115kV | NM-NG | 0 | 2021-02-28
0814 | Diamond Generating Corporation | CWW 300 MW DUN | 2019-04-03 | 300 | 300 | W | Chautauqua | NY | A | Dunkirk Substation 230kV | NM-NG | 0 | 2021-02-28
0816 | LIPA | NNC TTC Increase | 2019-04-05 | N/A | N/A | AC | Suffolk | NY | K | Northport Substation 138kV | LIPA | 0 | 2021-06-30
0817 | Quogue Energy Storage, LLC | Quogue Energy Storage | 2019-04-12 | 20 | 20 | ES | Suffolk | NY | K | Quogue Substation 69kV | LIPA | 0 | 2019-06-30
0818 | Setauket Energy Storage, LLC | Port Jeff 1-Terryville Energy Storage | 2019-04-15 | 20 | 20 | ES | Suffolk | NY | K | Port Jefferson - Terryville 69kV | LIPA | 0 | 2019-06-30
0819 | Setauket Energy Storage, LLC | Port Jeff 2-Terryville Energy Storage | 2019-04-15 | 20 | 20 | ES | Suffolk | NY | K | Port Jefferson - Terryville 69kV | LIPA | 0 | 2019-06-30
0820 | Setauket Energy Storage, LLC | Port Jeff 2-Stony Brook Energy Storage | 2019-04-15 | 20 | 20 | ES | Suffolk | NY | K | Port Jefferson - Stony Brook 69kV | LIPA | 0 | 2019-06-30
0821 | Setauket Energy Storage, LLC | Port Jeff -Mt. Sinai Energy Storage | 2019-04-15 | 20 | 20 | ES | Suffolk | NY | K | Port Jefferson - Mt. Sinai 69kV | LIPA | 0 | 2019-06-30
0822 | Astoria Generating Company LP | Whale Square Energy Storage 1 | 2019-04-15 | 58.2 | 58.2 | ES | Kings | NY | J | Narrows Barge Feeder 23162 | ConEd | 0 | 2024-12-31
0823 | Wildwood Energy Storage, LLC | Wildwood Energy Storage | 2019-04-15 | 116.7 | 116.7 | ES | Suffolk | NY | K | Wildwood Substation 138kV | LIPA | 0 | 2020-04-30
0824 | Wildwood Energy Storage, LLC | Wildwood Shoreham Energy Storage | 2019-04-15 | 76.9 | 76.9 | ES | Suffolk | NY | K | Shoreham Substation 69kV | LIPA | 0 | 2020-04-30
0825 | Setauket Energy Storage, LLC | Setauket Energy Storage | 2019-04-15 | 65.3 | 65.3 | ES | Suffolk | NY | K | Port Jefferson - Terryville 69kV | LIPA | 0 | 2025-01-31
0826 | NRG Astoria Storage LLC | Astoria Energy Storage 1 | 2019-04-18 | 40 | 40 | ES | Queens | NY | J | North Queens 27kV Bus | ConEd | 0 | 2023-01-31
0829 | NRG Arthur Kill Storage LLC | Arthur Kill Energy Storage 2 | 2019-04-24 | 60 | 60 | ES | Richmond | NY | J | Arthur Kill 138kV | ConEd | 0 | 2020-01-31
0830 | NRG Astoria Storage LLC | Astoria Energy Storage 2 | 2019-04-26 | 79.9 | 79.9 | ES | Queens | NY | J | Astoria West 138kV Substation | ConEd | 0 | 2023-01-31
0831 | Dimension NY 1 LLC | NY-19-0002 Sheredy | 2019-04-29 | 10.2 | 10.2 | ES | Broome | NY | C | Northside Substation 34.5kV | NYSEG | 0 | 2020-01-31
0836 | Astoria Generating Company, LP | Dock Battery Energy Storage 2 | 2019-05-07 | 56.3 | 56.3 | ES | Queens | NY | J | Astoria East Substation 138kV | ConEd | 0 | 2020-02-29
0837 | Astoria Generating Company, LP | Parking Lot Battery Energy Storage 2 | 2019-05-07 | 79 | 79 | ES | Queens | NY | J | Astoria East Substation 138kV | ConEd | 0 | 2020-02-29
0838 | NRG Astoria Storage LLC | Astoria Energy Storage 3 | 2019-05-09 | 20 | 20 | ES | Queens | NY | J | North Queens 27kV Substation | ConEd | 0 | 2023-01-31
0839 | NRG Astoria Storage LLC | Astoria Energy Storage 4 | 2019-05-09 | 20 | 20 | ES | Queens | NY | J | Astoria West 138kV Substation | ConEd | 0 | 2020-02-29
0840 | Hecate Grid Swiftsure LLC | Swiftsure Energy Storage | 2019-05-09 | 650 | 650 | ES | Richmond | NY | J | Fresh Kills 345kV | ConEd | 0 | 2024-11-30
0841 | TJA Clean Energy, LLC | Sharon Springs Interconnection | 2019-05-10 | 20 | 20 | S | Schoharie | NY | F | Sharon - Cobleskill 69kV Substation | NM-NG | 0 | 2021-07-31
0842 | Mitsubishi Hitachi Power Systems Americas, Inc. | Comet Solar | 2019-05-17 | 20 | 20 | S | Monroe | NY | B | Mortimer - Golah 115kV | NM-NG | 0 | 2020-01-31
0844 | Boralex US Development, LLC | NY37 Energy Storage | 2019-05-17 | 4 | 4 | ES | Jefferson | NY | E | Coffeen - West Adams 115kV Substation | NM-NG | 0 | 2020-12-31
0845 | sPower Development Company, LLC | Bloom Energy Storage Center | 2019-05-20 | 120 | 120 | ES | Kings | NY | J | Farragut 345kV Substation | ConEd | 0 | 2020-03-31
0846 | sPower Development Company, LLC | Rescue Energy Storage Center | 2019-05-20 | 300 | 300 | ES | NY | NY | J | East 13th Street 138kV Substation | ConEd | 0 | 2020-04-30
0847 | sPower Development Company, LLC | Chelsea Energy Storage Center | 2019-05-20 | 300 | 300 | ES | NY | NY | J | West 49th St Substation 345kV | ConEd | 0 | 2020-04-30
0848 | Fairway Solar NY LLC | Fairway Solar | 2019-05-20 | 20 | 20 | S | St. Lawrence | NY | E | McIntyre - Corning 115kV (Line#6) | NM-NG | 0 | 2025-08-31
0851 | ConnectGen Madison County LLC | Madison County Solar | 2019-05-23 | 20 | 20 | S | Madison | NY | E | Bouckville Substation | NYSEG | 0 | 2020-01-31
0852 | Niagara Dolomite Solar, LLC | Niagara Dolomite Solar | 2019-05-24 | 180 | 180 | S | Niagara | NY | A | Robinson Rd - Stolle Rd 230kV | NYSEG | 0 | 2024-12-31
0853 | Boralex US Development, LLC | NY16 Solar | 2019-05-24 | 20 | 20 | S | Washington | NY | F | Mohican - Schaghticoke 115kV | NM-NG | 0 | 2021-03-31
0854 | Boralex US Development, LLC | NY16 Energy Storage | 2019-05-24 | 4 | 4 | ES | Washington | NY | F | Battenkill - Mohican 115kV | NM-NG | 0 | 2019-10-04
0855 | Bald Mountain Solar LLC | NY13 Solar | 2019-05-24 | 20 | 20 | S | Washington | NY | F | Mohican - Schaghticoke 115kV | NM-NG | 0 | 2026-02-28
0856 | Boralex US Development, LLC | NY13 Energy Storage | 2019-05-24 | 4 | 4 | ES | Washington | NY | F | Battenkill - Mohican 115kV | NM-NG | 0 | 2019-10-04
0857 | EDF Renewables Development, Inc. | Columbia Solar Energy Center | 2019-05-28 | 350 | 350 | S | Herkimer | NY | E | Edic - Fraser 345kV | NYPA | 0 | 2024-05-31
0858 | EDF Renewables Development, Inc. | Genesee Road Solar Energy Center | 2019-05-28 | 250 | 250 | S | Erie | NY | A | Stolle Rd - Five Mile Rd 345kV | NYSEG | 0 | 2024-12-31
0859 | EDF Renewables Development, Inc. | Ridge View Solar Energy Center | 2019-05-28 | 350 | 350 | S | Niagara | NY | A | Somerset - Dysinger 345kV | NYSEG | 0 | 2024-12-31
0860 | EDF Renewables Development, Inc. | Rosalen Solar Energy Center | 2019-05-28 | 200 | 200 | S | Steuben | NY | B | Clay - Pannell 345kV | NYPA | 0 | 2024-07-31
0861 | Mitsubishi Hitachi Power Systems Americas, Inc. | Tonawanda Solar | 2019-05-29 | 20 | 20 | S | Niagara | NY | B | Lockport - Batavia 115kV | NM-NG | 0 | 2020-12-31
0862 | Mitsubishi Hitachi Power Systems Americas, Inc. | Farwell Solar | 2019-05-29 | 20 | 20 | S | Orleans | NY | B | Lockport - Mortimer 115kV | NM-NG | 0 | 2021-02-28
0866 | NY North Country, LLC | North Country Wind | 2019-06-03 | 298.2 | 298.2 | W | Franklin | NY | D | Willis - Moses 230 kV MW1 | NYPA | 0 | 2024-12-31
0867 | Somerset Solar Development LLC | Somerset Solar Development LLC | 2019-06-03 | 20 | 20 | S | Niagara | NY | A | Kintigh 345kV | NYSEG | 0 | 2020-01-31
0868 | Cayuga Solar LLC | Cayuga Solar LLC | 2019-06-03 | 19.9 | 19.9 | S | Cayuga | NY | C | Milliken Substation | NYSEG | 0 | 2020-01-31
0869 | SunEast Tabletop Solar LLC | Tabletop Solar | 2019-06-04 | 80 | 80 | S | Montgomery | NY | F | Clinton - Clinton Tap 115 kV | NM-NG | 0 | 2024-12-31
0871 | Invenergy Solar Project Development LLC | Verona Solar Energy Center I | 2019-06-05 | 250 | 250 | S | Oneida | NY | C | Clay - Edic 345kV | NYPA | 0 | 2024-06-30
0872 | Invenergy Solar Project Development LLC | Taproot Solar Energy Energy | 2019-06-05 | 300 | 300 | S | Montgomery | NY | E | Porter - Rotterdam 230kV | NM-NG | 0 | 2019-12-31
0873 | Invenergy Solar Project Development LLC | Verona Solar Energy Center II | 2019-06-05 | 250.0 | 250.0 | S | Oneida | NY | C | Clay - Edic 345kV | NYPA | 0 | 2024-05-31
0875 | SL Portland, LLC | SL Portland Solar | 2019-06-06 | 19.9 | 19.9 | S | Chautauqua | NY | A | Dunkirk - Falconer 115 kV | NM-NG | 0 | 2020-04-30
0876 | SL Selkirk, LLC | SL Selkirk Solar | 2019-06-06 | 19.9 | 19.9 | S | Albany | NY | F | New Scotland - Alps 345kV | NM-NG | 0 | 2019-10-31
0877 | SL York, LLC | SL York Solar | 2019-06-06 | 19.9 | 19.9 | S | Livingston | NY | B | Golah - S. Perry 115 kV | NM-NG | 0 | 2020-04-30
0878 | Energy Storage Resources, LLC | Pirates Island | 2019-06-10 | 100 | 100 | ES | Erie | NY | A | Huntley - Gardenville 115kV | NM-NG | 0 | 2024-09-30
0879 | Empire Community Solar LLC | Holley Road Solar | 2019-06-10 | 19.9 | 19.9 | S | Orleans | NY | B | Lockport - Mortimer 115kV | NM-NG | 0 | 10/31/22
0881 | New Bremen Solar, LLC | New Bremen Solar | 2019-06-10 | 100 | 100 | S | Lewis | NY | E | Bremen - Lowville 115kV | NM-NG | 0 | 2023-12-31
0884 | Dimension NY 1 LLC | Blooming Farm LLC | 2019-06-12 | 10.2 | 10.2 | ES | Orange | NY | G | Blooming Grove Substation 69kV | O&R | 0 | 2019-10-04
0886 | Empire State Land Holdings, LLC | Turin Highlands Solar | 2019-06-12 | 20 | 20 | S | Oneida | NY | E | Taylorville - Boonville 115kV | NM-NG | 0 | 2019-07-31
0888 | Sky Solar Inc. | Hornell Center 16 | 2019-06-13 | 17.6 | 17.6 | S | Allegany | NY | C | Moraine Substation 115kV | NYSEG | 0 | 2019-10-31
0889 | Energy Storage Resources, LLC | Peconic River II | 2019-06-20 | 19.2 | 19.2 | ES | Suffolk | NY | K | 8RX Moriches | LIPA | 0 | 2019-08-31
0890 | Energy Storage Resources, LLC | Queen City | 2019-06-20 | 19.2 | 19.2 | ES | Dutchess | NY | K | Knapps Corners | CHGE | 0 | 2019-10-04
0891 | Energy Storage Resources, LLC | Meredith Woods | 2019-06-24 | 19.2 | 19.2 | ES | NY | NY | J | Baron Blvd | ConEd | 0 | 2019-10-04
0892 | FourGen LLC | Holtsville Fuel Cell | 2019-07-15 | 20 | 20 | FC | Suffolk | NY | K | Holtsville 69kV | LIPA | 0 | 2020-07-31
0893 | FourGen LLC | Setauket Fuel Cell | 2019-07-15 | 20 | 20 | FC | Suffolk | NY | K | Terryville Substation 69kV | LIPA | 0 | 2020-07-31
0894 | Montgomery Energy Storage 1, LLC | Montgomery Energy Storage | 2019-07-15 | 20 | 20 | ES | Orange | NY | G | Walden - Montgomery 69kV | CHG&E | 0 | 2020-05-31
0895 | Dimension NY 1 LLC | Road Property | 2019-07-15 | 19.9 | 19.9 | ES | Suffolk | NY | K | Central Islip 138kV | LIPA | 0 | 2020-01-31
0896 | Sky Solar Inc. | Hornell Center 16 BESS | 2019-07-18 | 8 | 8 | ES | Allegany | NY | C | Moraine Substation 115kV | NYSEG | 0 | 2019-10-31
0897 | Mitsubishi Hitachi Power Systems Americas, Inc. | Bluejay Solar | 2019-08-01 | 5 | 5 | S | Allegany | NY |  |  | RG&E | 0 | 2019-10-31
0898 | Mitsubishi Hitachi Power Systems Americas, Inc. | Oak Orchard Solar | 2019-08-01 | 5 | 5 | S | Orleans | NY | A, B | Shelby | NM-NG | 0 | 2019-12-31
0900 | Granada Solar, LLC | Fowler Solar | 2019-08-09 | 20 | 20 | S | Madison | NY | E | Fenner - Whitman 115kV | NM-NG | 0 | 2020-02-29
0901 | TJA Clean Energy, LLC | Lacona Solar | 2019-08-16 | 20 | 20 | S | Oswego | NY | E | Lighthouse Hill - Black River 115kV | NM-NG | 0 | 2021-12-31
0902 | sPower Development Company, LLC | Yacht Club Energy Storage | 2019-08-16 | 300 | 300 | ES | NY | NY | J | Gowanus 345kV | ConEd | 0 | 2021-04-30
0903 | sPower Development Company, LLC | Goethals Energy Storage | 2019-08-16 | 300 | 300 | ES | NY | NY | J | Goethals 345kV | ConEd | 0 | 2021-04-30
0904 | Agilitas Energy, LLC | South Conduit Avenue Energy Storage | 2019-08-20 | 10 | 10 | ES | NY | NY | J | South Conduit Ave | ConEd | 0 | 2019-10-31
0905 | Agilitas Energy, LLC | Liberty Avenue Energy Storage | 2019-08-20 | 10 | 10 | ES | NY | NY | J | Liberty Ave | ConEd | 0 | 2019-10-31
0906 | NRG Arthur Kill Storage LLC | Arthur Kill Energy Storage 2 | 2019-08-28 | 20 | 20 | ES | NY | NY | J | Fresh Kills Substation | ConEd | 0 | 2020-02-29
0908 | NRG Astoria Storage LLC | Astoria Energy Storage 5 | 2019-09-12 | 20 | 20 | ES | Queens | NY | J | North Queens Substation 27kV | ConEd | 0 | 2020-02-29
0910 | Hartley Rd Energy Storage 1, LLC | 114 Hartley Rd-Goshen | 2019-09-24 | 10 | 10 | ES | Orange | NY | G | Hartley Substation 13.2kV | O&R | 0 | 2020-02-29
0911 | Dimension NY 1 LLC | Southold BESS | 2019-10-01 | 20 | 20 | ES | Suffolk | NY | K | Peconic - Southold 69kV | LIPA | 0 | 2022-04-30
0912 | Hecate Grid Intrepid 1 LLC | Intrepid Storage 69 | 2019-10-02 | 50 | 50 | ES | Nassau | NY | K | Barrett to Oil City 33-317 and 33-222 | LIPA | 0 | 2024-07-31
0913 | SED NY Holdings LLC | SunEast Manchester Solar LLC | 2019-10-04 | 20 | 20 | S | Ontario | NY | C | Station 127 (RGE)-Elbridge (NG) 115kV Line #7-983 | NM-NG | 0 | 2024-09-30
0914 | sPower Development Company, LLC | Loomis Creek Solar | 2019-10-07 | 100 | 100 | S | Columbia | NY | F | Churchtown Substation 115 kV | NYSEG | 0 | 2020-04-30
0915 | EDF Renewables Development, Inc. | Staten Island 1 Battery Storage | 2019-10-07 | 20 | 20 | ES | Richmond | NY | J | Fox Hills Substation 33kV | ConEd | 0 | 2020-09-30
0916 | EDF Renewables Development, Inc. | Hartley Battery Storage | 2019-10-07 | 20 | 20 | ES | Orange | NY | G | Hartley Road Substation 69kV | O&R | 0 | 2020-03-31
0917 | sPower Development Company, LLC | Loomis Creek ES | 2019-10-07 | 50 | 50 | ES | Columbia | NY | F | Churchtown Substation 115 kV | NYSEG | 0 | 2020-04-30
0918 | Hecate Grid Intrepid 1 LLC | Intrepid Storage 138 | 2019-10-09 | 250 | 250 | ES | Nassau | NY | K | Barrett to Valley Stream 138-291 & Barrett to Valley Stream 138-292 | LIPA | 0 | 2024-07-31
0919 | sPower Development Company, LLC | White Spring ES | 2019-10-10 | 100 | 100 | ES | Ontario | NY | C | Haley Road Substation 115 kV | NYSEG | 0 | 2021-06-30
0920 | sPower Development Company, LLC | White Spring Solar | 2019-10-10 | 200 | 200 | S | Ontario | NY | C | Haley Road Substation 115 kV | NYSEG | 0 | 2021-06-30
0921 | sPower Development Company, LLC | Line Creek ES | 2019-10-10 | 30 | 30 | ES | Schoharie | NY | F | Schoharie 69 kV | NM-NG | 0 | 2020-04-30
0922 | sPower Development Company, LLC | Line Creek Solar | 2019-10-10 | 50 | 50 | S | Schoharie | NY | F | Schoharie 69 kV | NM-NG | 0 | 2020-04-30
0923 | sPower Development Company, LLC | Far Rockaway Energy Storage Center | 2019-10-11 | 150 | 150 | ES | Queens | NY | K | Far Rockaway Substation 69 kV | LIPA | 0 | 2020-05-31
0924 | RICAL LLC | CBB | 2019-10-15 | 115 | 115 | ES | Dutchess | NY | G | Shenandoah Substation | CHGE | 0 | 2020-06-30
0925 | Hecate Grid Clermont 1 LLC | Clermont 1 | 2019-10-17 | 100 | 100 | ES | Suffolk | NY | K | West Babylon 69kV Substation | LIPA | 0 | 2023-05-31
0926 | Enel Energy Storage Holdings, LLC | Enel NYPA Astoria | 2019-10-18 | 100 | 100 | ES | Queens | NY | J | Astoria 138 kV substation | ConEd | 0 | 1/31/20
0927 | JERA Americas Inc. | Brunswick Energy Storage | 2019-10-21 | 100 | 100 | ES | Union | NJ | J | Goethals Substation 345kV | ConEd | 0 | 1/31/20
0928 | JERA Americas Inc. | Willow Bay Energy Storage | 2019-10-21 | 40 | 40 | ES | Richmond | NY | J | Fox Hills Substation 33kV | ConEd | 0 | 2020-03-31
0929 | EDF Renewables Development, Inc. | Morris Ridge Battery Storage | 2019-10-22 | 83 | 83 | ES | Livingston | NY | C | South Perry - Meyer 230 kV | NYSEG | 0 | 2024-05-31
0933 | Seven Creek Energy, LLC | Seven Creek Energy - Squab Hollow | 2019-10-31 | 290 | 290 | ES | Elk | PA | A | Homer City - Pierce Brook 345kV | NYSEG | 0 | 2021-04-30
0934 | Saturn Energy Storage LLC | Astoria BESS | 2019-10-31 | 70 | 68.6 | ES | Queens | NY | J | Astoria West Substation 138 kV | ConEd | 0 | 2020-04-30
0935 | SED NY Holdings LLC | Augustus Solar | 2019-11-01 | 20 | 20 | S | Oneida | NY | E | Brothertown - Oriskany Falls 46kV | NYSEG | 0 | 2024-11-30
0936 | AE - ESS Petracca, LLC | Petracca Place Energy Storage | 2019-11-01 | 10 | 10 | ES | Queens | NY | J | Corona 4kV | ConEd | 0 | 2020-05-31
0937 | Boralex US Development, LLC | NYSD Energy Storage | 2019-11-04 | 5.5 | 5.5 | ES | Saratoga | NY | F | Mechanicville 34.5 kV | NM-NG | 0 | 2020-03-31
0938 | KCE NY 12, LLC | KCE NY 12 | 2019-11-04 | 100 | 100 | ES | Suffolk | NY | K | Moriches Substation 69kV | LIPA | 0 | 2020-03-31
0939 | National Grid Generation LLC | Far Rockaway Power Station Battery Energy Storage System (BESS) | 2019-11-05 | 30 | 30 | ES | Queens | NY | K | Far Rockaway 69kV | LIPA | 0 | 2024-05-31
0940 | National Grid Generation LLC | Glenwood Power Station Battery Energy Storage System | 11/8/2019 | 50 | 50 | ES | Nassau | NY | K | Glenwood Substation (4YH) 138kV bus | LIPA | 0 | 2023-03-31
0941 | National Grid Generation LLC | Southampton Power Station Battery Energy Storage System (BESS) | 2019-11-08 | 30 | 30 | ES | Suffolk | NY | K | Southampton 69kV | LIPA | 0 | 2024-05-31
0942 | KCE NY 21, LLC | KCE NY 21 | 2019-11-08 | 60 | 60 | ES | Suffolk | NY | K | Pulaski 69kV | LIPA | 0 | 2024-05-31
0943 | Vistra Operations Company, LLC | Sithe Independence BESS | 2019-11-08 | 20 | 20 | ES | Oswego | NY | C | Sithe Independence 345kV | NM-NG | 0 | 2020-03-31
0944 | Invenergy Solar Development LLC | Verona Storage | 2019-11-12 | 100 | 100 | ES | Oneida | NY | C | Edic-Clay 345kV Line | NYPA | 0 | 2020-05-31
0945 | Niagara Grid I, LLC | Niagara Grid I | 2019-11-13 | 20 | 20 | ES | Erie | NY | A | Huntley - Praxair 115 kV Line #47 | NM-NG | 0 | 2024-06-30
0946 | Dimension NY 1 LLC | Helmer | 2019-11-14 | 21.3 | 21.3 | ES | Herkimer | NY | E | Old Forge - Raquette Lake 46 kV | NM-NG | 0 | 2020-01-31
0947 | Dimension NY 1 LLC | Livonia BESS | 2019-11-16 | 11.3 | 11.3 | ES | Livingston | NY | B | North Lakeville 34.5kV | NM-NG | 0 | 2022-10-31
0948 | Dimension NY 1 LLC | Webster BESS | 2019-11-18 | 8.8 | 8.8 | ES | Monroe | NY | B | 34.5 kV | RG&E | 0 | 2020-05-31
0949 | National Grid Generation LLC | Port Jefferson Power Station Battery Energy Storage System (BESS) | 2019-11-19 | 100 | 100 | ES | Suffolk | NY | K | Port Jefferson 138kV | LIPA | 0 | 2024-05-31
0951 | Cayuga Grid, LLC | Cayuga Grid, LLC | 2019-12-04 | 100 | 100 | ES | Erie | NY | A | New Gardenville 115kV Substation | NYSEG | 0 | 2023-04-30
0952 | Catskill Grid, LLC | Catskill Grid, LLC | 2019-12-04 | 100 | 100 | ES | Greene | NY | G | North Catskill - Milan 115kV | CHG&E | 0 | 2024-12-31
0954 | Empire Solar, LLC | Empire Solar | 2019-12-05 | 157.9 | 150 | S | Westfield | NY | A | South Ripley - Dunkirk 230 kV | NM-NG | 0 | 2024-05-31
0955 | VESI 26 LLC | Craillo Plaza | 2019-12-06 | 20 | 20 | ES | Rensselaer | NY | F | NGrid Rensselaer 34.5/ 13.2KV Substation | NM-NG | 0 | 2020-02-29
0957 | Holbrook Energy Storage, LLC | Holbrook Energy Storage | 2019-12-10 | 76.8 | 76.8 | ES | Suffolk | NY | K | Holtsville - Patchogue 69kV | LIPA | 0 | 2025-01-31
0958 | Empire Offshore Wind LLC | EI Oceanside | 2019-12-10 | 96 | 96 | W | Nassau | NY | K | Barrett - Valley Stream 138 kV Lines | LIPA | 0 | 2023-02-28
0959 | Empire Offshore Wind LLC | EI Oceanside 2 | 2019-12-11 | 1260 | 1260 | W | Nassau | NY | K | Barrett - Valley Stream 138 kV Lines | LIPA | 0 | 2024-04-30
0960 | SWEB Development USA, LLC | Cobleskill Solar | 2019-12-12 | 20 | 20 | S | Schoharie | NY | F | Cobleskill - Schoharie 69KV | NM-NG | 0 | 2023-10-31
0961 | Calpine Mid Atlantic Development, LLC | Bethpage Battery Energy Storage System | 2019-12-18 | 20 | 20 | ES | Nassau | NY | K | Grumman 69 kV | LIPA | 0 | 2024-10-31
0962 | Brookfield Power US Asset Management LLC | Beardslee Solar | 2019-12-19 | 20 | 20 | S | Herkimer | NY | E | St. Johnsville - Inghams 115kV | NM-NG | 0 | 11/30/22
0963 | Invenergy Storage Development LLC | Crooked Lake Storage | 2019-12-19 | 7 | 7 | ES | Yorktown | NY | H | Mohansic 13.2kV Substation | NYSEG | 0 | 2020-04-30
0964 | Invenergy Storage Development LLC | Berry Place Storage | 2019-12-20 | 10 | 10 | ES | Livingston | NY | A | Lakeville 34.5kV substation | NM-NG | 0 | 2020-01-31
0965 | Yaphank Energy Storage, LLC | Yaphank Energy Storage | 2019-12-21 | 76.8 | 77.6 | ES | Suffolk | NY | K | William Floyd - Brookhaven 69kV | LIPA | 0 | 2025-02-28
0966 | West Babylon Energy Storage, LLC | West Babylon Storage | 2019-12-21 | 40.3 | 40.3 | ES | Suffolk | NY | K | West Babylon - Lindenhurst 69kV | LIPA | 0 | 2024-05-31
0968 | SED NY Holdings LLC | Gouverneur Solar Project | 2020-01-09 | 20 | 20 | S | St. Lawrence | NY | E | North Gouverneur - Battle Hill 115kV | NM-NG | 0 | 2020-05-31
0969 | esVolta, LP | Modena Energy Storage I | 2020-01-09 | 6 | 6 | ES | Ulster | NY | G | Modena Substation | CHGE | 0 | 2020-02-29
0970 | esVolta, LP | Modena Energy Storage II | 2020-01-09 | 6 | 6 | ES | Ulster | NY | G | Modena Substation | CHGE | 0 | 2020-02-29
0972 | SWEB Development USA, LLC | Warner Hill Solar | 2020-01-10 | 20 | 20 | S | Schoharie | NY | F | Middleburg Tap - Middleburg 69kV | NM-NG | 0 | 2023-09-30
0973 | Wildwood Energy Storage, LLC | Wildwood-Riverhead Energy Storage | 2020-01-13 | 293.5 | 297.9 | ES | Suffolk | NY | K | Wildwood-Riverhead 138 kV | LIPA | 0 | 2021-08-30
0974 | KCE NY 19 LLC | KCE NY 19 | 2020-01-14 | 80 | 80 | ES | Orange | NY | G | Sugarloaf - Wisner 69kV | O&R | 0 | 2024-12-31
0975 | Dimension NY 1 LLC | Webb BESS | 2020-01-15 | 20 | 20 | ES | Herkimer | NY | E | Old Forge-Raquette Lake 46 kV | NM-NG | 0 | 2020-06-30
0976 | Invenergy Storage Development LLC | Esopus Valley Storage | 2020-01-16 | 10 | 10 | ES | Ulster | NY | G | Hurley Ave 34.5kV Substation | CHGE | 0 | 2020-04-30
0977 | Dimension NY 1 LLC | Dutchess BESS | 2020-01-16 | 6.6 | 6.6 | ES | Dutchess | NY | G | Pawling - Haviland Hollow 46kV | NYSEG | 0 | 2020-05-31
0978 | Hydroelectric Corporation | NY Hydro-Kinetic Project 1 | 2020-01-18 | 550 | 480 | H | Kings | NY |  | Sayreville Station 345kV |  | 0 | 2020-03-31
0980 | Invenergy Storage Development LLC | Heritage Storage | 2020-01-22 | 8 | 8 | ES | Erie | NY | A | Erie 34.5kV Substation | NYSEG | 0 | 2020-08-31
0981 | Invenergy Storage Development LLC | Oblong Storage | 2020-01-22 | 6 | 6 | ES | Dutchess | NY | G | Pawling 46kV Substation | NYSEG | 0 | 9/30/20
0982 | National Grid Generation LLC | West Babylon Power Station Battery Energy Storage System | 2020-01-22 | 50 | 50 | ES | Suffolk | NY | K | West Babylon 69kV | LIPA | 0 | 2024-05-31
0983 | JERA Americas Inc. | Winter Drive Energy Storage | 2020-01-28 | 8 | 8 | ES | Lancaster | NY | A | Erie Street Substation -34.5kV | NYSEG | 0 | 2020-05-31
0984 | JERA Americas Inc. | Empire Energy Storage | 2020-01-28 | 8 | 8 | ES | Monroe | NY | B | Station 55 34.5kV | RG&E | 0 | 2020-05-31
0985 | JERA Americas Inc. | Bristol Energy Storage | 2020-01-28 | 6 | 6 | ES | Ontario | NY | B | 34.5kV line | RG&E | 0 | 2020-05-31
0986 | JERA Americas Inc. | Pawling Energy Storage | 2020-01-29 | 6 | 6 | ES | Putnam | NY | G | 46kV line | NYSEG | 0 | 2020-05-31
0988 | Saturn Energy Storage LLC | Lancaster BESS | 2020-01-30 | 8 | 8 | ES | Erie | NY | A | Cemetery Rd - Erie St 34.5 kV | NYSEG | 0 | 2020-07-31
0989 | Saturn Energy Storage LLC | Pawling BESS | 2020-01-30 | 6 | 6 | ES | Dutchess | NY | H | Pawling-Corbin Rd 46 kV | NYSEG | 0 | 2020-07-31
0990 | Saturn Energy Storage LLC | Mohansic BESS | 2020-01-30 | 7 | 7 | ES | Westchester County | NY | H | The 13.2 kV 403 (1106340) line from Mohansic Substation running along Baldwin Rd | NYSEG | 0 | 2020-03-31
0991 | Saturn Energy Storage LLC | Bristol BESS | 2020-01-30 | 6 | 6 | ES | Ontario | NY | B | S Bristol-State Rt 28 34.5 kV | RG&E | 0 | 2020-07-31
0992 | KCE NY 25, LLC | KCE NY 25 | 2020-01-31 | 6 | 6 | ES | Ontario | NY | B | Station 146 34.5kV | RG&E | 0 | 2020-06-30
0993 | VESI 30 LLC | Empire Energy Storage | 2020-01-31 | 10 | 10 | ES | Monroe | NY | B | Station 55 - Station 73 34.5kV | RG&E | 0 | 2022-09-30
0994 | KCE NY 22, LLC | KCE NY 22 | 2020-02-12 | 90 | 90 | ES | Suffolk | NY | K | Holbrook - Sills Road 138kV | LIPA | 0 | 2024-05-31
0996 | SWEB Development USA, LLC | East Otto Solar Project | 2020-02-28 | 20 | 20 | S | Cattaraugus | NY | A | Line 803 near Snake Run Road | NM-NG | 0 | 2020-06-30
0997 | 212 Solar Development, LLC | 187 Finchville Turnpike, Mount Hope | 2020-03-05 | 20 | 20 | ES | Orange | NY | G | Cuddleback - Shoemaker 69kV | O&R | 0 | 9/30/20
0998 | 212 Solar Development, LLC | 0 Highland Lake Rd - Wallkill | 2020-03-05 | 20 | 20 | ES | Orange | NY | G | Cuddleback - Shoemaker 69kV | O&R | 0 | 2020-10-31
0999 | Suffolk BESS LLC | Suffolk BESS | 2020-03-06 | 79.7 | 79.7 | ES | Suffolk | NY | K | Port Jefferson 69 kV Substation | LIPA | 0 | 2020-09-30
1001 | Empire State Connector LLC | Empire State Connector II | 2020-03-20 | 1250 | 1250 | DC | Onondaga-NY | NY | E, J | Marcy - Rainey 345 kV | NYPA/ConEd | 0 | 2022-08-31
1002 | 212 Solar Development, LLC | 2143 Mount Hope Road | 2020-04-03 | 20 | 20 | ES | Orange | NY | G | Cuddleback - Shoemaker | O&R | 0 | 2020-10-31
1004 | Renewable Energy Aggregators, Inc. | Mifflin | 2020-04-13 | 300 | 300 | CR | Sullivan | NY | E | Coopers Corner 345 kV | NYSEG | 0 | 2024-05-31
1005 | sPower Development Company, LLC | East End Energy Storage Center | 2020-04-17 | 51.5 | 51.5 | ES | Suffolk | NY | K | Edwards Ave. 138 kV Substation | LIPA | 0 | 2020-09-30
1006 | NYC Energy | NYC Energy BNY Phase 1 | 2020-04-20 | 79.9 | 79.9 | ES | Kings | NY | J | Hudson Ave Substation | ConEd | 0 | 2020-12-31
1008 | KCE NY 26, LLC | KCE NY 26 | 2020-04-28 | 60 | 60 | ES | Suffolk | NY | K | Jamesport - Peconic 69kV | LIPA | 0 | 2024-05-31
1010 | OCS-A 0522, LLC | Vineyard Wind I | 2020-04-30 | 1403 | 1403 | W | Nassau | NY | K | East Garden City 345kV | NYPA | 0 | 2024-05-31
1011 | OCS-A 0522, LLC | Vineyard Wind II | 2020-04-30 | 1403 | 1403 | W | Suffolk | NY | K | Ruland Road 138kV | LIPA | 0 | 2024-05-31
1012 | Suffolk County Energy Storage II | Suffolk County Storage II | 2020-05-04 | 76.8 | 76.8 | ES | Suffolk | NY | K | Southold 69 kV | LIPA | 0 | 2025-01-31
1013 | Barrett Ridge Energy, LLC | Barrett Ridge Energy - PARs | 5/5/2020 | 168 | 168 | AC | Orange | NY | G | Sugarloaf 138 kV | O&R | 0 | 2023-04-30
1014 | ConnectGEN Chautauqua County LLC | South Ripley BESS | 2020-05-05 | 20 | 20 | ES | Chautauqua | NY | A | South Ripley 230kV substation | NM-NG | 0 | 5/31/21
1016 | Beacon Wind LLC | EI Steinway 1 | 2020-05-19 | 1300 | 1300 | W | Queens | NY | J | Mott Haven - Rainey 345 kV Circuits | ConEd | 0 | 2024-09-30
1017 | Beacon Wind LLC | EI Steinway 2 | 2020-05-19 | 1300 | 1300 | W | Queens | NY | J | Mott Haven - Rainey 345 kV Circuits | ConEd | 0 | 2024-09-30
1018 | Naturgy Candela DevCo LLC | Stone Mill Solar | 2020-05-21 | 20 | 20 | CR | Columbia | NY | F | Churchtown 115 kV | NYTransco | 0 | 2024-04-30
1019 | Naturgy Candela DevCo LLC | Marshville Solar | 2020-05-21 | 20 | 20 | CR | Montgomery | NY | F | Marshville 69 kV | NM-NG | 0 | 2023-10-31
1020 | Beacon Wind LLC | EI Fort Salonga | 2020-05-21 | 1300 | 1300 | W | Suffolk | NY | K | Northport 138 kV | LIPA | 0 | 2024-05-31
1021 | Beacon Wind LLC | EI East Shoreham | 2020-05-27 | 1300 | 1300 | W | Suffolk | NY | K | Shoreham 138 kV | LIPA | 0 | 2024-05-31
1022 | Beacon Wind LLC | EI Glenwood Landing | 2020-05-27 | 1300 | 1300 | W | Nassau | NY | K | Shore Road 345 kV | LIPA | 0 | 2024-05-31
1023 | KCE NY 27, LLC | KCE NY 27 | 2020-06-02 | 50 | 50 | ES | Suffolk | NY | K | Tiana - Quogue 69kV | LIPA | 0 | 2024-05-31
1024 | Renewable Energy Aggregators, Inc. | Cuomo Hydro 1 | 2020-06-03 | 300 | 300 | PS | Westchester | NY | H | Millwood 345kV Substation | ConEd | 0 | 2021-03-31
1025 | Renewable Energy Aggregators, Inc. | Cuomo Hydro 2 | 2020-06-03 | 300 | 300 | PS | Westchester | NY | I | Dunwoodie 345kV Substation | ConEd | 0 | 2021-03-31
1026 | Oriden LLC | Bonny Hill Solar | 2020-06-05 | 20 | 20 | S | Steuben | NY | C | Bath - Bath Muni 34.5 kV | NYSEG | 0 | 2020-09-30
1027 | Naturgy Candela DevCo LLC | Knickerbocker Solar | 2020-06-08 | 20 | 20 | CR | Rensselaer | NY | F | Schodack - Falls Park 115 kV Line #14 | NM-NG | 0 | 2024-05-31
1028 | Excelsior Reserve Energy | Raquette Lake Energy Storage | 2020-06-09 | 20 | 20 | ES | Hamilton | NY | E | Old Forge - Raquette Lake 46kV | NM-NG | 0 | 2022-06-30
1029 | Naturgy Candela DevCo LLC | Half Moon Solar | 2020-06-11 | 20 | 20 | CR | Rensselaer | NY | F | Valkin - Greenbush 115kV | NM-NG | 0 | 2024-05-31
1030 | Boralex US Development | NY109 Solar | 2020-06-15 | 20 | 20 | S | Fulton | NY | F | Stoner - Rotterdam 115kV | NM-NG | 0 | 2023-06-30
1032 | 212 Solar Development, LLC | 129 Round Hill Road | 2020-06-19 | 20 | 20 | ES | Orange | NY | G | Blooming Grove substation | O&R | 0 | 2020-10-31
1033 | 212 Solar Development, LLC | E Main Street, Wallkill | 2020-06-19 | 20 | 20 | ES | Ulster | NY | G | Shoemaker - E Wallkill line | O&R | 0 | 2020-10-31
1034 | 212 Solar Development, LLC | 30-35-90 Zwart Ln - Walden | 2020-06-19 | 20 | 20 | ES | Orange | NY | G | CHG&E WM Line | CHGE | 0 | 2020-08-31
1035 | Easton Solar LLC | NY08 Solar | 2020-06-22 | 20 | 20 | S | Washington | NY | F | Battenkill Substation 34.5kV | NM-NG | 0 | 2024-01-31
1036 | Juno Power Management LLC | Mainesburg ESS | 2020-06-22 | 130 | 130 | ES | Tioga | PA | C | Mainesburg - Watercure 345kV | NYSEG | 0 | 2024-10-31
1038 | ELP Rotterdam Solar LLC | ELP Rotterdam Solar | 2020-06-23 | 20 | 20 | S | Schenectady | NY | F | Rotterdam - Meco 115kV | NM-NG | 0 | 2024-03-31
1039 | Morris Solar NY LLC | Morris Solar | 2021-01-06 | 20 | 20 | S | St. Lawrence | NY | E | Battle Hill - Balmat 115kV | NM-NG | 0 | 2026-06-30
1040 | Riverline Energy Center, LLC | Riverline Energy Center | 2020-06-24 | 200 | 200 | ES | St. Lawrence | NY | E | Moses - Adirondack 230kV | NYPA | 0 | 2024-05-31
1041 | Silverline Energy Center, LLC | Silverline Energy Center | 2020-06-25 | 150 | 150 | CR | Tompkins | NY | C | Miliken - Etna 115 kV lines 974 and 975 | NYSEG | 0 | 2024-05-31
1042 | Fort Edward Solar LLC | Fort Edward Solar Farm (NY53) | 2020-06-26 | 100 | 100 | S | Washington | NY | F | Mohican - Battenkill 115kV Line #15 | NM-NG | 0 | 2024-12-31
1043 | SL Portland, LLC | SL Portland Solar | 2020-06-30 | 19.8 | 19.8 | S | Chautauqua | NY | A | Dunkirk - Falconer 115kV | NM-NG | 0 | 2022-12-31
1044 | Delaware River Solar | Broadway Road | 2020-07-01 | 19.9 | 19.9 | S | Genesee | NY | A | Attica - Darien Lake 34.5kV | NM-NG | 0 | 2020-10-31
1045 | Sunrise Wind LCC | NY Wind Holbrook 2 Uprate | 2020-07-03 | 1050 | 1050 | W | Suffolk | NY | K | Holbrook 138kV | LIPA | 0 | 2024-05-31
1046 | Island Park Energy Center, LLC | Barrett Energy Storage Center | 2020-07-06 | 200.0 | 200 | ES | Nassau | NY | K | Barrett 138 kV | LIPA | 0 | 2024-05-31
1047 | SED NY Holdings LLC | Millers Grove Solar | 2020-07-09 | 20 | 20 | S | Herkimer | NY | E | Porter - Watkins 115kV | NM-NG | 0 | 2026-08-31
1048 | Declaration Energy Center, LLC | Declaration Energy Center | 2020-07-14 | 300 | 300 | S | Seneca | NY | C | Border City 115 kV | NYSEG | 0 | 2024-05-31
1049 | Clean Energy Generation, LLC | Holbrook Energy Center | 2020-07-14 | 150 | 150 | ES | Suffolk | NY | K | Existing Holbrook (8D) 138 kV | LIPA | 0 | 2024-05-31
1050 | Clean Energy Generation, LLC | Holtsville Energy Center | 2020-07-14 | 150 | 150 | ES | Suffolk | NY | K | West Bus 138 kV | LIPA | 0 | 2024-05-31
1051 | SED NY Holding LLC | Transit Solar | 2020-07-21 | 20 | 20 | S | Genesee | NY | B | S.E Batavia - Golah 115kV | NM-NG | 0 | 2025-07-31
1052 | Capital Power Solar Holdings LLC | Madison Solar | 2020-07-22 | 20 | 20 | S | Madison | NY | E | Teal-Oneida 115kV (Line#2) | NM-NG | 0 | 2024-02-29
1053 | Hydroelectric Corporation | NY Kinetic Plant 1 | 2020-07-22 | 141.9 | 144 | H | NY | NY | J | Con Edison Gowanus Substation | ConEd | 0 | 2020-08-31
1054 | Birdie Energy Storage, LLC | Birdie Energy Storage | 2020-07-23 | 83 | 83 | ES | Westchester | NY | I | Elmsford 138 kV Substation | ConEd | 0 | 2020-09-30
1055 | SWEB Development USA LLC | Addison Solar | 2020-07-23 | 120 | 120 | S | Steuben | NY | C | Stony Ridge - Sullivan Park 115 kV | NYSEG | 0 | 2024-05-31
1056 | Bay State Wind | NY Wind - Shore Road | 2020-07-27 | 1272 | 1272 | W | Nassau | NY | K | Shore Road 138kV | LIPA | 0 | 2024-05-31
1057 | Bay State Wind | NY Wind - New Bridge Road | 2020-07-27 | 1325 | 1325 | W | Nassau | NY | K | New Bridge Road 138kV | LIPA | 0 | 2020-10-31
1058 | Bay State Wind | NY Wind - Pilgrim | 2020-07-27 | 1276 | 1276 | W | Suffolk | NY | K | Pilgrim Substation 138 kV | LIPA | 0 | 2024-05-31
1059 | ACE DEVCO NC, LLC | Jaton | 2020-07-31 | 16.2 | 16.2 | S | Oswego | NY | C | South Oswego - Clay 115 kV | NM-NG | 0 | 2024-02-29
1060 | AES DE DEVCO NC LLC | Delight Farm | 2020-07-31 | 16.8 | 16.8 | S | Cayuga | NY | C | Union Springs - Aurora 34.5 kV | NYSEG | 0 | 2022-03-31
1061 | ACE DEVCO NC, LLC | Teele | 2020-07-31 | 19.8 | 19.8 | S | St. Lawrence | NY | E | Alcoa - N. Ogdensburg 115 kV | NM-NG | 0 | 2024-12-31
1062 | AES DE DEVCO NC LLC | Hounsfield | 2020-07-31 | 19.8 | 19.8 | S | Jefferson | NY | E | West Adams - Coffeen St 115 kV | NM-NG | 0 | 2022-11-30
1063 | ACE DEVCO NC, LLC | Morrow Farms LLC | 2020-07-31 | 19.8 | 19.8 | S | Jefferson | NY | E | Thousand Island - Coffeen St 115 kV | NM-NG | 0 | 2022-09-30
1064 | AES DE DEVCO NC LLC | K. High | 7/31/2020 | 19.8 | 19.8 | S | Wayne | NY | B | Station 218 - Station 181 34.5kV | RG&E | 0 | 2023-04-30
1065 | Delaware River Solar | Hance Road | 2020-08-03 | 19.9 | 19.9 | S | Wayne | NY | B | Station 13A - Station 121 115kV | RG&E | 0 | 2020-10-31
1066 | Bay State Wind | NY Wind - Mott Haven | 2020-08-04 | 1272 | 1272 | W | Bronx | NY | J | Mott Haven 345 kV | ConEd | 0 | 2024-05-31
1067 | Viridity Energy Solutions, Inc. | Hudson Valley Storage | 2020-08-05 | 20 | 20 | ES | Ulster | NY | G | E Kingston Substation | CHGE | 0 | 2020-10-31
1068 | Juno Power Management LLC | Buchanan Point BESS | 2020-08-05 | 300 | 300 | ES | Westchester | NY | H | Buchanan North Substation 345kV | ConEd | 0 | 2024-10-31
1069 | AES DE DEVCO NC LLC | Richardson Solar | 2020-08-05 | 24 | 22 | S | St. Lawrence | NY |  | Ogdensburg - McIntyre115 kV | NM-NG | 0 | 2021-02-28
1070 | Delaware River Solar | 311 Douglas Road | 2020-08-05 | 19.9 | 19.9 | S | Tompkins | NY | C | Montour Falls-Coddington 115kV | NYSEG | 0 | 2021-02-28
1071 | Delaware River Solar | Katrina Falls | 2020-08-06 | 19.9 | 19.9 | S | Sullivan | NY | E | Coopers Corners-Rock Tavern 345kV | NYPA | 0 | 2021-02-28
1072 | Delaware River Solar | Route 318 | 2020-08-06 | 19.9 | 19.9 | S | Seneca | NY | C | Hook Road - Elbridge 115 kV | NM-NG | 0 | 2021-02-28
1073 | AES DE DEVCO NC LLC | Forrence Orchards | 2020-08-07 | 19.8 | 19.8 | S | Clinton | NY | D | Hallock Hill - Kents Falls 115kV | NYSEG | 0 | 2021-11-30
1074 | Honey Ridge Solar 1 | Honey Ridge Solar | 2020-08-11 | 80 | 80 | S | Jefferson | NY | C, E | Black River 115kV Substation | NM-NG | 0 | 2020-10-31
1075 | Moss Ridge Solar 1 | Moss Ridge Solar | 2020-08-11 | 46 | 46 | S | St. Lawrence | NY | E | Colton - Battle Hill, 115 kV | NM-NG | 0 | 2020-09-30
1076 | Minisink Valley Solar 1, LLC | Minisink Valley Solar | 2020-08-28 | 15 | 15 | S | Orange | NY | G | Shoemaker - Westtown 69kV | O&R | 0 | 2020-10-31
1077 | Rutland Center Solar 1, LLC | Rutland Center Solar | 2020-08-14 | 110 | 110 | S | Jefferson | NY | E | Middle Rd 115 kV | NM-NG | 0 | 2023-04-30
1078 | sPower Development Company, LLC | Cayuga Solar | 2020-08-18 | 207 | 207 | S | Tompkins | NY | C | Milliken 115 kV | NYSEG | 0 | 2021-01-31
1081 | KCE NY 28, LLC | KCE NY 28 | 2020-08-27 | 45 | 45 | ES | Suffolk | NY | K | Riverhead-Tuthill 69kV | LIPA | 0 | 2024-05-31
1082 | CDG Owego 2 | CDG Owego 2, LLC | 2020-08-27 | 19.6 | 19.6 | S | Tioga | NY | C | Line 513 - 34.5KV | NYSEG | 0 | 2021-02-28
1083 | Juno Power Management LLC | Tremont BESS | 2020-08-28 | 300 | 300 | ES | Bronx | NY | J | Tremont 345kV | ConEd | 0 | 2022-07-31
1084 | Juno Power Management LLC | EGC BESS | 2020-08-28 | 300 | 300 | ES | Nassau | NY | K | EGC - Carle Place line #361 and EGC - Roslyn line #362, 138kV | LIPA | 0 | 2024-05-31
1085 | Juno Power Management LLC | Oyster Shore BESS | 2020-08-28 | 500 | 500 | ES | Nassau | NY | K | Shore Road 345kV | LIPA | 0 | 2024-05-31
1086 | Juno Power Management LLC | Buchanan Point BESS II | 2020-08-28 | 500 | 500 | ES | Westchester | NY | H | Buchanan South 345 kV | ConEd | 0 | 2024-05-31
1087 | Attentive Energy LLC | Attentive Energy | 8/31/2020 | 1200 | 1200 | W | Nassau & Kings | NY | K | East Garden City Substation 345kV | NYPA | 0 | 2023-04-30
1088 | ConnectGen Cayuga County LLC | Harvest Hills Solar | 2020-09-01 | 200 | 200 | CR | Cayuga | NY | C | Wright Avenue - Milliken 115kV | NYSEG | 0 | 2024-10-31
1089 | Flat Creek Solar NY LLC | Flat Creek Solar | 2020-09-04 | 200 | 200 | S | Montgomery | NY | F | Edic to Princetown 345kV Line 352 | NYPA | 0 | 2026-06-30
1090 | SED NY Holding LLC | Westmorland Solar | 2020-09-04 | 20 | 20 | S | Oneida | NY | E | Yahnundasis - Clinton 46 kV | NM-NG | 0 | 2024-03-31
1091 | ELP Middleburgh Solar LLC | ELP Middleburgh Solar | 2020-09-08 | 20 | 20 | S | Schoharie | NY | F | Middleburgh - Cobleskill 115kV | NM-NG | 0 | 2020-12-31
1092 | SED NY Holding LLC | Hampton Corners Solar | 2020-09-04 | 20 | 20 | S | Livingston | NY | B | Station 128 - Station 7325 115 kV Line #923 | RG&E | 0 | 2024-11-30
1093 | Con Edison Transmission, Inc. | Clean Path NY | 2020-09-10 | 1300 | 1300 | DC | Oneida | NY | E,J | Marcy - Rainey 345kV | ConEd/ NYSEG | 0 | 2021-08-30
1094 | SED NY Holdings LLC | Chase Mills Solar | 2020-09-14 | 20 | 20 | S | St. Lawrence | NY | D | 115kV Line Brady to Alcoa (5.82miles from Brady, 13.9 miles from Alcoa) | NM-NG | 0 | 12/31/20
1095 | Northland Power U.S. Projects | Chautauqua Solar | 2020-09-14 | 20 | 20 | S | Chautauqua | NY | A | Line 123975 | NM-NG | 0 | 2020-10-31
1096 | Northland Power U.S. Projects | Alfred Oaks Solar | 2020-09-14 | 100 | 100 | CR | Allegany | NY | C | Andover - Palmeter 115 kV, Line 932 | NYSEG | 0 | 2025-01-31
1097 | Juno Power Management LLC | Hicksville Storage | 2020-09-16 | 125 | 125 | ES | Nassau | NY | K | Newbridge Road 138kV | LIPA | 0 | 2021-03-31
1098 | SED NY Holdings LLC | Kingbird Solar | 2020-09-16 | 20 | 20 | S | Chatauqua | NY | A | Dunkirk - Silver Creek 115 kV (Line#142) | NM-NG | 0 | 2024-09-30
1099 | Brownfield Group, LLC | Canal Solar | 2020-09-17 | 20 | 20 | S | Madison | NY | E | Bouckville Substation 46kV | NYSEG | 0 | 2020-10-31
1100 | Granada Solar, LLC | Hosmer Solar, LLC | 2020-09-28 | 20 | 20 | S | Rensselaer | NY | F | Schodack - Falls Park 115 kV | NYTransco | 0 | 2024-06-30
1101 | Saturn Energy Storage LLC | Chestertown BESS | 2020-10-01 | 20 | 20 | ES | Warren | NY | F | Chestertown-Warrensburg #6 | NM-NG | 0 | 2021-04-30
1102 | SWEB Development USA | Troupsburg Solar | 2020-10-05 | 20 | 20 | Solar | Steuben | NY | C | Woodhull 34.5 kV | NYSEG | 0 | 2024-04-30
1103 | Cypress Creek Renewables, LLC | Thousand Island Solar | 2020-10-06 | 110 | 110 | S | Jefferson | NY | E | Coffeen Street - Thousand Island 115 KV | NM-NG | 0 | 2024-09-30
1104 | Saturn Energy Storage LLC | Brockport BESS | 2020-10-07 | 20 | 20 | ES | Monroe | NY | A | Brockport - Albion 34.5 kV Line #308 | NM-NG | 0 | 2023-02-28
1106 | Northland Power U.S. Projects | Allegany 2 Battery | 2020-10-16 | 10 | 10 | ES | Allegany | NY | C | Andover - Palmeter 115 kV line | NYSEG/NM-NG | 0 | 2021-02-28
1107 | Juno Power Management LLC | Buchanan Point BESS III | 2020-10-19 | 300 | 300 | ES | Westchester | NY | H | Buchanan 345kV | ConEd | 0 | 4/30/22
1108 | SWEB Development USA, LLC | Bangor Solar | 2020-10-26 | 106.9 | 106.9 | S | Franklin | NY | D | Malone - Nicholville 115kV | NYSEG, NM-NG | 0 | 2024-05-31
1109 | SWEB Development USA, LLC | Worth Wind | 2020-10-27 | 92 | 92 | W | Jefferson | NY | E | E. Watertown - Lighthouse Hill 115kV | NM-NG | 0 | 2024-05-31
1110 | Saturn Energy Storage LLC | Hurley BESS | 2020-10-27 | 20 | 20 | ES | Ulster | NY | G | Hurley Ave Substation, 69 kV | CHGE | 0 | 12/31/20
1111 | Saturn Energy Storage LLC | Kingston BESS | 2020-10-30 | 20 | 20 | ES | Ulster | NY | G | Boulevard Substation 69kV | CHGE | 0 | 12/31/20
1112 | Caithness LI Energy Storage, LLC | CLIES 10MW | 2020-11-18 | 10 | 10 | ES | Suffolk | NY | K | Sills Road 138kV | LIPA | 0 | 10/31/22
1114 | Clean Energy Generation, LLC | Wading River Energy Center | 2020-11-19 | 50 | 50 | ES | Suffolk | NY | K | Wading River 138 kV | LIPA | 0 | 2024-05-31
1115 | Flat Creek Solar NY LLC | Flat Creek Solar | 2020-11-23 | 100 | 100 | S | Montgomery | NY | F | Edic - Princetown 345 kV Line# 352 | NYPA | 0 | 2026-06-30
1116 | Liberty Renewables Inc. | Blue Hill Wind | 2020-11-24 | 25.4 | 27.0 | W | Madison | NY | E | Morrisville 46 kV | NYSEG | 0 | 2024-07-31
1118 | BWBP Origination, LLC | Lyonsdale Marmon Rd | 2020-12-04 | 19 | 19 | S | Lewis | NY | E | Lyonsdale Substation | NM-NG | 0 | 2021-03-31
1119 | Granada Solar, LLC | Fuller Storage | 2020-12-04 | 20 | 20 | ES | Orange | NY | G | East Walden 115kV | CHG&E | 0 | 2024-06-30
1120 | Ravenswood Development, LLC | Catskills Renewable Connector | 2020-12-11 | 1200 | 1200 | DC | Greene/Queens | NY | F, J | New Scotland-Leeds 345kV, Rainey-Farragut | NGrid/ConEd | 0 | 2022-06-30
1121 | Ravenswood Development, LLC | Werner - Ravenswood | 2020-12-11 | 1200 | 1200 | DC | PJM/Queens | NY | J | Rainey - Farragut 345kV | ConEd | 0 | 2022-06-30
1124 | Liberty Renewables | Smokey Ave Wind | 2020-12-22 | 18 | 18 | W | Otsego | NY |  | Worcester - Schenevus 23 kV |  | 0 | 2021-05-31
1126 | ACE DEVCO NC, LLC | Richardson | 2021-01-04 | 19.8 | 19.8 | S | St. Lawrence | NY | E | N. Ogdensburg - McIntyre 115 kV line | NM-NG | 0 | 2023-11-30
1127 | CBB PARK LLC | CBB PARK | 2021-01-20 | 50 | 50 | ES | Dutchess | NY | G | Pleasant Valley 115 kV | CHGE | 0 | 2021-07-31
1128 | Northland Power U.S. Projects | Allegany 2 Battery 2 | 2021-01-21 | 20 | 20 | ES | Allegany | NY | C | Andover-Palmeter 115 kV Line 101990 | NYSEG | 0 | 2023-01-31
1129 | Boundless Energy NY, LLC | Phoenix | 2021-01-21 | 2000 | 2000 | DC | Oneida-Manhattan & Bronx | NY | E, J | Edic & Marcy - W. 49 St & Farragut | NM-NG, NYPA, ConEd | 0 | 2021-07-31
1131 | Avangrid Networks, Inc. | Excelsior Connect - Edic to Rainey | 2021-01-28 | 1310 | 1310 | DC | Oneida-Queens | NY | E, J | Edic - Rainey 345kV | NM-NG, ConEd | 0 | 5/31/22
1132 | Avangrid Networks, Inc. | Excelsior Connect - Edic to Farragut | 2021-01-28 | 1310 | 1310 | DC | Oneida-Brooklyn | NY | E, J | Edic - Farragut 345kV | NM-NG, ConEd | 0 | 2022-03-31
1133 | EDF Renewables Development, Inc. | Moraine Storage | 2021-02-11 | 5 | 5 | ES | Allegany | NY | C | Moraine Road Substation 115 kV | NYSEG | 0 | 2024-01-31
1134 | EDF Renewables Development | Tracy Storage | 2021-02-11 | 5 | 5 | ES | Jefferson | NY | E | Thousand Island - Coffeen 115 kV Line #4 | NM-NG | 0 | 2024-01-31
1135 | EDF Renewables Development, Inc. | Homer Storage | 2021-02-11 | 5 | 5 | ES | Cortland | NY | C | Cortland - Fenner 115kV | NM-NG | 0 | 2023-09-30
1136 | Honey Ridge Solar 1, LLC | Honey Ridge Solar | 2021-02-15 | 125 | 125 | CR | Jefferson | NY | E | Black River 115 kV | NM-NG | 0 | 2024-09-30
1137 | Invenergy Wind Development North America LLC | Salt Rush Wind | 2021-02-16 | 75 | 75 | W | Wyoming | NY | C | Stony Creek 230kV | NYSEG | 0 | 2024-07-31
1138 | Invenergy Solar Project Development LLC | Wintergreen Solar | 2021-02-16 | 75 | 75 | S | Montgomery | NY | F | Marshville 115kV | NM-NG | 0 | 2024-05-31
1139 | Invenergy Solar Project Development LLC | Seventy-Seven Solar | 2021-02-16 | 100 | 100 | S | Wyoming | NY | C | High Sheldon 230kV | NYSEG | 0 | 2024-05-31
1140 | Invenergy Solar Project Development LLC | Taproot Solar | 2021-02-16 | 205 | 205 | S | Montgomery | NY | F | Edic - Princetown 345kV Line# 352 | LS Power/NYPA | 0 | 2024-05-31
1141 | Invenergy Solar Project Development LLC | Twinleaf Solar | 2021-02-16 | 75 | 75 | S | Lewis | NY | E | Coffeen St-Taylorville 115kV | NM-NG | 0 | 2024-06-30
1142 | Minerva Power Connection LLC | Minerva BESS I | 2021-02-16 | 300 | 300 | ES | Manhattan | NY | J | W49th St 345kV | ConEd | 0 | 2024-05-31
1143 | Minerva Power Connection LLC | Minerva BESS II | 2021-02-16 | 600 | 600 | ES | Manhattan | NY | J | W 49th st 345kV | ConEd | 0 | 6/30/21
1144 | Boundless Energy NY, LLC | HG-Phoenix | 2021-02-18 | 2000 | 2000 | DC | Erie, Onondaga,NY, KIngs | NY | A,E,J | Gardenville and Edic/Marcy - W49th St & Farragut | NM-NG/NYPA/ NYSEG/ConEd | 0 | 2021-12-31
1145 | EDF Renewables Development, Inc. | Oceanside Energy Storage | 2021-02-18 | 36 | 36 | ES | Nassau | NY | K | Barrett 138 kV | LIPA | 0 | 2022-10-31
1146 | RWE Clean Energy Development, LLC | Champlain Solar | 2021-02-19 | 100 | 100 | S | Washington | NY | F | Mohican - Whitehall 115 kV Line #13 | NM-NG | 0 | 2024-07-31
1147 | Wawayanda Solar 1, LLC | Wawayanda Solar | 2021-02-26 | 12.6 | 12.6 | S | Orange | NY | G | Westtown to Shoemaker 69 kV Line #11 | O&R | 0 | 2023-10-31
1149 | Con Edison Transmission, Inc. | Clean Path NY II | 2021-03-12 |  |  |  | Delaware/Queens | NY | E, J | Fraser 345kv and Mott Haven 345 kv | NYSEG/ ConEd | 0 | 2021-08-30
1150 | Moss Ridge Solar 1, LLC | Moss Ridge Solar | 2021-03-16 | 60 | 60 | S | St. Lawrence | NY | E | Corning - Battle Hill 115 kV line #4 | NM-NG | 0 | 2025-01-31
1152 | BWC Rexmere Lakes, LLC | Harpersfield Bruce Hill Rd. | 2021-03-18 | 19.9 | 19.9 | S | Delaware | NY | E | Axtell Rd. Substation | NYSEG | 0 | 2021-08-30
1153 | Wood Street Battery Storage LLC | Wood Street Battery Storage | 2021-03-22 | 110 | 110 | ES | Putnam | NY | H | Wood Street 115kV | NYSEG | 0 | 2023-02-28
1154 | OYA Solar CDG LLC | OYA Fort Plain Solar | 2021-03-29 | 115 | 115 | S | Montgomery | NY | F | Clinton Road substation 115 kV | NM-NG | 0 | 2021-07-31
1155 | CHPE LLC | New Scotland Interconnection | 2021-04-02 | 500 | 500 | DC | Albany | NY | F, J | New Scotland Substation | NYPA/ NM-NG | 0 | 4/30/22
1156 | Green Power Energy, LLC | Cody Road Wind Farm | 2021-04-08 | 19.9 | 19.9 | W | Madison | NY | C | Cortland - Fenner Line #3 115 kV | NM-NG | 0 | 1/31/25
1157 | Minerva Power Connection LLC | Minerva Transmission | 2021-04-09 | 1200 | 1200 | DC | Manhattan | NY | J | W 49th St 345kV | ConEd | 0 | 10/31/21
1158 | Tyre Solar Energy Center | Gravel Road Solar | 2021-04-09 | 125.6 | 125 | S | Seneca | NY | C | Elbridge - Hook Rd 115kV | NM-NG/ NYSEG | 0 | 2022-01-31
1159 | Innisfree Storage LLC | Innisfree Storage | 2021-04-14 | 50 | 52.5 | ES | Suffolk | NY | K | Port Jefferson - Mt. Sinai 69 kV | LIPA | 0 | 2024-09-30
1160 | Arcade Solar, LLC | Arcade Solar | 2021-04-16 | 75 | 75 | S | Wyoming | NY | A | Village of Arcade Freedom 115 kV Substation | Village of Arcade | 0 | 2023-12-31
1161 | Garnet Energy Center, LLC, | Garnett Battery Storage | 2021-04-20 | 20 | 20 | ES | Cayuga | NY | B | Pannel - Clay 345 KV | NYPA | 0 | 2022-07-31
1162 | Ontario Valley Solar 1, LLC | Ontario Valley Solar | 4/26/2021 | 135 | 135 | CR | Jefferson | NY | E | Lyme Tap line off the Thousand Island – Coffeen 115 kV Line #4 | NM-NG | 0 | 2023-03-31
1163 | QMB2 Energy Storage, LLC | QMB2 Energy Storage, LLC | 2021-04-27 | 200 | 200 | ES | Queens | NY | J | Jamaica - Valley Stream 138kV | ConEd | 0 | 2024-05-31
1164 | Juno Power Management LLC | Glenwood BESS | 2021-05-05 | 75 | 75 | ES | Nassau | NY | K | Glenwood 4ZH 69kV | LIPA | 0 | 2024-07-31
1165 | West River Solar | West River Solar | 2021-05-07 | 20 | 20 | S | Saratoga | NY | F | Battenkill to Mohican 115kV line#15 | NM-NG | 0 | 2023-06-30
1167 | Clean Path NY LLC | CPNY | 2021-05-11 | 1300 | 1300 | DC | Delaware Queens | NY | E,J | Fraser 345kV sending Rainey 345kV receiving | NYSEG, ConEd | 0 | 2023-05-31
1168 | Invenergy Transmission LLC | CPNY-MH | 2021-05-11 | 1300 | 1300 | DC | Delaware, Bronx | NY | E, J | Fraser - Mott Haven 345kV | NYSEG/ ConEd | 0 | 12/31/21
1169 | Excelsior Energy Center, LLC | Excelsior Battery Storage | 2021-05-11 | 20 | 20 | ES | Genesee | NY | B | Byron 345 kV substation | NYPA | 0 | 2024-04-30
1170 | Tier Four Connector, LLC | Bowline to West 49th Street | 2021-05-12 | 1228 | 1228 | AC | Rockland/NY | NY | G, J | Bowline - West 49th St 345 kV | O&R/ConEd | 0 | 2022-01-31
1171 | ELP Stuyvesant Solar LLC | ELP Stuyvesant Solar | 2021-05-14 | 20 | 20 | S | Columbia | NY | F | Valkin - Falls Park 115 kV line #19 | Transco | 0 | 2024-01-31
1172 | Northland Power US Projects | Cowens Corners Solar | 2021-05-17 | 20 | 20 | CR | Cattaraugus | NY | A | Ellington - Randolph 34.5 kV | NYSEG | 0 | 2021-08-30
1173 | Northland Power US Projects | Christmiller Solar | 2021-05-17 | 20 | 20 | CR | Cattaraugus | NY | A | Dake Hill – Machias 34.5kV | NM-NG | 0 | 12/31/22
1174 | Boralex US Development | NY48 - Diamond Solar | 2021-05-17 | 60 | 60 | S | Herkimer | NY | E | Porter - Valley 115kV | NM-NG | 0 | 2024-12-31
1175 | OW Ocean Winds East, LLC | OW Ocean Winds East 1 | 2021-05-18 | 1200 | 1200 | W | Nassau | NY | K | Ruland Rd 138 kV | LIPA | 0 | 2024-07-31
1176 | OW Ocean Winds East, LLC | OW Ocean Winds East 2 | 2021-05-18 | 1200 | 1200 | W | Nassau | NY | K | Valley Stream 138 kV | LIPA | 0 | 2024-07-31
1177 | Southern Tier Energy Center, LLC | Southern Tier Energy Center | 2022-08-16 | 200 | 200 | ES | Tioga | NY | C | Oakdale to Watercure 345 kV L31 line | NYSEG | 0 | 2024-05-31
1178 | Newport Deerfield Solar LLC | NY115 - Newport Solar | 2021-05-19 | 130 | 130 | S | Oneida | NY | E | Porter - Deerfield 115 kV (Line#9) | NM-NG | 0 | 2024-12-31
1179 | Boralex US Development, LLC | NY38 B Solar | 2021-05-19 | 20 | 20 | S | Jefferson | NY | E | Coffeen - West Adams 115 kV | NM-NG | 0 | 2021-08-31
1180 | Union Energy Center, LLC | Union Energy Center, LLC | 2021-05-20 | 116 | 116 | ES | Putnam | NY | H | Union Valley - Croton Falls 115 kV line #991 | NYSEG | 0 | 2024-12-31
1181 | Northline Energy Center, LLC | Northline Energy Center | 2021-05-20 | 200 | 200 | ES | Clinton | NY | D | Pathnode-Duley 230 kV line | NYPA | 0 | 2024-05-31
1182 | Foothills Solar LLC | NY128 - Foothills Solar | 2021-05-20 | 40 | 40 | S | Fulton | NY | F | Mayfeild-Northville 69kV #8 | NM-NG | 0 | 2024-12-31
1185 | Empire Offshore Wind LLC | EI Empire ESS I | 2021-05-21 | 96 | 96 | ES | Nassau | NY | K | Barrett 138 kV Substation | LIPA | 0 | 2023-09-30
1186 | Empire Offshore Wind LLC | EI Empire ESS II | 2021-05-21 | 1440 | 1440 | CW | Nassau | NY | K | Barrett 138 kV Substation | LIPA | 0 | 6/30/21
1187 | Northland Power US Projects | Balcom Corners | 2021-05-27 | 20 | 20 | CR | Chautauqua | NY | A | Ellington - Frog Valley 34.5 kV | NYSEG | 0 | 2021-09-30
1189 | OW Ocean Winds East, LLC | OW Ocean Winds East 3 | 2021-05-27 | 1600 | 1600 | W | Nassau | NY | K | East Garden City 345 kV | NYPA | 0 | 2024-07-31
1190 | Bluepoint Wind, LLC. | OW Ocean Winds East 4 | 2021-05-28 | 1600 | 1600 | W | Brooklyn | NY | J | Brooklyn Clean Energy Hub 345 kV | ConEd | 0 | 2024-07-31
1191 | Northland Power U.S. Projects | Gunns Corners Solar | 2021-05-31 | 100 | 100 | CR | Jefferson | NY | E | Thousand Islands - Coffeen St. #4 115kV | NM-NG | 0 | 2024-05-31
1192 | OW Ocean Winds East, LLC | OW Ocean Winds East 6 | 2021-06-02 | 1600 | 1600 | W | Manhattan | NY | J | West 49th Street 345 kV | ConEd | 0 | 2024-05-31
1193 | OW Ocean Winds East, LLC | OW Ocean Winds East 5 | 2021-06-02 | 1600 | 1600 | W | Queens | NY | J | Rainey 345 kV | ConEd | 0 | 2024-05-31
1194 | Crane Brook Solar Project | Crane Brook Solar Project, LLC | 2021-06-03 | 130 | 130 | S | Cayuga | NY | C | State St - Clinton Corn 115kV Line | NM-NG | 0 | 2025-01-31
1195 | Dexter Solar, LLC | Dexter Solar | 2021-06-04 | 19.8 | 19.8 | S | Jefferson | NY | E | Dexter 23 kV Substation | NM-NG | 0 | 2021-07-31
1196 | Chelsea Road Energy Storage 1, LLC | Chelsea Energy Storage | 2021-06-07 | 30.4 | 30.4 | ES | Richmond | NY | J | Goethals Substation | ConEd | 0 | 2021-08-31
1197 | Northland Power U.S. Projects | Cold Creek Solar | 2021-06-08 | 120 | 120 | CR | Allegany | NY | B | Sta 162 to Sta 180 115 kV Line #907 | RG&E | 0 | 2023-11-30
1198 | Granada Solar, LLC | Stern Solar | 2021-06-09 | 20 | 20 | S | Renssalear | NY | F | Battenkill - Schaghticoke 115kV | NM-NG | 0 | 2024-11-30
1199 | Beacon Wind LLC | EI Steinway 1.1 | 2021-06-09 | 200 | 200 | W | Queens | NY | J | Mott Haven - Rainey 345 kV Circuits | ConEd | 0 | 2024-09-30
1200 | Beacon Wind LLC | EI Steinway 2.1 | 2021-06-09 | 300 | 300 | W | Queens | NY | J | Astoria East 138 kV | ConEd | 0 | 2024-05-31
1201 | PetaWatt Holdings, Inc. | St Lawrence Data and Agricultural Center | 2021-06-10 | 200 | 200 |  | St. Lawrence | NY | D | Dennison 115kV substation | NM-NG | 0 | 2021-08-31
1202 | Calpine Mid-Atlantic Development, LLC | Bethpage Large Battery Energy Storage Project | 2021-06-11 | 24 | 24 | ES | Nassau | NY | K | Grumman 69kV substation | LIPA | 0 | 2024-09-30
1203 | EDF Renewables Development, Inc. | Suffragette Solar Energy Center | 2021-06-14 | 50 | 50 | S | Seneca | NY | C | Hyatt Substation 34.5kV | NYSEG | 0 | 2024-05-31
1204 | Morrow Street Storage 2, LLC | Morrow Street Energy Storage | 2021-06-15 | 38 | 38 | ES | Richmond | NY | J | Goethals Substation | ConEd | 0 | 2021-08-31
1205 | Rocksdrift Energy Center, LLC | Rocksdrift Energy Center | 2021-06-16 | 300 | 300 | S | Herkimer | NY | E | Edic - Princetown 345kV Line 352 | NYPA | 0 | 2023-11-30
1206 | NY Interconnection LLC | NY Interconnection 2 | 2021-06-18 | 1200 | 1200 | W | Queens | NY | J | Rainey-Farragut 345kV line break of lines 61, 62 and 63 | ConEd | 0 | 2024-07-31
1207 | NY Interconnection LLC | NY Interconnection 1 | 2021-06-18 | 1200 | 1200 | DC | NY | NY | J | East 13th Street-Farragut 345 kV line 45 and line 46 | ConEd | 0 | 2024-05-31
1208 | Bluepoint Grid, LLC | Bluepoint Grid | 2021-06-20 | 20 | 20 | ES | Suffolk | NY | K | W. Yaphank - Holtsville 69kV | LIPA | 0 | 2021-11-30
1209 | Equinor Wind US LLC | Battoria | 2021-06-21 | 300 | 300 | ES | Queens | NY | J | Astoria East 138 kV | ConEd | 0 | 2022-03-31
1210 | Northland Power U.S. Projects | Gunns Corners Solar 2 | 2021-06-22 | 40 | 40 | CR | Jefferson | NY | E | Thousand Islands - Coffeen St. #4 115kV | NM-NG | 0 | 2024-05-31
1211 | Emeren US, LLC | Hardscrabble Solar LLC | 2021-06-25 | 19.9 | 19.9 | CR | Clinton | NY | D | Highfalls - Kents Falls 46 kV line L871 | NYSEG | 0 | 2023-05-31
1212 | EMEREN US, LLC | Roosevelt Solar LLC | 2021-06-25 | 19.9 | 19.9 | CR | St. Lawrence | NY | D | Akwesasne Station 825 Substation 34.5kV | NM-NG | 0 | 2024-12-31
1214 | Nexus Renewables U.S. Inc. | Ancram Solar Farm | 2021-06-30 | 20 | 20 | CR | Columbia | NY | G | Pulvers Corners 34.5kV | CHGE | 0 | 2021-08-31
1215 | Renesola Power Holdings LLC | Blank Hill Solar LLC | 2021-07-05 | 19.9 | 19.9 | CR | Livingston | CT | C | Moraine Road 115kV | NYSEG | 0 | 2021-09-30
1216 | ReneSola Power Holdings LLC | Cronk Solar LLC | 2021-07-08 | 19.9 | 19.9 | CR | Schuyler | NY | C | Bath - Montour Falls 115 kV | NYSEG | 0 | 2021-09-30
1217 | Emeren US, LLC | New Boston Solar LLC | 7/9/2021 | 49.9 | 49.9 | CR | Madison | NY | C | Line tap between Teal to Oneida 115 kV Substations (Line #2) | NM-NG | 0 | 2023-04-30
1218 | Farm East LLC | Locke Solar Farm | 2021-07-12 | 19.8 | 19.8 | S | Cayuga | NY | C | NYS-Locke 718 Substation | NYSEG | 0 | 2021-10-31
1219 | Nexamp Solar | 74972 Cicero | 7/26/2021 | 20 | 20 | S | Oneida | NY | C | Clay-Teall Line No.10, 115 kV line | NM-NG | 0 | 2023-03-31
1220 | Fresh Air Energy II | Lincoln ESC | 2021-07-26 | 100 | 100 | ES | Suffolk | NY | K | Holbrook - Saxville 69kV | LIPA | 0 | 2021-11-30
1221 | Anbaric Development Partners, LLC | Long Island Storage Center I | 2021-07-26 | 50 | 50 | ES | Suffolk | NY | K | Brookhaven - 8ER 138 kV | LIPA | 0 | 2023-10-31
1222 | Anbaric Development Partners, LLC | Long Island Storage Center II | 2021-07-26 | 100 | 100 | ES | Suffolk | NY | K | Brookhaven - 8ER 138 kV | LIPA | 0 | 2023-10-31
1223 | Fresh Air Energy II | Moffitt ESC | 2021-07-28 | 100 | 100 | ES | Suffolk | NY | K | Watson to Brightwaters 69kV | LIPA | 0 | 2024-05-31
1224 | Northland Power U.S. Projects | Sunwine Solar | 2021-07-28 | 50 | 50 | CR | Westfield | NY |  | Westfield Electric 115kV |  | 0 | 2021-10-31
1225 | Nexamp Solar | 26338 Westmoreland | 2021-07-29 | 20 | 20 | S | Oneida | NY |  | Oneida - Walesville 115kV | NM-NG | 0 | 2021-09-30
1226 | Nexamp Solar | 47763 Cayuta | 2021-08-04 | 20 | 20 | S | Schuyler | NY | C | Cayuta - Ridge Road 34.5kV Line #501 | NYSEG | 0 | 2024-09-30
1227 | Nexamp Solar | 18405 Scotch Ridge | 2021-08-04 | 20 | 20 | S | Schenectady | NY | F | Rotterdam-Schoharie 69kV line#18 | NM-NG | 0 | 2024-03-31
1228 | SWEB Development USA, LLC | Cuba Wind Project | 2021-08-12 | 86.5 | 86.5 | W | Alleghany | NY | A | Homer Hill - Andover 115 kV Line #157 | NM-NG | 0 | 2024-05-31
1229 | Stonewall Solar, LLC | Stonewall Solar, LLC. | 2021-08-16 | 145 | 145 | S | Delaware | NY | E | Colliers-Delhi 115KV | NYSEG | 0 | 2024-07-31
1231 | ConnectGen Montgomery County LLC | Mill Point Solar II | 2021-08-17 | 100 | 100 | CR | Montgomery | NY | E | New Scotland-Marcy 345kV | NM-NG | 0 | 2024-01-31
1232 | ConnectGen Cayuga County LLC | Harvest Hills Solar II | 2021-08-19 | 50 | 50 | S | Cayuga | NY | C | Wright Avenue - Cayuga 115kV | NYSEG | 0 | 2021-10-31
1233 | ACE Development Company | Maplewood Energy Storage | 2021-08-20 | 250 | 250 | ES | Albany | NY | F | Maplewood - Menands 115kV Line #19 & Maplewood - Reynolds 115kV Line #31 | NM-NG | 0 | 2023-10-31
1234 | ACE Development Company | Horseblock Energy Storage | 2021-08-20 | 100 | 100 | ES | Suffolk | NY | K | West Yaphank 69 kV Substation | LIPA | 0 | 2024-07-31
1235 | ACE Development Company | Peconic Energy Storage | 2021-08-20 | 100 | 100 | ES | Suffolk | NY | K | Holbrook - West Yaphank 69 kV | LIPA | 0 | 2022-12-31
1236 | Gravel Road Solar, LLC | Gravel Road Solar | 2021-08-23 | 128 | 128 | S | Seneca | NY | C | Station 127 (Hook Rd) -Elbridge and Mortimer-Elbridge 115 kV lines | NM-NG | 0 | 2024-12-31
1238 | ConnectGen Cayuga County LLC | Harvest Hills Solar 2 | 2021-08-25 | 100 | 100 | CR | Cayuga County | NY | C | Wright Avenue - Milliken 115kV line | NYSEG | 0 | 2024-07-31
1239 | NY Interconnection LLC | NY Interconnection 3 | 2021-09-02 | 130.3 | 122 | ES | NY | NY | J | Goethals - Fresh Kills 345kV | ConEd | 0 | 2024-05-31
1240 | Astoria Generating Company, L.P. | Gowanus Bay Energy Storage 1 | 2021-09-03 | 100 | 100 | ES | Kings | NY | J | Gowanus 138 kV substation (utilizing the existing feeder 42421) | ConEd | 0 | 2024-05-31
1241 | Astoria Generating Company, L.P. | Gowanus Bay Energy Storage 2 | 2021-09-03 | 49.2 | 49.2 | ES | Kings | NY | J | Feeder 42424 (Existing POI at Gowanus 138 kV) | ConEd | 0 | 2024-05-31
1242 | Light & Power Development, LLC | Ravenswood Energy Storage 3 | 2021-09-03 | 70 | 70 | ES | Queens | NY | J | Vernon 138kV | ConEd | 0 | 2021-11-30
1243 | Astoria Generating Company, L.P. | Whale Square Energy Storage 2 | 2021-09-03 | 95.7 | 95.7 | ES | Kings | NY | J | Greenwood 138kV substation, via Feeder 23162 | ConEd | 0 | 2024-05-31
1244 | Astoria Generating Company, L.P. | Whale Square Energy Storage 3 | 2021-09-03 | 49.2 | 49.2 | ES | Kings | NY | J | Greenwood 138 kV substation, via Feeder 23161 | ConEd | 0 | 2024-05-31
1246 | Hanwha Q CELLS USA | Amber Solar and Storage | 2021-09-14 | 232 | 232 | CR | St. Lawrence County | NY | D | Moses - Massena MMS 1 230kV | NYPA | 0 | 2023-02-28
1247 | Hanwha Q CELLS USA | Emerald Solar and Storage | 2021-09-14 | 174 | 174 | S | Genesee | NY | B | Lapp - East Batavia 115 kV | NM-NG | 0 | 2022-08-31
1248 | Hanwha Q CELLS USA | Garnet Solar and Storage | 2021-09-14 | 174 | 174 | S | Orleans | NY | B | Sour Springs 115 kV | NM-NG | 0 | 2022-03-31
1249 | Hanwha Q CELLS USA | Ruby Storage Project | 2021-09-14 | 115 | 115 | ES | Ontario | NY | C | Station 168 - Trelina Solar 115kV | NM-NG | 0 | 2024-05-31
1250 | Hanwha Q CELLS USA | Sapphire Solar and Storage | 2021-09-14 | 200 | 200 | CR | Wyoming | NY | C | South Perry - Meyer 230 kV | NYSEG | 0 | 2024-05-31
1251 | Hanwha Q CELLS USA | Topaz Storage Project | 2021-09-14 | 200 | 200 | ES | Rensselaer | NY | F | Knickerbocker 345 kV | Transco | 0 | 2023-05-31
1252 | Alliance Energy Storage, LLC | Hillburn Energy Storage | 2021-09-15 | 10 | 10 | ES | Rockland | NY | G | Hillburn | O&R | 0 | 2021-11-30
1253 | Alliance Energy Storage, LLC | Shoemaker Energy Storage | 2021-09-15 | 5.5 | 5.5 | ES | Orange | NY | G | Shoemaker | O&R | 0 | 2021-11-30
1254 | Barrett Hempstead Battery Storage | Barrett Hempstead Battery Storage | 2021-09-22 | 40 | 40 | ES | Nassau | NY | K | Barrett to Long Beach 33 kV circuit No 1(33-224) | LIPA | 0 | 2025-12-31
1256 | Canal Southampton Battery Storage | Canal Southampton Battery Storage | 2021-09-22 | 100 | 100 | ES | Suffolk | NY | K | Canal Substation 138kV | LIPA | 0 | 2025-01-31
1258 | Oriden LLC | Deerpark Energy Storage | 2021-09-22 | 50 | 50 | ES | Orange | NY | G | Deerpark 69 kV | O&R | 0 | 2022-02-28
1259 | Oriden LLC | Middletown Energy Storage | 2021-09-22 | 50 | 50 | ES | Orange | NY | G | Shoemaker 69 kV | O&R | 0 | 2021-11-30
1260 | BW Solar Holding | St. Regis River | 2021-09-23 | 85 | 85 | CR | St. Lawrence | NY | E | Dennison - Colton 115kV line #4 | NM-NG | 0 | 2024-05-31
1261 | Empire Offshore Wind LLC | EI Sunset Park 2 | 2021-09-24 | 48 | 48 | W | Kings | NY | J | Gowanus 345 kV | ConEd | 0 | 2023-02-28
1262 | East Coast Power LLC | Brunswick Energy Storage | 2021-09-24 | 150 | 165 | ES | Union | NJ | J | Goethals 345kV | ConEd | 0 | 2022-01-31
1263 | Ravenswood Energy Storage 4 | Ravenswood Energy Storage 4 | 2021-09-27 | 12 | 12 | ES | Queens | NY | J | Vernon 138kV | ConEd | 0 | 2021-11-30
1264 | ELP Claverack Solar II LLC | ELP Claverack Solar II LLC | 2021-09-27 | 20 | 20 | CR | Columbia | NY | F | Hudson - Churchtown 115kV | NYTransco/ NM-NG | 0 | 2022-01-31
1265 | Liberty Renewables Inc. | Monticello Hills Wind | 2021-09-28 | 31.5 | 31.5 | W | Otsego | NY | E | West Winfield - Richfield Springs 46 kV Line #812 | NYSEG | 0 | 2024-11-30
1266 | Microgrid Networks, LLC | Rust Street 21.8MW ESS | 2021-09-28 | 21.8 | 22.8 | ES | Queens | NY | J | Glendale 27kV | ConEd | 0 | 2021-11-30
1267 | Microgrid Networks, LLC | Rust Street 20 MW ESS Project | 2021-09-28 | 20 | 20 | ES | Queens | NY | J | Glendale 27kV | ConEd | 0 | 2021-11-30
1268 | Microgrid Networks, LLC | 1st Avenue 20 MW ESS Project | 2021-09-28 | 20 | 20 | ES | Kings | NY | J |  | ConEd | 0 | 2021-11-30
1269 | 174 Power Global Properties, LLC | The Bruckner | 2021-09-28 | 11.6 | 11.6 | ES | Bronx | NY | J |  | ConEd | 0 | 2021-11-30
1270 | Microgrid Networks, LLC | Hinsdale 21.8MW Bulk Storage Project | 2021-09-29 | 21.8 | 21.8 | ES | Kings | NY | J | Brownsville 27kV | ConEd | 0 | 2021-11-30
1271 | LS Power Grid NY Corporation I | Atlantic Gateway | 2021-10-07 |  |  | AC | Nassau,Suffolk,Westchester | NY | H; K | Barrett 138 kV, Ruland Road 138 kV, Millwood ? Buchanan 345 kV lines(W97/W98), Millwood ? Pleasant Valley 345 kV lines (W80/W81) | ConEd, LIPA | 0 | 2023-06-30
1272 | Equinor Wind US LLC | EI Sunset BESS | 2021-10-08 | 100 | 100 | ES | Kings | NY | J | Greenwood South 138 kV | ConEd | 0 | 2023-07-31
1273 | Anbaric Development Partners,LLC | Downstate Clean Powerlink | 2021-10-08 |  |  | AC | Nassau, Suffolk, Bronx, Westchester | NY | I,J,K | Mott Haven, Sprainbrook, Dunwoodie, Ruland Road, Newbridge, East Garden City, Syosset, Shore Road | ConEd, LIPA | 0 | 2023-11-30
1274 | NY Power Authority / NY Transco LLC. | Propel NY Energy ? Base Solution 2 | 2021-10-08 |  |  | AC | Nassau, Queens, Bronx, Westchester | NY | I; J; K | Sprain Brook 345 kV; Tremont 345 kV; Barrett138 kV; Shore Road 138 kV; Syosset 138 kV; Ruland Rd 138 kV | ConEd, LIPA | 0 | 2023-07-31
1275 | NY Power Authority / NY Transco LLC. | Propel NY Energy ? Base Solution 4 | 2021-10-08 |  |  | AC | Nassau, Suffolk, Queens, Bronx | NY | J; K | Tremont 345kV; Barrett138 kV; Shore Road 138 kV; Ruland Rd 138 kV | ConEd, LIPA | 0 | 2023-07-31
1276 | NY Power Authority / NY Transco LLC. | Propel NY Energy ? Base Solution 1 | 2021-10-08 |  |  | AC | Nassau, Queens, Bronx, and Westchester | NY | I; J; K | Sprain Brook 345 kV; Tremont 345 kV; East Garden City 345 kV; Barrett 138 kV; East Garden City 138 kV; Shore Road 138 kV; Ruland Rd 138 kV | LIPA, ConEd, NYPA | 0 | 2023-07-31
1277 | NY Power Authority / NY Transco LLC. | Propel NY Energy ? Base Solution 3 | 2021-10-09 |  |  | AC | Nassau, Queens, Bronx, Westchester | NY | I; J; K | Sprain Brook 345 kV; Tremont 345 kV; East Garden City 345 kV; Barrett 138 kV; East Garden City 138 kV; Shore Road 138 kV; Ruland Rd 138 kV | LIPA, ConEd, NYPA | 0 | 2023-07-31
1278 | NextEra Energy Transmission NY, Inc | NY Renewable Connect - Core 1 | 2021-10-10 |  |  | AC | Nassau, Suffolk, Westchester | NY | I,J,K | East Garden City 345 kV, Sprain Brook 345 kV, Dunwoodie 345 kV, Jamaica 138 kV, Valley Stream 138 kV | ConEd, LIPA | 0 | 2023-10-31
1279 | NextEra Energy Transmission NY, Inc | NY Renewable Connect - Core 2 | 2021-10-10 |  |  | AC | Nassau, Suffolk, Westchester | NY | I,J,K | East Garden City, Ruland Road, Sprain Brook, Dunwoodie, Jamaica, Valley Stream, Farragut | ConEd, LIPA | 0 | 2023-10-31
1280 | NextEra Energy Transmission NY, Inc | NY Renewable Connect - Core 3 | 2021-10-10 |  |  | AC | Nassau, Suffolk, Westchester | NY | I,J,K | East Garden City, Ruland Road, Sprain Brook, Dunwoodie, Jamaica, Valley Stream, Farragut, Northport, Pilgrim | ConEd, LIPA | 0 | 2023-10-31
1281 | NextEra Energy Transmission NY, Inc | NY Renewable Connect - Core 4 | 2021-10-10 |  |  | AC | Nassau, Suffolk, Westchester | NY | I,J,K | East Garden City, Ruland Road, Sprain Brook, Dunwoodie, Jamaica, Valley Stream, Farragut, Northport, Pilgrim | ConEd, LIPA | 0 | 2023-10-31
1282 | NextEra Energy Transmission NY, Inc | NY Renewable Connect - Core 5 | 2021-10-10 |  |  | AC | Nassau, Suffolk, Westchester | NY | I,J,K | East Garden City, Ruland Road, Sprain Brook, Dunwoodie, Jamaica, Valley Stream, Northport | ConEd, LIPA | 0 | 2023-10-31
1283 | NextEra Energy Transmission NY, Inc | NY Renewable Connect - Core 6 | 2021-10-10 |  |  | AC | Nassau, Queens, Suffolk, Westchester | NY | I,J,K | East Garden City, Ruland Road, Sprain Brook, Dunwoodie, Jamaica, Valley Stream, Northport, Pilgrim | ConEd, LIPA | 0 | 2023-10-31
1284 | NextEra Energy Transmission NY, Inc | NY Renewable Connect - Core 7 | 2021-10-10 |  |  | AC | Nassau, Suffolk, Westchester | NY | H,I,J,K | East Garden City, Ruland Road, Sprain Brook, Dunwoodie, Jamaica, Valley Stream, Northport, Pilgrim, Buchanan | ConEd, LIPA | 0 | 2023-10-31
1285 | NextEra Energy Transmission NY, Inc | NY Renewable Connect - Enhanced 1 | 2021-10-10 |  |  | AC | Nassau, Suffolk, Westchester | NY | H,I,J,K | East Garden City, Ruland Road, Sprain Brook, Dunwoodie, Farragut, Holbrook, Jamaica, Valley Stream, Northport, Pilgrim, Buchanan, Barrett | ConEd, LIPA | 0 | 2023-10-31
1286 | NextEra Energy Transmission NY, Inc | NY Renewable Connect - Enhanced 2 | 2021-10-10 |  |  | AC | Nassau, Suffolk, Westchester | NY | G,H,I,J,K | East Garden City, Ruland Road, Sprain Brook, Dunwoodie, Farragut, Holbrook, Jamaica, Valley Stream, Northport, Pilgrim, Buchanan, Ramapo | O&R, ConEd, LIPA | 0 | 2023-10-31
1287 | NextEra Energy Transmission NY, Inc | NY Renewable Connect - Plus 3 | 2021-10-10 |  |  | AC | Nassau, Suffolk, Westchester | NY | I,J,K | East Garden City, Ruland Road, Sprain Brook, Dunwoodie, Jamaica, Valley Stream, Northport, Pilgrim | ConEd, LIPA | 0 | 2023-10-31
1288 | Clean Path New York LLC | CPNY-X | 2021-11-23 |  |  | DC | Delaware, Queens | NY | E,J | Fraser 345 kV and Rainey 345 kV substations | NYSEG, ConEd | 0 | 2025-10-31
1290 | NY Power Authority / NY Transco LLC. | Propel NY Energy ? Alternate Solution 6 | 2021-10-11 |  |  | AC | Nassau, Queens, Bronx, Westchester | NY | I; J; K | Sprain Brook 345 kV; Dunwoodie 345 kV; Tremont 345 kV; East Garden City 345 kV; Barrett 138 kV; East Garden City 138 kV; Shore Road 138 kV; Syosset 138 kV; Ruland Rd 138 kV | LIPA, ConEd, NYPA | 0 | 2023-07-31
1291 | NY Power Authority / NY Transco LLC. | Propel NY Energy ? Alternate Solution 7 | 2021-10-11 |  |  | DC | Nassau, Queens, Bronx, Westchester | NY | I; J; K | Sprain Brook 345 kV; Dunwoodie 345 kV; Tremont 345 kV; Barrett 138 kV; Shore Road 138 kV; Syosset 138 kV; Ruland Rd 138 kV; Northport 138 kV | ConEd, LIPA | 0 | 2023-07-31
1292 | Liberty Renewables Inc. | Hemlock Hollow Wind | 2021-10-20 | 87.9 | 87.9 | W | Cattaraugus | NY | A | Homer Hill - Dugan Rd 115kV | NM-NG | 0 | 2024-07-31
1293 | ACE DevCo NC | White Springs Solar | 2021-10-22 | 20 | 20 | S | Ontario | NY |  | Haley Road 34.5 kV Substation | NYSEG | 0 | 2023-08-31
1294 | ACE DevCo NC | Moran Solar | 2021-10-22 | 20 | 20 | S | Fulton | NY | F | Inghams - Stoner 115 kV | NM-NG | 0 | 2024-02-29
1295 | Galehead Development, LLC | Putnam Mountain Solar | 2021-10-26 | 40 | 40 | S | Washington | NY | F | Whitehall - Cedar 115 kV | NM-NG | 0 | 2022-11-30
1296 | Nexamp Solar | 90662 Sing Sing Standalone Storage | 2021-10-28 | 20 | 20 | ES | Chemung | NY | J |  | ConEd | 0 | 2021-11-30
1297 | Algonquin Power Fund (America), Inc. | Deerpark Energy Storage | 2021-10-29 | 20 | 20 | ES | Orange | NY | G | Cuddebackville substation | O&R | 0 | 2022-01-31
1298 | Nexamp Solar | 87677 Clifton Springs Standalone Storage | 2021-10-29 | 20 | 20 | ES | Ontario | NY | J |  | ConEd | 0 | 2021-11-30
1299 | KCE NY 33, LLC | KCE NY 33 | 2021-10-29 | 20 | 20 | ES | Broome | NY | C | Langdon 34.5kV Substation | NYSEG | 0 | 2022-08-31
1300 | KCE NY 25, LLC | KCE NY 25, LLC | 2021-11-02 | 6 | 6 | ES | Ontario | NY | B | Substation 146 | RG&E | 0 | 2021-12-31
1301 | Pine Barrens Storage LLC | Pine Barrens Storage | 2021-11-09 | 75 | 75 | ES | Suffolk | NY | K | Brookhaven 138 kV Substation | LIPA | 0 | 2024-05-31
1302 | New Bremen Solar | Bremen Solar | 2021-11-10 | 102.3 | 100 | S | Lewis | NY | E | Bremen 115 kV Substation | NM-NG | 0 | 2022-03-31
1303 | Hanwha Q Cells USA | Agate Storage Project | 2021-11-12 | 200 | 200 | ES | Dutchess | NY | G | Manchester 115 kV substation | CHG&E | 0 | 2024-05-31
1304 | Hanwha Q CELLS USA | Coral Storage Project | 2021-11-12 | 100 | 100 | ES | Chemung | NY | C | Yawger 115 kV substation | NYSEG | 0 | 2024-05-31
1305 | Hanwha Q CELLS USA | Crystal Storage Project | 2021-11-12 | 175 | 175 | ES | Seneca | NY | C | Border City - Elbridge 115 kV Line#10 | NM-NG | 0 | 2024-05-31
1306 | Hanwha Q CELLS USA | Opal Storage Project | 2021-11-12 | 200 | 200 | ES | Orange | NY | G | East Walden 115 kV substation | CHG&E | 0 | 2024-05-31
1307 | Riverhead Energy | Riverhead Energy, LLC | 2021-11-16 | 100 | 100 | ES | Suffolk | NY | K | Riverhead - Jamesport 69kV | LIPA | 0 | 2024-05-31
1309 | Algonquin Power Fund (America), Inc. | Port Jefferson Energy Storage | 2021-12-07 | 48.7 | 48.7 | ES | Suffolk | NY | K | Port Jefferson 69kV Substation | LIPA | 0 | 2022-03-31
1310 | QMB1 Energy Storage | QMB1 Energy Storage | 2021-12-08 | 300 | 300 | ES | Nassua | NY | K | Ruland Rd. 138 kV | LIPA | 0 | 2024-07-31
1311 | Bronx Shores Energy Storage | Bronx Shores Energy Storage | 2021-12-08 | 300 | 300 | ES | Bronx | NY | J | Mott Haven 138 kV | ConEd | 0 | 2024-05-31
1312 | Saturn Energy Storage LLC | Orient Point BESS | 2021-12-10 | 15 | 15 | ES | Suffolk | NY | K | The existing 23kV line near PSEG?s 23 kV Orient substation | LIPA | 0 | 2022-02-28
1313 | Saturn Energy Storage LLC | Queensbury BESS | 2021-12-12 | 20 | 20 | ES | Warren | NY | F | Queensbury 34.5 kV substation | NM-NG | 0 | 2024-05-31
1314 | Regeneron Pharmaceuticals Inc | Regeneron Pharmaceutical INC | 2021-12-15 | 0.5 | 0.5 | S | Rensselaer | NY | F | On site - connecting to electrical SWGR. Technical point of interconnection for the campus is at the primary meter at the substation | NM-NG | 0 | 2022-03-31
1316 | ACE DevCo NC, LLC | Bay Breeze Solar | 2021-12-20 | 200 | 200 | S | Jefferson | NY | E | Lyme - North Watertown 115kV Line #13 | NM-NG | 0 | 2024-07-31
1317 | KCE NY 34, LLC | KCE NY 34 | 2021-12-21 | 13 | 13 | ES | Ulster | NY | G | 13.8 kV Saugerties Substation | CHGE | 0 | 2022-02-28
1318 | Algonquin Power Fund (America), Inc. | Saugerties Energy Storage | 2021-12-21 | 12.9 | 12.9 | ES | Ulster | NY | G | Saugerties substation 13.8 kV | CHGE | 0 | 2022-01-31
1319 | Grateful Storage LLC | Grateful Storage, LLC | 2021-12-23 | 100 | 100 | ES | Orange | NY | G | Chadwick Lake - East Walden 115 kV | CHG&E | 0 | 2023-12-31
1320 | Lake Ronkonkoma Storage LLC | Lake Ronkonkoma Storage, LLC | 2021-12-23 | 100 | 100 | ES | Suffolk | NY | K | Ronkonkoma 138 kV substation | LIPA | 0 | 2024-01-31
1321 | Dix Hills Storage LLC | Dix Hills, LLC | 2021-12-23 | 100 | 100 | ES | Suffolk | NY | K | Bagatelle Rd 138 kV | LIPA | 0 | 2024-05-31
1322 | Holtsville West Storage LLC | Holtsville West Storage, LLC | 2021-12-23 | 50 | 50 | ES | Suffolk | NY | K | Holtsville 69 kV substation | LIPA | 0 | 2024-07-31
1323 | Fresh Air Energy II | Lincoln ESC | 2022-01-07 | 100 | 100 | ES | SUFFOLK | NY | K | Holbrook - Bohemia 69kV | LIPA | 0 | 2024-05-31
1324 | AES | Somerset Solar Farm | 2022-01-20 | 212 | 212 | AC | USA | NY | A | Kintigh Switchyard 345kV | NYSEG | 0 | 2022-03-31
1325 | RWE Solar Development, LLC | McKean County Solar CSR Phase 1 | 2022-01-20 | 325 | 325 | CR | McKean | PA | A | Homer City - Pierce Brook 345 kV | NYSEG | 0 | 2024-05-31
1326 | RWE Solar Development, LLC | McKean County Solar CSR Phase 2 | 2022-01-20 | 325 | 325 | CR | McKean | PA | A | Homer City - Pierce Brook 345 kV | NYSEG | 0 | 2024-05-31
1327 | RWE Solar Development, LLC | McKean County BESS | 2022-01-20 | 170 | 170 | ES | McKean | PA | A | Homer City Station - Pierce Brook 345kV | NYSEG | 0 | 2022-04-30
1328 | EDF renewables development inc. | Wayland solar | 2022-01-26 | 120 | 120 | S | Steuben | NY | C | Meyer - Eelpot Road 115 kV | NYSEG | 0 | 2024-05-31
1330 | Avangrid Renewables | AGR NY-1 | 2022-02-17 | 1600 | 1600 | W | Kings | NY | J | Gowanus 345 kV Substation | ConEd | 0 | 2022-04-30
1331 | Solar Generation | Solar Generation Jennison Revitalization Facility | 2022-02-17 | 117.8 | 117.8 | S | Chenango | NY |  | Jennison 115 kV | NYSEG | 0 | 2023-08-31
1332 | Avangrid Renewables | AGR NY-2 | 2022-02-17 | 1600 | 1600 | W | Richmond | NY | J | Goethals 345 kV Substation | ConEd | 0 | 2022-04-30
1333 | QMB 1 Energy Storage | Newbridge-Ruland Storage | 2022-02-21 | 250 | 250 | ES | Nassau | NY | K | Ruland Rd - Newbridge 138 kV | LIPA | 0 | 2024-03-31
1334 | EDF renewables development inc. | Morris Sole Solar | 2022-02-23 | 110 | 110 | S | Livingston | NY | C | South Perry - Meyer 230 kV | NYSEG | 0 | 2024-05-31
1335 | Liberty Renewables Inc. | Hoffman Falls Wind 2 | 2022-02-24 | 102.5 | 102.5 | W | Madison | NY | C | Fenner-Shippey Road 115 kV Line #3 | NM-NG | 0 | 2024-05-31
1336 | Granada Solar, LLC | Abrams Solar | 2022-02-24 | 20 | 20 | S | St. Lawrence | NY |  | Alcoa - N. Ogdensburg 115 kV | NM-NG | 0 | 2023-08-31
1337 | Atlantic Shores Offshore Wind Bight, LLC | Atlantic Shores Offshore Wind Bight 1 | 2022-02-25 | 2100 | 2100 | W | Kings | NY | J | Gowanus 345 KV | ConEd | 0 | 2024-07-31
1338 | Atlantic Shores Offshore Wind Bight, LLC | Atlantic Shores Offshore Wind Bight 2 | 2022-02-25 | 2100 | 2100 | W | Richmond | NY | J | Goethals 345 kV | ConEd | 0 | 2024-07-31
1339 | Atlantic Shores Offshore Wind Bight, LLC | Atlantic Shores Offshore Wind Bight 3 | 2022-02-25 | 2100 | 2100 | W | Suffolk | NY | K | Ruland Road 138kV | LIPA | 0 | 2022-06-30
1340 | Atlantic Shores Offshore Wind Bight, LLC | Atlantic Shores Offshore Wind Bight 4 | 2022-02-25 | 2100 | 2100 | W | Kings | NY | J | Brooklyn Clean Energy Hub 345kV | ConEd | 0 | 2024-07-31
1341 | Atlantic Shores Offshore Wind Bight, LLC | Atlantic Shores Offshore Wind Bight 5 | 2022-02-25 | 2100 | 2100 | W | Richmond | NY | J | Fresh Kills 345 KV | ConEd | 0 | 2024-07-31
1342 | Astoria Renewables LLC | Astoria Annex Energy Storage | 2022-03-03 | 500 | 500 | ES | Queens | NY | J | Astoria Annex 345 kV | NYPA | 0 | 2024-05-31
1343 | Swift Current Energy | Moonlight Flats Solar Power | 2022-03-04 | 250 | 250 | S | Clearfield | PA | C | Homer City - Mainesburg 345 KV | NYSEG | 0 | 2024-05-31
1344 | Fresh Kills Battery Storage LLC | Fresh Kills Energy Storage | 2022-03-08 | 500 | 500 | ES | Richmond | NY | J | Fresh Kills 345 kV | ConEd | 0 | 2024-05-31
1345 | Staten Island Power LLC | Goethals Energy Storage Project | 2022-03-08 | 500 | 500 | ES | Richmond | NY | J | Goethals 345 kV | ConEd | 0 | 2024-05-31
1346 | Middletown Energy Storage, LLC | Middletown Energy Storage | 3/8/2022 | 100 | 100 | ES | Orange | NY | G | Tap Shoemaker-Chester 138kV line (line 27) | O&R | 0 | 2023-04-30
1347 | Hanwha Q CELLS USA | Celestine Storage | 2022-03-11 | 191.1 | 191.1 | ES | Steuben | NY | C | Bath 115 kV substation | NYSEG | 0 | 2022-06-30
1348 | Hanwha Q CELLS USA | Daphne Storage | 2022-03-11 | 45 | 45 | ES | Suffolk | NY | K | Moriches 69 kV | LIPA | 0 | 2024-05-31
1349 | Hanwha Q CELLS USA | Gemma Storage | 2022-03-11 | 190 | 190 | ES | Steuben | NY | C | Stoney Ridge 230 KV Substation | NYSEG | 0 | 2024-05-31
1350 | New Castle ESS LLC | Millwood Energy Storage | 2022-03-11 | 500 | 500 | ES | Westchester | NY | H | Millwood 345 kV Substation | ConEd | 0 | 2024-05-31
1351 | Yonkers Renewable Energy LLC | Sprain Brook Energy Storage | 2022-03-13 | 500 | 500 | ES | Westchester | NY | I | Sprain Brook 345 kV Substation | ConEd | 0 | 2024-05-31
1352 | Peekskill BESS LLC | Buchanan Energy Storage - North | 2022-03-13 | 500 | 500 | ES | Westchester | NY | H | Buchanan North 345 kV Substation | ConEd | 0 | 2024-05-31
1353 | Central Westchester Power LLC | Eastview Energy Storage Project | 2022-03-14 | 400 | 400 | ES | Westchester | NY | I | Eastview 138 kV Substation | ConEd | 0 | 2024-05-31
1354 | Hecate Energy Diamond Solar LLC | Diamond Solar | 2022-03-18 | 500 | 500 | S | Herkimer | NY | E | Edic to Gordon Rd 345 kV line | NM-NG | 0 | 2024-05-31
1355 | EDF Renewable Development, Inc | Rich Road Storage | 2022-03-23 | 20 | 20 | ES | St. Lawrence | NY | E | Moses - Adirondack 230 kV | NYPA | 0 | 2022-12-31
1356 | New Bremen Solar | Bremen Solar | 3/24/2022 | 100 | 100 | S | Lewis | NY | E | Taylorville - Boonville 115 kV | NM-NG | 0 | 2023-03-31
1357 | 174 Power Global Properties | Shoreham | 3/25/2022 | 100 | 100 | ES | Suffolk | NY | K | Shoreham 138 kV | LIPA | 0 | 2023-04-30
1358 | 174 Power Global Properties | West Babylon | 2022-03-25 | 130 | 130 | ES | Nassau | NY | K | West Babylon 69 kV | LIPA | 0 | 2022-10-31
1359 | EDF Renewable Development, Inc | Columbia Storage | 2022-03-31 | 20 | 20 | ES | Herkimer | NY | E | Edic - Fraser 345 kV | NYPA | 0 | 2022-12-31
1360 | Peekskill BESS LLC | Buchanan Energy Storage-South | 2022-04-07 | 500 | 500 | ES | Westchester | NY | H | Buchanan South 345 kV Substation | ConEd | 0 | 2024-05-31
1361 | Nexamp Solar LLC | Ditch Creek Solar | 2022-04-12 | 200 | 200 | CR | Madison | NY | C | Clay - Edic 345 kV | NYPA | 0 | 2024-10-31
1362 | EDF renewables development inc. | Fraser Storage | 2022-04-12 | 200 | 200 | ES | Delaware | NY | E | Fraser substation 115 kV | NYSEG | 0 | 2024-05-31
1363 | Delaware River Solar | State Route 52 | 2022-04-14 | 20 | 20 | S | Sullivan | NY | E | Liberty 34.5 kV substation | NYSEG | 0 | 2022-09-30
1364 | Bluewave Storage Origination LLC | NY Wappingers Falls Old Hopewell Rd Storage | 4/14/2022 | 40 | 40 | ES | Wappingers Falls | NY | G | North Chelsea - Myers Corners 69 kV | CHGE | 0 | 2023-03-31
1367 | Queensboro Development, LLC | Queensboro Renewable Express Circuit C | 2022-04-15 | N/A | N/A | AC | Queens | NY | J | New Ravenswood substation connecting to Rainey 345kV and Vernon 138kV | ConEd | 0 | 2023-02-28
1368 | Borrego Solar Systems, inc. | Hallock Ave Energy Storage | 2022-04-19 | 90 | 90 | ES | Suffolk | NY | K | Shoreham - Millers Place 138 kV | LIPA | 0 | 2022-11-30
1369 | Community Offshore Wind, LLC | Community OSW Valley Stream 1 | 2022-04-20 | 1100 | 1100 | W | Nassau | NY | K | Valley Stream 138kV | LIPA | 0 | 2022-09-30
1370 | Community Offshore Wind, LLC | Community OSW Ruland Road 1 | 2022-04-20 | 1100 | 1100 | W | Suffolk | NY | K | Ruland Road 138kV | LIPA | 0 | 2024-05-31
1371 | Community Offshore Wind, LLC | Community OSW Goethals 1 | 2022-04-20 | 1100 | 1100 | W | Staten Island | NY | J | Goethals 345 kV | ConEd | 0 | 2024-05-31
1372 | Community Offshore Wind, LLC | Community OSW Brooklyn CEH 1 | 2022-04-20 | 1100 | 1100 | W | Brooklyn | NY | J | Brooklyn Clean Energy Hub 345 kV | ConEd | 0 | 2024-05-31
1373 | Community Offshore Wind, LLC | Community OSW Barrett 1 | 2022-04-20 | 1100 | 1100 | W | Nassau | NY |  | Barrett 138 kV | LIPA | 0 | 2023-08-31
1374 | Community Offshore Wind, LLC | Community OSW East Garden City 1 | 2022-04-24 | 1100 | 1100 | W | Nassau | NY | K | East Garden City 345 kV | NYPA | 0 | 2024-05-31
1375 | Community Offshore Wind, LLC | Community OSW Valley Stream 2 | 2022-04-24 | 210 | 210 | W | Nassau | NY | K | Valley Stream 138kV | LIPA | 0 | 2022-09-30
1376 | Community Offshore Wind, LLC | Community OSW Ruland Road 2 | 2022-04-24 | 210 | 210 | W | Suffolk | NY | K | Ruland Road 138 kV | LIPA | 0 | 2023-11-30
1377 | Community Offshore Wind, LLC | Community OSW Goethals 2 | 2022-04-24 | 210 | 210 | W | Staten Island | NY | J | Goethals 345 kV | ConEd | 0 | 2024-05-31
1378 | Community Offshore Wind, LLC | Community OSW Brooklyn CEH 2 | 2022-04-24 | 210 | 210 | W | Brooklyn | NY | J | Brooklyn Clean Energy Hub 345 kV | ConEd | 0 | 2024-05-31
1379 | Community Offshore Wind, LLC | Community OSW Barrett 2 | 2022-04-24 | 210 | 210 | W | Nassau | NY |  | Barrett 138 kV | LIPA | 0 | 2023-08-31
1380 | Community Offshore Wind, LLC | Community OSW East Garden City 2 | 2022-04-24 | 210 | 210 | W | Nassau | NY | K | East Garden City 345 kV | NYPA | 0 | 2024-05-31
1381 | Bluewave Storage Origination LLC | NY Nassau 0 Waterbury Rd Storage A | 2022-04-28 | 25.2 | 25.2 | ES | Rensselaer | NY | F | Nassau-Hudson #9 Line 34.5 kV | NM-NG | 0 | 2024-02-29
1382 | OW Ocean Winds East | OW Ocean Winds East 7 | 2022-05-02 | 1600 | 1600 | W | Kings | NY | J | Gowanus 345 kV | ConEd | 0 | 2024-07-31
1383 | Bluewave Storage Origination LLC | NY Hudson Fairview Ave Storage | 2022-05-05 | 25.2 | 25.2 | ES | Columbia | NY | F | Nassau - Hudson 34.5kV | NM-NG | 0 | 2022-11-30
1384 | Daroga Power | Daroga Power Dover Plains Hydrogen Production Plant | 2022-05-19 |  |  |  | Dutchess | NY | H | Ten Mile River | NYSEG | 0 | 2022-08-31
1385 | Attentive Energy | Attentive Energy 1 | 2022-06-01 | 1310 | 1310 | W | Suffolk | NY | K | Sills Road Substation 138kV | LIPA | 0 | 2024-05-31
1386 | Attentive Energy | Attentive Energy 2 | 2022-06-01 | 1310 | 1310 | W | Brooklyn | NY | J | Farragut Substation 345 kV | ConEd | 0 | 2024-05-31
1387 | ClearCell Power | Glen Head Battery Energy Storage System | 2022-06-09 | 20.1 | 20.1 | ES | Nassau | NY | K | 1 Stanco Street Substation via a dedicated feeder from the project site | LIPA | 0 | 2022-08-31
1388 | NY Power Authority Development & LS Power Grid NY Corporation II | Kings Spoke 1310 | 2022-06-09 |  |  |  | Kings | NY | J | The proposed POI will be located at a new 345/138 kV transmission substation in East Flatbush, Brooklyn, ~4 miles from the Greenwood substation, ~3 miles from the Bensonhurst sub, ~4 miles from the Farragut, and ~3 miles from Brownsville substation. | ConEd | 0 | 2022-07-31
1389 | NY Power Authority & LS Power Grid NY Corporation II | Kings Spoke 2620 | 2022-06-09 |  |  |  | Kings | NY | J | The proposed POI will be located at a new 345/138 kV transmission substation in East Flatbush, Brooklyn, ~4 miles from the Greenwood substation, ~3 miles from the Bensonhurst substation, ~4 miles from the Farragut substation and ~3 mi from the Brownsville | ConEd | 0 | 2022-07-31
1390 | EDF Renewable Development Inc. | Ridge View Stoarge | 2022-06-10 | 20 | 20 | S | Niagara | NY | A | Kintigh-Dysinger 345kV | NYSEG | 0 | 2022-12-31
1391 | ACE DevCo NC, LLC | Beck Solar | 2022-06-21 | 20 | 20 | S | Chautauqua | NY | A | Hartfield - Moon Road 115 kV line | NM-NG | 0 | 2024-01-31
1392 | Swift Solar LLC | Swift Solar | 2022-06-23 | 300 | 300 | CR | Herkimer | NY | F | Edic - Princetown 345 kV #351 line | NYPA | 0 | 2024-05-31
1393 | Mineral Basin Solar Power, LLC | Mineral Basin II Solar Power | 2022-06-23 | 222 | 222 | S | Clearfield | PA | C | Homer City - Mainesburg 345 kV | NYSEG | 0 | 2024-05-31
1394 | Bluewave Storage Origination LLC | NY Greenport 85 Middle Rd Storage | 2022-06-23 | 104.2 | 104.2 | ES | Columbia | NY | G | North Catskill - Churchtown Line #5 115 kV and Lafarge- Churchtown Line #8 115 kV | NM-NG | 0 | 2024-02-29
1395 | Excelsior Reserve Energy | Raquette Lake Energy Storage / CAMP | 2022-06-23 | 20 | 20 | ES | Hamilton | NY | E | Raquette Lake - Eagle Bay 46 kV line | NM-NG | 0 | 2024-02-29
1396 | NY Interconnection LLC | NY Interconnection 4 | 2022-06-30 | 900 | 900 | W | NY | NY | J | Fox Hills 138 kV Substation | ConEd | 0 | 2024-05-31
1397 | NY Power Authority | Hell Gate Energy Storage | 2022-07-01 | 95 | 96 | ES | Bronx | NY | J | Hell Gate Bus Section 2 - 138kV | NYPA | 0 | 2024-05-31
1398 | NY Power Authority | Harlem River Yards Energy Storage | 2022-07-01 | 106 | 107 | ES | Bronx | NY | J | Hell Gate Annex - 138kV voltage | NYPA | 0 | 2024-05-31
1399 | NY Power Authority | Pouch Energy Storage | 2022-07-01 | 51 | 52 | ES | Staten Island | NY | J | Fox Hills 138kV Substation | ConEd | 0 | 2024-05-31
1400 | NY Power Authority | Gowanus Energy Storage | 7/1/2022 | 102 | 103 | ES | Brooklyn | NY | J | Greenwood 138kV Substation with alternate feed connected to Gowanus Substation ~ | ConEd | 0 | 2023-03-31
1401 | NY Power Authority | Brentwood Energy Storage | 2022-07-01 | 51 | 52 | ES | Suffolk | NY | K | Brentwood Substation Bus #1 - 69kV | LIPA | 0 | 2024-05-31
1402 | NY Power Authority | Flynn Energy Storage | 2022-07-01 | 160 | 160 | ES | Suffolk | NY | K | Holtsville 138 kV substation | LIPA | 0 | 2024-05-31
1403 | Poplar Energy Center, LLC | Poplar 1 Energy Center | 2022-07-11 | 60 | 60 | ES | Suffolk | NY | K | Riverhead -Tuthill 69 kV Line | LIPA | 0 | 2024-05-31
1404 | Winner Solar, LLC | Winner Solar | 2022-07-14 | 120 | 120 | S | Clinton County | PA | C | Homer City - Mainesburg 345kV | NYSEG | 0 | 2024-09-30
1405 | Athens Energy Stoarge LLC | Athens Energy Storage | 2022-07-16 | 300 | 300 | ES | Greene | NY | F | Leeds 3-Van Wagner 345 kV Line | NM-NG | 0 | 2024-05-31
1406 | North Seneca Solar Project LLC | North Seneca Storage | 2022-07-22 | 19.9 | 19.9 | ES | Seneca | NY | C | Farmington-Hamilton 115 kV Line Tap | NM-NG | 0 | 2023-10-31
1407 | Crane Brook Solar Project | Crane Brook Storage | 2022-07-22 | 19.9 | 19.9 | ES | Cayuga | NY | C | State St. - Clinton Corn 115 kV | NM-NG | 0 | 2023-07-31
1408 | Bluewave Storage Origination LLC | NY Schodack 634 Knickerbocker Rd Storage | 7/25/2022 | 57 | 57 | ES | Rensselaer | NY | F | Schodack – Valkin line 14 115 kV | NYTransco | 0 | 2023-03-31
1409 | Grateful Storage LLC | Grateful Storage, LLC | 2022-08-26 | 250 | 250 | ES | Orange | NY | G | Rock Tavern - Roseton 345kV | CHG&E | 0 | 2024-07-31
1410 | Cayuga Solar LLC | Cayuga Solar LLC | 2022-07-29 | 19.6 | 19.6 | S | Cayuga | NY | C | NYS-Locke 718 34.5 kV Substation | NYSEG | 0 | 2024-11-30
1411 | Bluewave Storage Origination LLC | NY Johnstown 378 State Hwy 334 Storage | 8/1/2022 | 62.5 | 62.5 | ES | Fulton | NY | F | Inghams - Meco #15 115 kV line | NM-NG | 0 | 2023-03-31
1412 | Poplar Energy Center, LLC | Poplar 2 Energy Center | 2022-08-10 | 20 | 20 | ES | Suffolk | NY | K | Riverhead-Tuthill 69kV | LIPA | 0 | 2023-02-28
1413 | Catlin Creek Energy Storage 1, LLC | Catlin Creek Storage | 2022-08-10 | 70 | 70 | ES | Orange County | NY | G | Westtown - Shoemaker 69 kV line #11 | O&R | 0 | 2024-08-31
1414 | Glove City Energy Center, L.L.C. | Glove City Energy Center | 2022-08-10 | 100 | 100 | S | Fulton | NY | F | Stoner to Inghams 115 kV line | NM-NG | 0 | 2022-09-30
1415 | Microgrid Networks, LLC | 57-77 Rust St | 2022-08-11 | 22.5 | 22.5 | ES | Queens | NY | J | Glendale 27kV | ConEd | 0 | 2022-12-31
1416 | Bluewave Storage Origination LLC | NY Mahopac 45 Margaret Rd Storage | 2022-08-15 | 162.5 | 162.5 | ES | Putnam | NY | H | Croton Falls - Union valley 115 kV | NYSEG | 0 | 2023-02-28
1417 | Liberty Renewables Inc. | Russet Ridge Wind | 2022-08-19 | 118 | 118 | W | Livingston | NY | C | Eelpot Road 115kV substation | NYSEG | 0 | 2024-05-31
1418 | New Hartford Solar LLC | New Hartford Solar Farm | 2022-08-22 | 20 | 20 | CR | Oneida | NY | E | Line #1 115kV YAHNUNDASIS-CHADWICKS | NM-NG | 0 | 2024-06-30
1419 | Vineyard Mid-Atlantic | Vineyard Mid-Atlantic 1 | 2022-08-24 | 1350 | 1350 | W | Kings | NY | J | Gowanus 345 kV | Coned | 0 | 2024-05-31
1420 | Glove City Energy Center, LLC | Glove City Solar | 2022-08-25 | 100 | 100 | S | Fulton | NY | F | Inghams - Stoner 115kV line #9 | NM-NG | 0 | 2024-05-31
1421 | Origis Development | Lockport Storage | 2022-08-29 | 186.2 | 186.2 | ES | Niagara | NY | A | Robinson Road 230 kV Substation | NYSEG | 0 | 2024-05-31
1422 | Pivot Energy Development LLC | Pivot Burnell | 8/31/2022 | 20 | 20 | CR | Clinton | NY | D | Lyon Mountain - Saranac 115 kV | NYSEG | 0 | 2023-04-30
1423 | Pivot Energy Development LLC | Pivot Macvean | 8/31/2022 | 19.8 | 19.8 | CR | Fulton | NY | F | Amsterdam to Ephratah 69kV | NM-NG | 0 | 2023-03-31
1424 | Pivot Energy Development LLC | Pivot Woodsmen | 8/31/2022 | 20 | 20 | CR | Oneida | NY | E | Boonville - Porter 115kV line 1 | NM-NG | 0 | 2023-04-30
1425 | Pivot Energy Development LLC | Pivot Woodsmen BESS | 2022-08-31 | 19.8 | 19.8 | ES | Oneida | NY | E | Boonville - Porter 115kV Line 1 | NM-NG | 0 | 2023-11-30
1426 | Pivot Energy Development LLC | Pivot Macvean BESS | 8/31/2022 | 19.8 | 19.8 | ES | Fulton | NY | F | Amsterdam - Ephratah 69kV (Line#7) | NM-NG | 0 | 2023-03-31
1427 | Pivot Energy Development LLC | Pivot Burnell BESS | 8/31/2022 | 20 | 20 | ES | Clinton | NY | D | Lyon Mountain - Saranac 115kV | NYSEG | 0 | 2023-03-31
1428 | Vineyard Northeast | Vineyard Northeast 1 | 2022-09-01 | 1350 | 1350 | W | Kings County | NY | J | Gowanus 345kV | ConEd | 0 | 2024-05-31
1429 | Bluewave Storage Origination LLC | NY Southold 50100 County Rd 48 Storage B | 9/1/2022 | 45.7 | 45.7 | ES | Suffolk | NY | K | 8B Peconic to 8J Southold 69kV line (69-957) | LIPA | 0 | 2023-03-31
1430 | Origis Development | Van Buren Storage | 2022-09-06 | 150 | 150 | ES | Chautauqua | NY | A | Dunkirk to Falconer 115 kV transmission | NM-NG | 0 | 2024-05-31
1431 | Juno Power Management | oyster shore III | 2022-09-06 | 300 | 300 | ES | Nassau | NY | K | Shore road 138 kV | LIPA | 0 | 2023-04-30
1432 | Cherry Valley Energy Center, L.L.C. | Cherry Valley Solar | 2022-09-07 | 125 | 125 | S | Montgomery | NY | F | Edic - Princetown 345kV Line #351 | NYPA | 0 | 2024-05-31
1433 | NY Interconnection LLC | NY Interconnection 5 | 2022-09-09 | 150 | 150 | W | NY | NY | J | Fox Hills 138kV Substation | ConEd | 0 | 2024-05-31
1434 | NY Interconnection LLC | NY Interconnection 6 | 2022-09-09 | 1050 | 1050 | W | Richmond | NY | J | Goethals-Gowanus 345kV Line Break | ConEd | 0 | 2024-05-31
1435 | New York Power Authority & LS Power Grid New York Corporation II | Kings Spoke | 2022-09-12 | N/A | N/A | AC | Kings | NY | J | Greenwood-Bensonhurst and Farragut-Brownsville 138 kV feeders | ConEd | 0 | 2023-04-30
1436 | North Foothills Energy Center, LLC | North Foothills | 2022-09-13 | 100 | 100 | S | FRANKLIN | NY | D | Malone 115 kV Substation | NM-NG | 0 | 2024-05-31
1437 | Northland Power U.S. Projects | North Norwich Solar | 2022-09-14 | 120 | 120 | CR | Chenango County | NY | E | County Line-East Norwich Tap 115 kV NYSEG | NYSEG | 0 | 2024-05-31
1438 | NY Interconnection LLC | NY Interconnection 7 | 2022-09-15 | 270 | 270 | W | Richmond | NY | J | Goethals-Gowanus 345kV line break | ConEd | 0 | 2024-05-31
1439 | East Bridge Storage, LLC | East Bridge Energy Storage | 2022-09-16 | 125 | 125 | ES | Sullivan | NY | E | Coopers Corner - Shortcut Rd 115 kV | NYSEG | 0 | 2024-03-31
1440 | Gloversville Storage, LLC | Gloversville Storage | 2022-09-21 | 50 | 50 | ES | Fulton | NY | F | MECO 115 kV Substation | NM-NG | 0 | 2024-03-31
1441 | Northbrook Lyons Falls LLC | Lyons Falls Mill Repowering Project | 9/22/2022 | 11 | 11 | H | Lewis | NY | E | 115kV Taylorville-Boonville Line 6 via the Lyonsdale Hydro tap | NM-NG | 0 | 2023-04-30
1442 | Mulberry Energy Storage 1, LLC | Mulberry Energy Storage | 2022-09-28 | 130 | 130 | ES | Saratoga | NY | F | Luther Forest - Eastover Road #308 115kV line | NM-NG | 0 | 2024-04-30
1443 | Vineyard Mid-Atlantic | Vineyard Mid-Atlantic 2 | 2022-09-28 | 1330 | 1330 | W | Nassau | NY | K | East Garden City 345 kV Substation | NYPA | 0 | 2024-07-31
1444 | Hollyhock Solar, LLC | Hollyhock Solar | 2022-11-15 | 20 | 20 | S | Albany | NY | F | Leeds-New Scotland 115 kV, Unionville-Callanan Industries 34.5 kV | NM-NG | 0 | 2023-01-31
1445 | Apalachin Solar LLC | Friendship Solar Farm | 2022-09-30 | 20 | 20 | CR | Allegany | NY | B | The POI provided in the IR was Connection to one pole of the 34 kV transmission line coming from substation 8333G (Substation address: 52 PA Ave, Friendship, NY). The line number has been identified by RGE as line # 760 34.5kV line | RG&E | 0 | 2023-05-31
1447 | Capital Region Energy Storage LLC | New Scotland BESS Project | 2022-10-10 | 600 | 600 | ES | Albany | NY | F | New Scotland 345 kV Substation | NM-NG | 0 | 2024-09-30
1448 | KCE NY 30, LLC | KCE NY 30 | 2022-10-11 | 50 | 50 | ES | Suffolk | NY | K | West Babylon 69kV substation | LIPA | 0 | 2024-05-31
1449 | KCE NY 31, LLC | KCE NY 31 | 2022-10-11 | 50 | 50 | ES | Suffolk | NY | K | Shoreham 138 kV | LIPA | 0 | 2024-05-31
1450 | NYG Energy LLC | Stewart Rock Energy Storage | 2022-10-11 | 150 | 150 | ES | Orange | NY | G | Rock Tavern 345KV | CHG&E | 0 | 2023-12-31
1451 | Empire Reserve Energy, LLC | Babylon Storage | 2022-10-13 | 50 | 50 | ES | Suffolk | NY | K | Pinelawn 69 kV station | LIPA | 0 | 2024-05-31
1452 | CS Grass River Solar, LLC | Grass River Solar | 2022-10-17 | 80 | 80 | S | St. Lawrence County | NY | E | Alcoa - N. Ogdensburg 115kV line #13 | NM-NG | 0 | 2024-05-31
1453 | Delaware River Solar | Soper Road | 10/25/2022 | 20 | 20 | S | Wyoming | NY | C | Perry Center 34.5 kV substation | NYSEG | 0 | 2023-04-30
1454 | Ozone Renewables | Short Tract Energy Storage | 2022-10-25 | 20 | 20 | ES | Livingston | NY | B | RG&E Short Tract Road Substation | RG&E | 0 | 2023-02-28
1455 | Vineyard Northeast LLC | Vineyard Northeast 2 | 2022-10-31 | 1345 | 1345 | W | Kings | NY | J | Farragut 345 kV Substation | ConEd | 0 | 2024-05-31
1456 | Bluewave Storage Origination LLC | NY Amsterdam 152 Persons Rd Storage | 2022-10-31 | 114.8 | 114.8 | ES | Montgomery | NY | F | Stoner ? Rotterdam 115 kV line#12 | NM-NG | 0 | 2023-06-30
1457 | Hanwha Q CELLS USA Corp. | Jasper Storage | 2022-11-01 | 300 | 300 | ES | West Henrietta | NY | B | Henrietta (S255) 345 kV Substation | RG&E | 0 | 2024-05-31
1458 | SED NY Holdings LLC | TableTop Solar II | 2022-11-07 | 20 | 20 | S | Montgomery | NY | F | Clinton ERCC - Clinton Tap 115kV | NM-NG | 0 | 2024-05-31
1459 | ELP Chatham Storage LLC | ELP Chatham Storage | 2022-11-17 | 20 | 20 | ES | Columbia | NY | F | Chatham 34.5kV Substation | NYSEG | 0 | 2023-01-31
1460 | Bay State Wind | NY Wind - Pilgrim Uprate | 2022-11-08 | 1400 | 1400 | W | Suffolk County | NY | K | Pilgrim 138 kV | LIPA | 0 | 2024-05-31
1461 | Genesee County Economic Devel. | WNY STAMP | 2022-11-08 |  |  |  | Genesee | NY | B | Kintigh/Niagara - New Rochester 345kV | NYPA | 0 | 2022-12-31
1462 | Kearsarge Solar | Kearsarge Gloversville | 2022-11-11 | 20 | 20 | S | Fulton | NY | F | Gloversville - Hill Street #3 69kV | NM-NG | 0 | 2023-11-30
1463 | Bluewave Storage Origination LLC | NY Amsterdam 516 Millers Corners Rd Storage | 2022-11-11 | 430 | 430 | ES | Montgomery | NY | E | Edic to Princetown 345 kV transmission line ? Ckt ID 1 | LS Power | 0 | 2023-06-30
1464 | EDF Renewables inc. | Sage Creek Solar | 11/11/2022 | 250 | 250 | S | Oswego | NY | C | Edic - Fitzpatrick 345 kV | NYPA/NM-NG | 0 | 2023-03-31
1466 | Bluewave Storage Origination LLC | NY New Paltz 540 State Rte 32 S Storage | 11/15/2022 | 217 | 220.7 | ES | Ulster | NY | G | Modena-Ohioville 115 kV line | CHGE | 0 | 2023-03-31
1467 | Origis Development | Homer Hill Storage | 2022-11-16 | 54.7 | 54.7 | ES | Cattaraugus | NY | A | Homer Hill 34.5 kV Substation | NM-NG | 0 | 2024-05-31
1468 | Bay State Wind | NY Wind - Mott Haven Uprate | 2022-11-16 | 128 | 128 | W | The Bronx | NY | J | Mott Haven 345 kV | ConEd | 0 | 2024-05-31
1469 | YSG | Commodore | 2022-11-17 | 1200 | 1200 | ES | Oneida County | NY | E | connection to a new breaker position on the 345 kV Bus (Bus #147833) at Marcy | NYPA | 0 | 2023-01-31
1470 | ABUNDANT SOLAR POWER (US-NY-MARKHAM HOLLOW RD-001) LLC | Suny Fabius - Transmission Connected Solar PV Project | 2022-11-18 | 18 | 18 | S | Tully | NY | C | Tilden - Cortland 18 115kV | NM-NG | 0 | 2024-05-31
1471 | Crossbuck Energy Storage LLC | Crossbuck Energy Storage LLC | 2022-11-22 | 100 | 100 | ES | Greene County | NY | G | Coxsackie 69 kV substation | CHG&E | 0 | 2024-09-30
1472 | Origis Development | Highland Storage | 2022-11-23 | 115.1 | 115.1 | ES | Ulster | NY | G | Marlboro 115 kV Substation | CHG&E | 0 | 2024-05-31
1473 | Capital Region Energy Storage LLC | Leeds BESS Project | 2022-11-28 | 600 | 600 | ES | Greene | NY | F | Leeds 345 kV substation | NM-NG | 0 | 2024-05-31
1474 | Bluewave Storage Origination LLC | NY Catskill 0 Route 9W Storage | 11/29/2022 | 245 | 245 | ES | Greene | NY | G | 115 kV North Catskill-Churchtown 5 Line and Feura Bush -North Catskill 2 Line | NM-NG | 0 | 2023-03-31
1475 | SR1 Shift NY I | Upper Falls Solar | 2022-11-29 | 46 | 46 | CR | Wyoming | NY | B | Line 907 Substation 162, Alleghany (S1185) and Houghton Substation (S180). 115kV | RG&E | 0 | 2024-05-31
1476 | Vineyard Mid-Atlantic LLC | Vineyard Mid-Atlantic 3 | 2022-11-30 | 1330 | 1330 | W | Nassau | NY | K | East Garden City 345 kV Substation | NYPA | 0 | 2024-05-31
1477 | Terra-Gen Development Company | Nine Mile Wind Farm | 11/30/2022 | 120 | 120 | W | Allegany | NY | A | Homer Hill 115kV Substation (135282) | NM-NG | 0 | 2023-04-30
1478 | Mount Hope Stand Alone Storage 1, LLC | Mount Hope Stand Alone Storage | 2022-11-30 | 50 | 50 | ES | Orange | NY | G | 69 kV Line 13 - Cuddlebackville to Shoemaker Substation | O&R | 0 | 2024-03-31
1479 | Emeren US, LLC | Cedar Lake Solar | 2022-11-30 | 8.4 | 8.4 | CR | St. Lawrence | NY | E | Mine Road - Colony 34.5 kV Line 28 (ES 899) | NM-NG | 0 | 2024-02-29
1480 | Renesola Power Holdings LLC | Perryville Solar | 2022-12-01 | 18.6 | 18.6 | CR | Madison | NY | C | Chittenango-Rathbun 34.5kV line | NM-NG | 0 | 2022-12-31
1481 | Renesola Power Holdings LLC | Rush Creek Solar | 2022-12-01 | 19.9 | 19.9 | CR | Onondaga | NY | C | Tilden Station-Cardiff/Lords Hill 34.5kV | NM-NG | 0 | 2022-12-31
1482 | Renesola Power Holdings LLC | Quarry Solar | 2022-12-01 | 19.9 | 19.9 | CR | Madison | NY | C | Perryville-Whitman 34.5kV | NM-NG | 0 | 2022-12-31
1483 | Emeren US, LLC | Battle Hill Solar | 2022-12-01 | 35 | 35 | CR | St. Lawrence | NY | E | Battle Hill 115kV Substation | NM-NG | 0 | 2023-06-30
1485 | Sandlot Energy LLC | Sandlot | 2022-12-15 | 600 | 600 | ES | Suffolk County | NY | K | Northport - Pilgrim 138kV Line (138-679A&B) | LIPA | 0 | 2024-05-31
1486 | Bluewave Storage Origination LLC | NY Whitesboro 0 Westmoreland Rd Storage | 2022-12-16 | 40 | 40 | ES | Oneida | NY | E | Oneida - Yahnundasis #6 115kV | NM-NG | 0 | 2024-02-29
1487 | ACE DevCo NC, LLC | Three Rivers Energy Storage | 2022-12-22 | 80 | 80 | ES | Onondaga | NY | C | Curtis Street - Teall 115 kV Line #13 | NM-NG | 0 | 2024-07-31
1488 | ACE DevCo NC, LLC | Speckhardt Energy Storage | 2022-12-22 | 100 | 100 | ES | Rensselaer | NY | F | Greenbush 115 kV Substation | NM-NG | 0 | 2024-03-31
1489 | ACE DevCo NC, LLC | Block Perch Solar | 2022-12-22 | 100 | 100 | S | Chautauqua | NY | A | Moons to Falconer 115 kV Line #175 | NM-NG | 0 | 2024-09-30
1490 | ACE DevCo NC, LLC | Westtown Energy Storage | 2022-12-22 | 100 | 100 | ES | Orange County | NY | G | Westtown 69 kV Substation | O&R | 0 | 2024-11-30
1491 | ACE DevCo NC, LLC | Wallkill Energy Storage | 2022-12-22 | 100 | 100 | ES | Ulster County | NY | G | Ohioville 115 kV Substation Bus 2 | CHG&E | 0 | 2023-04-30
1492 | ACE DevCo NC, LLC | Sidecar Solar | 2022-12-22 | 100 | 100 | S | Tioga | NY | C | 115 kV South Owego Substation | NYSEG | 0 | 2024-05-31
1493 | Queensboro Development, LLC | Queensboro Renewable Express Circuit A | 2022-12-21 | 1310 | 1310 | W | Queens | NY | J | Rainey and Vernon Substations | ConEd | 0 | 2024-08-01
1494 | ACE DevCo NC, LLC | Wishbone Solar | 2022-12-22 | 200 | 200 | S | Steuben | NY | C | Canandaigua to Stony Ridge 230 kV Line | NYSEG | 0 | 2024-11-30
1495 | ACE DevCo NC, LLC | Argos Solar | 2022-12-22 | 150 | 150 | S | Tompkins | NY | C | Etna 115 kV substation | NYSEG | 0 | 2024-11-30
1496 | Yellow Feather Energy Center | Yellow Feather Energy Center | 2022-12-22 | 110 | 110 | S | Montgomery | NY | F | Inghams to Center Street 115 kV Line Tap | NM-NG | 0 | 2024-05-31
1497 | Sweet Valley Energy Center | Sweet Valley Solar | 2022-12-22 | 200 | 200 | S | Genesee | NY | B | Dysinger - Station 255 (Henrietta) #1 345kV line | NYPA | 0 | 2024-05-31
1498 | Sweet Valley Energy Center | Sweet Valley Storage | 2022-12-22 | 200 | 200 | ES | Genesee | NY | B | Dysinger - Station 255 (Henrietta) #1 345kV line | NYPA | 0 | 2024-05-31
1499 | RWE Solar Development | Farmhouse BESS | 2022-12-29 | 150 | 150 | ES | Orange | NY | G | Roseton 345 kV Substation | CHG&E | 0 | 2024-05-31
1500 | RWE Solar Development | Sullivan County Solar & BESS | 2023-01-05 | 200 | 200 | CR | Sullivan | NY | E | Coopers Corner - Middletown Tap 345 kV line | NYPA | 0 | 2024-05-31
1501 | RWE Solar Development | Zulu BESS | 2023-01-06 | 150 | 150 | ES | Orange | NY | G | Bethlehem Road 115 kV Substation | CHG&E | 0 | 2024-05-31
1502 | Oswego Clean Energy LLC | Oswego Solar | 2023-01-13 | 24.9 | 24.9 | S | Oswego | NY | C | Oswego 115 kV Substation | NM-NG | 0 | 2024-07-31
1503 | Bay State Wind | NY Wind - Pilgrim CSR | 2023-01-15 | 1400 | 1400 | CW | Suffolk County | NY | K | Pilgrim 138 kV | LIPA | 0 | 2024-05-31
1504 | Bay State Wind | NY Wind - Mott Haven CSR | 2023-01-15 | 1400 | 1400 | CW | The Bronx | NY | J | Mott Haven 345 kV | ConEd | 0 | 2024-05-31
1505 | East Setauket energy Storage, LLC | East Setauket Energy Storage II | 2023-01-19 | 300 | 300 | ES | Suffolk | NY | K | Holbrook to Miller Place 138kV | LIPA | 0 | 2024-05-31
1506 | Sourdough Energy Storage LLC | Sourdough Energy Storage LLC | 2023-01-24 | 100 | 100 | ES | Suffolk County | NY | K | Pulaski 69kV substation | LIPA | 0 | 2024-10-31
1507 | Ramapo Storage Project 1 | Ramapo Storage Project 1 | 2023-01-31 | 500 | 500 | ES | Rockland | NY | G | Ramapo Substation (345kV) | ConEd | 0 | 2024-05-31
1508 | Robin MDS BESS, LLC | Robin MDS BESS | 1/31/2023 |  |  | ES | Niagara | NY | A | Robinson Road 34.5 kV | NYSEG | 0 | 2023-04-30
1509 | ACE DevCo NC, LLC | Cayuga Solar | 2023-02-01 | 100 | 100 | S | Tompkins | NY | C | Milliken (Cayuga) 115 kV Substation | NYSEG | 0 | 2023-04-30
1510 | Ramapo Storage Project 2 | Ramapo Storage Project 2 | 2023-02-02 | 500 | 500 | ES | Rockland | NY | G | Ramapo Substation (345kV) | ConEd | 0 | 2024-05-31
1511 | Palladium Storage LLC | Palladium Storage | 2023-02-03 | 255 | 255 | ES | Bronx | NY | J | Mott Haven 138 kV substation | ConEd | 0 | 2024-05-31
1512 | Delaware River Solar | Prospect Hill Road | 2023-02-08 | 20 | 20 | S | Orange | NY | G | 69 kV Mongaup to Cuddebackville | O&R | 0 | 2023-07-31
1513 | Watson Storage LLC | Watson Storage System #1 | 2023-02-08 | 50 | 50 | ES | Queens | NY | J | Glendale 27kV Substation | ConEd | 0 | 2023-02-28
1514 | Watson Storage LLC | Watson Storage System #2 | 2023-02-08 | 50 | 50 | ES | Queens | NY | J | Glendale 27kV Substation | ConEd | 0 | 2023-02-28
1515 | Solaris Energy Storage LLC | Solaris Energy Storage | 2023-02-09 | 270 | 270 | ES | Kings | NY | J | Greenwood 138kV Substation | ConEd | 0 | 2024-05-31
1516 | Fort Edward Solar | Fort Edward Solar Farm (NY53) | 2023-02-10 | 100 | 100 | S | Washington | NY | F | Mohican-Battenkill 115kV Line #15 | NM-NG | 0 | 2023-02-28
1517 | Newport Deerfield Solar | NY115 - Newport Solar | 2023-02-13 | 130 | 130 | S | Oneida | NY | E | Porter - Deerfield 115 kV (Line#9) | NM-NG | 0 | 2023-02-28
1518 | Hodson Energy Rush LLC | Rush Solar & BESS | 2023-02-13 | 21 | 21 | CR | Monroe | NY | B | Mortimer to Golah 115kV | NM-NG | 0 | 2024-05-31
1519 | SATURN ENERGY STORAGE | Dayton Energy Storage Project | 2023-02-13 | 20 | 20 | ES | Cattaraugus | NY | A | 34.5 kV Dayton substation | NYSEG | 0 | 2024-05-31
1520 | SATURN ENERGY STORAGE | Nile Energy Storage Project | 2023-02-13 | 20 | 20 | ES | Allegany | NY | A | 34.5 kV Nile substation | RGE | 0 | 2023-06-30
1523 | Foothills Solar | Foothills Solar | 2023-02-15 | 40 | 40 | S | Fulton | NY | F | Vails Mills-Northville 69kV | NGrid | 0 | 2023-02-28
1524 | Hodson Energy Little Falls LLC | Little Falls Solar & BESS | 2023-02-21 | 83.2 | 78 | CR | Herkimer | NY | E | Inghams 115kV - Watkins Road 115kV | NM-NG | 0 | 2024-05-31
1525 | ELP Clay Storage LLC | ELP Clay Storage | 2023-02-24 | 165 | 165 | ES | Onondaga | NY | C | 115 kV Line #7 Clay-Lighthouse Hill | NM-NG | 0 | 2024-05-31
1526 | Radial Power LLC (Radial Power BESS NY LLC) | OATT NYISO Tuxedo Project | 2/25/2023 | 5 | 5 | ES | Orange County | NY | G | 55 NY 17, Tuxedo Park, NY 10987 | O&R | 0 | 2023-03-31
1527 | Hollyhock Solar, LLC | Hollyhock Solar | 2/28/2023 |  |  | CR | Albany | NY | F | Leeds-New Scotland 115 kV | NM-NG | 0 | 2023-04-30
1528 | Coopers Corner Storage Project 1 LLC | Coopers Corner Storage Project 1 | 2023-03-02 | 250 | 250 | ES | Sullivan | NY | E | Coopers Corners 345 kV substation | NYSEG | 0 | 2024-05-31
1529 | Coopers Corner Storage Project 2 LLC | Coopers Corner Storage Project 2 | 2023-03-02 | 250 | 250 | ES | Sullivan | NY | E | Coopers Corners 345 kV Substation | NYSEG | 0 | 2024-05-31
1530 | New York Power Authority | Westchester Wind | 2023-03-02 | N/A | N/A | AC | Westchester | NY | I | Sprainbrook-Eastview 345kV #1N, #1S, and #2S. | ConEd | 0 | 2023-05-31
1531 | SATURN ENERGY STORAGE | Alden Energy Storage Project | 2023-03-07 | 17.3 | 17.3 | ES | Erie | NY | A | 34.5 kV Alden substation | NYSEG | 0 | 2023-05-31
1532 | Beaver Falls, LLC | Beaver Falls Energy Storage | 2023-03-07 | 79 | 79 | ES | Lewis | NY | E | Adirondack Substation 115kV | NYPA | 0 | 2024-05-31
1533 | Syracuse, LLC | Syracuse Energy Storage | 2023-03-07 | 79 | 79 | ES | Onondaga | NY | C | Kamine Syracuse 115 kV substation | NM-NG | 0 | 2024-05-31
1534 | ACE DevCo NC, LLC | Westtown II Energy Storage | 2023-03-08 | 20 | 20 | ES | Orange County | NY | G | Westtown 69 kV substation | O&R | 0 | 2024-11-30
1535 | Eden Renewables | New Scotland BES 1 and 2 | 2023-03-10 | 1350 | 1350 | ES | Albany | NY | F | New Scotland 345 kV Substation | NM-NG | 0 | 2024-05-31
1537 | Nexamp Solar | Pulaski Street Storage | 2023-03-28 | 20 | 20 | ES | Suffolk | NY |  | Tuthill-Riverhead 69kV Line | LIPA | 0 | 2023-08-31
1538 | SATURN ENERGY STORAGE | Kenmore Energy Storage Project | 2023-03-20 | 20 | 20 | ES | Erie | NY | A | National Grid 115kV Line 46, 2.98 miles from Praxair (Buffalo Sewer) 115kV station and 3.21 miles from Huntley 115kV station. | NM-NG | 0 | 2023-06-30
1539 | GSI Development Corp. | Mulberry Energy Storage Project | 2023-03-30 | 20 | 20 | ES | Erie | NY | F | 34.5 kV Mulberry substation | NYSEG | 0 | 2024-03-31
1540 | Nexamp | Cayuta Add-on | 2023-03-20 | 2 | 2 | ES | Schuyler | NY | C | The POI will be located 1.78mi from Cayuta 34.5kV substation and 11.78mi from Ridge Road 230kV substation. Utilizes the same gen-tie line to deliver power to the POI at existing 34.5 kV pole located at 42.272362°, -76.731007° | NYSEG | 0 | 2023-05-31
1541 | Nexamp Solar | Stonewall Add-on | 2023-03-27 | 19.7 | 19.7 | ES | Delaware | NY | E | Fraser - Colliers 115 kV | NYSEG | 0 | 2024-09-30
1542 | Blue Sky Interconnect, LLC. | Blue Sky Interconnect 1 | 2023-03-28 | 1310 | 1310 | W | Brooklyn | NY |  | Gowanus to Farragut 345 kV Line #41 and #42 | ConEd | 0 | 2023-08-31
1543 | Blue Sky Interconnect, LLC | Blue Sky Interconnect 2 | 2023-03-28 | 2620 | 2620 | W | Brooklyn | NY |  | Gowanus to Farragut 345 kV Line #41 and #42 | ConEd | 0 | 2023-08-31
1544 | EDF renewables inc. | Sage Creek Solar | 2023-03-30 | 250 | 250 | S | Oswego | NY | C | Edic to Fitzpatrick 345 kV line | NYPA/NM-NG | 0 | 2023-07-31
1545 | Elevate Arthur Kill, LLC | Elevate Arthur Kill II, LLC | 2023-04-10 | 180 | 180 | ES | Richmond | NY | J | Fresh Kills 345 kV substation | ConEd | 0 | 2024-05-31
1546 | Port Jefferson Energy Storage, LLC | Port Jefferson Energy Storage | 2023-04-21 | 400 | 400 | ES | Suffolk | NY | K | Port Jefferson 138kV station | LIPA | 0 | 2024-05-31
1547 | South Suffolk Energy Storage | South Suffolk Energy Storage | 2023-04-21 | 100 | 100 | ES | Suffolk | NY | K | Centereach 69 kV Substation | LIPA | 0 | 2024-05-31
1548 | Holbrook Energy Storage | Holbrook II Energy Storage | 2023-04-21 | 400 | 400 | ES | Suffolk | NY | K | West Bus 138 kV Substation | LIPA | 0 | 2024-05-31
1549 | Rolling Upland Wind Farm LLC | Rolling Upland Wind Farm LLC | 2023-04-25 | 79.8 | 79.8 | W | Madison | NY | E | County-Brothertown Line 115kV | NYSEG | 0 | 2024-05-31
1550 | KCE NY 35, LLC | KCE NY 35 | 2023-04-27 | 200 | 200 | ES | Greene | NY | F | Leeds 345kV substation | NM-NG | 0 | 2024-05-31
1551 | Terra-Gen Development Company, LLC | Nine Mile Wind Energy | 2023-05-04 | 200 | 200 | W | Allegany | NY | A | Homer Hill 115kV Substation | NM-NG | 0 | 2023-06-30
1552 | Emeren US, LLC | Kettlebail Solar | 2023-05-09 | 250 | 250 | CR | Cortland | NY | C | Clarks Corner - Lafayette Station 345 kV | NM-NG | 0 | 2024-05-31
1553 | KCE NY 36, LLC | KCE NY 36 LLC | 2023-05-09 | 150 | 150 | ES | Oneida | NY | E | Yahnundasis substation 115kV | NM-NG | 0 | 2024-04-30
1554 | RWE Solar Development | Sullivan County Solar & BESS Uprate | 2023-05-10 | 60 | 60 | CR | Sullivan | NY | E | Coopers Corner - Middletown Tap 345 kV line | NYPA | 0 | 2024-05-31
1556 | North Bergen Liberty Generating | Liberty BESS | 2023-05-12 | 600 | 600 | ES | Hudson County | NJ | J | W49th St 345kV substation | ConEd | 0 | 2024-05-31
1557 | Blue Spruce Storage LLC | Blue Spruce Storage | 2023-05-18 | 245 | 245 | ES | Bronx | NY | J | Hell Gate Annex 138KV Substation | NYPA | 0 | 2024-05-31
1558 | Roma Storage LLC | Roma Storage | 2023-05-18 | 255 | 255 | ES | Queens | NY | J | Astoria East 138KV Substation | ConEd | 0 | 2024-05-31
1559 | SED NY Holdings LLC | Flat Creek Storage | 2023-05-22 | 300 | 300 | ES | Montgomery | NY | F | Edic to Princetown 345kV Line 352 | NYPA | 0 | 2024-05-31
1560 | YSG Land Holdings, LLC | Ramadi Utility | 2023-05-26 | 136 | 140 | ES | Suffolk | NY | K | 138 KV LIPA Transmission System at LIPA Existing Sills Road Substation | LIPA | 0 | 2023-07-31
1561 | Wild Ox Solar Project, LLC | Wild Ox Solar | 2023-05-31 | 131.7 | 131.7 | CR | Yates | NY | C | Eelpot Rd to Flat St 115 kV | NYSEG | 0 | 2024-05-31
1562 | Iris Bloom Solar Project | Iris Bloom Solar Project, LLC | 2023-06-02 | 151.8 | 151.8 | CR | Chautauqua | NY | A | Moon Road Sub, 115 kV | NM-NG | 0 | 2024-05-31
1563 | Middletown Energy Storage LLC | Middletown Energy Storage | 2023-06-07 | 100 | 100 | ES | Orange | NY | G | Shoemaker-Chester 138kV line #27 | O&R | 0 | 2024-05-31
1564 | Terra-Gen Development Company, LLC | Arch Energy Storage | 2023-06-07 | 250 | 250 | ES | Orange | NY | G | Rock Tavern 345kV Substation | CHGE | 0 | 2024-07-31
1565 | North River Development, LLC | North River | 2023-06-09 | 1310 | 1310 | DC | Sullivan and Queens | NY | E, J | Coopers Corner 345 kV substation (sending) and Rainey 345 kV substation (receiving) | NYSEG, ConEd | 0 | 2024-05-31
1566 | Golden Knight Solar, LLC | Golden Knight Solar | 2023-06-13 | 140 | 140 | S | St. Lawrence | NY | D | Colton to Malone Line #3 115kV | NM-NG | 0 | 2024-05-31
1567 | Anbaric Development Partners | Hera Power Link 1200 | 2023-06-14 | 0 | 0 | DC | Kings County | NY |  | Brooklyn Clean Energy Hub 345kV | ConEd | 0 | 2023-08-31
1568 | Anbaric Development Partners | Hera Power Link 1500 | 2023-06-14 | 0 | 0 | DC | Kings County | NY |  | Brooklyn Clean Energy Hub 345kV | ConEd | 0 | 2023-08-31
1569 | Appian Way Energy Partners East LLC | Meyer XF Upgrade Proposal | 2023-06-16 |  |  | AC | Livingston | NY |  | MEYER 115kV_1 BK4S, MEYER 230kV_1 BK4P | NYSEG | 0 | 2023-08-31
1570 | QMB 2 Energy Storage, LLC | QMB2 Storage II | 2023-06-20 | 200 | 200 | ES | Queens | NY | J | Corona 138kV station | ConEd | 0 | 2024-05-31
1571 | Marathon Power LLC | Marathon | 2023-06-22 | 59 | 59 | ES | Suffolk County | NY | K | Greenlawn 138kV Substation | LIPA | 0 | 2024-05-31
1572 | Empire Reserve Energy, LLC | Orchard BESS | 2023-06-23 | 80 | 80 | ES | Ulster County | NY | G | 115 kV Modena Substation | CHGE | 0 | 2024-05-31
1573 | Empire Reserve Energy, LLC | Sugarloaf BESS | 2023-06-23 | 180 | 180 | ES | Orange County | NY | G | 138kV Sugarloaf Substation | O&R | 0 | 2024-05-31
1574 | Mission Clean Energy | Cassiopeia Energy Center | 2023-06-27 | 200 | 200 | ES | Onondaga | NY | C | Geres Lock 115 kV Substation | NM-NG | 0 | 2024-05-31
1575 | NJR Clean Energy Ventures III Corporation | Barrington Solar | 2023-06-29 | 18.4 | 18.4 | S | Yates | NJ | C | Porter's corner to Dundee 34.5kV Line, Line #594 | NYSEG | 0 | 2024-11-30
1576 | ACE DevCo NC, LLC | Riptide Storage | 2023-07-06 | 200 | 200 | ES | Suffolk | NY | K | Edwards Avenue 138 kV Substation | LIPA | 0 | 2024-09-30
1577 | ACE DevCo NC, LLC | Gillie Brook Solar | 2023-07-06 | 200 | 200 | S | Onondaga | NY | C | Elbridge 115 kV Substation | NM-NG | 0 | 2024-04-30
1578 | Saturn Energy Storage | Alden Energy Storage Project | 2023-07-11 | 17.1 | 17.1 | ES | Erie | NY | A | Alden 34.5kV | NYSEG | 0 | 2023-10-31
1579 | ELP Holland Solar LLC | ELP Holland Solar | 2023-07-13 | 20 | 20 | CR | Erie | NY | A | A new 34.5kV three breaker ring bus switching station, tapped on the NYSEG?s existing 34.5 kV line #520 from NYSEG?s Cobble Hill_34.5 kV to NYSEG?s Stolle Rd_34.5 kV. 10.5 miles from Cobble Hill_34.5 kV, 17 miles to Stolle Rd_34.5 kV. | NYSEG | 0 | 2023-09-30
1580 | Terra-Gen Development Company | Alcazar Energy Storage | 2023-07-17 | 250 | 250 | ES | Ulster | NY | G | Hurley 345kV Substation | CHGE | 0 | 2024-05-31
1581 | Nexamp Solar | Mud Mill Storage | 2023-07-17 |  |  | ES | Onondaga | NY | C | Bartell 13.2kV Substation | NM-NG | 0 | 2023-07-31
1582 | Nexamp Solar | Moreau Storage | 2023-07-17 |  |  | ES | Saratoga | NY | F | Hudson Falls-McCrea St 17 Sub-Transmission 34.5kV line | NM-NG | 0 | 2023-09-30
1583 | Liberty Renewables | Agricola Wind 2 | 2023-07-21 | 79.3 | 79.3 | W | Cayuga | NY | C | 115kV line # 973 from Milliken to Wright Ave | NYSEG | 0 | 2024-05-31
1584 | PA-Hockenberry | PA-Hockenberry | 2023-07-28 | 400 | 400 | S | Jefferson | PA | A | Homer City - Pierce Brook 345 kV | NYSEG | 0 | 2024-05-31
1585 | Bear Peak Power LLC | BPP NY Lansing BESS I | 2023-07-31 | 200 | 200 | ES | Tompkins | NY | C | Milliken 115 kV Substation | NYSEG | 0 | 2024-05-31
1586 | RWE Solar Development | Basecamp BESS | 2023-07-31 | 170 | 170 | ES | Chautauqua | NY | A | Arkwright 115 kV Substation | NM-NG | 0 | 2024-05-31
1587 | RWE Solar Development | Erie Canal BESS | 2023-07-31 | 230 | 230 | ES | Niagara | NY | A | Robinson Road 115 kV | NYSEG; | 0 | 2024-05-31
1588 | NYSERDA | BR Project 2 | 2023-08-01 | 14.5 | 14.5 | CR | Tompkins | NY | C | Peruville 34.5kV Substation | NYSEG | 0 | 2024-05-31
1589 | Grid Connected Infrastructure, LLC | Lighthouse Energy Storage | 2023-08-07 | 250 | 250 | ES | Monroe | NY | A | Dunkirk to Gardenville 230 kV line #74 | NM-NG | 0 | 2024-05-31
1590 | Grid Connected Infrastructure, LLC | Icebox Energy Storage | 2023-08-07 | 202.3 | 202.3 | ES | Onondaga | NY | C | Solvay Station 57 115kV | NM-NG | 0 | 2024-05-31
1591 | Apalachin Solar LLC | Cuba Solar Farm | 2023-08-07 | 20 | 20 | CR | Allegany | NY | A | 115 kV transmission line between HOMER HILL substation and ANDOVER #157 substation | NM-NG | 0 | 2024-11-30 | 80 | 4
1592 | Jupiter Power LLC | EGC BESS II | 2023-08-16 | 200 | 200 | ES | Nassau | NY | K | East Garden City 345kV bus | NYPA | 0 | 2024-05-31
1593 | Bluewave Origination LLC | NY New Scotland 99 New Scotland South Rd Storage | 2023-08-17 | 181.4 | 181.4 | ES | Albany | NY | F | 115 kV New Scotland substation | NM-NG | 0 | 2024-05-31
1594 | Budbreak Solar, LLC | Budbreak Solar I | 2023-08-23 | 100 | 100 | S | Yates | NY | C | Greenidge to Montour Falls 115kV Line | NYSEG | 0 | 2024-05-31
1595 | Budbreak Solar, LLC | Budbreak Solar II | 2023-08-23 | 100 | 100 | S | Yates | NY | C | Greenidge Substation | NYSEG | 0 | 2023-12-31
1596 | Budbreak Storage, LLC | Budbreak Storage I | 2023-08-23 | 100 | 100 | ES | Yates | NY | C | Greenidge to Montour 115kV Line | NYSEG | 0 | 2024-05-31
1597 | Budbreak Storage, LLC | Budbreak Storage II | 2023-08-23 | 100 | 100 | ES | Yates | NY | C | Greenidge to Texas Eastern 115kV Line | NYSEG | 0 | 2024-05-31
1598 | Nexamp Solar | Green Street Storage | 2023-08-25 |  |  | ES | Cayuga | NY | C | Green Street 34.5kV | NYSEG | 0 | 2023-12-31
1599 | Braen Energy LLC | Braen Energy Storage Project | 2023-08-31 | 500 | 500 | ES | Rockland | NY | G | Con Edison Ramapo Substation | ConEd | 0 | 2023-10-31
1600 | Andrew van Doorn | NY - 74 Michigan Hill Rd - 1 | 2023-08-31 |  |  | S | Tioga | NY | C | Feeder: 4304201 34.5kv Substation: NYS-HARFORD 524 | NYSEG | 0 | 2023-09-30
1601 | Andrew van Doorn | NY - 74 Michigan Hill Rd - 2 | 2023-08-31 |  |  | S | Tioga | NY | C | Feeder: 4304201 Substation: NYS-HARFORD 524 | NYSEG | 0 | 2023-09-30
1602 | Roma Storage LLC | Roma Storage 2 | 2023-09-05 | 255 | 255 | ES | Queens | NY | J | ConEd Vernon 138KV Substation | ConEd | 0 | 2023-10-31
1603 | Blue Frost Energy Center, LLC | Blue Frost | 2023-09-05 | 400 | 400 | ES | Montgomery | NY | F | Princetown - Edic 345 kV | LS Power | 0 | 2024-05-31
1604 | Blue Frost Energy Center, LLC | Blue Frost | 2023-09-05 | 400 | 400 | ES | Montgomery | NY | E | Marcy - New Scotland 345 kV | NM-NG | 0 | 2024-05-31
1605 | Grid Connected Infrastructure, LLC | Eastwater Energy Storage | 2023-09-07 | 101.1 | 101.1 | ES | Onondaga | NY | B | Mortimer 115 kV Bus | NM-NG | 0 | 2023-11-30
1606 | Jericho Solar Park | Jericho Solar | 2023-09-11 | 100 | 100 | S | Franklin | NY | D | NYPA's Willis Sub @115kV | NYPA | 0 | 2024-05-31
1607 | North Creek Solar LLC | 117656 North Creek Solar+Storage | 2023-09-14 | 206.7 | 206.7 | CR | Herkimer | NY | E, F | Edic- Gordon Road 345 kV Line #14 | NM-NG | 0 | 2024-05-31
1608 | Consolidated Edison | Fresh Kills Battery Storage | 2023-09-20 | 11.6 | 11.6 | ES | USA | NY | J | Fresh Kills Substation | ConEd | 0 | 2023-09-30
1609 | Bear Peak Power | BPP NY Somerset BESS I | 2023-09-22 | 200 | 200 | ES | Niagara | NY | A | NYSEG KINTIGH 345 kV Station. | NYSEG | 0 | 2024-05-31
1610 | Bluepoint Wind LLC | Bluepoint Wind 1 | 2023-09-26 | 1310 | 1310 | W | Brooklyn County | NY | J | Brooklyn Clean Energy Hub 345 kV | ConEd | 0 | 2024-05-31
1611 | Bluepoint Wind LLC | Bluepoint Wind 2 | 2023-09-26 | 1310 | 1310 | W | Kings County | NY | J | Gowanus 345 kV | ConEd | 0 | 2024-05-31
1612 | Bluepoint Wind LLC | Bluepoint Wind 3B | 2023-09-26 | 1310 | 1310 | W | Richmond | NY | J | Goethals- Gowanus 345 kV underground transmission lines #25 and #26 | ConEd | 0 | 2024-02-29
1613 | Bluepoint Wind LLC | Bluepoint Wind 4 | 2023-09-26 | 1381.8 | 1381.1 | W | Nassau | NY | K | East Garden City 345 kV | NYPA | 0 | 2024-05-31
1614 | Bluepoint Wind LLC | Blue Point Wind 3A | 2023-09-26 | 1310 | 1310 | W | Richmond | NY | J | Goethals - Gowanus 345 kV underground transmission lines #25 and #26 | ConEd | 0 | 2024-05-31
1615 | KCE NY 38 LLC | KCE NY 38 | 2023-09-26 | 250 | 250 | ES | Columbia | NY | F | Transco 115kV Churchtown substation bus | Transco | 0 | 2024-07-31
1616 | YSG Community Solar | Ramadi Utility | 2023-09-27 | 140 | 140 | ES | Suffolk | NY | K | Sills Road 138kV Substation | LIPA | 0 | 2024-05-31
1617 | P&M Brick LLC | POWI Project | 2023-09-27 |  |  |  | Albany | NY |  | 345 Interconnection to Line between New Scotland and Knickerbocker 69 kV Interconnection to CHG&E 69kV Loop, | NM-NG, CHGE and NY Transco | 0 | 2024-01-31
1618 | Nexamp Solar | Cayuta Add-on | 2023-10-10 | 2 | 2 | ES | Schuyler | NY | C | Cayuta - Ridge Road 34.5 kV line, Line#501 | NYSEG | 0 | 2024-04-30
1619 | Braen Energy LLC | Braen Energy Storage Phase 1 | 2023-10-11 | 500 | 500 | ES | Rockland | NY | G | Ramapo 345 kV | ConEd | 0 | 2024-07-31
1620 | Nexamp Solar | Jerry Smith Storage | 2023-10-12 | 20 | 20 | ES | Tompkins | NY | C | Miliken- Ludlowville 34.5kV line | NYSEG | 0 | 2024-05-31
1621 | BPUS Generation Development LLC | Porter Energy Storage | 2023-10-12 | 50 | 50 | ES | Essex | NY | F | 115kV Hague Road Substation | NM-NG | 0 | 2024-05-31
1622 | BPUS Generation Development LLC | Hudson Energy Storage | 2023-10-17 | 200 | 200 | ES | Greene | NY | F | 345kV Leeds Substation | NM-NG | 0 | 2024-05-31
1623 | Emeren US, LLC | Altona Energy Storage | 2023-10-25 | 19.9 | 19.9 | ES | Clinton | DE | D | 46 kV bus at the NYSEG Flat Rock Substation | NYSEG | 0 | 2024-03-31
1624 | Emeren US, LLC | Lake City Storage | 2023-10-25 | 120 | 120 | ES | Clinton | NY | D | Lyon Mountain - Kent Falls 115 kV line | NYSEG | 0 | 2024-05-31
1625 | Emeren US, LLC | Marble River Storage | 2023-10-25 | 160 | 160 | ES | Clinton | NY | D | NYPA 230 kV Ryan Substation | NYPA | 0 | 2024-05-31
1626 | HW Power, LLC | Cross County Energy Storage | 2023-10-25 | 200 | 200 | ES | Westchester | NY | H, I | Eastview to Buchanan 345kV line | ConEd | 0 | 2024-09-30
1628 | Anbaric Development Partners | Hera Power Link 1200 | 2023-11-02 | 1200 | 1200 | DC | Kings | NY | J | Brooklyn Clean Energy Hub 345 kV | ConEd | 0 | 2024-04-30
1629 | Anbaric Development Partners | Hera Power Link 1500 | 2023-11-02 | 1500 | 1500 | DC | Kings | NY | J | Brooklyn Clean Energy Hub 345 kV | ConEd | 0 | 2024-04-30
1630 | Orange & Rockland | Suffern Quarry Data Center | 2023-11-03 |  |  |  | Rockland | NY | G | We anticipate a new substation being built on our site off of a transmission line tower that abuts our property. Additionally, we may need to tie in for redundancy to the Hillburn Area Substation | O&R | 0 | 2023-12-31
1631 | Eden Renewables | New Scotland BESS | 2023-11-03 | 1350 | 1350 | ES | Albany | NY | F | Princetown - New Scotland 345kv Line | NM-NG | 0 | 2024-01-31
1632 | Shallow Seam Energy Storage | Shallow Seam BESS | 2023-11-08 | 400 | 400 | ES | Clearfield | PA | C | Homer City to Mainesburg 345 kV Line | NYSEG | 0 | 2024-05-31
1634 | North Farm Solar LLC | North Farm Solar LLC | 2023-11-14 | 19.9 | 19.9 | S | Clinton | NY | D | Plattsburgh Substation - 115kV | NYPA | 0 | 2024-05-31
1635 | BPUS Generation Development LLC | Malone Energy Storage | 2023-11-15 | 80 | 80 | ES | Franklin | NY | D | 115kV Malone Substation | NM-NG | 0 | 2024-05-31
1636 | BPUS Generation Development LLC | Vail Energy Storage | 2023-11-15 | 35 | 35 | ES | Fulton | NY | F | 69 kV Vail Substation | NM-NG | 0 | 2024-05-31
1637 | Elevate Bethlehem LLC | Elevate Bethlehem LLC | 2023-11-16 | 120 | 120 | ES | Albany | NY | F | Albany Steam 115 kV Substation | NM-NG | 0 | 2024-05-31
1638 | ACE DevCo NC, LLC | Beck Storage | 2023-11-16 | 85 | 85 | ES | Chautauqua | NY | A | 159 Moon Rd to Hartfield | NM-NG | 0 | 2024-05-31
1639 | Genesee River Solar, LLC | Prospect Hill Road | 2023-11-20 | 20 | 20 | Solar | Orange | NY | G | 69 kV Mongaup to Cuddebackville | O & R | 0 | 2024-04-30
1640 | Genesee River Solar, LLC | Douglas Road Solar | 2023-11-21 | 20 | 20 | S | Tompkins | NY | C | Line 982 between Montour Falls and Coddington Substation 115kV | NYSEG | 0 | 2024-05-31
1641 | 174 Power Global Properties | Harlem River II | 2023-11-21 | 79.9 | 79.9 | ES | Queens | NY | J | NYPA's Hell Gate Annex 138 kV | NYPA ConEd | 0 | 2023-12-31
1642 | Light & Power Development | Queensboro B | 2023-11-28 | 1310 | 1310 | W | Queens | NY | J | Ravenswood Substation 345kV | ConEd | 0 | 2024-05-31
1643 | Community Offshore Wind, LLC | Community OSW Brooklyn CEH 3 | 2023-11-28 | 1364.5 | 1310 | W | Brooklyn | NY | J | 345 kV Brooklyn Clean Energy Hub | ConEd | 0 | 2024-05-31
1644 | ACE DevCo NC, LLC | White Springs | 2023-11-28 | 150 | 150 | S | Ontario | NY | C | Haley Road to AES Greenidge Substation 115 kV | NYSEG | 0 | 2024-11-30
1645 | Emeren US, LLC | Battle Hill Storage | 2023-11-29 | 80 | 80 | ES | St. Lawrence | NY | E | 115 kV Battle Hill Substation | NM-NG | 0 | 2024-05-31
1647 | Black Cherry Wind Power | Black Cherry Wind 1 | 2023-12-05 | 300 | 300 | W | Mckean County | PA | A | Five Mile 345 kV to Homer City 345 kV line | NM-NG | 0 | 2024-05-31
1648 | Black Cherry Wind Power | Black Cherry Wind 2 | 2023-12-05 | 300 | 300 | W | Mckean County | PA | A | Five Mile - Homer City 345 kV line | NM-NG | 0 | 2024-05-31
1649 | Black Cherry Wind Power | Black Cherry Battery | 2023-12-05 | 400 | 400 | ES | Mckean County | PA | A | Five Mile 345 kV to Homer City 345 kV line | NM-NG | 0 | 2024-05-31
1650 | Emeren US, LLC | Moose Creek 1 | 2023-12-12 | 130 | 130 | ES | Lewis | NY | E | Boonville Substation 115 kV | NM-NG | 0 | 2024-03-31
1651 | Independence BESS LLC | Independence BESS | 2023-12-14 | 200 | 200 | ES | Oswego | NY | C | Independence 345kV substation | NM-NG | 0 | 2024-02-29
1652 | ACE DevCo NC, LLC | Coopers Corner BESS | 2023-12-20 | 300 | 300 | ES | Sullivan | NY | E | Coopers Corner 345 kV Substation | NYSEG | 0 | 2024-08-31
1653 | Community Offshore Wind, LLC | Community OSW Barrett 3 | 2023-12-21 | 1310 | 1310 | W | Nassau | NY | K | Liotta 138kV | LIPA | 0 | 2024-05-31
1654 | Hydrostor USA Holdings, Inc , a subsidiary of Hydrostor Inc | Antelope Energy Storage Center | 2023-12-21 | 500 | 500 | ES | Lewis | NY | E | Adirondack 345kV substation | NYPA | 0 | 2024-05-31
1655 | ACE DevCo NC,LLC | West Laurens | 2023-12-21 | 350 | 350 | S | Ostego | NY | E | Marcy 345 kV to Coopers Corner 345 kV | NYPA | 0 | 2024-09-30
1656 | Hydrostor USA Holdings, Inc , a subsidiary of Hydrostor Inc | Chinook Energy Storage Center | 2023-12-21 | 500 | 500 | ES | Lewis | NY | E | Chases Lake 345kV substation | NM-NG | 0 | 2024-05-31
1657 | BayWa r.e. Development LLC | Lincoln Park | 2023-12-27 | 150 | 150 | ES | Ulster | NY | G | LINCOLN PARK-EAST KINGSTON 115 kV | CHGE | 0 | 2024-05-31
1658 | BayWa r.e. Development LLC | North Catskill Energy Storage | 2023-12-27 | 100 | 100 | ES | Greene | NY | G | North Catskill 69 kV | CHGE | 0 | 2024-05-31
1659 | ACE DevCo NC,LLC | Krenzer Solar | 2023-12-27 | 150 | 150 | S | Monroe | NY | B | Station 128 to Station 82 115 kV | RGE | 0 | 2024-09-30
1660 | Emeren US, LLC | Valcour Storage | 2023-12-28 | 150 | 150 | ES | Clinton | NY | D | Patnode Substation 230 kV | NYPA | 0 | 2024-05-31
1661 | Crown Point Solar LLC | Crown Point Solar | 2023-12-28 | 20 | 20 | CR | Essex | NY | F | 115kV Line #2 between Ticonderoga substation and Republic substation | NM-NG | 0 | 2024-04-30
1662 | Deerpark Energy Storage | Deerpark Energy Storage | 2024-01-09 | 50 | 50 | ES | Orange | NY | G | Cuddebackville 69 kV Substation | O&R | 0 | 2024-05-31
1663 | Saugerties Energy Storage | Saugerties Energy Storage | 2024-01-09 | 50 | 50 | ES | Ulster | NY | G | Line tap to Cements - Saugerties 69 kV circuit | CHGE | 0 | 2024-05-31
1664 | MN8 Energy Operating Company | Janes Rd Storage | 2024-01-10 | 100 | 100 | ES | Monroe | NY | B | Station 69 to Station 7 115 kV line tap | RG&E | 0 | 2024-05-31
1665 | MN8 Energy Operating Company | Buffalo Avenue Storage | 2024-01-10 | 150 | 150 | ES | Niagra | NY | A | Station 184(Olin) 115 kV | NM-NG | 0 | 2024-05-31
1666 | MN8 Energy Operating Company | River Road Storage | 2024-01-10 | 250 | 250 | ES | Erie | NY | A | Huntley 115 kV Substation | NM-NG | 0 | 2024-05-31
1668 | Genesee River Solar, LLC | State Route 26 Solar | 2024-01-17 |  |  | S | Courtland | NY | C | Line Tap of 34.5kv subtransmission line, adjacent to 115kv Line ID: 108289, connecting between NYSEG substation at Parcel ID 151.00-01-35.100 approximately 0.67 Miles to the west, and NYSEG substation Smithville Flats 144864 approximately 6.07 miles east | NYSEG | 0 | 2024-03-31
1669 | SR1 Shift Holdco I | Keshequa Creek Solar | 2024-01-17 | 20 | 20 | CR | Livingston | NY | C | Line 934 Between South Perry and Meyer 115kV | NYSEG | 0 | 2024-05-31
1673 | Abei Energy Green XIII | VINO | 2024-02-09 |  |  | S | Greene | NY | G | LAWRENCE (125110) --N.CAT 6 (125116) | CHGE | 0 | 2024-03-31
1674 | Eden Devco LP | Oakdale BESS | 2024-02-14 | 1091 | 1091 | ES | Broome | NY | C | Oakdale 345kv Substation | NYSEG | 0 | 2024-05-31
1675 | Blue Stone Renewable XXIII | HELIOS | 2024-02-16 |  |  | S | RENSSELAER | NY | F | (137563) EASTOVER - (137895) SCHAGHTICOKW | NM-NG | 0 | 2024-03-31
1676 | Eden DevCo | New Scotland BESS | 2024-02-16 | 1350 | 1350 | ES | Albany | NY | F | Princetown - New Scotland 345kv Line 361 | LS Power | 0 | 2024-05-31
1677 | Abundant Solar Power INC. | NY-5632 D Turnpike Road | 2024-02-28 | 18.05 | 18.05 | S | Stueben | NY | C | Line Tap between Bath to Benett 115 kV Substation | NYSEG | 0 | 2024-05-31
1678 | NSF Aurelius BESS | NSF Aurelius BESS, LLC | 2024-03-01 | 100 | 100 | ES | Cayuga | NY | C | NYSEG Wright Ave 115 kV Substation | NYSEG | 0 | 2024-05-31
1679 | SR1 Shift NY I | Smokey Hollow Solar | 2024-03-11 | 70 | 70 | CR | Wyoming | NY | C | South Perry to Indeck Silver Springs Energy Center 115k, Line 101 | NYSEG | 0 | 2024-05-31
1680 | USLE West Leyden Road I LLC | USLE West Leyden Road I LLC | 2024-03-29 |  |  | CR | Oneida | NY | E | Municipal Commission of Boonville 115kV bus at West Street substation, connected to the National Grid 115kV Boonville-Porter line | NM-NG, MCBoonville | 0 | 2024-05-31
1684 | Abundant Solar Power | NY-Markham Hollow Road | 2024-05-23 |  |  |  | Onondaga | NY | C | Tilden Substation, Cortland 18 substation via 115kv line. | NM-NG | 0 | 2024-05-31
1685 | energyRe Giga-Projects USA, LLC | Clean Borough Power Link #1 | 2024-05-30 |  |  |  | Richmond,Kings,Queens,West Chester | NY | J | Brooklyn Clean Energy Hub 345kV; Farragut 345kV; Goethals 345kV, Astoria Annex 345kV, Sprain Brook 345kV | CONED, NYPA | 0 | 2025-08-31
1686 | energyRe Giga-Projects USA, LLC | Clean Borough Power Link #2 | 2024-05-30 |  |  |  | New York, Richmond, Kings | NY | J | Brooklyn Clean Energy Hub 345kV; Farragut 345kV; West 49 St - East13 St 345kV lines; Goethals 345kV, | CONED | 0 | 2025-08-31
1687 | energyRe Giga-Projects USA, LLC | Clean Borough Power Link #3 | 2024-05-30 |  |  |  | Richmond, New York, Kings, Queens | NY | J | Brooklyn Clean Energy Hub 345kV; Mott Haven - Rainey 345kV lines; Rainey 345kV; Astoria West 138kV; Farragut 345kV; Astoria Annex 345kV, Goethals 345 kV | CONED, NYPA | 0 | 2025-08-31
1688 | Viridon New York Inc. | Liberty Link 1 | 2024-05-31 |  |  |  | Kings, Westchester, Richmond | NY | I, J | Brooklyn Clean Energy Hub (BCEH) 345kV, Farragut 345kV, Sprain Brook 345kV, Goethals 345kV | Con Edison | 0 | 2025-11-30
1689 | Viridon New York Inc. | Liberty Link 2 | 2024-05-31 |  |  |  | Kings, Westchester, Richmond | NY | I, J | Brooklyn Clean Energy Hub (BCEH) 345kV, Farragut 345kV, Sprain Brook 345kV, Goethals 345kV | Con Edison | 0 | 2025-11-30
1690 | Viridon New York Inc. | Liberty Link 3 | 2024-05-31 |  |  |  | Kings, New York, Richmond | NY | J | Brooklyn Clean Energy Hub (BCEH) 345kV, Farragut 345kV, W49th Street 345kV - E13th Street 345 kV lines, Goethals 345kV | Con Edison | 0 | 2025-11-30
1691 | New York Transco LLC | Energy Link New York Solution 1 | 2024-06-13 |  |  |  | Kings, Westchester, Queens, Richmond | NY | I,J | Brooklyn Clean Energy Hub 345kV; Farragut 345kV; Goethals 345kV, Astoria Annex 345kV, Sprain Brook 345kV | CONED, NYPA | 0 | 2025-10-31
1692 | New York Transco LLC | Energy Link New York Solution 2 | 2024-06-13 |  |  |  | Kings, Westchester, Queens, Richmond | NY | I, J | Brooklyn Clean Energy Hub 345 kV, Farragut 345 kV, Sprain Brook 345 kV, Astoria Annex 345 kV, Goethals 345 kV | CONED, NYPA | 0 | 2025-10-31
1693 | New York Transco LLC | Energy Link New York Solution 3 | 2024-06-13 |  |  |  | Kings, Westchester, Queens, Richmond | NY | I, J | Brooklyn Clean Energy Hub 345 kV, Farragut 345 kV, Sprain Brook 345 kV, Astoria Annex 345 kV, Goethals 345 kV, Gowanus- Goethals 345 kV lines | CONED, NYPA | 0 | 2025-10-31
1694 | New York Transco LLC | Energy Link New York Solution 4 | 2024-06-13 |  |  |  | Kings, Westchester, Queens, Richmond | NY | I, J | Brooklyn Clean Energy Hub 345 kV, Farragut 345 kV, Sprain Brook 345 kV, Astoria Annex 345 kV, Goethals 345 kV | CONED, NYPA | 0 | 2025-10-31
1695 | New York Transco LLC | Energy Link New York Solution 5 | 2024-06-13 |  |  |  | Kings, Richmond, Queens, Westchester | NY | I,J | Brooklyn Clean Energy Hub 345kV; Farragut 345kV; Goethals 345kV, Astoria Annex 345kV, Sprain Brook 345kV | CONED, NYPA | 0 | 2025-10-31
1696 | New York Transco LLC | Energy Link New York Solution 6 | 2024-06-13 |  |  |  | Kings, Westchester, Queens, Richmond | NY | I,J | Brooklyn Clean Energy Hub 345kV; Farragut 345kV; Rainey 345kV; Astoria West 138kV; Mott Haven - Rainey 345kV lines; Goethals 345kV; Astoria Annex 345kV; Sprain Brook 345kV | CONED, NYPA | 0 | 2025-10-31
1697 | New York Transco LLC | Energy Link New York Solution 7 | 2024-06-13 |  |  |  | Brooklyn & Staten Island | NY | I,J | Brooklyn Clean Energy Hub 345kV; Farragut 345kV; Rainey 345kV; Astoria West 138kV; Mott Haven - Rainey 345kV lines; Goethals 345kV, Astoria Annex 345kV; Sprain Brook 345kV; Gowanus- Goethals 345kV lines | CONED, NYPA | 0 | 2025-10-31
1698 | New York Transco LLC | Energy Link New York Solution 10 | 2024-06-13 |  |  |  | Kings, Westchester, Queens, Richmond | NY | I, J | Brooklyn Clean Energy Hub 345kV, Farragut 345kV, Sprain Brook 345kV , Astoria Annex 345kV , Goethals 345kV , Mott Haven - Rainey 345kV substations, Gowanus - Goethals 345kV , Astoria West 345 kV, Rainey 345 kV | CONED, NYPA | 0 | 2025-10-31
1699 | New York Power Authority & LS Power Grid New York Corporation I | Five Boro Energy Connect ? Mint | 2024-06-13 |  |  |  | Kings,Queens,NY,Bronx,Delaware, | NY | E, J | Brooklyn Clean Energy Hub 345kV, Farragut 345kV, Rainey 345kV, Academy 345kV, Mott Haven 345kV, Astoria Annex 345kV, Fraser 345kV | CONED, NYPA, NYSEG | 0 | 2025-07-31
1700 | New York Transco LLC | Energy Link New York Solution 8 | 2024-06-15 |  |  |  | Kings,Bronx,Queens,Westchester,Richmond | NY | I,J | Brooklyn Clean Energy Hub 345kV; Mott Haven 345kV; Rainey 345kV; Gowanus 345kV; Sprain Brook 345kV ; Goethals 345 kV | CONED | 0 | 2025-10-31
1701 | New York Transco LLC | Energy Link New York Solution 9 | 2024-06-15 |  |  |  | Kings,Bronx,Queens,Westchester,Richmond | NY | I,J | Brooklyn Clean Energy Hub 345kV; Mott Haven 345kV; Rainey 345kV; Gowanus 345kV; Sprain Brook 345kV, Goethals 345 kV | CONED | 0 | 2025-10-31
1702 | New York Power Authority & LS Power Grid New York Corporation I | Five Boro Energy Connect ? Sage | 2024-06-15 |  |  |  | Kings, Queens, New York, Bronx | NY | J | Brooklyn Clean Energy Hub 345 kV, Farragut 345 kV, Academy 345 kV, Astoria Annex 345 kV, Mott Haven 345 kV, Mott Haven - Rainey 345 kV Lines, | CONED, NYPA | 0 | 2025-07-31
1703 | New York Power Authority & LS Power Grid New York Corporation I | Five Boro Energy Connect - Ruby | 2024-06-15 |  |  |  | Kings, Queens, New York, Bronx | NY | J | Brooklyn Clean Energy Hub 345 kV, Farragut 345 kV, Rainey 345 kV, West 49 Street 345 kV, Mott Haven 345 kV, Astoria Annex 345 kV, Mott Haven - Rainey 345kV Lines | CONED, NYPA | 0 | 2025-07-31
1704 | New York Power Authority & LS Power Grid New York Corporation I | Five Boro Energy Connect - Rose | 2024-06-15 |  |  |  | Kings, Queens, New York, Bronx | NY | J | Brooklyn Clean Energy Hub 345 kV, Farragut 345 kV, Rainey 345 kV, West 49 Street 345 kV, Mott Haven 345 kV, Astoria Annex 345 kV, Mott Haven - Rainey 345kV Lines | CONED, NYPA | 0 | 2025-07-31
1705 | New York Power Authority & LS Power Grid New York Corporation I | Five Boro Energy Connect ? Olive | 2024-06-15 |  |  |  | Kings/Queens/NY/Bronx/Delaware | NY | E, J | Brooklyn Clean Energy Hub 345 kV, Farragut 345 kV, Rainey 345 kV, Academy 345 kV, Mott Haven 345 kV, Astoria Annex 345kV , Fraser, Mott Haven - Rainey 345kV Lines, | CONED, NYPA, NYSEG | 0 | 2025-07-31
1706 | New York Power Authority & LS Power Grid New York Corporation I | Five Boro Energy Connect ? Kelly | 2024-06-17 |  |  |  | Kings, Queens, New York, Bronx | NY | J | Brooklyn Clean Energy Hub 345kV, Farragut 345kV, Rainey 345kV, Academy 345kV, Mott Haven 345 kV, Astoria Annex 345kV, Tremont 345kV, Mott Haven - Rainey 345kV Lines, | Con Edison, NYPA | 0 | 2025-07-31
1707 | New York Power Authority & LS Power Grid New York Corporation I | Five Boro Energy Connect ? Hazel | 2024-06-17 |  |  |  | Kings/Queens/NY/Bronx/Delaware | NY | E, J | Brooklyn Clean Energy Hub 345kV, Farragut 345kV, Rainey 345kV, Academy 345kV, Mott Haven 345kV, Astoria Annex 345kV, Fraser 345kV, Mott Haven - Rainey 345kV Lines, | Con Edison, NYPA, NYSEG | 0 | 2025-07-31
1708 | New York Power Authority & LS Power Grid New York Corporation I | Five Boro Energy Connect ? Navy | 2024-06-17 |  |  |  | Kings,Queens,Bronx,Richmond,Westchester | NY | I, J | Brooklyn Clean Energy Hub 345kV, Farragut 345kV, Astoria Annex 345kV, Mott Haven 345kV, Rainey 345kV, Dunwoodie 345kV, Sprain Brook 345kV, Gowanus - Goethals 345kV Lines, Mott Haven - Rainey 345kV Lines, Gowanus 345 kV | Con Edison, NYPA | 0 | 2025-07-31
1709 | New York Power Authority & LS Power Grid New York Corporation I | Five Boro Energy Connect ? Royal | 2024-06-17 |  |  |  | Kings,Queens,Bronx,Richmond,Westchester, | NY | J | Brooklyn Clean Energy Hub 345kV, Farragut 345kV, Rainey 345kV, Astoria Annex 345kV, Mott Haven 345kV, Tremont 345kV, W49th St 345kV, Gowanus - Goethals 345kV Lines, Mott Haven - Rainey 345kV Lines, Gowanus 345 kV | Con Edison, NYPA | 0 | 2025-07-31
1710 | New York Power Authority & LS Power Grid New York Corporation I | Five Boro Energy Connect ? Golden | 2024-06-17 |  |  |  | Kings,Queens,NY,Bronx,Westchester,Delawa | NY | E, I, J | Brooklyn Clean Energy Hub 345kV, Farragut 345kV, Rainey 345kV, Academy 345kV, Astoria Annex 345kV, Mott Haven 345kV, Dunwoodie 345kV, Fraser 345kV, Vernon 138kV, Mott Haven - Rainey 345kV Lines | Con Edison, NYPA, NYSEG, | 0 | 2025-07-31
1711 | New York Power Authority & LS Power Grid New York Corporation I | Five Boro Energy Connect ? Honey | 2024-06-17 |  |  |  | Kings,Queens,NY,Bronx,Delaware | NY | E, J | Brooklyn Clean Energy Hub 345kV, Farragut 345kV, Rainey 345kV, Academy 345kV, Astoria Annex 345kV, Mott Haven 345kV, Vernon 138kV, Fraser 345kV, | Con Edison, NYPA, NYSEG, | 0 | 2025-07-31
1712 | New York Power Authority & LS Power Grid New York Corporation I | Five Boro Energy Connect ? Cobalt | 2024-06-17 |  |  |  | Kings,Queens,NY,Bronx,Richmond,Delaware | NY | E, J | Brooklyn Clean Energy Hub 345kV, Farragut 345kV, Rainey 345kV, Academy 345kV, Astoria Annex 345kV, Mott Haven 345kV, Gowanus - Goethals 345kV Lines, Mott Haven - Rainey 345kV Lines, Fraser 345kV, Gowanus 345 | Con Edison, NYPA, NYSEG | 0 | 2025-07-31
1727 | Empire Generating Co., LLC | Wet Compression | 2025-02-18 |  |  |  | Rensselaer | NY | F | Reynolds Road Line 5 through existing on-site infrastructure and metering. | NM-NG | 0
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY
NY

## Cluster Projects-Withdrawn
Cluster Projects - Withdrawn, note all queue projects in this list may not have been validated
Queue Pos. | Owner/Developer | Project Name | Date of IR | SP (MW) | WP (MW) | Type/ Fuel | County | State | Z | Interconnection Point | Utility | S | Last Update
C24-001 | Vineyard Mid-Atlantic LLC | Vineyard Mid-Atlantic East | 2024-08-01 | 1187 | 1187 | W | Nassau | NY | K | Ruland Rd 345kV | NYPA | 0 | 2025-01-31
C24-002 | Atlantic Shores Offshore Wind Bight LLC | ATLANTIC SHORES OFFSHORE WIND PROJECT 4 | 2024-08-01 | 1400 | 1400 | W | Kings | NY | J | BROOKLYN CLEAN ENERGY HUB NORTH 345kV | ConEd | 0 | 2025-02-28
C24-006 | ATLANTIC SHORES OFFSHORE WIND BIGHT LLC | ATLANTIC SHORES OFFSHORE WIND PROJECT 5 | 2024-08-01 | 1400 | 1400 | W | Suffolk | NY | K | RULAND ROAD 345 kV | NYPA | 0 | 2025-03-31
C24-007 | KCE NY 38, LLC | KCE NY 32 | 2024-08-01 | 250 | 250 | ES | Columbia | NY | F | Churchtown 115kV Substation | Transco | 0 | 2024-09-30
C24-009 | Vineyard Northeast LLC | Vineyard Northeast | 2024-08-01 | 884 | 884 | W | Nassau County | NY | K | Ruland Rd 345kV substation. | NYPA | 0 | 2024-12-31
C24-011 | ATLANTIC SHORES OFFSHORE WIND LLC | ATLANTIC SHORES OFFSHORE WIND PROJECT 3 | 2024-08-01 | 1400 | 1400 | W | kings county | NY | J | BROOKLYN CLEAN ENERGY HUB 345kV | ConEd | 0 | 2025-02-28
C24-012 | Empire Wind 2 LLC | EI Melville | 2024-08-01 | 1240 | 1240 | W | Offshore | NY | K | Ruland Road 345 kV | NYPA | 0 | 2025-03-31
C24-014 | Roma Storage | Roma Storage | 2024-08-01 | 150 | 150 | ES | Queens | NY | J | Astoria East 138 kV | ConEd | 0 | 2025-02-28
C24-015 | Good Ole 77 Energy LLC | Seventy Seven Project | 2024-08-01 | 100 | 100 | S | Wyoming | NY | C | High Sheldon 230 kV | NYSEG | 0 | 2025-11-30
C24-016 | Salt Rush Wind Energy LLC | Salt Rush Wind Energy | 2024-08-01 | 150 | 150 | W | Warsaw | NY | C | Stony Creek 230 kV | NYSEG | 0 | 2025-11-30
C24-017 | Community Offshore Wind, LLC | COSW Barrett | 2024-08-01 | 1310 | 1310 | W | Suffolk | NY | K | Barrett 345kV | Transco | 0 | 2024-11-30
C24-018 | Granite Twinleaf Solar Energy LLC | Twinleaf Solar | 2024-08-01 | 75 | 75 | S | Croghan | NY | E | Taylorville to North Carthage 115 kV ckt 1 | NM-NG | 0 | 2025-03-31
C24-019 | American Wintergreen Solar Energy LLC | American Wintergreen | 2024-08-01 | 75 | 75 | S | Canajoharie | NY | F | Marshville - Clinton 115 kV, Line #12 | NM-NG | 0 | 2024-12-31
C24-020 | Verona Solar II LLC | Verona Solar II | 2024-08-01 | 115 | 115 | S | Verona | NY | E | Oneida - Rome 115kV, Line 1 | NM-NG | 0 | 2025-01-31
C24-022 | Community Offshore Wind, LLC | COSW BCEH | 2024-08-01 | 1310 | 1310 | W | Kings | NY | J | Brooklyn Clean Energy Hub 345 kV | ConEd | 0 | 2025-01-31
C24-023 | KCE NY 26, LLC | KCE NY 26 | 2024-08-01 | 60 | 60 | ES | Suffolk | NY | K | Jamesport - Peconic 69kV | LIPA | 0 | 2025-02-28
C24-024 | Verona Solar | Verona Solar I | 2024-08-01 | 199 | 199 | S | Durhamville | NY | C | Clay - Edic 345kV, Line 2-15 | NYPA | 0 | 2025-11-30
C24-025 | KCE NY 32, LLC | KCE NY 32 | 2024-08-01 | 79 | 79 | ES | Orange | NY | G | Cuddebackville 69 kV | O&R | 0 | 2025-01-31
C24-026 | Taproot Solar LLC | Taproot Solar | 2024-08-01 | 185 | 185 | S | Montgomery | NY | F | Edic - Princetown 345 kV, Line #351 | LSPower | 0 | 2025-11-30
C24-027 | EDF Renewables Development, Inc. | Moraine Solar Energy Center | 2024-08-01 | 93.55 | 93.55 | S | Allegany | NY | C | 115kV Moraine Road Substation | NYSEG | 0 | 2025-01-31
C24-028 | EDF Renewables Development, Inc. | Tracy Solar Energy Center | 2024-08-01 | 119 | 119 | S | Jefferson | NY | E | Thousand Island - Lyme 115kV | NM-NG | 0 | 2025-01-31
C24-029 | Bull Run Solar LLC | Bull Run Solar | 2024-08-01 | 100 | 100 | S | Clinton | NY | D | 230 kV Ellenburg Substation | NYPA | 0 | 2025-01-31
C24-030 | Bluepoint Wind LLC | Bluepoint Wind 2 | 2024-08-01 | 1310 | 1310 | W | Nassau | NY | K | East Garden City 345 kV | NYPA | 0 | 2025-03-31
C24-031 | BayWa r.e Projects LLC. | Crossbuck Energy Storage, LLC | 2024-08-01 | 100 | 100 | ES | Greene | NY | G | Coxsackie 69 kV substation | CHGE | 0 | 2025-10-31
C24-034 | Kalmia Storage, LLC | Kalmia Storage, LLC | 2024-08-01 | 50 | 50 | ES | Suffolk | NY | K | Holtsville 69 kV | LIPA | 0 | 2025-10-31
C24-035 | Dix Hills Storage, LLC | Dix Hills Storage, LLC | 2024-08-01 | 100 | 100 | ES | Suffolk | NY | K | Ruland-Pilgrim 138kV | LIPA | 0 | 2024-12-31
C24-036 | Queensboro Development, LLC | Queensboro Renewable Express Circuit A | 2024-08-01 | 1310 | 1310 | W | Queens | NY | J | Rainey East 345kV | ConEd | 0 | 2024-11-30
C24-037 | Northland Power U.S. Projects Inc | Gunns Corners Solar | 2024-08-01 | 140 | 140 | S | Jefferson | NY | E | Thousand Islands-Coffeen Line 4: Lyme Tap 115kV | NM-NG | 0 | 2025-02-28
C24-038 | Prologis Energy LLC | Long Island City Energy Storage | 2024-08-01 | 68 | 68 | ES | Queens | NY | J | Queensbridge 138kV | ConEd | 0 | 2025-10-31
C24-039 | Golden Knight Solar, LLC | Golden Knight Solar | 2024-08-01 | 140 | 140 | S | St. Lawrence | NY | D | Colton - Malone Line 3 115 kV | NM-NG | 0 | 2025-10-31
C24-040 | EDF Renewables Development, Inc. | Rich Road Solar Energy Center | 2024-08-01 | 240 | 240 | CR | St. lawrence | NY | E | Haverstock - Adirondack 345KV line HA2 | NYPA | 0 | 2025-01-31
C24-041 | BayWa r.e. Solar Projects LLC | Vestal Battery Storage | 2024-08-01 | 110 | 110 | ES | Broome | NY | C | Castle Garden - Jones 115 kV | NYSEG | 0 | 2025-01-31
C24-043 | EDF Renewables Development, Inc. | Rosalen Solar Energy Center | 2024-08-01 | 200 | 200 | CR | Wayne | NY | B | 345kV PM2 between Pannell-Clay | NYPA | 0 | 2025-02-28
C24-044 | BayWa r.e Projects LLC. | Honey Bee Battery Storage, LLC | 2024-08-01 | 199 | 199 | ES | Rensselaer | NY | F | North Troy -Hoosick Line 5 115 kV | NM-NG | 0 | 2025-06-30
C24-045 | New Scotland BESS | New Scotland BESS | 2024-08-01 | 1350 | 1350 | ES | Albany | NY | F | New Scotland 345kV | NM-NG | 0 | 2025-03-31
C24-046 | Oakdale BESS | Robinson Hill BESS | 2024-08-01 | 1117 | 1091 | ES | Broome | NY | C | Oakdale 345kv Substation | NYSEG | 0 | 2025-03-31
C24-049 | BayWa r.e Projects LLC. | North Catskill DG LLC | 2024-08-01 | 100 | 100 | ES | Greene | NY | G | North Catskill -Churchtown 115 kV | CHGE | 0 | 2025-10-31
C24-050 | Grateful Storage, LLC | Grateful Storage, LLC | 2024-08-01 | 250 | 250 | ES | Orange | NY | G | Rock Tavern - Roseton 345 kV | CHGE | 0 | 2025-08-31
C24-051 | Liberty Renewables Inc. | Russet Ridge Wind | 2024-08-01 | 119.1 | 119.1 | W | Steuben | NY | C | Meyer-Eelpot 115 kV | NYSEG | 0 | 2025-02-28
C24-053 | Liberty Renewables Inc. | Agricola Wind | 2024-08-01 | 97 | 97 | W | Cayuga | NY | C | Milliken - Wright Ave 115kV Line 973 | NYSEG | 0 | 2024-10-31
C24-054 | Liberty Renewables Inc. | Hoffman Falls Wind | 2024-08-01 | 72 | 72 | W | Madison | NY | C | Fenner - Shippy Rd 115 kV | NM-NG | 0 | 2025-01-31
C24-055 | Sketch Book Storage 1, LLC | Sketch Book Storage | 2024-08-01 | 100 | 100 | ES | Columbia | NY | F | 115 kV Falls Park Substation | NYSEG | 0 | 2025-02-28
C24-056 | BGTF US Development Holdings LLC | Naples Energy Storage | 2024-08-01 | 120 | 120 | ES | Steuben | NY | C | Eelpot Road 115 kV | NYSEG | 0 | 2025-02-28
C24-057 | Empire Reserve Energy, LLC | Highland BESS | 2024-08-01 | 79 | 79 | ES | Orange County | NY | G | Sugarloaf 138kV | O&R | 0 | 2025-11-30
C24-058 | Slide Energy Center, LLC | Slide Energy Center | 2024-08-01 | 79 | 79 | ES | Ulster | NY | G | Hurley Ave 115 kV substation | CHGE | 0 | 2025-08-31
C24-059 | Empire Reserve Energy, LLC | Orchard BESS | 2024-08-01 | 100 | 100 | ES | Ulster County | NY | G | 115kV Modena Substation | CHGE | 0 | 2025-11-30
C24-063 | Empire Reserve Energy, LLC | Heritage BESS | 2024-08-01 | 125 | 125 | ES | Orange County | NY | G | Shoemaker - Sugarloaf 138kV | O&R | 0 | 2025-08-31
C24-065 | Hanwha Q CELLS USA Corp. | Maplehurst Energy Park | 2024-08-01 | 75 | 75 | CR | Chautauqua | NY | A | Dunkirk - Falconer 115kV Line #160 | NM-NG | 0 | 2025-09-30
C24-067 | Empire Reserve Energy, LLC | Gala Grove BESS | 2024-08-01 | 125 | 125 | ES | Suffolk | NY | K | Wildwood - Riverhead 138 kV | LIPA | 0 | 2025-11-30
C24-068 | Holbrook Energy Storage, LLC | Holbrook Energy Storage II | 2024-08-01 | 260 | 260 | ES | Suffolk | NY | K | West Bus 138kV | LIPA | 0 | 2024-12-31
C24-069 | South Suffolk Energy Storage, LLC | South Suffolk Storage | 2024-08-01 | 77 | 77 | ES | Suffolk | NY | K | Centereach 69kV | LIPA | 0 | 2024-12-31
C24-070 | Port Jefferson Energy Storage, LLC | Port Jefferson Energy Storage | 2024-08-01 | 168 | 168 | ES | Suffolk | NY | K | Port Jefferson 138kV | LIPA | 0 | 2024-12-31
C24-071 | Sweetwaters Energy Center LLC | Sweetwaters Energy Center | 2024-08-01 | 125 | 125 | ES | Suffolk | NY | K | Kings Substation 138kV | LIPA | 0 | 2025-09-30
C24-073 | GCI Icebox Energy Storage, LLC | Icebox Energy Storage | 2024-08-02 | 50 | 50 | ES | Onondaga | NY | C | Solvay Station 34.5 kV | NM-NG | 0 | 2025-05-31
C24-075 | Shore Rd ESS LLC | Oyster shore Energy storage | 2024-08-02 | 275 | 275 | ES | Nassau | NY | K | Shore Road 138 kV | LIPA | 0 | 2025-01-31
C24-076 | SUNXI LLC | Springbrooke | 2024-08-05 | 82.8 | 82.8 | S | Genesee | NY | B | Southeast Batavia-Golah Line 119 | NM-NG | 0 | 2025-04-30
C24-077 | Abundant Solar Power Inc. | NY-5632 Turnpike Rd | 2024-08-06 | 19.94 | 19.94 | S | Steuben | NY | C | Bath - Howard 115 kV Line | NYSEG | 0 | 2025-02-28
C24-078 | Abundant Solar Power Inc. | NY-MARKHAM HOLLOW RD | 2024-08-07 | 19.98 | 19.98 | S | Onondaga | NY | C | Tilden-Cortland Line 18 | NM-NG | 0 | 2025-06-30
C24-080 | the New York Power Authority | Greenwood Heights Energy Storage | 2024-08-08 | 130 | 130 | ES | Kings | NY | J | Greenwood 138kV Substation | ConEd | 0 | 2025-09-30
C24-082 | Terra-Gen Development, LLC | Arch 1 | 2024-08-09 | 100 | 100 | ES | Orange | NY |  | Rock Tavern 345kV Substation (South position)- ROCK TAV - Bus#: 125001 |  | 0
C24-083 | Terra-Gen Development, LLC | Arch 2 | 2024-08-09 | 150 | 150 | ES | Orange | NY |  | Rock Tavern 345kV Substation (South position)- ROCK TAV - Bus#: 125001 |  | 0
C24-084 | Terra-Gen Development, LLC | Arch 3 | 2024-08-09 | 100 | 100 | ES | Orange | NY |  | Rock Tavern 345kV Substation (North position)- ROCK TAV - Bus#: 125001 |  | 0
C24-086 | Terra-Gen Development Company, LLC | Arch 1 | 2024-08-09 | 100 | 100 | ES | Orange | NY | G | Rock Tavern 345kV Substation | CHGE | 0 | 2025-10-31
C24-087 | Terra-Gen Development Company, LLC | Arch 2 | 2024-08-09 | 150 | 150 | ES | Orange | NY | G | Rock Tavern 345kV Substation | CHGE | 0 | 2025-10-31
C24-089 | Braen Energy LLC | Braen Energy Storage Phase 1 | 2024-08-14 | 500 | 500 | ES | Rockland | NY | G | Ramapo 345kV Substation | ConEd | 0 | 2025-02-28
C24-090 | Quantum DPI group | Cuba Solar Facility | 2024-08-15 | 22 | 22 | CR | Allegany | NY | A | HOMER HILL - ANDOVER 115kV line #157 | NM-NG | 0 | 2025-11-30
C24-091 | BPP NY Somerset BESS I LLC | BPP NY Somerset BESS I LLC | 2024-08-19 | 199.5 | 199.5 | ES | Niagara | NY | A | Kintigh 345kV | NYSEG | 0 | 2025-05-31
C24-092 | Quantum DPI Group | Scio Solar Facility | 2024-08-20 | 50 | 50 | CR | Allegany | NY | A | Homer Hill to ANDOVER 115kV Line 157 | NM-NG | 0 | 2025-11-30
C24-095 | Westerlo Solar LLC | Westerlo Solar | 2024-08-23 | 40 | 40 | CR | Albany | NY | G | Westerlo-New Baltimore 69kV Line #NW | CHGE | 0 | 2025-02-28
C24-096 | ACE DevCo NC,LLC | Coopers Corner BESS | 2024-08-23 | 300 | 300 | ES | Sullivan | NY | E | Coopers Corner 345 kV Substation | NYSEG | 0 | 2025-01-31
C24-099 | Crown Point Solar LLC | Crown Point Solar | 2024-08-26 | 20 | 20 | CR | Essex | NY | F | Ticonderoga to Republic 115Kv Line 2 | NM-NG | 0 | 2025-02-28
C24-100 | RWE Solar Development, LLC | Erie Canal BESS | 2024-08-26 | 230 | 230 | ES | Niagara | NY | A | Robinson Road 115 kV | NYSEG | 0 | 2024-09-30
C24-101 | MN8 Energy Development Company LLC | Halo Energy Storage | 2024-08-26 | 100 | 100 | ES | Wyoming County | NY | C | South Perry Substation 230 kV | NYSEG | 0 | 2025-02-28
C24-102 | ELP Rotterdam Solar LLC | ELP Rotterdam Solar | 2024-08-27 | 35 | 35 | CR | Schenectady | NY | F | Rotterdam-Maple Ave 115kV Line 10. | NM-NG | 0 | 2025-02-28
C24-103 | Bath Solar LLC | Bath Solar | 2024-08-27 | 185 | 185 | CR | Steuben | NY | C | Avoca 230 kV - Stoney Ridge 230 kV Line #68 | NYSEG | 0 | 2025-02-28
C24-105 | ELP Clay Storage LLC | ELP Clay Storage | 2024-08-28 | 199 | 199 | ES | Onondaga | NY | C | Clay-Lighthouse Hill 115kV, Line #7 | NM-NG | 0 | 2025-02-28
C24-106 | Granby Storage LLC | Granby Storage | 2024-08-28 | 150 | 150 | ES | Oswego | NY | C | South Oswego to Curtis Street 115kV Line 10 | NM-NG | 0 | 2025-05-31
C24-107 | Boralex US Development LLC | NY125B - Two Rivers Solar | 2024-08-29 | 200 | 200 | S | St. Lawrence | NY | D | Haverstock to Willis 345kV HW2 Line | NYPA | 0 | 2025-01-31
C24-109 | Falls Park Energy Storage Project, LLC | Falls Park Energy Storage | 2024-08-29 | 100 | 100 | ES | Columbia | NY | F | FALLS PARK 115 kV | NYSEG | 0 | 2025-10-31
C24-110 | Fort Covington Solar LLC | NY125A - Fort Covington Solar | 2024-08-29 | 250 | 250 | S | Franklin | NY | D | 345 kV line HW1 from Haverstock to Willis | NYPA | 0 | 2025-01-31
C24-112 | Boralex US Development LLC | NY48 - Diamond Solar | 2024-08-29 | 60 | 60 | S | Herkimer | NY | E | Porter - Valley 115 kV, Line #4 | NM-NG | 0 | 2025-02-28
C24-113 | Newport Deerfield Solar LLC | NY115 - Newport Solar | 2024-08-29 | 130 | 130 | S | Oneida | NY | E | Porter - Deerfield 115 kV, Line #9 | NM-NG | 0 | 2025-02-28
C24-114 | Foothills Solar LLC | NY128 - Foothills Solar | 2024-08-29 | 40 | 40 | S | Fulton | NY | F | Mayfield to Northville 69kV line #8 | NM-NG | 0 | 2024-12-31
C24-115 | Iris Bloom Solar Project, LLC | Iris Bloom Solar | 2024-08-30 | 150 | 150 | CR | Chautauqua | NY | A | Moon Road Sub 115 kV | NM-NG | 0 | 2025-10-31
C24-116 | Wild Ox Solar Project, LLC | Wild Ox Solar | 2024-08-30 | 130 | 130 | CR | Yates | NY | C | Eelpot Road to Flat St Substations 115 kV line | NYSEG | 0 | 2024-10-31
C24-117 | RWE Solar Development, LLC | Town Line Solar CSR Phase I | 2024-08-30 | 240 | 240 | HSR | Sullivan | NY | E | Coopers Corner to Middletown Tap 345 kV Line | NYPA | 0 | 2024-09-30
C24-118 | Rutland Center Solar 1, LLC | Rutland Center Solar | 2024-08-30 | 75 | 75 | S | Jefferson County | NY | E | Staplin Creek Station 115 kV | NM-NG | 0 | 2025-08-31
C24-119 | North Bergen Liberty Generating LLC | Liberty BESS | 2024-09-02 | 1200 | 1200 | ES | Hudson | NJ | J | West 49th Street 345 kV Substation | ConEd | 0
C24-120 | Field Day Solar Project, LLC | Field Day Solar | 2024-09-03 | 300 | 300 | CR | Oneida | NY | E | Boonville to Rome 115KV Line 3 | NM-NG | 0 | 2025-10-31
C24-121 | Beacon Harbor Solar Project, LLC | Beacon Harbor Solar | 2024-09-03 | 195 | 195 | CR | Jefferson | NY | E | Thousand Islands-Coffeen Line 4: Lyme Tap 115kV | NM-NG | 0 | 2025-10-31
C24-122-002 | BGTF US Development Holdings LLC | Capital Energy Storage | 2024-09-04 | 190 | 190 | ES | Albany | NY | E | Marcy to New Scotland 345 kV line 18 | NM-NG | 0 | 2025-02-28
C24-123 | ACE DevCo NC,LLC | Wallkill Energy Storage | 2024-09-05 | 100 | 100 | ES | Ulster | NY | G | Ohioville 115kV Substation | CHGE | 0 | 2025-01-31
C24-124 | BGTF US Development Holdings LLC | Dunkirk Energy Storage | 2024-09-05 | 100 | 100 | ES | Chautauqua | NY | A | Dunkirk-Laona Line 162 115kV | NM-NG | 0 | 2025-02-28
C24-126 | BGTF US Development Holdings LLC | Pine Grove Energy Storage | 2024-09-05 | 150 | 150 | ES | Lewis | NY | E | Austin Road 345 kV | NM-NG | 0 | 2025-02-28
C24-127 | BGTF US Development Holdings LLC | Crescent Energy Storage | 2024-09-05 | 75 | 75 | ES | Chautauqua | NY | A | Moons Road to Falconer 115 kV Line 175 | NM-NG | 0 | 2025-09-30
C24-128 | Winner Solar, LLC | Winner Solar | 2024-09-05 | 120 | 120 | S | Clinton County | PA | C | Homer City - Mainesburg 345kV Line | NYSEG | 0 | 2025-02-28
C24-132 | HW Power, LLC | Cross County Energy Storage | 2024-09-06 | 130 | 130 | ES | Westchester | NY | I | Eastview to Buchanan, 345 kV | ConEd | 0 | 2025-04-30
C24-133 | MN8 Energy Development Company LLC | Janes Road Energy Storage | 2024-09-06 | 100 | 100 | ES | Monroe | NY | B | Station 7 - Station 69 115 kV Line #917 | RG&E | 0 | 2024-11-30
C24-134 | MN8 Energy Development Company LLC | River Road Energy Storage | 2024-09-06 | 247.5 | 247.5 | ES | Erie | NY | A | Packard-Huntley 230 kV Line#78 | NM-NG | 0 | 2025-02-28
C24-136 | Emeren US, LLC | Marble River Storage | 2024-09-06 | 160 | 160 | ES | Clinton | NY | D | Ryan 230kV Substation | NYPA | 0 | 2025-09-30
C24-137 | ACE DevCo NC, LLC | Gillie Brook | 2024-09-06 | 60 | 60 | S | Onondaga | NY | C | Elbridge 115 kV Substation | NM-NG | 0 | 2025-06-30
C24-140 | Emeren US, LLC | Altona Energy Storage | 2024-09-09 | 40 | 40 | ES | Clinton | NY | D | Flatrock 46kV | NYSEG | 0 | 2025-01-31
C24-141 | Upper Falls Solar | Upper Falls Solar | 2024-09-09 | 46 | 46 | CR | Wyoming | NY | B | Station 162 - Station 180 115kV, Line 907 | RGE | 0 | 2024-09-30
C24-142 | Nexus Renewables U.S. Inc. | Beaver Kill Storage | 2024-09-09 | 12 | 12 | ES | Ulster | NY | G | CHGE SAUGERTIES Substation, Feeder 3003, 13.8kV |  | 0 | 2024-10-31
C24-143 | Smokey Hollow Solar | Smokey Hollow Solar | 2024-09-09 | 70 | 70 | CR | Wyoming | NY | B | Line 907 Substation 162 and Houghton Substation (S180). 115kV | RGE | 0 | 2024-10-31
C24-144 | Granada Solar, LLC | Blue Line Solar | 2024-09-09 | 70 | 70 | S | St Lawrence County | NY | E | Battle Hill - Corning 115 kV (National Grid Line #4) | NM-NG | 0 | 2024-12-31
C24-145 | ACE DevCo NC,LLC | Riptide Storage | 2024-09-10 | 200 | 200 | ES | Suffolk | NY | K | Edwards Ave 138kV Substation | LIPA | 0 | 2025-03-31
C24-146 | BGTF US Development Holdings LLC | Amsterdam Energy Storage | 2024-09-10 | 100 | 100 | ES | Montgomery | NY | F | Stoner to Amsterdam 115 kV Line | NM-NG | 0 | 2024-09-30
C24-147 | Emeren US, LLC | Battle Hill Storage | 2024-09-10 | 79.9 | 79.9 | ES | St. Lawrence | NY | E | Battle Hill 115kV | NM-NG | 0 | 2025-05-31
C24-149 | Manchester Solar NY LLC | Manchester Solar | 2024-09-11 | 20 | 20 | S | Ontario | NY | C | Station 127(Hooks Rd)-Elbridge Line 7 115kV | NM-NG | 0 | 2025-10-31
C24-150 | Kingbird Solar NY LLC | Kingbird Solar | 2024-09-11 | 20 | 20 | S | Chautauqua | NY | A | Gardenville to Dunkirk 115kV Line - Line #142 | NM-NG | 0 | 2025-10-31
C24-151 | ACE DevCo NC, LLC | Richardson BESS | 2024-09-11 | 100 | 100 | ES | Lawrence | NY | E | McIntyre 115 kV Substation | NM-NG | 0 | 2025-01-31
C24-152 | Antelope Energy Storage LLC | Antelope Energy Storage Center | 2024-09-11 | 500 | 500 | ES | Croghan | NY | E | Adirondack 345kV substation | NYPA | 0 | 2025-09-30
C24-153 | Hydrostor USA Holdings, Inc , a subsidiary of Hydrostor Inc | Chinook Energy Storage Center | 2024-09-11 | 500 | 500 | ES | Lewis | NY | E | Adirondack - Austin Road Line #13, 345kV line. | NM-NG | 0 | 2025-03-31
C24-155 | Zenobe Stockton LLC | Zenobe Stockton LLC | 2024-09-12 | 100 | 100 | ES | Chautauqua | NY | A | Moon Road 115kV | NM-NG | 0 | 2025-07-31
C24-156 | Granada Solar, LLC | Grass River Solar | 2024-09-12 | 80 | 80 | S | St. Lawrence County | NY | E | N. Ogdensburg - Alcoa 115 kV Line (Line # 13) | NM-NG | 0 | 2025-11-30
C24-157 | Granada Solar, LLC | Fuller Storage | 2024-09-12 | 20 | 20 | ES | Orange | NY | G | East Walden 1115 kV Substation | CHGE | 0 | 2025-04-30
C24-158 | KCE NY 27, LLC | KCE NY 27 | 2024-09-12 | 50 | 50 | ES | Suffolk | NY | K | Quogue - Tiana 69kV | LIPA | 0 | 2025-02-28
C24-159 | Viridity Energy Solutions | Cruiser BESS | 2024-09-12 | 100 | 100 | ES | Suffolk County | NY | K | Pulaski 69kV | LIPA | 0 | 2025-07-31
C24-160 | Viridity Energy Solutions | Mustang BESS | 2024-09-12 | 95 | 95 | ES | Orange County | NY | G | Hartley 69 kV | O&R | 0 | 2025-08-31
C24-161 | Emeren US, LLC | Cedar Lake Storage | 2024-09-13 | 300 | 300 | ES | St. Lawrence | NY | E | Moses (Haverstock) - Adirondack 345 kV line | NYPA | 0 | 2024-10-31
C24-164 | KCE NY 28, LLC | KCE NY 28 | 2024-09-16 | 45 | 45 | ES | Suffolk | NY | K | Riverhead - Tuthill 69kV | LIPA | 0 | 2025-02-28
C24-166 | KCE NY 41, LLC | KCE NY 41 | 2024-09-16 | 100 | 100 | ES | Suffolk | NY | K | West Yaphank 69kV Substation | LIPA | 0 | 2024-10-31
C24-168 | Northland Power U.S. Projects Inc | Ball Hill BESS | 2024-09-17 | 250 | 250 | ES | Chautauqua | NY | A | Stebbins Road 230kV | NM-NG | 0 | 2025-02-28
C24-169 | Endurance Power LLC | Endurance | 2024-09-17 | 75 | 75 | ES | Nassau | NY | K | Jericho- New Cassel 69kV | LIPA | 0 | 2025-09-30
C24-170 | Zenith Power LLC | Zenith BESS | 2024-09-17 | 165 | 165 | ES | Onondaga | NY | C | Geres Lock-Tilden Line 16 115kV | NM-NG | 0 | 2025-01-31
C24-171 | Fieldstone Power Station LLC | North Chelsea (Fieldstone Power Station) | 2024-09-17 | 150 | 150 | ES | Dutchess | NY | G | North Chelsea 115 kV Substation | CHGE | 0 | 2025-02-28
C24-172 | Blue Stone Renewable XVI | BRESH HYBRID | 2024-09-17 | 59.2 | 59.2 | CR | Ulster | NY | G | BOULEVARD 69 kV SUBSTATION | CHGE | 0 | 2025-03-31
C24-174 | Bay State Wind | Long Island Wind | 2024-09-17 | 1310 | 1310 | W | Suffolk | NY | K | Ruland Road 345kV | NYPA | 0 | 2025-03-31
C24-177 | Jericho Power Station LLC | Commack(Jericho Power Station) | 2024-09-17 | 35 | 35 | ES | Suffolk | NY | K | Commack 69 kV Substation | LIPA | 0 | 2025-11-30
C24-179 | Silverline Energy Center, LLC | Silverline Energy Center | 2024-09-17 | 150 | 150 | CR | Tompkins | NY | C | Miliken to Etna Line #974 115 kV line | NYSEG | 0 | 2025-07-31
C24-180 | East Setauket Energy Storage, LLC | East Setauket Storage | 2024-09-17 | 125 | 125 | ES | Suffolk | NY | K | Holbrook - North Shore Beach 138kV line | LIPA | 0 | 2024-11-30
C24-181 | Setauket energy Storage, LLC | Setauket Storage | 2024-09-17 | 65.3 | 65.3 | ES | Setauket | NY | K | Terryville - Port Jefferson 69kV | LIPA | 0 | 2025-03-31
C24-184 | Tabletop Solar NY LLC | Tabletop Solar | 2024-09-18 | 80 | 80 | S | Fort Plain | NY | F | Clinton Tap off the Inghams-Meco-Marshviille Line 15 115kV | NM-NG | 0 | 2025-09-30
C24-185 | Flat Creek Solar NY LLC | Flat Creek Solar | 2024-09-18 | 200 | 200 | S | Montgomery | NY | F | Edic to Princetown 345kV Line 352 | NYPA | 0 | 2024-10-31
C24-186 | Blue Stone Renewable III | THOR SOLAR | 2024-09-18 | 36.6 | 36.6 | S | RENSSELAER | NY | F | Schodack - Falls Park 115kV | Transco | 0 | 2025-11-30
C24-187 | Flat Creek Solar NY LLC | Flat Creek Solar II | 2024-09-18 | 100 | 100 | S | Montgomery | NY | F | Edic to Princetown 345kV Line #352 | NYPA | 0 | 2024-10-31
C24-188 | Wheelhouse Solar Energy Center, LLC | Wheelhouse Solar Energy Center | 2024-09-18 | 350 | 350 | CR | Herkimer, Oswego | NY | F | Edic 345 kV to Princetown 345 kV circuit #352 | NYPA | 0 | 2025-02-28
C24-191 | Zenobe Rotterdam LLC | Zenobe Rotterdam LLC | 2024-09-19 | 100 | 100 | ES | Schenectady | NY | F | Rotterdam 115kV | NM-NG | 0 | 2025-07-31
C24-192 | Blue Frost Energy Center, LLC | Blue Frost Solar | 2024-09-19 | 200 | 200 | S | Montgomery | NY | E | Marcy - New Scotland 345kV line 18 | NM-NG | 0 | 2024-12-31
C24-193 | North Seneca Solar Project, LLC | North Seneca | 2024-09-19 | 90 | 90 | S | Seneca | NY | C | Hooks Road - Elbridge 115kV line #7 | NM-NG | 0 | 2024-12-31
C24-194 | Sapphire Sun Energy Center, LLC | Sapphire Sun | 2024-09-19 | 120 | 120 | S | Allegany | NY | A | Homer Hill-Andover Line 157 115kV line | NM-NG | 0 | 2024-12-31
C24-195 | Sweet Valley Energy Center, LLC | Sweet Valley Solar | 2024-09-19 | 100 | 100 | S | Genesee | NY | B | Dysinger - Station 255 345kV, line #1 | NYPA | 0 | 2024-12-31
C24-196 | Yellow Feather Energy Center, LLC | Yellow Feather | 2024-09-19 | 90 | 90 | S | Fulton and Montgomery | NY | F | Inghams-Stoner Line 9 115kV | NM-NG | 0 | 2024-12-31
C24-197 | Sweet Valley Energy Center, LLC | Sweet Valley Storage | 2024-09-19 | 200 | 200 | ES | Genesee | NY | B | Dysinger - Station 255 (Henrietta) #1 345kV line | NYPA | 0 | 2024-12-31
C24-198 | Blue Frost Energy Center, LLC | Blue Frost Storage I | 2024-09-19 | 200 | 200 | ES | Montgomery | NY | E | Marcy - New Scotland 345kV line | NM-NG | 0 | 2024-11-30
C24-199 | Blue Frost Energy Center, LLC | Blue Frost Storage II | 2024-09-19 | 200 | 200 | ES | Montgomery | NY | E | Edic - Gordon Road 345kV Line 14 | NM-NG | 0 | 2024-11-30
C24-200 | BGTF US Development Holdings LLC | Hickory Hill Energy Storage | 2024-09-19 | 100 | 100 | ES | Montgomery | NY | F | Inghams-Meco-Marshville Line 15/12 115kV | NM-NG | 0 | 2024-12-31
C24-201 | Yellow Barn Solar, LLC | Yellow Barn Solar | 2024-09-19 | 160 | 160 | S | Tompkins | NY | C | Milliken - Etna 115 kV #975 | NYSEG | 0 | 2024-12-31
C24-203 | Renew Development HoldCo LLC | Mill Run BESS | 2024-09-19 | 260 | 260 | ES | Onondaga | NY | C | Elbridge - Geres Lock 115kV 18 & 19 lines | NM-NG | 0 | 2025-02-28
C24-204 | Declaration Energy Center, LLC | Declaration Energy Center | 2024-09-19 | 550 | 550 | CR | Seneca | NY | B | Clay - Pannell (Station 122), Line #1 345 kV line | NYPA | 0 | 2025-07-31
C24-206 | York Run Solar, LLC | York Run Solar, LLC | 2024-09-19 | 90 | 90 | S | Chautauqua | NY | A | Falconer - Warren 115 kV line #171 | NM-NG | 0 | 2024-10-31
C24-208 | Independence BESS LLC | Independence BESS | 2024-09-19 | 200 | 200 | ES | Oswego | NY | C | Independence 345 KV | NM-NG | 0 | 2025-02-28
C24-209 | ACE DevCo NC LLC | Sidecar | 2024-09-20 | 50 | 50 | S | Tioga | NY | C | S Owego Substation to Goudey Substation tap line 115 kV | NYSEG | 0 | 2025-02-28
C24-210 | The Commodore Storage, LLC | Marcy BESS 1 | 2024-09-20 | 120 | 120 | ES | Oneida | NY | E | Volney - Marcy | NYPA | 0 | 2024-10-31
C24-211 | The Commodore Storage, LLC | Marcy BESS 2 | 2024-09-20 | 195 | 195 | ES | Oneida | NY | E | Volney - Marcy 345 kV | NM-NG | 0 | 2025-07-31
C24-212 | The Commodore Storage, LLC | Marcy BESS 3 | 2024-09-20 | 435 | 435 | ES | Oneida | NY | E | Marcy-Volney 345 kV Line | NYPA | 0 | 2024-10-31
C24-213 | Zenobe Lancaster LLC | Zenobe Lancaster LLC | 2024-09-20 | 100 | 100 | ES | Erie | NY | A | Pavement 115kV Substation | NYSEG | 0 | 2025-07-31
C24-214 | Mulberry Energy Storage 1, LLC | Mulberry Energy Storage | 2024-09-20 | 130 | 130 | ES | Saratoga County | NY | F | Luther Forest-Eastover Rd 115kV Line 308 | NM-NG | 0 | 2025-05-31
C24-215 | Mount Hope Stand Alone Storage 1, LLC | Mount Hope Storage | 2024-09-20 | 50 | 50 | ES | Orange County | NY | G | Cuddebackville-Shoemaker stations 69 kV Line #13 | O&R | 0 | 2025-09-30
C24-216 | Zenobe Harmony LLC | Zenobe Harmony LLC | 2024-09-20 | 100 | 100 | ES | Chautauqua | NY | A | Dunkirk-Falconer Line 160 115kV | NM-NG | 0 | 2025-06-30
C24-218 | Poplar Energy Center | Poplar Energy Center, LLC | 2024-09-20 | 60 | 60 | ES | Suffolk | NY | K | Riverhead - Tuthill 69kV | LIPA | 0 | 2025-11-30
C24-219 | ACE DevCo NC, LLC | Krenzer | 2024-09-20 | 150 | 150 | S | Monroe | NY | B | Station 128 to Station 82 115 kV | RG&E | 0 | 2025-01-31
C24-220 | ACE DevCo NC, LLC | Blue Mountain BESS | 2024-09-20 | 100 | 100 | ES | Ulster | NY | G | Saugerties to Hurley 69 kV Line | CHGE | 0 | 2024-11-30
C24-221-003 | Snowy Knoll Wind Project, LLC | Snowy Knoll Wind Project | 2024-09-20 | 350 | 350 | CW | Oneida | NY | E | Edic - Fraser 345kV | NYPA | 0 | 2025-02-28
C24-222 | Knickerbocker Energy Storage Project, LLC | Knickerbocker Energy Storage | 2024-09-20 | 300 | 300 | ES | Schodack Landing | NY | F | KNICKERBOCKER 345 kV | Transco | 0 | 2025-10-31
C24-223 | Mission Clean Energy Devco, LLC | Queen Energy Center | 2024-09-20 | 140 | 140 | ES | Tompkins | NY | C | Etna - Milliken 115 kV line | NYSEG | 0 | 2025-10-31
C24-226 | Lucy?s Energy Reserve LLC | South Dow (Lucy's Energy Reserve) | 2024-09-20 | 175 | 175 | ES | Chautauqua | NY | A | Falconer 115kV Substation | NM-NG | 0 | 2025-03-31
C24-227 | Lucy?s Energy Reserve LLC | South Dow 2 (Lucy's Energy Reserve 2) | 2024-09-20 | 125 | 125 | ES | Chautauqua | NY | A | Falconer-South Dow Line 154 115kV | NM-NG | 0 | 2025-07-31
C24-228 | Winterberry Wind LLC | Winterberry Wind | 2024-09-21 | 100 | 100 | W | Bradford | PA | C | Hillside to East Towanda 230 kV | NYSEG | 0 | 2024-10-31
C24-229 | Buttercup Wind LLC | Buttercup Wind | 2024-09-21 | 49.9 | 49.9 | W | Chautauqua | NY | A | Dunkirk-Falconer Line 160 115kV | NM-NG | 0 | 2025-02-28
C24-231 | Azalea Wind LLC | Azalea Wind 1 | 2024-09-21 | 50 | 50 | W | Schuyler | NY | C | Montour Falls Substation to Coddington Road Substation 115kV | NYSEG | 0 | 2024-10-31
C24-232 | Azalea Wind LLC | Azalea Wind 2 | 2024-09-21 | 50 | 50 | W | Schuyler | NY | C | Montour Falls Substation (#130830) to Coddington Road Substation 115kV (#130787) | NYSEG | 0 | 2024-10-31
C24-234 | RWE Solar Development, LLC | Zulu BESS | 2024-09-22 | 70 | 70 | ES | Orange | NY | G | Bethlehem Road 115kV | CHGE | 0 | 2025-09-30
C24-235 | RWE Clean Energy Development, LLC | Champlain Solar Uprate | 2024-09-22 | 30 | 30 | S | Washington | NY | F | Mohican - Whitehall 115 kV Line 13 | NM-NG | 0 | 2025-09-30
C24-236 | RWE Clean Energy Development, LLC | Champlain Solar | 2024-09-22 | 90 | 90 | S | Washington | NY | F | Mohican - Whitehall 115 kV Line 13 | NM-NG | 0 | 2025-09-30
C24-237 | SBMT Energy Center, LLC | SBMT Energy Center, LLC | 2024-09-23 | 160 | 160 | ES | Kings County | NY | J | 345kV Gowanus Substation | ConEd | 0 | 2025-11-30
C24-239 | Zenobe Americas Inc. | Zenobe Wellsville LLC | 2024-09-23 | 100 | 100 | ES | Allegany | NY | A | Homer Hill - Andover 115 kV Line 157 | NM-NG | 0 | 2025-05-31
C24-240 | ACE DevCo NC LLC | Moran 2 | 2024-09-23 | 100 | 100 | S | Fulton | NY | F | Inghams-Stoner Line 9 115 kV | NM-NG | 0 | 2024-11-30
C24-241 | Genesee River Solar | Soper Road Solar | 2024-09-23 | 20 | 20 | S | Wyoming | NY | C | Perry Center Substation | NYSEG | 0 | 2024-10-31
C24-242 | Genesee River Solar | State Route 26 Solar | 2024-09-23 | 20 | 20 | S | Cortland | NY | C | Willet - Tarbell 34.5kV | NYSEG | 0 | 2024-11-30
C24-243 | Genesee River Solar | Gravel Road Solar | 2024-09-23 | 128 | 128 | S | Seneca | NY | C | Lovers Lane-Elbridge Line 6 & Station 168-Elbridge Line 2 | NM-NG | 0 | 2024-10-31
C24-244 | New York Power Authority | Utica Solar PV Project | 2024-09-23 | 20 | 20 | S | Oneida | NY | E | Deerfield - Schuyler 46kV Line 22 | NM-NG | 0 | 2025-10-31
C24-245 | PA-Hockenberry LLC | PA-Hockenberry LLC | 2024-09-23 | 400 | 400 | S | Jefferson | PA | A | Tap on Homer City to Pierce Brook 345kV line | NYSEG | 0 | 2025-04-30
C24-246 | ACE DevCo NC LLC | Block Perch solar | 2024-09-23 | 85 | 85 | S | Chautauqua | NY | A | Moon Road-Falconer Line 175 115V | NM-NG | 0 | 2025-02-28
C24-247 | Nexamp Solar LLC | Jerry Smith Energy Storage | 2024-09-23 | 34.9 | 34.9 | ES | Tompkins | NY | C | Milliken to Ludlowville 34.5kV Line #522 | NYSEG | 0 | 2025-02-28
C24-248 | Dove Energy Storage | Dove Energy Storage | 2024-09-23 | 79.9 | 79.9 | ES | Montgomery | NY | F | St. Johnsville - Marshville, Line id #11 (CLCPA rebuild), 115 kV, | NM-NG | 0 | 2025-02-28
C24-249 | Empire Solar LLC | Empire | 2024-09-23 | 60 | 60 | S | Chautaqua | NY | A | Dunkirk-South Ripley Line 68 230kV | NM-NG | 0 | 2025-02-28
C24-250 | Honey Ridge Solar 1, LLC | Honey Ridge Solar | 2024-09-23 | 100 | 100 | S | Jefferson | NY | E | Black River - North Carthage 115 kV, Line #1 | NM-NG | 0 | 2025-02-28
C24-251 | Vidal Blanc Storage 1, LLC | Vidal Blanc Storage | 2024-09-23 | 100 | 100 | ES | Ulster | NY | G | Galeville-Kerhonkson 115kV | CHGE | 0 | 2025-09-30
C24-252 | Nexamp Solar LLC | Maple City Energy Storage | 2024-09-23 | 79 | 79 | ES | Steuben | NY | C | Bennett Substation 115kV | NYSEG | 0 | 2025-03-31
C24-254 | Genovia Storage LLC | Genovia Storage | 2024-09-23 | 300 | 300 | ES | Basom | NY | B | 345 kV Line 1 QP580_POI2 (# 148773) Substation to Q721_POI (#149914) Substation | NYPA | 0 | 2024-12-31
C24-255 | Saltgrass Storage LLC | Saltgrass Storage | 2024-09-23 | 50 | 50 | ES | Nassau | NY | K | Line 33-222 and 33-317 LIPA 33kV | LIPA | 0 | 2025-03-31
C24-256 | Springer Storage | Springer Storage | 2024-09-23 | 79.9 | 79.9 | ES | Washington | NY | F | Mohican-Whitehall Line 13 115kV | NM-NG | 0 | 2025-02-28
C24-257 | Grapevine Storage LLC | Grapevine Storage | 2024-09-23 | 200 | 200 | ES | Fredonia | NY | A | Gardenville-Dunkirk Line 74 230kV | NM-NG | 0 | 2025-03-31
C24-258 | Genovia Storage LLC | Genovia Storage | 2024-09-23 | 300 | 300 | ES | Basom | NY | B | QP580_POI2 - Q721_POI 345 kV Line | NYPA | 0 | 2024-12-31
C24-259 | Nexamp Solar LLC | Christmas Tree | 2024-09-23 | 25 | 25 | CR | Schuyler | NY | C | Cayuta to Ridge Road 34.5 kV Line# 501 | NYSEG | 0 | 2025-02-28
C24-260 | ACE DevCo NC, LLC | West Laurens | 2024-09-23 | 350 | 350 | S | Otsego | NY | E | Marcy to Coopers Corner - 345 kV | NYPA | 0 | 2024-11-30
C24-261 | Beacon Wind LLC | EI Steinway 1 | 2024-09-23 | 1300 | 1300 | W | Queens | NY | J | Mott Haven to Rainey 345kV line tap | ConEd | 0 | 2025-02-28
C24-262 | Beacon Wind | EI Steinway 1.1 | 2024-09-23 | 1600 | 1600 | W | Queens | NY | J | Mott Haven - Rainey 345kV circuits | ConEd | 0 | 2024-10-31
C24-263 | Jefferson Energy Storage | Jefferson Energy Storage | 2024-09-23 | 100 | 100 | ES | Lewis | NY | E | Austin Rd. - Edic #11, 345 kV | NM-NG | 0 | 2025-02-28
C24-264 | Berry Farm Storage 1, LLC | Berry Farm Storage | 2024-09-23 | 120 | 120 | ES | Chautauqua | NY | A | L160 115 kV line (Dunkirk and Falconer) | NM-NG | 0 | 2025-02-28
C24-265 | Calpine Mid-Atlantic Development, LLC | Bethpage Battery Storage Project | 2024-09-23 | 44 | 44 | ES | Nassau | NY | K | LIPA Grumann B 69 kV Substation | LIPA | 0 | 2025-09-30
C24-266 | Summersweet Energy Center, LLC | Summersweet Energy Center | 2024-09-23 | 199 | 199 | ES | Orange county | NY | G | Sugarloaf - Sterling Forest 138 kV | O&R | 0 | 2025-10-31
C24-267 | ACE DevCo NC LLC | Beck Storage | 2024-09-23 | 85 | 85 | ES | Chautauqua | NY | A | Moon Road-Hartfield Line 159 115 kV | NM-NG | 0 | 2024-12-31
C24-268 | Arnold Energy Storage | Arnold Energy Storage | 2024-09-24 | 79.9 | 79.9 | ES | St. Lawrence | NY | D | Colton - Malone 115kV Line 3 | NM-NG | 0 | 2025-02-28
C24-269 | Stonewall Solar LLC | Stonewall Solar | 2024-09-24 | 145 | 145 | CR | Delaware | NY | E | Fraser Tap-Colliers 115 kV line #951 | NYSEG | 0 | 2025-02-28
C24-270 | Bassett Energy Storage | Bassett Energy Storage | 2024-09-24 | 79.9 | 79.9 | ES | Steuben | NY | C | Spencer Hill 115 kV Substation | NYSEG | 0 | 2026-04-30
C24-271 | Sturgeon Pool BESS, LLC | Margarita Storage | 2024-09-24 | 110 | 110 | ES | Ulster | NY | G | Sturgeon Pool 115 kV | CHGE | 0 | 2024-11-30
C24-272 | Kerhonkson, LLC | File Cabinet Storage | 2024-09-24 | 100 | 100 | ES | Ulster | NY | G | GALEVILLE to KERHONKS 115 kV | CHGE | 0 | 2024-10-31
C24-273 | National Grid Generation LLC | Glenwood Power Station Battery Energy Storage System (BESS) | 2024-09-24 | 50 | 50 | ES | Nassau | NY | K | LIPA Glenwood 69kV Substation | LIPA | 0 | 2025-10-31
C24-274 | National Grid Generation LLC | Southampton Power Station Battery Energy Storage System (BESS) | 2024-09-24 | 31.96 | 31.96 | ES | Suffolk | NY | K | Southampton 69kV | LIPA | 0 | 2025-10-31
C24-275 | Springville BESS, LLC | Warrior Storage | 2024-09-24 | 100 | 100 | ES | Erie | NY | A | Gardenville to Arcade 115 kV Line 151 | NM-NG | 0 | 2024-10-31
C24-276 | Cobble Hill BESS, LLC | Dime Energy Storage | 2024-09-24 | 150 | 150 | ES | Erie | NY | A | Cobble Hill 115 kV Substation | NYSEG | 0 | 2024-10-31
C24-277 | Tierken Storage 1, LLC | Tierken Storage | 2024-09-24 | 50 | 50 | ES | Rensselaer | NY | F | Reynolds Road - Greenbush 115 kV Line #9 | NM-NG | 0 | 2024-11-30
C24-278 | New York Power Authority | Sullivan-Woodbourne Solar Project | 2024-09-24 | 100 | 100 | S | Sullivan | NY | E | Mountaindale - Woodbourne 115 kV line | NYSEG | 0 | 2025-03-31
C24-279 | New York Power Authority | Eastern Solar PV Project | 2024-09-24 | 30 | 30 | S | Ulster | NY | G | Kerhonkson to Honks Falls 69kV line | CHGE | 0 | 2025-03-31
C24-280 | National Grid Generation LLC | Wading River Power Station Battery Energy Storage System (BESS) | 2024-09-24 | 50 | 50 | ES | Suffolk | NY | K | Wading River 138 kV Substation | LIPA | 0 | 2025-10-31
C24-282 | 82 Shingle House Rd, LLC | Millwood Energy Storage | 2024-09-25 | 273.5 | 273.5 | ES | Westchester | NY | H | Millwood West 345kV | ConEd | 0 | 2025-10-31
C24-285 | ACE DevCo NC,LLC | North Watertown BESS | 2024-09-26 | 200 | 200 | ES | Jefferson | NY | E | 115kV North Watertown Substation | NM-NG | 0 | 2025-02-28
C24-286 | Mastodon Storage 1, LLC | Mastodon Storage | 2024-09-26 | 80 | 80 | ES | Orange | NY | G | Rock Tavern - Sugarloaf 115 kV Line SL | Transco | 0 | 2024-10-31
C24-287 | ACE DevCo NC,LLC | Harrigan Solar | 2024-09-26 | 100 | 100 | S | Franklin | NY | D | Willis to Lyon Mountain Line Tap 115 kV | NYSEG | 0 | 2025-01-31
C24-288 | ACE DevCo NC, LLC | Mossy Bank Solar | 2024-09-27 | 200 | 200 | S | Steuben | NY | C | Prattsburgh Wind farm to Stony Ridge Line Tap 230 kV | NYSEG | 0 | 2025-02-28
C24-289 | Genovia Storage LLC | Genovia Storage | 2024-09-27 | 300 | 300 | ES | Genesee | NY | B | 345 kV Line 1 QP580_POI2 Substation to Q721_POI Substation | NYPA | 0 | 2025-03-31
C24-290 | ACE DevCo NC,LLC | Cazenovia Solar | 2024-09-27 | 80 | 80 | S | Madison | NY | C | Fenner-Shippey Line 3 115 kV | NM-NG | 0 | 2025-01-31
C24-291 | BayWa r.e. Solar Projects, LLC | Pine Hill Energy Storage | 2024-09-27 | 120 | 120 | ES | Ulster | NY | E | Belleayre 115 kV | NYSEG | 0 | 2024-12-31
C24-292 | BayWa r.e Projects LLC. | Loganberry Energy Storage, LLC | 2024-09-27 | 150 | 150 | ES | Chautauqua | NY | A | Dunkirk to Falconer Line 160 115 kV | NM-NG | 0 | 2025-06-30
C24-294 | Birch Whistler, LLC | Birch-Whistler | 2024-09-27 | 100 | 100 | W | Delaware | NY | E | Line Tap Edic to Fraser Line, 345kV | NYPA | 0 | 2025-02-28
C24-295 | ACE DevCo NC,LLC | Winn Hill Solar | 2024-09-27 | 60 | 60 | S | Broome | NY | C | Kattelville to Jennison Line Tap 115 kV | NYSEG | 0 | 2025-01-31
C24-296 | ACE DevCo NC LLC | Medina Solar | 2024-09-27 | 100 | 100 | S | Orleans | NY | B | Connection on Brunner to Sour Springs 115 kV Line 118 | NM-NG | 0 | 2025-01-31
C24-297 | Deer River Wind, LLC | Deer River Wind | 2024-09-27 | 100 | 100 | W | Lewis | NY | E | Black River-Lighthouse Hill Line 5 115kV | NM-NG | 0 | 2025-10-31
C24-298 | Black Cherry Wind Power, LLC | Black Cherry Wind 1 | 2024-09-29 | 350 | 350 | W | Cameron & McKean | PA | A | Homer City - Piercebrook 345kV | NYSEG | 0 | 2025-02-28
C24-299 | Black Cherry Wind Power, LLC | Black Cherry Wind 2 | 2024-09-29 | 150 | 150 | W | Cameron, Elk, and McKean | PA | A | Homer City - Piercebrook 345kV | NYSEG | 0 | 2025-02-28
C24-302 | McMullen Pond LLC | NY Oswego 200 Erie St Storage | 2024-09-30 | 142 | 142 | ES | Oswego | NY | C | Oswego - S Oswego 115kV circuit 3 | NM-NG | 0 | 2025-02-28
C24-303 | Bergholtz Creek LLC | NY Niagara Falls 5800 Niagara Falls Blvd Storage | 2024-09-30 | 161 | 161 | ES | Niagara | NY | A | Packard - Huntley Line 77 230kV | NM-NG | 0 | 2025-07-31
C24-305 | BW Solar Holding Inc. | St. Regis River LLC | 2024-10-01 | 58.5 | 58.5 | CR | St. Lawrence | NY |  | Lawrence - A [136781] to Sugar Island [136806] 115kV line. |  | 0 | 2024-10-31
C24-306 | Oriden | Lock 26 BESS | 2024-10-01 | 50 | 50 | ES | Wayne | NY | C | Clyde 115kV | RG&E | 0 | 2025-02-28
C24-307 | Oriden | Marshville BESS | 2024-10-01 | 50 | 50 | ES | Montgomery | NY | F | Marshville 115kV Substation | NM-NG | 0 | 2025-03-31
C24-308 | Oriden | Chazy Lake BESS | 2024-10-01 | 50 | 50 | ES | Clinton | NY | D | Patnode 230kV | NYPA | 0 | 2025-03-31
C24-309 | Black Cherry Wind Power, LLC | Black Cherry BESS | 2024-10-01 | 400 | 400 | ES | McKean | PA | A | Homer City to Piercebrook 345kV Line | NYSEG | 0 | 2025-02-28
C24-310 | Fresh Air Energy II, LLC | Lincoln ESC | 2024-10-02 | 100 | 100 | ES | Suffolk | NY | K | Holbrook - Bohemia Ckt#1, 69kV | LIPA | 0 | 2025-03-31
C24-311 | Fresh Air Energy II, LLC | Moffitt ESC | 2024-10-02 | 100 | 100 | ES | Suffolk | NY | K | Watson (Bus #129777) - Brightwaters (Bus #129723) Ckt #2, 69 kV | LIPA | 0 | 2024-10-31
C24-312 | BW Solar Holding Inc. | St. Regis | 2024-10-02 | 58.5 | 58.5 | CR | St. Lawrence | NY | E | Dennison-Colton #5 115 kV Line. | NM-NG | 0 | 2025-11-30
C24-313 | New York Power Authority | Southport Solar PV Project | 2024-10-02 | 42 | 42 | S | Chemung | NY | C | Caton Ave. 115 kV Station | NYSEG | 0 | 2025-03-31
C24-314 | GB II New York | Bethlehem Energy Center Uprate | 2024-10-03 | 875 | 926.1 | CC | Albany | NY | F | Albany Steam Station, Jawside of 6177, 6277, 6377, 6477 Disconnects | NM-NG | 0 | 2024-12-31
C24-315 | Arthur Kill Power | Arthur Kill Upgrade | 2024-10-03 | 369.9 | 369.9 | ST | Richmond | NY |  | Fresh Kills Substation between breakers BT1-4 and BT1-3 |  | 0 | 2024-12-31
C24-316 | DOVER PLAINS ENERGY PROPERTIES LLC | DOVER NY BESS | 2024-10-03 | 1000 | 1000 | ES | DUTCHESS | NY | G | Pleasant Valley-Cricket Valley 345kV | ConEd | 0 | 2025-03-31
C24-319 | Ditch Creek Solar LLC | Ditch Creek | 2024-10-05 | 199.5 | 199.5 | CR | Madison | NY | C | CLAY to EDIC 345 kV Line #15 Circuit #2 | NYPA | 0 | 2025-02-28
C24-320 | Nexamp Solar LLC | Boonville Standalone Storage | 2024-10-05 | 79 | 79 | ES | Lewis | NY | E | 115kV Boonville-Waters Road Line#8 (proposed as Boonville-Taylorville Line#6) | NM-NG | 0 | 2025-10-31
C24-322 | Rolling Upland Wind Farm LLC | Rolling Upland Wind Farm | 2024-10-07 | 79.8 | 79.8 | W | Madison and Oneida County | NY | E | County Line-Brothertown 115kV | NYSEG | 0 | 2025-10-31
C24-323 | Echo Lake Solar LLC | Echo Lake | 2024-10-07 | 79.9 | 79.9 | CR | Oneida | NY | E | 115 kV Boonville Village - Porter Line #1, Circuit #1 | NM-NG | 0 | 2025-02-28
C24-325 | Origis Development LLC | Van Buren Storage | 2024-10-08 | 150 | 150 | ES | Chautauqua | NY | A | Dunkirk to Falconer 115kV Line 160 | NM-NG | 0 | 2025-10-31
C24-327 | North Creek Solar LLC | North Creek | 2024-10-08 | 199.5 | 199.5 | CR | Oneida | NY | E | EDIC to GORDON ROAD 345kV, Line #14 | NM-NG | 0 | 2025-02-28
C24-328 | SWEB Development USA LLC | WEB Worth Wind | 2024-10-08 | 63.6 | 68.61 | W | Jefferson | NY | E | 115 kV Middle Road - Lighthouse Hill Line 6 | NM-NG | 0 | 2024-10-31
C24-329 | SWEB Development USA LLC | WEB Addison Solar | 2024-10-08 | 100 | 100 | S | Steuben | NY | C | Stony Ridge - Sullivan Park 115 kV | NYSEG | 0 | 2025-03-31
C24-330 | Granada Solar, LLC | Pine Hill Storage | 2024-10-08 | 120 | 120 | ES | Chautauqua | NY | A | Homer Hill - Falconer 115kV, Line #154 | NM-NG | 0 | 2024-12-31
C24-332 | Granada Solar, LLC | Stoner Trail Storage | 2024-10-09 | 100 | 100 | ES | Fulton | NY | F | Inghams-Stoner 115kV line 9 and Meco-Maple Ave 115kV line 22 | NM-NG | 0 | 2025-10-31
C24-334 | the New York Power Authority | Flynn Energy Storage | 2024-10-09 | 170 | 170 | ES | Suffolk | NY | K | West Bus - 138kV | LIPA | 0 | 2025-03-31
C24-335 | PA-Fritz Kiln LLC | PA-Fritz Kiln LLC | 2024-10-09 | 300 | 300 | S | Elk | PA | A | Tap on Homer City - Pierce Rd 345kV line | NYSEG | 0 | 2025-04-30
C24-339 | Capital Region Energy Storage LLC | Chateauguay BESS | 2024-10-10 | 200 | 200 | ES | Greene | NY | F | Leeds 345kV | NM-NG | 0 | 2025-01-31
C24-340 | Solitude Solar, LLC d/b/a U.S. Light Energy | USLE West Leyden Road I LLC | 2024-10-10 | 19.6 | 19.6 | CR | Oneida | NY | E | Weststreet Boonville 115kV | MC Boonville | 0 | 2024-12-31
C24-342 | Beacon Wind Land LLC | AGRE Storage | 2024-10-11 | 125 | 125 | ES | Queens | NY | J | Astoria West 138 kV | ConEd | 0 | 2025-06-30
C24-343 | Avangrid Renewables, LLC | AGR NY1 | 2024-10-11 | 1152 | 1229 | W | Nassau | NY | K | East Garden City 345 kV | NYPA | 0 | 2025-03-31
C24-344 | Deerpark Energy Storage, LLC | Deerpark Energy Storage | 2024-10-11 | 50 | 50 | ES | Orange | NY | G | Cuddebackville 69kV Substation | O&R | 0 | 2025-11-30
C24-345 | Athens Energy Storage LLC | Athens Energy Storage | 2024-10-12 | 300 | 300 | ES | Greene | NY | G | Tap of Leeds-Van Wagner 345kV line 92 | NM-NG | 0 | 2024-11-30
C24-346 | Middletown Energy Storage LLC | Middletown Energy Storage | 2024-10-12 | 100 | 100 | ES | Orange | NY | G | Shoemaker-Chester 138kV, Line 27 | O&R | 0 | 2025-01-31
C24-347 | Hodson Energy Little Falls LLC | Little Falls Solar | 2024-10-14 | 78 | 78 | S | Herkimer | NY | E | Watkins Road-Inghams Line 2 115kV | NM-NG | 0 | 2025-03-31
C24-348 | ConnectGen Cayuga County LLC | Harvest Hills Solar | 2024-10-14 | 200 | 200 | S | Cayuga | NY | C | Wright Avenue - Milliken 115kV Line 973 | NYSEG | 0 | 2025-11-30
C24-349-005 | RIC Development, LLC | Richland III Solar | 2024-10-14 | 79.9 | 79.9 | S | Oswego | NY | C | Indeck Oswego - Tar Hill Line 2 115kV | NM-NG | 0 | 2025-02-28
C24-350 | Hickling Storage, LLC | Hickling Storage, LLC | 2024-10-14 | 90 | 90 | ES | Steuben | NY | C | 115kV Hickling Substation | NYSEG | 0 | 2025-10-31
C24-351 | CEDAR HOLDCO LLC | Green Isles Energy Storage | 2024-10-15 | 400 | 400 | ES | Suffolk | NY | K | Brookhaven - Sills Rd 138 kV Circuit #1 | LIPA | 0 | 2025-03-31
C24-353 | Caithness LI Energy Storage LLC | CLIES 70 MW | 2024-10-15 | 70 | 70 | ES | Suffolk | NY | K | Sills Road 138kV substation | LIPA | 0 | 2024-10-31
C24-354 | AMBAR POWER HOLDCO LLC | Bayonne Energy Storage I | 2024-10-15 | 600 | 600 | ES | Hudson | NJ | J | Gowanus 345 kV | ConEd | 0 | 2025-02-28
C24-355 | AMBAR POWER HOLDCO LLC | Bayonne Energy Storage II | 2024-10-15 | 400 | 400 | ES | Hudson | NJ | J | Gowanus Substation 345 kV | ConED | 0 | 2025-01-31
C24-356 | Five Mile Energy, LLC | 5Mile Storage Project | 2024-10-15 | 360 | 360 | ES | Cattaraugus | NY | A | Five Mile 345 kV | NM-NG | 0 | 2025-01-31
C24-357 | Glove City Energy Center, LLC | Glove City Solar | 2024-10-15 | 100 | 100 | S | Montgomery | NY | F | Stoner (137906) to Inghams (137228) 115kV line | NM-NG | 0 | 2025-06-30
C24-359 | Hambletonian Energy Storage II LLC | Sugar Loaf Energy Storage II | 2024-10-15 | 300 | 300 | ES | Orange | NY | G | Sugarloaf 138 kV Substation | O&R | 0 | 2025-02-28
C24-360 | North Foothills Energy Center, LLC | North Foothills Solar | 2024-10-15 | 100 | 100 | S | Franklin | NY | D | line tap between 115kV NMNG Lake Colby (136777) and Malone (136783) substations | NM-NG | 0 | 2024-10-31
C24-361 | Cherry Valley Energy Center, LLC | Cherry Valley Solar | 2024-10-15 | 125 | 125 | S | Montgomery | NY | F | Edic to Princetown Line #351, 345 kV | NYPA | 0 | 2025-11-30
C24-365 | Genesee River Solar, LLC | Ford Hill Road Solar | 2024-10-15 | 19.6 | 19.6 | S | Cortland | NY | C | Whitney Point Southwest 34.5kV substation | NYSEG | 0 | 2024-10-31
C24-367 | Lewis Wind, LLC | Lewis Wind | 2024-10-15 | 100 | 100 | W | Lewis | NY | E | Volney-Marcy Line 19 345kV line | NM-NG | 0 | 2025-06-30
C24-368 | CEDAR HOLDCO LLC | Huntley Energy Storage | 2024-10-15 | 300 | 300 | ES | Erie | NY | A | Huntley 230 kV Substation | NM-NG | 0 | 2025-03-31
C24-369 | Winterberry Wind LLC | Winterberry Wind | 2024-10-15 | 50 | 50 | W | Bradford | PA | C | Hillside - East Towanda 230 kV | NYSEG | 0 | 2024-10-31
C24-371 | EZ ENERGY SOLUTIONS LLC | EZ ENERGY SOLUTIONS LLC 5802 BESS | 2024-10-15 | 328.9 | 328.9 | ES | KINGS | NY | J | Gowanus 138 kV | ConEd | 0 | 2024-10-31
CR24-1001 | Suffolk County Energy Storage II, LLC | Suffolk County Storage II | 2024-09-18 |  |  | ES | Suffolk | NY | K | Southold 69kV station. | LIPA | 0 | 2024-12-31
CR24-1005 | KCE NY 29, LLC | KCE NY 29 | 2024-10-15 |  |  | ES | Suffolk |  | K | Kings 138 kV | LIPA | 0 | 2024-10-31

## In Service
Queue |  |  | Date | SP | WP | Type/ | Location |  | Z | Interconnection |  |  | Last Update | Availability | Proposed | Proposed
Pos. | Owner/Developer | Project Name | of IR | (MW) | (MW) | Fuel | County | State |  | Point | Utility | S |  | of Studies | In-Service | COD
0001 | Con Edison | Middletown Station | 1989-09-15 | N/A | N/A | AC | Orange County | NY | G | Coop Corn-Rock Tav Lines | NYPA | 14 | 2002-03-31 | None | I/S | N/A
0002 | Athens Gen Co./ PG&E | Athens Gen | 1998-04-27 | 1080 |  | NG | Athens | NY | F | Leeds-Pl.Val. 91 Line | NM-NG | 14 | 2004-05-31 | SRIS | I/S | N/A
0003 | PSEG Power NY | Bethlehem Energy Center | 1998-04-27 | 350 |  | NG | Albany | NY | F | Albany 115kV | NM-NG | 14 | 2005-07-31 | SRIS | I/S | N/A
0004 | TransEnergie US, Ltd | CT-LI DC Tie-line | 1998-07-20 | 330 |  | DC | Shoreham | NY | K | Shoreham, Long Island | LIPA | 14 | 2003-12-31 | SRIS,CY01 | I/S | I/S
0011 | East Coast Power-Linden Venture LP | East Coast Power-Linden | 1999-03-25 | 20 |  | NG | Linden | NY | J | Goethals | CONED | 14 | 2002-03-31 |  | I/S | I/S
0017 | KeySpan Energy, Inc. | KeySpan Ravenswood | 1999-04-21 | 270 |  | NG | NY | NY | J | Vernon | CONED | 14 |  | SRIS,CY01,CY02 | I/S | I/S
0018 | NYPA | Poletti Expansion | 1999-04-30 | 500 |  | NG | Queens | NY | J | Astoria 138kV | CONED | 14 | 2008-02-26 | SRIS, CY01 | I/S | I/S
0025 | Consolidated Edison of NY | East River Repowering | 1999-08-10 | 288 |  | NG | NY | NY | J | E. 13th St. 138kV | CONED | 14 |  | SRIS, CY01 | I/S | I/S
0031 | SCS Energy, LLC | Astoria Energy - Phase 1 | 1999-11-16 | 500 |  | NG | Queens | NY | J | Astoria 138kV | CONED | 14 | 2008-02-26 | SRIS, CY01 | Part I/S | Part I/S
0055 | Canastota Wind Power, LLC | Fenner Wind Energy Fac. | 2000-03-14 | 30 |  | W | Madison | NY | C | Fenner-Whitman | NM-NG | 14 |  | SRIS,CY02 | I/S | I/S
0066 | TransEnergie HQ | Langlois Converter | 2000-06-02 | 100 | N/A | AC |  | Quebec |  | Langlois, Quebec | NM-NG | 14 |  | SRIS | I/S | N/A
0069 | Empire Generating Co., LLC | Empire Generating | 2000-07-14 | 635 |  | NG | Rensselaer | NY | F | Reynolds Road 345kV | NM-NG | 14 | 2010-09-30 | SRIS, CY05 | I/S | N/A
0079 | NYPA | Harlem River Yards | 2000-12-05 | 79.9 |  | CT | NY | NY | J | Hell Gate Substation | CONED | 14 |  | SRIS,CY01 | I/S | N/A
0080 | NYPA | Hell Gate | 2000-12-05 | 79.9 |  | CT | NY | NY | J | Hell Gate Substation | CONED | 14 |  | SRIS,CY01 | I/S | I/S
0081 | NYPA | Vernon Blvd | 2000-12-05 | 79.9 |  | CT | NY | NY | J | Vernon Substation | CONED | 14 |  | SRIS,CY01 | I/S | I/S
0082 | NYPA | N First St and Grand Ave | 2000-12-05 | 44 |  | CT | NY | NY | J | Vernon-Greenwood line | CONED | 14 |  | SRIS,CY01 | I/S | I/S
0083 | NYPA | 23rd St and 3rd Ave | 2000-12-05 | 79.9 |  | CT | NY | NY | J | Gowanus Substation | CONED | 14 |  | SRIS,CY01 | I/S | I/S
0084 | NYPA | Fox Hills | 2000-12-05 | 44 |  | CT | NY | NY | J | Fox Hills Substation | CONED | 14 |  | SRIS,CY01 | I/S | I/S
0085 | NYPA | Brentwood | 2000-12-05 | 44 |  | CT | Nassau | NY | K | Brentwood 69 kV | LIPA | 14 |  | SRIS,CY01 | I/S | I/S
0094 | Atlantic Energy, LLC | Project Neptune DC PJM-LI | 2001-05-22 | 660 |  | DC | Nassau | NY-NJ | K | Newbridge Road 138kV | LIPA | 14 | 2008-10-14 | SRIS, CY05 | I/S | I/S
0095 | KeySpan Energy Development Corp. | Glenwood Gas Plant | 2001-05-22 | 79.9 |  | CT | Nassau | NY | K | Glenwood 69 kV | LIPA | 14 |  |  | I/S | I/S
0099 | Central Hudson Gas & Electric | Rock Tavern Transformer | 2001-06-28 | N/A | N/A | AC | Orange | NY | G | Rock Tavern | CHG&E | 14 |  | SRIS | I/S | N/A
0107 | Caithness Long Island, LLC | Caithness Long Island | 2001-10-09 | 310 |  | NG | Suffolk | NY | K | Brookhaven-Holbrook or H'ville 138kV | LIPA | 14 | 2009-11-30 | SRIS, CY06 | I/S | N/A
0115 | Central Hudson Gas & Electric | East Fishkill Transformer | 2002-04-24 | N/A | N/A | AC | Dutchess | NY | G | East Fishkill 345kV/115kV | CONED/CHG&E | 14 | 2013-03-31 | None | I/S | N/A
0121 | KeySpan Energy for LIPA | Holtsville Emergency Gen | 2002-05-31 | 66 |  | CT | Suffolk | NY | K | Holtsville | LIPA | 14 |  | SRIS | I/S | N/A
0122 | KeySpan Energy for LIPA | Shoreham Emergency Gen | 2002-05-31 | 66 |  | CT | Suffolk | NY | K | Holtsville | LIPA | 14 |  | SRIS | I/S | N/A
0123 | KeySpan Energy for LIPA | Wading River Emergency Gen | 2002-05-31 | 79.9 |  | CT | Suffolk | NY | K | Holtsville | LIPA | 14 |  | SRIS | I/S | I/S
0125 | East Coast Power, LLC | Linden VFT Inter-Tie | 2002-07-18 | 300 | N/A | AC | Richmond | NY-NJ | J | Goethals 345kV | CONED | 14 | 2009-11-30 | SRIS, CY06 | I/S | I/S
0127A | Airtricity Munnsville Wind Farm, LLC | Munnsville - Phase 1 | 2002-10-09 | 34.5 |  | W | Madison | NY | E | 46kV line | NYSEG | 14 | 2013-03-31 | SRIS, CY06 | Part I/S | Part I/S
0133 | KeySpan Energy for LIPA | Holtsville Emergency Gen | 2003-05-15 | 66 |  | CT | Suffolk | NY | K | Holtsville | LIPA | 14 |  | SRIS | I/S | I/S
0135 | UPC Wind Management, LLC | Canandaigua Wind Farm | 2003-05-30 | 82.5 | 82.5 | W | Steuben | NY | C | Avoca 230kV line | NYSEG | 14 | 2009-03-02 | SRIS, CY06 | I/S | I/S
0136 | Rochester Gas & Electric | Rochester Transmission | 2003-06-12 | N/A | N/A | AC | Monroe | NY | B | RG&E System | RG&E | 14 | 2009-04-08 | SRIS | I/S | N/A
0138 | Entergy Nuclear Operations, Inc. | Indian Point 2 Uprate | 2003-07-23 | 36 |  | NU | Westchester | NY | H | Buchanan 345kV | CONED | 14 | 2009-04-08 | SRIS, CY05 | I/S | I/S
0139 | Entergy Nuclear Operations, Inc. | Indian Point 3 Uprate | 2003-07-23 | 38 |  | NU | Westchester | NY | H | Indian Point 345kV | CONED | 14 | 2009-04-08 | SRIS, CY05 | I/S | I/S
0141 | Flat Rock Wind Power, LLC | Flat Rock Wind Power | 2003-08-27 | 321 |  | W | Lewis | NY | E | Adirondack-Porter 230kV | NM-NG | 14 | 2008-02-26 | SRIS, CY05 | I/S | I/S
0143 | Constellation | Ginna Uprate Project | 2004-01-30 | 95 |  | NU | Wayne | NY | B | Ginna-115kV | RG&E | 14 | 2008-02-26 | SRIS, CY05 | I/S | I/S
0144 | Sheldon Energy, LLC | High Sheldon Windfarm | 2004-02-18 | 112.5 | 112.5 | W | Wyoming | NY | C | Stolle Rd-Meyer 230kV | NYSEG | 14 | 2009-06-24 | SRIS, CY06,CY07 | I/S | I/S
0145 | KeySpan Energy for LIPA | LIPA Summer Mobile Gens | 2004-03-02 | 96 |  | NG | Suffolk | NY | K | Holtsville and Shoreham 138kV | LIPA | 14 | 2008-02-26 | SRIS | I/S | I/S
0146 | Con Edison | Mott Haven Substation | 2004-03-16 | N/A | N/A | AC | Westchester | NY | J | Dunwoodie-Rainey lines | CONED | 14 | 2009-04-08 | SRIS | I/S | N/A
0149 | KeySpan Energy for LIPA | LIPA Wading River Em Gen | 2004-06-03 | 79.9 |  | CT | Suffolk | NY | K | Wading River | LIPA | 14 |  | SRIS | I/S | I/S
0153 | Con Edison | Sprain Brook-Sherman Creek | 2004-08-13 | 500 | N/A | AC | Westchester | NY | I, J | Sprain Brook & Sherman Creek | CONED | 14 | 2011-03-31 | SIS | I/S | N/A
0156 | Hardscrabble Wind Power, LLC | Fairfield Wind Project | 2004-09-28 | 74 | 74 | W | Herkimer | NY | E | Valley-Inghams 115kV | NM-NG | 14 | 2011-02-28 | SRIS, CY06 | I/S | I/S
0160A | Innovative Energy Systems Inc. | DANC | 2004-11-19 | 6.4 | 6.4 | M | Jefferson | NY | E | 115kV | NM-NG | 14 | 2008-10-14 |  | I/S | I/S
0161 | Marble River, LLC | Marble River Wind Farm | 2004-12-07 | 83 | 83 | W | Clinton | NY | D | Willis-Plattsburgh WP-1 230kV | NYPA | 14 | 2013-03-31 | SRIS, FS | I/S | I/S
0171 | Marble River, LLC | Marble River II Wind Farm | 2005-02-08 | 132.2 | 132.2 | W | Clinton | NY | D | Willis-Plattsburgh WP-2 230kV | NYPA | 14 | 2013-03-31 | SRIS, FS | I/S | I/S
0172 | Noble Environmental Power, LLC | Clinton Windfield | 2005-02-14 | 79.5 | 79.5 | W | Clinton | NY | D | Willis-Plattsburgh WP-2 230kV | NYPA | 14 | 2008-10-14 | SRIS, CY06 | I/S | I/S
0173 | Noble Environmental Power, LLC | Bliss Windfield | 2005-02-14 | 72 | 72 | W | Wyoming | NY | A | Arcade Substation 115kV | Village of Arcade | 14 | 2008-10-14 | SRIS, CY06 | I/S | I/S
0174 | Noble Environmental Power, LLC | Altona Windfield | 2005-02-14 | 99 | 99 | W | Clinton | NY | D | Willis-Plattsburgh WP-1 230kV | NYPA | 14 | 2009-03-02 | SRIS, CY06 | I/S | I/S
0175 | Noble Environmental Power, LLC | Ellenburg Windfield | 2005-02-14 | 81 | 81 | W | Clinton | NY | D | Willis-Plattsburgh WP-2 230kV | NYPA | 14 | 2008-10-14 | SRIS, CY06 | I/S | I/S
0177 | Noble Wethersfield Windpark, LLC | Wethersfield 230kV | 2005-02-14 | 126 | 126 | W | Wyoming | NY | C | Stolle-Meyer 230kV | NYSEG | 14 | 2009-03-02 | FES,SRIS,CY07 | I/S | I/S
0182 | Howard Wind, LLC | Howard Wind | 2005-03-21 | 57.4 | 57.4 | W | Steuben | NY | C | Bennett-Bath 115kV | NYSEG | 14 | 2011-12-31 | FES, SRIS, CY07 | I/S | I/S
0185 | NY Power Authority | Blenheim Gilboa Storage | 2005-03-29 | 120 | 120 | PS | Schoharie | NY | F | Valenti Rd., Gilboa 345kV | NYPA | 14 | 2010-06-30 | SRIS, CY06 | I/S | I/S
0199 | UPC Wind Management, LLC | Canandaigua II | 2005-07-26 | 42.5 | 42.5 | W | Steuben | NY | C | Meyer - Avoca 230kV | NYSEG | 14 | 2009-04-08 | SRIS, CY07 | I/S | I/S
0201A | Innovative Energy Systems | Seneca Energy Expansion | 2005-09-02 | 17.6 | 17.6 | M | Seneca | NY | C | 34.5kV | NYSEG | 14 | 2008-04-22 |  | I/S | I/S
0201B | Minnesota Methane, LLC | MM Albany Landfill | 2005-09-15 | 2 | 4 | M | Albany | NY | F | 34.5kV | NM-NG | 14 | 2008-10-14 |  | I/S | I/S
0206 | Hudson Transmission Partners | Hudson Transmission | 2005-12-14 | 660 | 660 | DC | NY - Bergen | NY-NJ | J | West 49th Street 345kV | CONED | 14 | 2013-06-30 | FES, SRIS, FS | I/S | I/S
0209A | Casella Waste Systems | Hyland Landfill | 2006-02-28 | 6.4 | 6.4 | M | Livingston | NY | C | 34.5kV | NYSEG | 14 | 2008-10-14 |  | I/S | I/S
0211 | Noble Environmental Power, LLC | Clinton II Windfield | 2006-04-03 | 21 | 21 | W | Clinton | NY | D | Willis-Plattsburgh WP-2 230kV | NYPA | 14 | 2008-10-14 | SRIS, CY07 | I/S | I/S
0212 | Noble Environmental Power, LLC | Bliss II Windfield | 2006-04-03 | 28.5 | 28.5 | W | Wyoming | NY | A | Freedom Substation 115kV | Village of Arcade | 14 | 2008-10-14 | SRIS, CY07 | I/S | I/S
0214 | Noble Chateaugay Windpark, LLC | Chateaugay Windpark | 2006-04-03 | 106.5 | 106.5 | W | Franklin-Clinton | NY | D | Willis-Plattsburgh 230kV | NYPA | 14 | 2009-03-02 | FES, SRIS, CY07 | I/S | I/S
0216 | Nine Mile Point Nuclear, LLC | Nine Mile Point Uprate | 2006-05-05 | 168 | 168 | NU | Oswego | NY | C | Scriba Station 345kV | NM-NG | 14 | 2013-03-31 | SRIS, FS | I/S | I/S
0217A | New Athens Generating Co., LLC | Athens SPS Project | 2006-06-30 | N/A | N/A | AC | Greene-W.Chester | NY | F, H | Athens - Millwood | NM-NG/CONED | 14 | 2009-04-08 | SIS | I/S | N/A
0224A | Bio-Energy Partners | High Acres Landfill | 2006-08-25 | 6.4 | 6.4 | M | Monroe | NY | C | 34.5 | NYSEG | 14 | 2008-12-22 |  | I/S | I/S
0225 | NY State Electric & Gas | Ithaca Transmission | 2006-09-07 | N/A | N/A | AC | Thompkins | NY | C | Oakdale - Lafayette 345kV | NYSEG | 14 | 2011-01-31 | SIS | I/S | N/A
0232 | Bayonne Energy Center, LLC | Bayonne Energy Center | 2006-11-27 | 500 | 500 | D | Bayonne | NJ | J | Gowanus Substation 345kV | ConEd | 14 | 2013-03-31 | FES, SRIS, CY09 | I/S | I/S
0233 | Erie Boulevard Hydro Power, LP | Sherman Island Uprate | 2006-11-27 | 8.5 | 8.5 | H | Warren | NY | F | Spier - Queensbury 115kV | NM-NG | 14 | 2010-02-16 | SRIS,CY08 | I/S | I/S
0234 | Steel Winds, LLC | Steel Winds II | 2006-12-08 | 15 | 15 | W | Erie | NY | A | Substation 11A 115kV | NM-NG | 14 | 2012-01-31 | SRIS, CY08 | I/S | I/S
0237A | Chautauqua County | Chautauqua Landfill | 2007-01-11 | 6.4 | 6.4 | M | Chautauqua | NY | A | Hartfield  South Dow 34.5kV | NM-NG | 14 | 2009-10-28 | FES,SIS,FS | I/S | I/S
0245 | Innovative Energy System, Inc. | Fulton County Landfill | 2007-04-17 | 3.2 | 3.2 | M | Montgomary | NY | F | Ephratah  Amsterdam 69kV | NM-NG | 14 | 2011-11-30 | FES,SIS,CY09 | I/S | I/S
0250 | Seneca Energy II, LLC | Ontario | 2007-07-02 | 5.6 | 5.6 | M | Ontario | NY | C | Haley Rd. - Hall 34.5kV | NYSEG | 14 | 2013-03-31 | FES,FS | I/S | I/S
0251 | CPV Valley, LLC | CPV Valley Energy Center | 2007-07-05 | 677.6 | 690.6 | D | Orange | NY | G | Coopers  Rock Tavern 345kV | NYPA | 14 | 2018-03-31 | FES, SRIS, FS | I/S | I/S
0260 | Stephentown Regulation Services, LLC | Stephentown | 2007-09-25 | 20 | 20 | F | Rensselaer | NY | F | Stephentown 115kV | NYSEG | 14 | 2011-11-30 | SIS,CY10 | I/S | I/S
0263 | Stony Creek Wind Farm, LLC | Stony Creek Wind Farm | 2007-10-12 | 92.8 | 92.8 | W | Wyoming | NY | C | Stolle Rd - Meyer 230kV | NYSEG | 14 | 2014-03-31 | FES, SRIS, CY10 | I/S | I/S
0270A | National Grid | Luther Forest Transmission | 2007-12-18 | N/A | N/A | AC | Saratoga | NY | F | Ngrid 115kV | NM-NG | 14 | 2008-10-14 | SIS | I/S | N/A
0284 | Broome Energy Resources, LLC | Nanticoke Landfill | 2008-03-06 | 1.6 | 1.6 | M | Broome | NY | C | Nanticoke Landfill Plant 34.5kV | NYSEG | 14 | 2013-09-30 | FES | I/S | I/S
0289 | NY State Electric & Gas | Corning Valley Trans. | 2008-04-01 | N/A | N/A | AC | Steuben | NY | C | Avoca and Hillside 230kV | NYSEG | 14 | 2011-09-30 | SIS | I/S | N/A
0294 | Orange & Rockland | Ramapo-Sugarloaf | 2008-04-29 | N/A | N/A | AC | Orange/Rockland | NY | G | Ramapo - Sugarloaf 138kV | O&R | 14 | 2015-04-30 | SIS | I/S | N/A
0308 | Astoria Energy II, LLC | Astoria Energy II | 2008-08-20 | 576 | 617.2 | NG | Queens | NY | J | Astoria 345kV | NYPA | 14 | 2011-11-30 | SRIS | I/S | I/S
0318 | AES Energy Storage, LLC | Westover Energy Storage | 2008-12-03 | 20 | 20 | ES | Broome | NY | C | Westover 115kV | NYSEG | 14 | 2010-12-31 | None | I/S | I/S
0326 | NYSEG/RG&E | Rochester SVC/PST Trans. | 2009-03-09 | N/A | N/A | AC | Monroe | NY | B | Station 124 115kV | NYSEG | 14 | 2014-04-30 | SIS | I/S | N/A
0330 | Long Island Solar Farm LLC | Upton Solar Farms | 2009-04-07 | 31.5 | 32 | S | Suffolk | NY | K | 8ER Substation 69kV | LIPA | 14 | 2011-11-30 | SRIS | I/S | I/S
0331 | National Grid | Northeast NY Reinforcement | 2009-04-22 | N/A | N/A | AC | Saratoga | NY | F | NGrid 230kV | NM-NG | 14 | 2019-03-31 | SIS | I/S | N/A
0333 | National Grid | Western NY Reinforcement | 2009-05-05 | N/A | N/A | AC | Cattaraugus | NY | A | NGrid 115kV | NM-NG | 14 | 2019-03-31 | SIS | I/S | N/A
0337 | Long Island Power Authority | Northport Norwalk Harbor | 2009-07-14 | N/A | N/A | AC | Suffolk | NY | K | Northport 138kV | LIPA | 14 | 2011-01-31 | SIS | I/S | N/A
0339 | RG&E | Transmission Reinforcement | 2009-08-17 | N/A | N/A | AC | Monroe | NY | B | Niagara - Kintigh 345kV | RG&E | 14 | 2019-04-30 | SIS | I/S | N/A
0340 | RG&E | Brown's Race III | 2009-09-02 | 2 | 2 | H | Monroe | NY | B | Station 6 34.5 kV | RG&E | 14 | 2012-01-31 | None | I/S | I/S
0342 | Albany Energy, LLC | Albany Landfill | 2009-09-03 | 6.4 | 6.4 | M | Albany | NY | F | 34.5kV | NM-NG | 14 | 2013-03-31 | None | I/S | I/S
0353 | Chautauqua County | Chautauqua County Landfill | 2010-04-26 | 3.2 | 3.2 | M | Chautauqua | NY | A | Hartfield  South Dow 34.5kV | NM-NG | 14 |  | None | I/S | I/S
0355 | Brookfield Renewable Power | Stewarts Bridge Hydro | 2010-08-03 | 3 | 3 | H | Saratoga | NY | F | Spier Falls - EJ West 115kV | NM-NG | 14 | 2015-04-30 | SRIS, FS | I/S | I/S
0368 | Consolidated Edison Co. of NY | Feeder 76 Ramapo to Rock Tavern | 2011-10-13 | N/A | N/A | AC | Orange, Rockland | NY | G | Ramapo to Rock Tavern 345 kV | ConEd/CenHud | 14 | 2016-05-31 | SIS | I/S | N/A
0373 | NY Power Authority | Coopers Corners Shunt Reactor | 2011-12-21 | N/A | N/A | AC | Sullivan | NY | E | Coopers Corners 345 kV | NYSEG | 14 | 2015-08-31 | SIS | I/S | N/A
0375 | Eagle Creek Hydro, LLC | Eagle Creek Hydro | 2012-03-06 | 0.8 | 0.8 | H | Sullivan | NY | E | Rio 69kV Switchyard | O&R | 14 | 2014-01-31 | None | I/S | I/S
0378 | Invenergy NY LLC | Marsh Hill Wind | 2012-03-29 | 16.2 | 16.2 | W | Steuben | NY | C | Jasper - Marshall Warriner 34.5kV | NYSEG | 14 | 2014-12-31 | None | I/S | I/S
0380 | NY Power Authority | Marcy South Reinforcement | 2012-05-14 | N/A | N/A | AC | Oneida-Sullivan | NY | E | Marcy/Edic-Coopers Corners 345kV | NYSEG | 14 | 2016-07-31 | SIS | I/S | N/A
0387 | Cassadaga Wind, LLC | Cassadaga Wind | 2012-07-19 | 126.5 | 126.5 | W | Chautauqua | NY | A | Dunkirk - Moon 115 kV | NM-NG | 14 | 2020-05-31 | FES, SRIS, FS | I/S | I/S
0390 | Trail Co. | Farmers Valley Substation | 2012-09-14 | N/A | N/A | AC | Cattaraugus | NY-PA | A | Homer City - Stolle Rd. 345kV | NM-NG/NYSEG | 14 | 2016-06-30 | SIS | I/S | N/A
0394 | Trail Co. | Mainesburg Substation | 2012-10-16 | N/A | N/A | AC | Chemung | NY-PA | C | Homer City - Watercure 345kV | NYSEG | 14 | 2015-12-31 | SIS | I/S | N/A
0395 | Copenhagen Wind Farm, LLC | Copenhagen Wind | 2012-11-12 | 79.9 | 79.9 | W | Lewis | NY | E | Black River-Lighthouse Hill 115kV | NM-NG | 14 | 2019-03-31 | FES, SRIS, FS | I/S | I/S
0396 | Baron Winds, LLC | Baron Winds | 2012-11-30 | 238.8 | 238.8 | W | Steuben | NY | C | Hillside - Meyer 230kV | NYSEG | 15 | 2022-12-31 | FES, SRIS, FS | IS | I/S
0396A | New York State Electric & Gas | Wood Street Transformer | 2012-12-14 | N/A | N/A | AC | Putnam | NY | G | Wood St. 345/115kV | NYSEG | 14 | 2025-10-31 | SIS | I/S | I/S
0397 | Jericho Rise Wind Farm, LLC | Jericho Rise Wind | 2012-12-21 | 77.7 | 77.7 | W | Franklin | NY | D | Willis Substation 115kV | NYPA | 14 | 2017-02-28 | SRIS, FS | I/S | I/S
0403 | PSEG Power NY | Bethlehem Energy Center Uprate | 2013-05-28 | 72 | 51.2 | D | Albany | NY | F | Bethlehem Energy Center | NM-NG | 14 | 2019-03-31 | FES, SRIS, FS | I/S | I/S
0421 | Arkwright Summit Wind Farm LLC | Arkwright Summit | 2013-11-01 | 78.4 | 78.4 | W | Chautauqua | NY | A | Dunkirk - Falconer 115 kV | NM-NG | 14 | 2021-08-31 | SRIS, FS | IS | I/S
0422 | NextEra Energy Resources, LLC | Eight Point Wind Energy Center | 2013-11-07 | 101.8 | 101.8 | W | Steuben-Allegany | NY | C | Bennett 115kV | NYSEG | 14 | 2021-03-31 | FES, SRIS, FS | IS | I/S
0429 | Orange & Rockland | North Rockland Station | 2014-02-12 | N/A | N/A | AC | Steuben | NY | G | Line Y88 345kV | ConEd | 14 | 10/31/2025 | SIS | IS | I/S
0430 | H.Q. Energy Services U.S. Inc. | Cedar Rapids Transmission | 2014-03-05 | N/A | N/A | AC | St. Lawrence | NY | D | Dennison - Alcoa 115kV | NM-NG | 14 | 10/31/2025 | SIS, FS | IS | I/S
0431 | Greenidge Generation | Greenidge Unit #4 | 2014-04-11 | 106.3 | 106.3 | NG | Yates | NY | C | Greenidge Substation 115kV | NYSEG | 14 | 2018-02-28 | SIS, FS | 10/2021 | N/A
0432 | NY State Electric & Gas | South Perry Transformer | 2014-04-15 | N/A | N/A | AC | Wyoming | NY | B | South Perry Substation 115kV | NYSEG | 14 | 2018-07-31 | SRIS, FS | I/S | I/S
0444 | Cricket Valley Energy Center, LLC | Cricket Valley Energy Center II | 2014-06-18 | 1020 | 1132 | CC | Dutchess | NY | G | Pleasant Valley - Long Mt. 345kV | ConEd | 14 | 2019-07-31 | SIS | I/S | N/A
0461 | Consolidated Edison Co. of NY | East River 1 Uprate | 2014-12-01 | 2 | 2 | CT | NY | NY | J | East River Complex | ConEd | 14 | 2019-12-31 | SRIS, FS | IS | I/S
0462 | Consolidated Edison Co. of NY | East River 2 Uprate | 2014-12-01 | 2 | 2 | CT | NY | NY | J | East River Complex | ConEd | 14 | 2019-12-31 | SRIS, FS | IS | I/S
0467 | Shoreham Solar Commons LLC | Shoreham Solar | 2014-12-22 | 25 | 25 | S | Suffolk | NY | K | Ridge - Wildwood 69kV | LIPA | 14 | 2019-07-31 | SRIS, FS | IS | I/S
0477 | Riverhead Solar Farm LLC | Riverhead Solar | 2015-02-18 | 20 | 20 | S | Suffolk | NY | K | Edwards Substation 138kV | LIPA | 14 | 2019-05-31 | SRIS, FS | IS | I/S
0490 | NY Power Authority | Marcy South Series Comp | 2015-03-16 | N/A | N/A | AC | Oneida-Sullivan | NY | E | Marcy/Edic-Coopers Corners 345kV | NYSEG/NM-NG | 14 | 2016-07-31 | FES, SIS, FS | IS | I/S
0505 | Ball Hill Wind Energy, LLC | Ball Hill Wind | 2015-06-02 | 103 | 103 | W | Chautauqua | NY | A | Dunkirk - Gardenville 230kV | NM-NG | 14 | 2023-10-31 | FES, SRIS, FS | IS | I/S
0510 | Bayonne Energy Center | Bayonne Energy Center II | 2015-08-03 | 120.4 | 129.4 | D | Hudson | NJ | J | Gowanus Substation 345kV | ConEd | 14 | 2019-12-31 | SIS | I/S | N/A
0513 | Orangeville Energy Storage LLC | Orangeville | 2015-09-21 | 20 | 20 | ES | Wyoming | NY | C | Stony Creek 230kV | NYSEG | 14 | 2021-12-31 | SRIS, FS | IS | I/S
0517 | National Grid | Western NY Reactors & Capacitors | 2015-10-14 | N/A | N/A | AC | Niagara | NY | A | Packard - Huntley 230kV | NM-NG | 14 | 2016-06-30 | SIS, FS | I/S | 04/2022
0531 | Number Three Wind LLC | Number 3 Wind Energy | 2016-01-11 | 103.9 | 103.9 | W | Lewis | NY | E | Taylorville - Boonville 115kV | NM-NG | 14 | 2023-07-31 | FES, SRIS, FS | IS | I/S
0543 | National Grid | Segment B Knickerbocker-PV | 2016-05-04 | N/A | N/A | AC | Albany-Dutchess | NY | F, G | Greenbush - PV 345kV | NM-NG/NYSEG/ CHGE/ConEd | 15 | 2022-04-30 | SIS | IS | 12/2023-06/2025
0545A | NextEra Energy Transmission NY, Inc. | Empire State Line Alt | 2016-05-17 | N/A | N/A | AC | Niagara-Erie | NY | A | Dysinger - Stolle 345kV | NYPA/NYSEG | 14 | 2022-04-30 | SIS | I/S | N/A
0546 | PPM Roaring Brook, LLC | Roaring Brook Wind | 2016-05-19 | 79.7 | 79.7 | W | Lewis | NY | E | Chases Lake Substation 230kV | NM-NG | 14 | 2022-01-31 | SIS, FS | IS | I/S
0556 | LS Power Grid NY, LLC | Segment A Double Circuit | 2016-07-06 | N/A | N/A | AC | Oneida-Albany | NY | E, F | Edic - New Scotland 345kV | NM-NG | 15 | 2022-04-30 | SIS, FS | IS | I/S
0566 | New York Power Authority | MA 1 & 2 Rebuild | 2016-08-04 | N/A | N/A | AC | St. Lawrence-Lewis | NY | D, E | Moses & Adirondack 230kV | NYPA | 14 | 2022-09-30 | SIS | IS | I/S
0570 | Hecate Energy Albany 1 LLC | Albany County 1 | 2016-08-17 | 20 | 20 | S | Albany | NY | F | Long Lane - Lafarge 115kV | NM-NG | 14 | 2023-12-31 | SIS, FS | IS | I/S
0579 | Bluestone Wind, LLC | Bluestone Wind | 2016-09-21 | 111.8 | 111.8 | W | Broome | NY | E | Afton - Stilesville 115kV | NYSEG | 14 | 2023-12-31 | FES, SRIS, FS | IS | I/S
0583 | Erie Boulevard Hydropower, LP | Fulton | 2016-10-31 | 1.3 | 1.3 | H | Oswego | NY | C | Fay St. 34.5kV | NM-NG | 14 | 2018-03-31 | FES, SRIS, FS | I/S | I/S
0598 | Hecate Energy Albany 2 LLC | Albany County 2 | 2017-01-10 | 20 | 20 | S | Albany | NY | F | Long Lane - Lafarge 115kV | NM-NG | 14 | 2023-12-31 | SIS, FS | IS | I/S
0612 | South Fork Wind, LLC | South Fork Wind Farm | 2017-02-14 | 96 | 96 | OSW | Suffolk | NY | K | East Hampton 69kV | LIPA | 14 | 2024-07-31 | SRIS, FS | IS | I/S
0618 | High River Energy Center, LLC | High River Solar | 2017-03-27 | 90 | 90 | S | Montgomery | NY | F | Inghams - Rotterdam 115kV | NM-NG | 14 | 2024-07-31 | SRIS, FS | IS | I/S
0619 | East Point Energy Center, LLC | East Point Solar | 2017-03-27 | 50 | 50 | S | Schoharie | NY | F | Cobleskill - Marshville 69kV | NM-NG | 14 | 2024-04-30 | SRIS, FS | IS | I/S
0631 | CHPE LLC | NS Power Express | 2017-05-02 | 1000 | 1000 | DC | Quebec - NY | NY | J | Astoria Annex 345kV | NYPA | 12 | 2023-06-30 | SRIS, FS | IS | I/S
0638 | Pattersonville Solar Facility, LLC | Pattersonville | 2017-07-11 | 20 | 20 | S | Montgomery | NY | F | Rotterdam - Meco 115kV | NM-NG | 14 | 2023-07-31 | FES, SIS, FS | IS | I/S
0678 | LI Solar Generation, LLC | Calverton Solar Energy Center | 2017-10-26 | 22.9 | 22.9 | S | Suffolk | NY | K | Edwards Substation 138kV | LIPA | 14 | 2022-09-30 | SIS, FS | IS | I/S
0682 | Grissom Solar, LLC | Grissom Solar | 2018-01-17 | 20 | 20 | S | Montgomery | NY | F | Ephratah - Florida 115kV | NM-NG | 14 | 2022-11-30 | FS | I/S | I/S
0695 | South Fork Wind, LLC | South Fork Wind Farm II | 2018-02-16 | 40 | 40 | OSW | Suffolk | NY | K | East Hampton 69kV | LIPA | 14 | 2024-07-31 | SRIS, FS | IS | I/S
0696 | Eagle Creek Hydro Power, LLC | Swinging Bridge Unit 3 | 2018-03-21 | 1.2 | 1.2 | H | Orange | NY | G | Swing Bridge 69 kV | O&R | 14 | 2019-05-31 | SRIS, FS | IS | I/S
0701 | KCE NY 1, LLC | KCE NY 1 | 2018-03-15 | 20 | 20 | ES | Saratoga | NY | F | Luther Forest 34.5kV | NYSEG | 14 | 2019-12-31 | FES, SIS, FS | IS | I/S
0717 | Morris Ridge Solar Energy Center, LLC | Morris Ridge Solar Energy Center | 2018-06-04 | 177 | 177 | S | Steuben | NY | C | South Perry - Meyer 230kV | NYSEG | 14 | 2024-09-30 | FES, SRIS, FS | 09-2024 | 11-2024
0730 | Darby Solar, LLC | Darby Solar | 2018-06-11 | 20 | 20 | S | Washington | NY | F | Mohican - Schaghticoke 115kV | NM-NG | 14 | 2022-11-30 | FES, SIS | IS | I/S
0731 | Branscomb Solar, LLC | Branscomb Solar | 2018-06-11 | 20 | 20 | S | Washington | NY | F | Battenkill - Eastover 115kV | NM-NG | 14 | 2021-12-31 |  | IS | I/S
0735 | ELP Stillwater Solar LLC | ELP Stillwater Solar | 2018-06-12 | 20 | 20 | S | Saratoga | NY | F | Luther Forest - Mohican 115kV | NM-NG | 14 | 2023-11-30 | FES, SIS, FS | IS | I/S
0748 | Regan Solar, LLC | Regan Solar | 2018-08-09 | 20 | 20 | S | Montgomery | NY | F | Market Hill - Johnstown 69kV | NM-NG | 14 | 2022-12-31 |  | IS | I/S
0758 | Sithe/Independence Power Partners, LP | Sithe Independence | 2018-09-06 | 9 | 27 | CC | Oswego | NY | C | Sithe 345kV Substation | NM-NG | 14 | 2023-12-31 | SRIS, FS | IS | I/S
0759 | KCE NY 6, LLC | KCE NY 6 | 2018-09-06 | 20 | 20 | ES | Erie | NY | A | Gardenville - Bethlehem Steel Wind 115kV Line #150 | NM-NG | 14 | 2022-01-31 | SIS | IS | I/S
0768 | Janis Solar, LLC | Janis Solar | 2018-10-01 | 20 | 20 | S | Cortland | NY | C | Willet 34.5kV | NYSEG | 14 | 2022-11-30 | FES, SIS, FS | I/S | I/S
0769 | NY Power Authority | North County Energy Storage | 2018-10-05 | 20 | 20 | ES | Franklin | NY | D | Willis 115kV | NYPA | 14 | 2023-09-30 | SIS | IS | I/S
0775 | Puckett Solar, LLC | Puckett Solar | 2018-10-22 | 20 | 20 | S | Chenango | NY | C | Chenango Forks 34.5kV | NYSEG | 14 | 2022-09-30 | SIS, FS | IS | I/S
0781 | NY Power Authority | Marcy South SSR Detection | 2018-12-03 | N/A | N/A | AC | Delaware | NY | E | Fraser - Annex 345 kV Substation | NYPA | 14 | 2019-09-30 | SIS, FS | IS | I/S
0887 | CHPE LLC | CH Uprate | 2019-06-12 | 250 | 250 | DC | Quebec-NY | NY | J | Astoria Annex 345kV | NYPA | 14 | 2023-06-30 | SRIS, FS | IS | I/S
1125 | New York Power Authority and National Grid | Northern New York Priority Transmission Project (NNYPTP) | 2020-12-22 | N/A | N/A | AC | St. Lawrence-Lewis | NY | D, E | 1. Moses 230 kV substation 2. Haverstock 345 kV sub (new) 3. Massena 230 kV substation 4. Adirondack 345 kV sub (new) 5. Willis 230 kV substation 6. Ryan & Patnode 230 kV substations 7. Chases Lake 345 kV sub (new) 8. Marcy 345 kV sub 9. Edic 345 kV sub | NYPA, NM-NG | 15 | 2025-06-30 | FS | IS | I/S