## Interconnection Queue
Queue Pos. | Developer/Interconnection Customer | Project Name | Date of IR | SP (MW) | WP (MW) | Type/ Fuel | Energy Storage Capability | Minimum_Duration Full Discharge | County | State | Z | Points of Interconnection | Utility | Affected Transmission Owner (ATO) | S | Last Updated Date | Availability of Studies | IA Tender Date | CY/FS Complete Date | Proposed In-Service/Initial Backfeed Date | Proposed Sync Date | Proposed COD
276 | Homer Solar Energy Center LLC | Homer Solar Energy Center | 2008-01-30 | 90 | 90 | S |  |  | Cortland | NY | C | Cortland - Fenner 115kV | NM-NG |  | 11 | 2023-07-31 | FES, SRIS, FS | 2021-02-08 | 2021-02-08 | 03-2026 | 03-2026 | 04-2026
0396A | New York State Electric & Gas | Wood Street Transformer | 2012-12-14 | N/A | N/A | AC |  |  | Putnam | NY | G | Wood St. 345/115kV | NYSEG |  | 12 | 2024-05-31 | SIS |  |  | 12/2024 | N/A | N/A
0429 | Orange & Rockland | North Rockland Station | 2014-02-12 | N/A | N/A | AC |  |  | Steuben | NY | G | Line Y88 345kV | ConEd |  | 12 | 2022-03-31 | SIS |  |  | 06/2024 | N/A | N/A
0430 | H.Q. Energy Services U.S. Inc. | Cedar Rapids Transmission | 2014-03-05 | N/A | N/A | AC |  |  | St. Lawrence | NY | D | Dennison - Alcoa 115kV | NM-NG |  | 12 | 2019-12-31 | SIS, FS | 2018-10-02 | 2018-03-19 | 10/2021 | N/A | N/A
0495 | Mohawk Solar LLC | Mohawk Solar | 2015-04-02 | 90.5 | 90.5 | S |  |  | Montgomery | NY | F | St. Johnsville - Marshville 115kV | NM-NG |  | 11 | 2022-09-30 | FES, SRIS, FS | 2021-02-08 | 2021-02-08 | 06/2027 | 10/2027 | 11/2027
0519 | Canisteo Wind Energy LLC | Canisteo Wind | 2015-11-02 | 289.8 | 289.8 | W |  |  | Steuben | NY | C | Bennett 115kV | NYSEG |  | 11 | 2025-03-31 | FES, SRIS, FS | 2021-02-08 | 2021-02-08 | 10-2026 | 01-2027 | 12-2027
0521 | Bull Run Energy LLC | Bull Run II Wind | 2015-12-15 | 449 | 449 | W |  |  | Clinton | NY | D | Patnode-Duley, Ryan-Plattsburgh 230kV | NYPA |  | 10 | 2025-03-31 | FES, SRIS, FS | 2023-01-11 | 2023-01-11 | 08-2027 | 09-2027 | 05-2028
0522 | NYC Energy LLC | NYC Energy | 2015-12-16 | 79.9 | 79.9 | ES |  | 4 | Kings | NY | J | Hudson Avenue East 138kV | ConEd |  | 10 | 2025-01-31 | FES, SRIS, FS |  | 2024-12-16 | 05-2027 | 05-2027 | 06-2027
0535 | Riverhead Solar 2, LLC | Riverhead Solar 2 | 2016-02-23 | 36 | 36 | S |  |  | Suffolk | NY | K | Edwards 138kV | LIPA |  | 11 | 2024-09-30 | FES, SRIS, FS | 2021-02-08 | 2021-02-08 | 09-2026 | 12-2026 | 01-2027
0545 | Sky High Solar, LLC | Sky High Solar | 2016-05-16 | 20 | 20 | S |  |  | Onondaga | NY | C | Tilden -Tully Center 115kV | NM-NG |  | 11 | 2022-01-31 | FES, SIS, FS | 2019-10-01 | 2019-09-17 | TBD | TBD | TBD
0564 | Rock District Solar, LLC | Rock District Solar | 2016-07-25 | 20 | 20 | S |  |  | Schoharie | NY | F | Sharon - Cobleskill 69kV | NM-NG |  | 11 | 2021-08-31 | SIS, FS | 2020-07-10 | 2020-06-03 | 01-2027 | 12-2026 | 02-2027
0565 | Tayandenega Solar, LLC | Tayandenega Solar | 2016-07-25 | 20 | 20 | S |  |  | Montgomery | NY | F | St. Johnsville - Inghams 115kV | NM-NG |  | 11 | 2024-07-31 | SIS, FS | 2020-07-01 | 2020-06-03 | 06-2024 | 06-2024 | 06-2026
0566 | New York Power Authority | MA 1 & 2 Rebuild | 2016-08-04 | N/A | N/A | AC |  |  | St. Lawrence-Lewis | NY | D, E | Moses & Adirondack 230kV | NYPA |  | 12 | 2022-09-30 | SIS |  |  | 6-2023 | N/A | N/A
0571 | Heritage Wind, LLC | Heritage Wind | 2016-09-01 | 200.1 | 200.1 | W |  |  | Genesee | NY | B | Lockport - Mortimer 115kV | NM-NG |  | 11 | 2023-09-30 | FES, SRIS, FS | 2023-01-11 | 2023-01-11 | 05-2026 | 06-2026 | 09-2026
0572 | Hecate Energy Greene 1 LLC | Greene County 1 | 2016-09-06 | 20 | 20 | S |  |  | Greene | NY | G | Coxsackie - North Catskill 69kV | CHG&E |  | 11 | 2025-05-31 | SIS, FS | 2020-02-18 | 2020-01-24 | 05-2027 | 04-2027 | 06-2027
0573 | Hecate Energy Greene 2 LLC | Greene County 2 | 2016-09-06 | 10 | 10 | S |  |  | Greene | NY | G | Coxsackie 13.8kV | CHG&E |  | 11 | 2025-05-31 | SIS, FS | 2020-02-18 | 2020-01-24 | 05-2027 | 04-2027 | 06-2027
0575 | Little Pond Solar, LLC | Little Pond Solar | 2016-09-16 | 20 | 20 | S |  |  | Orange | NY | G | Mongaup - Shoemaker 69kV | O&R |  | 11 | 2025-02-28 | FES, SIS, FS | 2021-01-29 | 2020-12-16 | 07-2027 | 04-2026 | 09-2027
0580 | Genesee County Economic Devel. | WNY STAMP | 2016-09-27 | 300 | 300 | L |  |  | Genesee | NY | B | Kintigh/Niagara - New Rochester 345kV | NYPA |  | 12 | 2025-03-31 | SIS |  |  | 05-2026 | N/A | NA
0581 | SunEast Hills Solar LLC | Hills Solar | 2016-10-06 | 20 | 20 | S |  |  | Herkimer | NY | E | Fairfield - Inghams 115kV | NM-NG |  | 11 | 2024-05-31 | FES, SIS, FS | 2020-04-07 | 2020-02-11 | 10-2026 | 06-2026 | 12-2026
0584 | SunEast Dog Corners Solar LLC | Dog Corners Solar | 2016-11-02 | 20 | 20 | S |  |  | Cayuga | NY | C | Aurora 34.5kV | NYSEG |  | 11 | 2024-05-31 | SIS, FS | 2019-06-21 | 2019-05-08 | 03-2026 | 03-2026 | 04-2026
0586 | SunEast Watkins Road Solar LLC | Watkins Rd Solar | 2016-11-08 | 20 | 20 | S |  |  | Herkimer | NY | E | Watkins Rd - Ilion 115kV | NM-NG |  | 11 | 2024-04-30 | SIS, FS | 2020-02-18 | 2019-11-25 | 03-2026 | 02-2026 | 07-2026
0590 | Scipio Solar NY LLC | Scipio Solar | 2016-12-02 | 18 | 18 | S |  |  | Cayuga | NY | C | Scipio 34.5kV | NYSEG |  | 11 | 2025-03-31 | SIS, FS | 2019-05-22 | 2019-03-21 | 09-2026 | 09-2026 | 12-2026
0591 | SunEast Highview Solar LLC | Highview Solar | 2016-12-02 | 20 | 20 | S |  |  | Wyoming | NY | C | South Perry 34.5kV | NYSEG |  | 11 | 2024-05-31 | SIS, FS | 2021-02-08 | 2021-02-08 | TBD | TBD | TBD
0592 | Niagara NY Solar LLC | Niagara Solar | 2016-12-02 | 20 | 20 | S |  |  | Wyoming | NY | A | Bennington 34.5kV | NYSEG |  | 11 | 2024-09-30 | SIS, FS | 2019-05-22 | 2019-04-18 | 03-2025 | 04-2025 | 12-2026
0596 | Alle-Catt Wind Energy LLC | Alle Catt II Wind | 2017-01-04 | 339.1 | 339.1 | W |  |  | Cattaraugus | NY | A | Stolle Rd - Five Mile Rd 345kV | NM-NG |  | 12 | 2022-09-30 | SRIS, FS | 2021-02-08 | 2021-02-08 | 05-2026 | 05-2026 | 12-2026
0617 | Watkins Glen Solar Energy Center, LLC | Watkins Glen Solar | 2017-03-27 | 50 | 50 | S |  |  | Schuyler | NY | C | Bath - Montour Falls 115kV | NYSEG |  | 11 | 2025-01-31 | SRIS, FS | 2020-12-04 | 2021-02-08 | 03-2028 | 04/2028 | 04-2028
0620 | Gateway Solar Energy Center, LLC | Gateway Solar Energy Center | 2017-03-27 | 180 | 180 | S |  |  | St. Lawrence | NY | D | Massena - Moses 230kV | NYPA |  | 11 | 2025-02-28 | FES, SRIS, FS | 2021-02-08 | 2021-02-08 | 02-2028 | 02-2028 | 04-2028
0631 | CHPE LLC | NS Power Express | 2017-05-02 | 1000 | 1000 | DC |  |  | Quebec - New York | NY | J | Astoria Annex 345kV | NYPA |  | 12 | 2023-06-30 | SRIS, FS | 2023-01-11 | 2023-01-11 | 05-2026 | 05-2026 | 05-2026
0637 | Flint Mine Solar LLC | Flint Mine Solar | 2017-06-29 | 100 | 100 | S |  |  | Greene | NY | G | LaFarge - Pleasant Valley 115kV, Feura Bush - North Catskill 115kV | NM-NG |  | 11 | 2022-09-30 | FES, SRIS, FS | 2021-02-08 | 2021-02-08 | 12-2025 | 12-2025 | 5-2026
0644 | Hecate Energy Columbia County 1, LLC | Columbia County 1 | 2017-07-26 | 60 | 60 | S |  |  | Columbia | NY | F | Craryville 115kV | NYSEG |  | 11 | 2024-06-30 | FES, SRIS, FS | 2021-02-08 | 2021-02-08 | 12-2026 | 12-2026 | 2-2027
0670 | SunEast Skyline Solar LLC | SunEast Skyline Solar LLC | 2017-09-21 | 20 | 20 | S |  |  | Westmoreland | NY | E | Campus Rd - Clinton 46kV | NM-NG |  | 11 | 2023-07-31 | FES, SIS, FS | 2020-08-13 | 2020-07-31 | 11/2027 | 10/2027 | 4/2028
0683 | KCE NY 2, LLC | KCE NY 2 | 2018-01-18 | 200 | 200 | ES |  | 4 | Montgomery | NY | G | Coldenham 115kV | CHG&E |  | 11 | 2024-03-31 | SRIS, FS | 2021-03-16 | 2021-02-08 | 05-2027 | 05-2027 | 06-2027
0704 | Bear Ridge Solar, LLC | Bear Ridge Solar | 2018-03-20 | 100 | 100 | S |  |  | Niagara | NY | A | Mountain- Lockport 115kV | NM-NG |  | 10 | 2025-02-28 | SRIS, FS | 2021-02-08 | 2021-02-08 | 01-2027 | 04-2027 | 04-2027
0706 | High Bridge Wind, LLC | High Bridge Wind | 2018-04-25 | 100.8 | 100.8 | W |  |  | Chenango | NY | E | E. Norwich - Jennison 115kV | NYSEG |  | 11 | 2025-04-30 | SRIS, FS |  | 2021-02-08 | 09-2026 | 09-2026 | 11-2026
0710 | Horseshoe Solar Energy LLC | Horseshoe Solar | 2018-05-29 | 180 | 180 | S |  |  | Livingston | NY | B | Golah 115kV | NM-NG |  | 10 | 2025-03-31 | FES, FS | 2023-01-11 | 2023-01-11 | 02-2028 | 02-2028 | 05-2028
0716 | Moraine Solar Energy Center, LLC | Moraine Solar Energy Center | 2018-06-04 | 93.5 | 93.5 | S |  |  | Allegany | NY | C | Moraine 115kV | NYSEG |  | 10 | 2025-01-31 | FES, SRIS, FS |  | 2024-12-16 | 04-2027 | 04-2027 | 10-2027
0720 | Trelina Solar Energy Center, LLC | Trelina Solar Energy Center | 2018-06-07 | 79.8 | 79.8 | S |  |  | Seneca | NY | C | Border City - Station 168 115 KV | NYSEG |  | 11 | 2025-01-31 | SRIS, FS | 2021-02-08 | 2021-02-08 | 04-2028 | 03-2028 | 04-2028
0721 | Excelsior Energy Center, LLC | Excelsior Energy Center | 2018-06-07 | 280 | 280 | S |  |  | Genesee | NY | B | Dysinger - N. Rochester 345kV | NYPA |  | 11 | 2024-12-31 | SRIS, FS | 2021-01-22 | 2021-02-08 | 04-2026 | 09-2026 | 11-2026
0734 | ELP Ticonderoga Solar LLC | Ticonderoga Solar | 2018-06-12 | 20 | 20 | S |  |  | Essex | NY | F | Ticonderoga 115kV - Republic Line 2 | NM-NG |  | 11 | 2025-02-28 | FES, SIS, FS | 2021-03-18 | 2021-07-31 | 11-2026 | 02-2025 | 12-2026
0737 | Empire Offshore Wind LLC | Empire Wind 1 | 2018-06-12 | 816 | 816 | OSW |  |  | Kings | NY | J | Gowanus 345kV | ConEd |  | 11 | 2024-01-31 | SRIS, FS | 2021-02-08 | 2021-02-08 | 06-2025 | 11-2025 | 12-2026
0744 | Mitchell Energy Facility, LLC | Magruder BESS | 2018-07-18 | 20 | 20 | ES |  |  | Ulster | NY | G | East Walden - Modena 115kV | CHG&E |  | 11 | 2025-02-28 | SIS, FS | 2021-04-06 | 2021-03-04 | 02-2028 | 03-2028 | 04-2028
0766 | Sunrise Wind LLC | Sunrise Wind | 2018-09-28 | 880 | 880 | OSW |  |  | Suffolk | NY | K | Holbrook 138kV & West Bus 138kV | LIPA |  | 11 | 2025-04-30 | SRIS, FS | 2023-01-11 | 2023-01-11 | 06-2025 | 07-2026 | 07-2027
0774 | Tracy Solar Energy Center, LLC | Tracy Solar Energy Center | 2018-10-18 | 119 | 119 | S |  |  | Jefferson | NY | E | Thousand Island - Lyme 115kV | NM-NG |  | 10 | 2025-01-31 | SRIS, FS |  | 2024-12-16 | 05-2028 | 05-2028 | 11-2028
0776 | Greenidge Generation LLC | Greenidge Load | 2018-10-22 | 60 | 60 | L |  |  | Yates | NY | C | Greenidge 115kV | NYSEG |  | 7 | 2024-04-30 | SIS |  |  | 06-2025 | N/A | N/A
0777 | White Creek Solar, LLC | White Creek Solar | 2018-11-01 | 135 | 135 | S |  |  | Livingston | NY | B | Sta 82 - Sta 128 115kV | RG&E |  | 10 | 2025-05-31 | SRIS, FS |  | 2024-12-16 | 10-2027 | 10-2027 | 11-2027
0783 | ConnectGen Chautauqua County LLC | South Ripley Solar and BESS | 2018-12-07 | 270 | 270 | CR |  | 4 | Chautauqua | NY | A | South Ripley Substation 230kV | NM-NG |  | 11 | 2025-03-31 | FES, SRIS, FS | 2023-01-11 | 2023-01-11 | 07-2027 | 07-2027 | 12-2027
0787 | Levy Grid, LLC | Levy Grid, LLC | 2018-12-20 | 150 | 150 | ES |  | 2 | Erie | NY | A | Gardenville Subsation 115kV | NM-NG |  | 10 | 2022-11-30 | SRIS, FS | 2023-01-11 | 2023-01-11 | 08-2025 | 08-2025 | 08-2025
0800 | Rich Road Solar Energy Center, LLC | Rich Road Solar Energy Center | 2019-02-20 | 240 | 240 | CR |  | 4 | St. Lawrence | NY | E | Moses - Adirondack 230 kV Line #2 (MA2) | NYPA |  | 10 | 2025-01-31 | FES, SRIS, FS |  | 2024-12-16 | 10-2027 | 10-2027 | 04-2028
0801 | Prattsburgh Wind, LLC | Prattsburgh Wind Farm | 2019-02-21 | 147 | 147 | W |  |  | Steuben | NY | C | Stoney Ridge - Canadaigua 230kV | NYSEG |  | 10 | 2025-04-30 | SRIS, FS | 2023-01-11 | 2023-01-11 | 06-2027 | 06-2027 | 09-2027
0804 | KCE NY 10, LLC | KCE NY 10 | 2019-03-22 | 20 | 20 | ES | 80 |  | Erie | NY | A | Erie Substation 34.5kV | NYSEG |  | 11 | 2024-04-30 | FES, SIS, FS | 2022-10-20 | 2022-04-28 | 08-2026 | 08-2026 | 10-2026
0805 | Oxbow Hill Solar, LLC | Oxbow Hill Solar | 2019-03-22 | 140 | 140 | S |  |  | Madison | NY | C | Fenner 115kV Substation | NM-NG |  | 10 | 2024-04-30 | FES, FS | 2023-02-09 | 2023-01-11 | 10-2025 | 10-2025 | 12-2026
0807 | SunEast Hilltop Solar LLC | Hilltop Solar | 2019-03-28 | 20 | 20 | S |  |  | Rensselaer | NY | F | Eastover - Schaghticoke 115kV | NM-NG |  | 11 | 2024-09-30 | SIS, FS | 2021-04-07 | 2021-02-23 | 04/2028 | 03/2028 | 05/2028
0811 | Hecate Energy Cider Solar LLC | Cider Solar | 2019-04-03 | 500 | 500 | S |  |  | Genesee | NY | B | Dysinger - New Rochester 345kV | NYPA |  | 11 | 2024-06-30 | SRIS, FS | 2023-01-11 | 2023-01-11 | 05-2026 | 05-2026 | 01-2027
0815 | Bayonne Energy Center III, LLC | Bayonne Energy Center III | 2019-04-05 | 49.8 | 49.8 | ES |  | 4 | Kings | NY | J | Gowanus 345kV | ConEd |  | 10 | 2025-02-28 | SRIS, FS | 2023-04-25 | 2023-01-11 | 07-2026 | 08-2026 | 09-2026
0827 | Lighthouse Arthur Kill, LLC | Arthur Kill Energy Storage 1 | 2019-04-22 | 15 | 15 | ES |  |  | Richmond | NY | J | Fresh Kills 13.8kV | ConEd |  | 11 | 2023-11-30 | FS | 2022-07-07 | 2022-01-20 | 04-2025 | 07-2025 | 09-2025
0828 | SunEast Valley Solar LLC | Valley Solar | 2019-04-24 | 20 | 20 | S |  |  | Tioga | NY | C | Owego 34.5kV Substation | NYSEG |  | 11 | 2025-04-30 | SIS, FS | 2021-01-22 | 2020-11-03 | 01-2027 | 01-2027 | 01-2027
0832 | Hawthorn Solar, LLC | CS Hawthorn Solar | 2019-05-06 | 20 | 20 | S |  |  | Rensselaer | NY | F | North Troy - Hoosick 115kV | NM-NG |  | 11 | 2025-01-31 | FES, FS | 2022-07-13 | 2022-06-27 | 05-2026 | 04-2026 | 12-2026
0833 | Dolan Solar, LLC | Dolan Solar | 2019-05-06 | 20 | 20 | S |  |  | Washington | NY | F | Battenkill - Mohican 115kV | NM-NG |  | 11 | 2025-01-31 | SIS, FS | 2021-04-13 | 2021-03-01 | 12-2026 | 11-2026 | 12-2026
0834 | Eastern Generation, LLC | Luyster Creek Energy Storage 2 | 2019-05-07 | 79 | 79 | ES | 316 | 4 | Queens | NY | J | Astoria West 138kV | ConEd |  | 10 | 2025-01-31 | SRIS, FS |  | 2024-12-16 | 01-2027 | 01-2027 | 05-2027
0835 | Eastern Generation, LLC | Luyster Creek Energy Storage 1 | 2019-05-07 | 56.3 | 57.3 | ES | 225 | 4 | Queens | NY | J | Astoria West 138kV | ConEd |  | 10 | 2025-04-30 | SRIS, FS | 2023-02-22 | 2023-01-11 | 01-2027 | 01-2027 | 01-2027
0843 | Sandy Creek Solar LLC | NY37 Solar | 2019-05-17 | 20 | 20 | S |  |  | Jefferson | NY | E | Coffeen - West Adams 115kV Substation | NM-NG |  | 10 | 2025-02-28 | SIS, FS | 2023-05-17 | 2023-04-04 | 11-2026 | 11-2026 | 12-2026
0848 | SunEast Fairway Solar LLC | Fairway Solar | 2019-05-20 | 20 | 20 | S |  |  | St. Lawrence | NY | E | McIntyre - Corning 115kV (Line#6) | NM-NG |  | 11 | 2022-03-31 | SIS, FS | 2021-05-10 | 2021-05-05 | TBD | TBD | TBD
0850 | Cayuga Operating Company, LLC | Cayuga Load | 2019-05-21 | 50 | 50 | L |  |  | Cayuga | NY | C | Milliken 115kV | NYSEG |  | 7 | 2024-04-30 | SIS |  |  | 12-2026 | N/A | N/A
0855 | Bald Mountain Solar LLC | NY13 Solar | 2019-05-24 | 20 | 20 | S |  |  | Washington | NY | F | Mohican - Schaghticoke 115kV | NM-NG |  | 11 | 2022-04-30 | SIS, FS | 2021-10-07 | 2021-08-27 | TBD | TBD | TBD
0863 | Highbanks Solar LLC | Highbanks Solar | 2019-05-29 | 20 | 20 | S |  |  | Livingston | NY | B | S158 High banks 34.5 kV | RG&E |  | 10 | 2024-04-30 | SIS, FS | 2022-10-17 | 2022-08-05 | 12-2025 | 01-2026 | 02-2026
0864 | Greens Corners Solar LLC | NY38 Solar | 2019-05-29 | 120 | 120 | S |  |  | Jefferson | NY | E | Coffeen - West Adams 115kV | NM-NG |  | 11 | 2024-04-30 | SRIS, FS | 2023-01-11 | 2023-01-11 | 12-2026 | 11-2026 | 12-2026
0865 | Flat Hill Solar NY LLC. | Flat Hill Solar | 2019-05-31 | 20 | 20 | S |  |  | Herkimer | NY | E | Inghams-Valley 46kV Line 27 | NM-NG |  | 11 | 2023-08-31 | SIS, FS | 2022-09-15 | 2022-08-19 | 11-2025 | 11-2025 | 12-2025
0880 | Brookside Solar, LLC | Brookside Solar | 2019-06-10 | 100 | 100 | S |  |  | Franklin | NY | D | Chateaugay - Willis 115kV | NYSEG |  | 10 | 2025-05-31 | SRIS, FS |  | 2024-12-16 | 11-2027 | 11-2027 | 12-2027
0882 | Riverside Solar, LLC | Riverside Solar | 2019-06-10 | 100 | 100 | S |  |  | Jefferson | NY | E | Lyme Substation 115kV | NM-NG |  | 10 | 2025-01-31 | FES, SRIS, FS |  | 2024-12-16 | 09-2027 | 09-2027 | 12-2027
0883 | Garnet Energy Center, LLC | Garnet Energy Center | 2019-06-11 | 200 | 200 | S |  |  | Cayuga | NY | B | Pannell - Clay 345kV | NYPA |  | 10 | 2025-02-28 | FS | 2023-01-11 | 2023-01-11 | 11-2027 | 11-2027 | 04-2028
0885 | SunEast Grassy Knoll Solar LLC | Grassy Knoll Solar | 2019-06-12 | 20 | 20 | S |  |  | Herkimer | NY | E | Watkins Rd - Inghams 115kV | NM-NG |  | 11 | 2023-08-31 | SIS, FS | 2022-09-15 | 2022-08-15 | 11-2025 | 11-2025 | 12-2025
0887 | CHPE LLC | CH Uprate | 2019-06-12 | 250 | 250 | DC |  |  | Quebec-NY | NY | J | Astoria Annex 345kV | NYPA |  | 12 | 2023-06-30 | SRIS, FS | 2022-07-08 | 2023-01-11 | 05-2026 | 05-2026 | 05-2026
0899 | Sithe/Independence Power Partners, LP | Scriba-Volney Series Reactor | 2019-08-02 | N/A | N/A | AC |  |  | Oswego | NY | C | Volney - Scriba 345 kV | NM-NG |  | 11 | 2025-05-31 | SIS |  |  | 03-2026 | N/A | N/A
0907 | Harlem River ESS, LLC | Harlem River Yard | 2019-09-04 | 79.9 | 79.9 | ES |  | 4 | Queens | NY | J | Hell Gate 138kV | NYPA |  | 10 | 2025-02-28 | SRIS, FS | 2023-02-10 | 2023-01-11 | 11-2027 | 11-2027 | 01-2028
0930 | Eastern Generation, LLC | Luyster Creek Energy Storage 3 | 2019-10-25 | 15 | 15 | ES |  |  | Queens | NY | J | North Queens 27kV | ConEd |  | 10 | 2025-03-31 | SIS, FS |  | 2024-04-16 | 01-2027 | 01-2027 | 03-2027
0931 | East River ESS, LLC | Astoria Energy Storage | 2019-10-28 | 100 | 100 | ES | 400 | 4 | Queens | NY | J | Astoria West 138kV | ConEd |  | 10 | 2023-03-31 | SRIS, FS | 2023-01-11 | 2023-01-11 | 10-2026 | 04-2026 | 03-2026
0932 | Hatchery Solar LLC | Hatchery Solar | 2019-10-29 | 20 | 20 | S |  |  | Livingston | NY | B | Caledonia - Golah 34.5 kV | NM-NG |  | 10 | 2024-11-30 | SIS, FS |  | 2024-10-10 | TBD | TBD | TBD
0950 | Hemlock Ridge Solar LLC | Hemlock Ridge Solar | 2019-11-21 | 200 | 200 | S |  |  | Orleans | NY | B | Lockport - Mortimer 115kV | NM-NG |  | 10 | 2025-03-31 | SRIS, FS |  | 2024-12-16 | 04-2027 | 03-2027 | 05-2027
0953 | Sugar Maple Solar, LLC | Sugar Maple Solar | 2019-12-05 | 125 | 125 | S |  |  | Lewis | NY | E | North Carthage - Taylorville #8 and Black River - Taylorville #2 115kV | NM-NG |  | 10 | 2025-01-31 | SRIS, FS |  | 2024-12-16 | 09-2027 | 09-2027 | 12-2027
0956 | Holtsville Energy Storage, LLC | Holtsville 138kV Energy Storage | 2019-12-10 | 110 | 110 | ES | 2380 | 8 | Suffolk | NY | K | West Bus 138 kV | LIPA |  | 11 | 2024-03-31 | SRIS, FS | 2023-01-11 | 2023-01-11 | 06-2026 | 07-2026 | 09-2026
0967 | KCE NY 5 LLC | KCE NY 5 | 2019-12-27 | 94 | 94 | ES | 376 | 4 | Ulster | NY | G | Ohioville 115 kV | CHG&E |  | 10 | 2025-01-31 | SRIS, FS |  | 2024-12-16 | 11-2027 | 11-2027 | 12-2027
0971 | East Setauket Energy Storage, LLC | East Setauket Energy Storage | 2020-01-10 | 125 | 125 | ES | 2383.6 | 8 | Suffolk | NY | K | Holbrook - Miller Place 138kV | LIPA |  | 10 | 2025-02-28 | FS |  | 2025-02-11 | 02-2027 | 03-2027 | 04-2027
0979 | North Country Data Center | North Country Data Center | 2020-01-22 | 176 | 176 | L |  |  | St. Lawrence | NY | D | Reynolds 115kV | NYPA |  | 6 | 2023-07-31 | SIS |  |  | 12-2024 | N/A | N/A
0987 | Sunrise Wind LLC | Sunrise Wind II | 2020-01-29 | 44 | 44 | OSW |  |  | Suffolk | NY | K | Holbrook 138kV | LIPA |  | 11 | 2025-04-30 | FS | 2023-01-11 | 2023-01-11 | 06-2025 | 07-2026 | 07-2027
0995 | Alabama Solar Park LLC | Alabama Solar Park LLC | 2020-02-27 | 130 | 130 | S |  |  | Genesee | NY | B | Lockport - Batavia 115kV (Line#112) | NM-NG |  | 10 | 2025-01-31 | FS |  | 2024-12-16 | 07-2028 | 07-2028 | 10-2028
1000 | SED NY Holdings LLC | SunEast Flat Stone Solar LLC | 2020-03-18 | 20 | 20 | S |  |  | Oneida | NY | E | Oneida - Rome 115kV | NM-NG |  | 10 | 2024-03-31 | SIS, FS |  | 2024-03-14 | 09-2026 | 09-2026 | 11-2026
1003 | Clear View LLC | Clear View Solar | 2020-04-06 | 20 | 20 | S |  |  | Steuben | NY | C | Eelpot Road 34.5 kV | NYSEG |  | 11 | 2024-05-31 | SIS, FS | 2022-09-06 | 2022-07-08 | 11-2025 | 10-2025 | 12-2025
1007 | NYC Energy | NYC Energy LLC - Phase 2 | 2020-04-22 | 220.1 | 220.1 | ES | 880.4 | 4 | Kings | NY | J | Hudson Ave 138 kV | ConEd |  | 10 | 2025-01-31 | SRIS, FS |  | 2024-12-16 | 05-2027 | 05-2027 | 06-2027
1009 | Yellow Barn Solar, LLC | Yellow Barn Solar | 2020-04-30 | 160 | 160 | S |  |  | Tompkins | NY | C | Milliken - Etna 115 kV line #975 | NYSEG |  | 10 | 2025-01-31 | SRIS, FS |  | 2024-12-16 | 11-2025 | 11-2025 | 12-2025
1015 | Somers Solar, LLC | Somers Solar, LLC | 2020-05-05 | 20 | 20 | S |  |  | Washington | NY | F | Mohican - Battenkill 115kV | NM-NG |  | 11 | 2024-12-31 | FS |  | 2024-03-14 | 09-2026 | 10-2026 | 12-2026
1031 | ConnectGen Montgomery County LLC | Mill Point Solar | 2020-06-18 | 250 | 250 | CR | 700 | 4 | Montgomery | NY | E | Marcy - New Scotland 345kV | NM-NG |  | 10 | 2025-01-31 | SRIS, FS |  | 2024-12-16 | 07-2028 | 07-2028 | 12-2028
1039 | SED NY Holdings LLC | Morris Solar | 2021-01-06 | 20 | 20 | S |  |  | St. Lawrence | NY | E | Battle Hill - Balmat 115kV | NM-NG |  | 10 | 2025-05-31 | SIS, FS |  | 2024-03-14 | 01-2028 | 02-2028 | 03-2028
1047 | SED NY Holdings LLC | Millers Grove Solar | 2020-07-09 | 20 | 20 | S |  |  | Herkimer | NY | E | Porter - Watkins 115kV | NM-NG |  | 11 | 2025-03-31 | SIS, FS |  | 2024-03-28 | 09-2026 | 09-2026 | 12-2026
1051 | SED NY Holding LLC | Transit Solar | 2020-07-21 | 20 | 20 | S |  |  | Genesee | NY | B | S.E Batavia - Golah 115kV | NM-NG |  | 10 | 2024-03-31 | SIS, FS |  | 2024-03-14 | 08-2025 | 09-2025 | 12-2025
1079 | Somerset Solar, LLC | Somerset Solar | 2020-08-18 | 125 | 125 | S |  |  | Niagara | NY | A | Kintigh 345 kV | NYSEG |  | 10 | 2025-01-31 | SRIS, FS |  | 2024-12-16 | 01-2027 | 01-2027 | 03-2027
1080 | Mineral Basin Solar Power, LLC | Mineral Basin Solar Power | 2020-08-21 | 401.6 | 401.6 | S |  |  | Clearfield | PA | C | Homer City - Mainesburg 345KV | NYSEG |  | 10 | 2025-01-31 | SRIS, FS |  | 2024-12-16 | 10-2027 | 10-2027 | 05-2028
1089 | Flat Creek Solar NY LLC | Flat Creek Solar | 2020-09-04 | 200 | 200 | S |  |  | Montgomery | NY | F | Edic to Princetown 345kV Line 352 | NYPA |  | 10 | 2025-04-30 | SRIS, FS |  | 2024-12-16 | 10-2028 | 10-2028 | 11-2028
1113 | Caithness LI Energy Storage, LLC | CLIES 20 MW | 2020-11-18 | 20 | 20 | ES |  |  | Suffolk | NY | K | Sills Road 138 kV | LIPA |  | 10 | 2025-03-31 | SIS, FS |  | 2024-06-13 | 12-2027 | 10-2027 | 12-2027
1115 | SED NY Holdings LLC | Flat Creek Solar 2 | 2020-11-23 | 100 | 100 | S |  |  | Montgomery | NY | F | Edic - Princetown 345 kV Line# 352 | NYPA |  | 10 | 2025-01-31 | SRIS, FS |  | 2024-12-16 | 10-2028 | 10-2028 | 11-2028
1117 | Caithness LI Energy Storage, LLC | CLIES 70MW | 2020-11-25 | 70 | 70 | ES | 420 | 6 | Suffolk | NY | K | Sills Road 138kV | LIPA |  | 10 | 2025-03-31 | SRIS, FS |  | 2025-02-11 | 12-2027 | 12-2027 | 12-2027
1122 | Microgrid Networks, LLC | East Fishkill | 2020-12-11 | 205 | 205 | ES | 800 | 4 | Dutchess | NY | G | Shenandoah 115kV | CHG&E |  | 10 | 2025-01-31 | SRIS, FS |  | 2024-12-16 | 05-2028 | 05-2028 | 11-2028
1123 | KCE NY 29, LLC | KCE NY 29 | 2020-12-14 | 150 | 150 | ES | 600 | 4 | Suffolk | NY | K | Kings 138 kV | LIPA |  | 10 | 2025-04-30 | FS |  | 2024-12-16 | 11-2027 | 11-2027 | 12-2027
1125 | New York Power Authority and National Grid | Northern New York Priority Transmission Project (NNYPTP) | 2020-12-22 | N/A | N/A | AC |  |  | St. Lawrence-Lewis | NY | D, E | 1. Moses 230 kV substation 2. Haverstock 345 kV sub (new) 3. Massena 230 kV substation 4. Adirondack 345 kV sub (new) 5. Willis 230 kV substation 6. Ryan & Patnode 230 kV substations 7. Chases Lake 345 kV sub (new) 8. Marcy 345 kV sub 9. Edic 345 kV sub | NYPA, NM-NG |  | 11 | 2025-05-31 | FS |  | 2023-02-14 | 12-2025 | N/A | N/A
1130 | Hoffman Falls Wind LLC | Hoffman Falls Wind | 2021-01-27 | 72 | 72 | W |  |  | Madison | NY | C | Cortland - Fenner 115kV Line #3 | NM-NG |  | 10 | 2025-01-31 | FS |  | 2024-12-16 | 10-2027 | 10-2027 | 12-2027
1148 | Liberty Renewables Inc. | Agricola Wind | 2021-03-10 | 97 | 97 | W |  |  | Cayuga | NY | C | Milliken to Wright Ave 115 kV line #973 | NYSEG |  | 10 | 2025-01-31 | SRIS, FS |  | 2024-12-16 | 10-2027 | 10-2027 | 12-2027
1151 | York Run Solar, LLC | York Run Solar | 2021-03-18 | 90 | 90 | S |  |  | Chautauqua | NY | A | Falconer - Warren 115 kV line #171 | NM-NG |  | 10 | 2025-01-31 | SRIS, FS |  | 2024-12-16 | 05-2026 | 06-2026 | 08-2026
1166 | BR Project 1 LLC | BR Benson Mines Solar | 2021-05-07 | 12.1 | 12.1 | S |  |  | St. Lawrence | NY | E | Brown's Falls to Newton Falls #22 34.5kV Line | NM-NG |  | 10 | 2024-11-30 | SIS, FS |  | 2024-10-16 | 07-2026 | 08-2026 | 10-2026
1183 | Fort Covington Solar LLC | NY125A - Fort Covington Solar | 2021-05-20 | 250 | 250 | S |  |  | Franklin | NY | D | Moses-Willis 230 kV (MW1) | NYPA |  | 10 | 2025-01-31 | SRIS, FS |  | 2024-12-16 | 07-2027 | 07-2027 | 08-2027
1184 | Boralex US Development | NY125B - Two Rivers Solar | 2021-05-20 | 200 | 200 | S |  |  | St-Lawrence | NY | D | Moses-Willis 230kV (MW2) | NYPA |  | 10 | 2025-01-31 | SRIS, FS |  | 2024-12-16 | 07-2027 | 07-2027 | 08-2027
1188 | North Seneca Solar Project | North Seneca Solar Project, LLC | 2021-05-27 | 105 | 105 | S |  |  | Seneca | NY | C | Hooks Road - Elbridge 115kV line#7 | NM-NG |  | 10 | 2025-01-31 | SRIS, FS |  | 2024-12-16 | 06-2027 | 06-2027 | 09-2027
1213 | Petawatt Holdings, Inc. | St Lawrence Data and Agricultural Center | 2021-06-28 | 200 | 200 | L |  |  | St. Lawrence | NY | D | Dennison 115kV substation | NM-NG |  | 6 | 2023-01-14 | SIS |  |  | 01-2026
1237 | Sugar Maple Solar | Sugar Maple Energy Storage | 2021-08-24 | 20 | 20 | ES | 80 |  | Jefferson | NY | E | North Carthage-Taylorville #8 and Black River-Taylorville #2 115 kV lines | NM-NG |  | 10 | 2024-10-31 | SIS |  |  | 06-2026 | 09-2026 | 12-2026
1254 | Barrett Hempstead Battery Storage | Barrett Hempstead Battery Storage | 2021-09-22 | 40 | 40 | ES | 80 | 2 | Nassau | NY | K | Barrett to Long Beach 33 kV circuit No 1(33-224) | LIPA |  | 10 | 2025-02-28 | SRIS, FS |  | 2025-02-11 | 12-2025 | 01-2026 | 03-2026
1255 | Holtsville Brookhaven Battery Storage | Holtsville Brookhaven Battery Storage | 2021-09-22 | 79.9 | 79.9 | ES | 159.8 | 2 | Suffolk | NY | K | Line 69-849 from West Yaphank to North Bellport | LIPA |  | 10 | 2025-02-28 | SRIS |  |  | 12-2025 | 01-2026 | 03-2026
1257 | Edwards Calverton Battery Storage | Edwards Calverton Battery Storage | 2021-09-22 | 60 | 60 | ES | 120 | 2 | Suffolk | NY | K | Edwards Avenue Substation at 138 kV | LIPA |  | 10 | 2025-02-28 | SRIS, FS |  | 2025-02-11 | 12-2025 | 01-2026 | 03-2026
1288 | Clean Path New York LLC | CPNY-X | 2021-11-23 | 1300 | 1300 | DC |  |  | Delaware, Queens | NY | E,J | Fraser 345 kV and Rainey 345 kV substations | NYSEG, ConEd |  | 10 | 2025-01-31 | SRIS, FS |  | 2024-12-16 | 06-2028 | 06-2028 | 12-2028
1289 | New York Power Authority / New York Transco LLC. | Propel NY Energy - Alternate Solution 5 | 2021-10-11 | N/A | N/A | AC |  |  | Nassau, Queens, Bronx, Westchester | NY | I; J; K | Sprain Brook 345 kV; Tremont 345 kV; East Garden City 345 kV; Barrett 138 kV; East Garden City 138 kV; Shore Road 138 kV; Syosset 138 kV; Ruland Rd 138 kV | LIPA, ConEd, NYPA |  | 9 | 2024-12-31 | SIS |  |  | 06/29-06/30
1308 | New York Power Authority | Richmond Spoke | 2021-12-02 | N/A | N/A | AC |  |  | Richmond | NY | J | Goethals - Gowanus 345 kV | ConEd |  | 6 | 2022-07-31 | SIS |  |  | 12-2030
1315 | Sabey Data Center Properties, LLC | SDC St. Lawrence | 2021-12-20 | 120 | 120 | L |  |  | St. Lawrence | NY | D | Moses-Reynolds MRG-1 and Moses-Reynolds MRG-2 at 115kV | NYPA |  | 6 | 2022-09-30 | SIS |  |  | 08-2025
1329 | ELP Granby Solar II LLC | ELP Granby Solar II | 2022-02-11 | 20 | 20 | CR | 5 | 4 | Oswego | NY | C | Curtis Street - Teall 115 kV | NM-NG |  | 10 | 2024-11-30 | FES, SIS, FS |  | 2024-10-07 | 09-2026 | 10-2026 | 12-2026
1365 | Queensboro Development, LLC | Queensboro Renewable Express Circuit A | 2022-04-15 | N/A | N/A | DC |  |  | Queens | NY | J | Rainey 345 kV substation and Vernon 138 kV substation | ConEd |  | 6 | 2022-07-31 | SIS |  |  | 04-2029
1366 | Queensboro Development, LLC | Queensboro Renewable Express Circuit B | 2022-04-15 | N/A | N/A | DC |  |  | Queens | NY | J | Rainey 345 kV substation and Vernon 138 kV substation | ConEd |  | 6 | 2024-03-31 | SIS |  |  | 04-2029
1465 | Digihost Technologies, Inc. | Digihost load | 2022-11-14 | 50.2 | 50.2 | L |  |  | Niagara | NY | A | Walck Rd. 115kV | NM-NG |  | 5 | 2025-04-30 |  |  |  | 08-2027
1484 | GCEDC | 580 STAMP load increase | 2022-12-02 | 300 | 300 | L |  |  | Genesee | NY | B | 115 kv STAMP substation | NM-NG |  | 6 | 2023-12-31 | SIS |  |  | 12-2025
1536 | Micron New York Semiconductor Manufacturing LLC | White Pine Phase 1 | 2023-03-11 | 480 | 480 | L |  |  | Onondaga | NY | C | Clay 345 kV Substation | NM-NG |  | 6 | 2024-02-29 | SIS |  |  | 06-2026
1555 | North Bergen Liberty Generating LLC | Liberty Green Line | 2023-05-12 | N/A | N/A | AC |  |  | New York County | NY | J | Con Edison W 49th St 345kV Substation | ConEd, PJM |  | 2 | 2025-04-30 |  |  |  | 01-2029
1627 | Micron New York Semiconductor Manufacturing LLC | Micron Fab 2 | 2023-10-31 | 576 | 507 | L |  |  | Onondaga | NY | C | National Grid Clay 345 kV Substation | NM-NG |  | 5 | 2024-06-30 |  |  |  | 09-2030
1646 | P&M Brick LLC | POWI Project | 2023-11-30 | 50 | 50 | L |  |  | Albany | NY | F | New Scotland to Knickerbocker 345kV line | NM-NG | NY Transco, LSPNY, CHGE | 5 | 2024-07-31 |  |  |  | 01-2027
1667 | Consolidated Edison Company of New York | Designated Public Policy Project Rainey Breaker Replacement | 2024-01-12 | N/A | N/A | AC |  |  | New York | NY | J | Rainey 345kV Substation | ConEd |  | 7 | 2024-07-31 |  |  |  | 05-2030
1670 | Lake Mariner Data LLC | Lake Mariner Data II | 2024-01-23 | 250 | 250 | L |  |  | Niagara | NY | A | Kintigh 345kV Substation | NYSEG |  | 6 | 2025-04-30 | SIS |  |  | 06-2025
1671 | NYSEG | Meyer Substation Rebuild and South Perry Substation Rebuild | 2024-02-02 | N/A | N/A | AC |  |  | Wyoming/Livingston | NY | C | Meyer 115kV, 34.5, 230kV South Perry 115kV, 34.5kV, 69kV | NYSEG | RG&E | 4 | 2025-04-30 |  |  |  | 12-2030
1672 | National Grid | Ames Road Station | 2024-02-05 | N/A | N/A | AC |  |  | Montgomery | NY | E,F | 345kV Edic Princetown 351 345kV Edic Princetwon 352 115kV Saint Johnsville Mashville 11 115kV Clinton Marshville 12 | NM-NG, LS Power | NYPA | 4 | 2024-02-29 |  |  |  | 01-2028
1681 | Niagara Falls Redevelopment LLC | Niagara Digital Campus | 2024-04-09 | 140 | 140 | L |  |  | Niagara | NY | A | Adams to Packard 115kV lines 187 and 188 | NM-NG |  | 5 | 2025-03-31 |  |  |  | 12-2027
1683 | Cayuga Operating Company, LLC | Cayuga Compute | 2024-04-24 | 88 | 88 | L |  |  | Tompkins | NY | C | Milliken substation 115kV | NYSEG |  | 5 | 2025-05-31 |  |  |  | 10-2026
1685 | energyRe Giga-Projects USA, LLC | Clean Borough Power Link #1 | 2024-05-30 | N/A | N/A | DC |  |  | Richmond,Kings,Queens,West Chester | NY | J | Brooklyn Clean Energy Hub 345kV; Farragut 345kV; Goethals 345kV, Astoria Annex 345kV, Sprain Brook 345kV | CONED, NYPA | PJM | 5 | 2025-02-28 |  |  |  | 12-2032
1686 | energyRe Giga-Projects USA, LLC | Clean Borough Power Link #2 | 2024-05-30 | N/A | N/A | DC |  |  | New York, Richmond, Kings | NY | J | Brooklyn Clean Energy Hub 345kV; Farragut 345kV; West 49 St - East13 St 345kV lines; Goethals 345kV, | CONED | NYPA, PJM | 5 | 2025-02-28 |  |  |  | 12-2032
1687 | energyRe Giga-Projects USA, LLC | Clean Borough Power Link #3 | 2024-05-30 | N/A | N/A | DC |  |  | Richmond, New York, Kings, Queens | NY | J | Brooklyn Clean Energy Hub 345kV; Mott Haven - Rainey 345kV lines; Rainey 345kV; Astoria West 138kV; Farragut 345kV; Astoria Annex 345kV, Goethals 345 kV | CONED, NYPA | PJM | 5 | 2025-02-28 |  |  |  | 12-2032
1688 | Viridon New York Inc. | Liberty Link 1 | 2024-05-31 | N/A | N/A | DC |  |  | Kings, Westchester, Richmond | NY | I, J | Brooklyn Clean Energy Hub (BCEH) 345kV, Farragut 345kV, Sprain Brook 345kV, Goethals 345kV | Con Edison | PJM | 5 | 2025-02-28 |  |  |  | 12-2032
1689 | Viridon New York Inc. | Liberty Link 2 | 2024-05-31 | N/A | N/A | DC |  |  | Kings, Westchester, Richmond | NY | I, J | Brooklyn Clean Energy Hub (BCEH) 345kV, Farragut 345kV, Sprain Brook 345kV, Goethals 345kV | Con Edison | PJM | 5 | 2025-02-25 |  |  |  | 12-2032
1690 | Viridon New York Inc. | Liberty Link 3 | 2024-05-31 | N/A | N/A | DC |  |  | Kings, New York, Richmond | NY | J | Brooklyn Clean Energy Hub (BCEH) 345kV, Farragut 345kV, W49th Street 345kV - E13th Street 345 kV lines, Goethals 345kV | Con Edison | PJM | 5 | 2025-02-25 |  |  |  | 12-2032
1691 | New York Transco LLC | Energy Link New York Solution 1 | 2024-06-13 | N/A | N/A | DC |  |  | Kings, Westchester, Queens, Richmond | NY | I,J | Brooklyn Clean Energy Hub 345kV; Farragut 345kV; Goethals 345kV, Astoria Annex 345kV, Sprain Brook 345kV | CONED, NYPA | PJM | 5 | 2025-02-28 |  |  |  | 01-2033
1692 | New York Transco LLC | Energy Link New York Solution 2 | 2024-06-13 | N/A | N/A | DC |  |  | Kings, Westchester, Queens, Richmond | NY | I, J | Brooklyn Clean Energy Hub 345 kV, Farragut 345 kV, Sprain Brook 345 kV, Astoria Annex 345 kV, Goethals 345 kV | CONED, NYPA | PJM | 5 | 2025-02-28 |  |  |  | 01-2033
1693 | New York Transco LLC | Energy Link New York Solution 3 | 2024-06-13 | N/A | N/A | DC |  |  | Kings, Westchester, Queens, Richmond | NY | I, J | Brooklyn Clean Energy Hub 345 kV, Farragut 345 kV, Sprain Brook 345 kV, Astoria Annex 345 kV, Goethals 345 kV, Gowanus- Goethals 345 kV lines | CONED, NYPA | PJM | 5 | 2025-02-28 |  |  |  | 01-2033
1694 | New York Transco LLC | Energy Link New York Solution 4 | 2024-06-13 | N/A | N/A | DC |  |  | Kings, Westchester, Queens, Richmond | NY | I, J | Brooklyn Clean Energy Hub 345 kV, Farragut 345 kV, Sprain Brook 345 kV, Astoria Annex 345 kV, Goethals 345 kV | CONED, NYPA | PJM | 5 | 2025-02-28 |  |  |  | 01-2033
1695 | New York Transco LLC | Energy Link New York Solution 5 | 2024-06-13 | N/A | N/A | DC |  |  | Kings, Richmond, Queens, Westchester | NY | I,J | Brooklyn Clean Energy Hub 345kV; Farragut 345kV; Goethals 345kV, Astoria Annex 345kV, Sprain Brook 345kV | CONED, NYPA | PJM | 5 | 2025-02-28 |  |  |  | 01-2033
1696 | New York Transco LLC | Energy Link New York Solution 6 | 2024-06-13 | N/A | N/A | DC |  |  | Kings, Westchester, Queens, Richmond | NY | I,J | Brooklyn Clean Energy Hub 345kV; Farragut 345kV; Rainey 345kV; Astoria West 138kV; Mott Haven - Rainey 345kV lines; Goethals 345kV; Astoria Annex 345kV; Sprain Brook 345kV | CONED, NYPA | PJM | 5 | 2025-02-28 |  |  |  | 01-2033
1697 | New York Transco LLC | Energy Link New York Solution 7 | 2024-06-13 | N/A | N/A | DC |  |  | Brooklyn & Staten Island | NY | I,J | Brooklyn Clean Energy Hub 345kV; Farragut 345kV; Rainey 345kV; Astoria West 138kV; Mott Haven - Rainey 345kV lines; Goethals 345kV, Astoria Annex 345kV; Sprain Brook 345kV; Gowanus- Goethals 345kV lines | CONED, NYPA | PJM | 5 | 2025-02-28 |  |  |  | 01-2033
1698 | New York Transco LLC | Energy Link New York Solution 10 | 2024-06-13 | N/A | N/A | DC |  |  | Kings, Westchester, Queens, Richmond | NY | I, J | Brooklyn Clean Energy Hub 345kV, Farragut 345kV, Sprain Brook 345kV , Astoria Annex 345kV , Goethals 345kV , Mott Haven - Rainey 345kV substations, Gowanus - Goethals 345kV , Astoria West 345 kV, Rainey 345 kV | CONED, NYPA | PJM | 5 | 2025-02-28 |  |  |  | 01-2033
1699 | New York Power Authority & LS Power Grid New York Corporation I | Five Boro Energy Connect ? Mint | 2024-06-13 | N/A | N/A | DC |  |  | Kings,Queens,NY,Bronx,Delaware, | NY | E, J | Brooklyn Clean Energy Hub 345kV, Farragut 345kV, Rainey 345kV, Academy 345kV, Mott Haven 345kV, Astoria Annex 345kV, Fraser 345kV | CONED, NYPA, NYSEG | PJM | 5 | 2025-02-28 |  |  |  | 10-2032
1700 | New York Transco LLC | Energy Link New York Solution 8 | 2024-06-15 | N/A | N/A | DC |  |  | Kings,Bronx,Queens,Westchester,Richmond | NY | I,J | Brooklyn Clean Energy Hub 345kV; Mott Haven 345kV; Rainey 345kV; Gowanus 345kV; Sprain Brook 345kV ; Goethals 345 kV | CONED | NYPA, PJM | 5 | 2025-02-28 |  |  |  | 01-2033
1701 | New York Transco LLC | Energy Link New York Solution 9 | 2024-06-15 | N/A | N/A | DC |  |  | Kings,Bronx,Queens,Westchester,Richmond | NY | I,J | Brooklyn Clean Energy Hub 345kV; Mott Haven 345kV; Rainey 345kV; Gowanus 345kV; Sprain Brook 345kV, Goethals 345 kV | CONED | NYPA, PJM | 5 | 2025-02-28 |  |  |  | 01-2033
1702 | New York Power Authority & LS Power Grid New York Corporation I | Five Boro Energy Connect ? Sage | 2024-06-15 | N/A | N/A | DC |  |  | Kings, Queens, New York, Bronx | NY | J | Brooklyn Clean Energy Hub 345 kV, Farragut 345 kV, Academy 345 kV, Astoria Annex 345 kV, Mott Haven 345 kV, Mott Haven - Rainey 345 kV Lines, | CONED, NYPA | PJM | 5 | 2025-02-28 |  |  |  | 09-2032
1703 | New York Power Authority & LS Power Grid New York Corporation I | Five Boro Energy Connect - Ruby | 2024-06-15 | N/A | N/A | DC |  |  | Kings, Queens, New York, Bronx | NY | J | Brooklyn Clean Energy Hub 345 kV, Farragut 345 kV, Rainey 345 kV, West 49 Street 345 kV, Mott Haven 345 kV, Astoria Annex 345 kV, Mott Haven - Rainey 345kV Lines | CONED, NYPA | PJM | 5 | 2025-02-28 |  |  |  | 09-2032
1704 | New York Power Authority & LS Power Grid New York Corporation I | Five Boro Energy Connect - Rose | 2024-06-15 | N/A | N/A | DC |  |  | Kings, Queens, New York, Bronx | NY | J | Brooklyn Clean Energy Hub 345 kV, Farragut 345 kV, Rainey 345 kV, West 49 Street 345 kV, Mott Haven 345 kV, Astoria Annex 345 kV, Mott Haven - Rainey 345kV Lines | CONED, NYPA | PJM | 5 | 2025-02-28 |  |  |  | 09-2032
1705 | New York Power Authority & LS Power Grid New York Corporation I | Five Boro Energy Connect ? Olive | 2024-06-15 | N/A | N/A | DC |  |  | Kings/Queens/NY/Bronx/Delaware | NY | E, J | Brooklyn Clean Energy Hub 345 kV, Farragut 345 kV, Rainey 345 kV, Academy 345 kV, Mott Haven 345 kV, Astoria Annex 345kV , Fraser, Mott Haven - Rainey 345kV Lines, | CONED, NYPA, NYSEG | PJM | 5 | 2025-02-28 |  |  |  | 06-2033
1706 | New York Power Authority & LS Power Grid New York Corporation I | Five Boro Energy Connect ? Kelly | 2024-06-17 | N/A | N/A | DC |  |  | Kings, Queens, New York, Bronx | NY | J | Brooklyn Clean Energy Hub 345kV, Farragut 345kV, Rainey 345kV, Academy 345kV, Mott Haven 345 kV, Astoria Annex 345kV, Tremont 345kV, Mott Haven - Rainey 345kV Lines, | Con Edison, NYPA | PJM | 5 | 2025-02-28 |  |  |  | 08-2033
1707 | New York Power Authority & LS Power Grid New York Corporation I | Five Boro Energy Connect ? Hazel | 2024-06-17 | N/A | N/A | DC |  |  | Kings/Queens/NY/Bronx/Delaware | NY | E, J | Brooklyn Clean Energy Hub 345kV, Farragut 345kV, Rainey 345kV, Academy 345kV, Mott Haven 345kV, Astoria Annex 345kV, Fraser 345kV, Mott Haven - Rainey 345kV Lines, | Con Edison, NYPA, NYSEG | PJM | 5 | 2025-02-28 |  |  |  | 12-2033
1708 | New York Power Authority & LS Power Grid New York Corporation I | Five Boro Energy Connect ? Navy | 2024-06-17 | N/A | N/A | DC |  |  | Kings,Queens,Bronx,Richmond,Westchester | NY | I, J | Brooklyn Clean Energy Hub 345kV, Farragut 345kV, Astoria Annex 345kV, Mott Haven 345kV, Rainey 345kV, Dunwoodie 345kV, Sprain Brook 345kV, Gowanus - Goethals 345kV Lines, Mott Haven - Rainey 345kV Lines, Gowanus 345 kV | Con Edison, NYPA | PJM | 5 | 2025-02-28 |  |  |  | 09-2032
1709 | New York Power Authority & LS Power Grid New York Corporation I | Five Boro Energy Connect ? Royal | 2024-06-17 | N/A | N/A | DC |  |  | Kings,Queens,Bronx,Richmond,Westchester, | NY | J | Brooklyn Clean Energy Hub 345kV, Farragut 345kV, Rainey 345kV, Astoria Annex 345kV, Mott Haven 345kV, Tremont 345kV, W49th St 345kV, Gowanus - Goethals 345kV Lines, Mott Haven - Rainey 345kV Lines, Gowanus 345 kV | Con Edison, NYPA | PJM | 5 | 2025-02-28 |  |  |  | 05-2033
1710 | New York Power Authority & LS Power Grid New York Corporation I | Five Boro Energy Connect ? Golden | 2024-06-17 | N/A | N/A | DC |  |  | Kings,Queens,NY,Bronx,Westchester,Delawa | NY | E, I, J | Brooklyn Clean Energy Hub 345kV, Farragut 345kV, Rainey 345kV, Academy 345kV, Astoria Annex 345kV, Mott Haven 345kV, Dunwoodie 345kV, Fraser 345kV, Vernon 138kV, Mott Haven - Rainey 345kV Lines | Con Edison, NYPA, NYSEG, | PJM | 5 | 2025-02-28 |  |  |  | 10-2033
1711 | New York Power Authority & LS Power Grid New York Corporation I | Five Boro Energy Connect ? Honey | 2024-06-17 | N/A | N/A | DC |  |  | Kings,Queens,NY,Bronx,Delaware | NY | E, J | Brooklyn Clean Energy Hub 345kV, Farragut 345kV, Rainey 345kV, Academy 345kV, Astoria Annex 345kV, Mott Haven 345kV, Vernon 138kV, Fraser 345kV, | Con Edison, NYPA, NYSEG, | PJM | 5 | 2025-02-28 |  |  |  | 10-2033
1712 | New York Power Authority & LS Power Grid New York Corporation I | Five Boro Energy Connect ? Cobalt | 2024-06-17 | N/A | N/A | DC |  |  | Kings,Queens,NY,Bronx,Richmond,Delaware | NY | E, J | Brooklyn Clean Energy Hub 345kV, Farragut 345kV, Rainey 345kV, Academy 345kV, Astoria Annex 345kV, Mott Haven 345kV, Gowanus - Goethals 345kV Lines, Mott Haven - Rainey 345kV Lines, Fraser 345kV, Gowanus 345 | Con Edison, NYPA, NYSEG | PJM | 5 | 2025-02-28 |  |  |  | 10-2033
1713 | Project Sycamore - Orangeburg | Project Sycamore Orangeburg | 2024-06-19 | 25.3 | 25.3 | L |  |  | Rockland | NY | G | Oak Street 138kV | O&R |  | 4 | 2025-03-31 |  |  |  | 06-2026
1714 | Robert Delcalzo | Hudson Valley Data Center | 2024-07-02 | 25 | 25 | L |  |  | Rockland | NY | G | Line 60 138KV - Ramp to Tallman | O&R |  | 4 | 2024-07-31 |  |  |  | 02-2027
1715 | Jerry Martin | 1547 CSR - Orangeburg LLC | 2024-07-02 | 60 | 60 | L |  |  | Rockland | NJ | G | 138kV Line 703 between Corporate Drive and Harings Corner | O&R |  | 4 | 2025-04-30 |  |  |  | 01-2027
1716 | DataBank Holdings, LLC | Orangeburg Expansion Phase 2 | 2024-08-05 | 60 | 60 | L |  |  | Orange | NY | G | Oak St 38kV substation | O&R |  | 4 | 2025-05-31 |  |  |  | 12-2027
1717 | Holtec Decommissioning International (HDI) | Proposed Datacenters at 450 Broadway, Buchanan, NY, 10511 | 2024-08-07 | 200 | 200 | L |  |  | Westchester | NY | H | Buchanan 138kV Substation | ConEd |  | 4 | 2024-09-30 |  |  |  | 09-2026
1721 | WF Industrial XII LLC | Brookhaven Logistics Center | 2024-10-28 | 176.6 | 176.6 | L |  |  | Suffolk | NY | K | 138-872 Holbrook to Sills Rd or 138-873 West Bus to Sills Rd. | LIPA |  | 4 | 2025-05-31 |  |  |  | 01-2027
1725 | Greenidge Generation, LLC | Greenidge 200 MW Data Center Project | 2024-12-20 | 200 | 200 | L |  |  | Yates | NY | C | New York State Electric & Gas (NYSEG) - Greenidge 115 kV Substation | NYSEG |  | 4 | 2025-04-30 |  |  |  | 03-2028
1726 | Riverview Innovation & Technology Campus, Inc. | Data & Technology Campus | 2025-01-31 | 300 | 300 | L |  |  | Erie | NY | A | National Grid 230kV line 77 | NM-NG |  | 4 | 2025-05-31 |  |  |  | 01-2027
1728 | Arconic Corporation | Arsenal Data Site 250 | 2025-03-07 | 250 | 250 | L |  |  | St Lawrence | NY | E | Denniston Substation | NYPA | National Grid | 4 | 2025-05-31 |  |  |  | 03-2027
1729 | Arconic Corporation | Arsenal Data Site 500 | 2025-03-07 | 500 | 500 | L |  |  | St Lawrence | NY | E | Denniston Substation | NYPA | National Grid | 4 | 2025-05-31 |  |  |  | 03-2027
1730 | Arconic Corporation | Arsenal Data Site 1000 | 2025-03-07 | 1000 | 1000 | L |  |  | St Lawrence | NY | E | Denniston Substation | NYPA | National Grid | 4 | 2025-05-31 |  |  |  | 03-2027
1731 | ZeroC Data Centers, LLC | New York State Artificial Intelligence Data Center | 2025-03-14 | 300 | 300 | L |  |  | St. Lawrence | NY | D | Dennison 115kV substation | NM-NG | HQ, NYPA, ALCOA | 4 | 2025-04-30 |  |  |  | 10-2026
1732 | Wulf Compute LLC | Wulf Compute Data Center II | 2025-03-29 | 250 | 250 | L |  |  | Niagara | NY | A | Kintigh sub-station | NYSEG | NYPA, NM-NG, IESO | 4 | 2025-05-31 |  |  |  | 06-2026
1733 | Cayuga Operating Company, LLC | Cayuga Data | 2025-03-29 | 162 | 162 | L |  |  | Tompkins | NY | C | Milliken Substation | NYSEG |  | 4 | 2025-05-31 |  |  |  | 08-2026
1735 | Turin Management LLC | Remington Factory Redevelopment | 2025-05-02 | 120 | 120 | L |  |  | Herkimer | NY | F | Murphy Station City of Ilion, Bus Number 147905, 115kV | Village of Ilion | National Grid | 1 | 2025-05-31 |  |  |  | 07-2028
1736 | Ranalli SuperDC LLC | Ranalli SuperDC | 2025-05-07 | 300 | 300 | L |  |  | Onondaga | NY | C | Feeds from Clay Substation | NM-NG | NYPA | 1 | 2025-05-31 |  |  |  | 05-2028
| Number of new projects during May |  | 2
| Number of new projects year to date |  | 11
| Number withdrawn during May |  | 5
| Number withdrawn year to date |  | 97
NOTES: | ● The column labeled 'SP' refers to the maximum summer megawatt electrical output. The column labeled 'WP' refers to the maximum winter megawatt electrical output.
● Type / Fuel Key: ST=Steam Turbine, CT=Combustion Turbine, CC, CS= Steam Turbine & Combustion Turbine, H=Hydro, PS=Pumped Storage, W=Wind, OSW= Off-Shore Wind, NU=Nuclear, NG=Natural Gas, M=Methane, SW=Solid Waste, S=Solar, Wo=Wood, F=Flywheel ES=Energy Storage, O=Oil, C=Coal, D=Dual Fuel, AC,
DC, L=Load, FC=Fuel Cell,CW=CSR - ES + Wind, CR=CSR - ES + Solar
● The column labeled 'Z' refers to the zone
● The column labeled 'S' refers to the status of the project in the NYISO's LFIP. Key: 1=Scoping Meeting Pending, 2=FES Pending, 3=FES in Progress,3A=FES Approved/Performed, 4=SRIS/SIS Pending, 5=SRIS/SIS in Progress,5P=SRIS Commenced, Stopped and Pending Adoption of IP, 6=SRIS/SIS Approved, 7=FS Pending, 8=Rejected Cost Allocation/Next FS Pending, 9=FS in Progress, 10=Accepted Cost Allocation/IA in Progress,
11=IA Completed, 12=Under Construction, 13=In Service for Test, 14=In Service Commercial, 0=Withdrawn, 15=Partial In-Service, P=Pending Adoption of IP Compliance with Order 2023
● Availability of Studies Key: None=Not Available, FES=Feasibility Study Available, SRIS=System Reliability Impact Study Available, FS=Facilities Study and/or ATRA Available
● CY Completion/SGIA Tender refers to the Attachment X milestone used to apply the 4-year COD limitation.
● Proposed In-Service Dates, Proposed Initial Synchronization Dates and Commercial Operation Dates (COD) are shown in format Year/Qualifier, where Qualifier may indicate the month, season, or quarter.
DPS/State - SIR Interconnection Queue (for Projects not subject to the NYISO process):
http://www3.dps.ny.gov/W/PSCWeb.nsf/All/286D2C179E9A5A8385257FBF003F1F7E?OpenDocument

## Cluster Projects
Queue Pos. | Interconnection Customer Name | Project Name | Date of IR | SP (MW) | WP (MW) | Type/ Fuel | Energy Storage Capability | Minimum_Duration Full Discharge | County | State | Z | Points of Interconnection | Utility | Affected Transmission Owner (ATO) | S | Last Updated Date | Availability of Studies | IA Tender Date | Proposed In-Service/Initial Backfeed Date | Proposed Sync Date | Proposed COD
C24-003 | Vineyard Mid-Atlantic LLC | Vineyard Mid-Atlantic West | 2024-08-01 | 1321 | 1321 | OSW |  |  | Nassu | NY | K | East Garden City 345kV | NYPA | LIPA, Transco | 4 | 2025-02-28 |  |  | 01-2031 | 08-2031 | 03-2032
C24-004 | Palladium Storage LLC | Palladium Storage | 2024-08-01 | 140 | 140 | ES | 560 | 4 | Bronx | NY | J | Hell Gate Annex 138KV Substation | NYPA | ConEd | 4 | 2025-03-31 |  |  | 06-2028 | 07-2028 | 08-2028
C24-005 | Blue Spruce Storage LLC | Blue Spruce Storage | 2024-08-01 | 300 | 300 | ES | 1200 | 4 | Bronx | NY | J | Mott Haven 138KV Bus | ConEd |  | 4 | 2025-03-31 |  |  | 06-2028 | 07-2028 | 08-2028
C24-008 | KCE NY 30, LLC | KCE NY 30 | 2024-08-01 | 50 | 50 | ES | 200 | 4 | Suffolk | NY | K | West Babylon 69 kV | LIPA |  | 4 | 2025-02-28 |  |  | 05-2028 | 09-2028 | 10-2028
C24-010 | KCE NY 21, LLC | KCE NY 21 | 2024-08-01 | 60 | 60 | ES | 240 | 4 | Suffolk | NY | K | Pulaski 69kV Substation | LIPA |  | 4 | 2025-02-28 |  |  | 09-2029 | 10-2029 | 12-2029
C24-013 | Battery Park Storage LLC | Battery Park Storage | 2024-08-01 | 190 | 190 | ES | 760 | 4 | Brooklyn | NY | J | Greenwood 138KV | ConEd |  | 4 | 2025-03-31 |  |  | 06-2028 | 07-2028 | 08-2028
C24-014 | Roma Storage | Roma Storage | 2024-08-01 | 150 | 150 | ES | 600 | 4 | Queens | NY | J | Astoria East 138 kV | ConEd |  | 4 | 2025-02-28 |  |  | 06-2028 | 07-2028 | 08-2028
C24-015 | Good Ole 77 Energy LLC | Seventy Seven Project | 2024-08-01 | 100 | 100 | S |  |  | Wyoming | NY | C | High Sheldon 230 kV | NYSEG |  | 4 | 2025-02-28 |  |  | 10-2029 | 01-2030 | 05-2030
C24-016 | Salt Rush Wind Energy LLC | Salt Rush Wind Energy | 2024-08-01 | 150 | 150 | W |  |  | Warsaw | NY | C | Stony Creek 230 kV | NYSEG |  | 4 | 2025-02-28 |  |  | 08-2030 | 08-2030 | 11-2030
C24-021 | Bluepoint Wind LLC | Bluepoint Wind 1 | 2024-08-01 | 1310 | 1310 | OSW |  |  | Kings | NY | J | Brooklyn Clean Energy Hub 345kV Substation | CONED |  | 4 | 2025-02-28 |  |  | 01-2033 | 07-2033 | 12-2033
C24-023 | KCE NY 26, LLC | KCE NY 26 | 2024-08-01 | 60 | 60 | ES | 480 | 8 | Suffolk | NY | K | Jamesport - Peconic 69kV | LIPA |  | 4 | 2025-02-28 |  |  | 09-2029 | 10-2029 | 12-2029
C24-024 | Verona Solar | Verona Solar I | 2024-08-01 | 199 | 199 | S |  |  | Durhamville | NY | C | Clay - Edic 345kV, Line 2-15 | NYPA | NM-NG | 4 | 2025-02-28 |  |  | 09-2030 | 09-2030 | 12-2030
C24-026 | Taproot Solar LLC | Taproot Solar | 2024-08-01 | 185 | 185 | S |  |  | Montgomery | NY | F | Edic - Princetown 345 kV, Line #351 | LSPower | NYPA, NM-NG | 4 | 2025-02-28 |  |  | 03-2030 | 03-2030 | 07-2030
C24-031 | BayWa r.e Projects LLC. | Crossbuck Energy Storage, LLC | 2024-08-01 | 100 | 100 | ES | 400 | 4 | Greene | NY | G | Coxsackie 69 kV substation | CHGE | Transco | 4 | 2025-03-31 |  |  | 07-2030 | 08-2030 | 12-2030
C24-032 | BayWa r.e Projects LLC. | Oakdale Battery Storage LLC | 2024-08-01 | 150 | 150 | ES | 600 | 4 | Broome | NY | C | Oakdale 115 kV | NYSEG |  | 4 | 2025-03-31 |  |  | 03-2030 | 04-2030 | 08-2030
C24-033 | KCE NY 31, LLC | KCE NY 31 | 2024-08-01 | 50 | 50 | ES | 200 | 4 | Suffolk | NY | K | Shoreham 138kV | LIPA |  | 4 | 2025-02-28 |  |  | 05-2027 | 09-2027 | 12-2027
C24-034 | Kalmia Storage, LLC | Kalmia Storage, LLC | 2024-08-01 | 50 | 50 | ES | 210 | 4.2 | Suffolk | NY | K | Holtsville 69 kV | LIPA |  | 4 | 2025-02-28 |  |  | 09-2029 | 10-2029 | 01-2030
C24-037 | Northland Power U.S. Projects Inc | Gunns Corners Solar | 2024-08-01 | 140 | 140 | S |  |  | Jefferson | NY | E | Thousand Islands-Coffeen Line 4: Lyme Tap 115kV | NM-NG |  | 4 | 2025-02-28 |  |  | 09-2027 | 10-2027 | 12-2027
C24-038 | Prologis Energy LLC | Long Island City Energy Storage | 2024-08-01 | 68 | 68 | ES | 272 | 4 | Queens | NY | J | Queensbridge 138kV | ConEd |  | 4 | 2025-02-28 |  |  | 07-2030 | 08-2030 | 12-2030
C24-039 | Golden Knight Solar, LLC | Golden Knight Solar | 2024-08-01 | 140 | 140 | S |  |  | St. Lawrence | NY | D | Colton - Malone Line 3 115 kV | NM-NG | NYSEG | 4 | 2024-02-28 |  |  | 02-2030 | 05-2030 | 05-2030
C24-042 | Liberty Renewables Inc. | Hoffman Falls Wind 2 | 2024-08-01 | 29.8 | 29.8 | W |  |  | Madison | NY | C | Fenner - Shippy Rd Line 3 115 kV | NM-NG |  | 4 | 2025-02-28 |  |  | 10-2027 | 11-2027 | 12-2027
C24-043 | EDF Renewables Development, Inc. | Rosalen Solar Energy Center | 2024-08-01 | 200 | 200 | CR | 80 | 4.75 | Wayne | NY | B | 345kV PM2 between Pannell-Clay | NYPA | RG&E / NM-NG | 4 | 2025-02-28 |  |  | 07-2029 | 07-2029 | 11-2029
C24-044 | BayWa r.e Projects LLC. | Honey Bee Battery Storage, LLC | 2024-08-01 | 199 | 199 | ES | 796 | 4 | Rensselaer | NY | F | North Troy -Hoosick Line 5 115 kV | NM-NG |  | 4 | 2025-03-31 |  |  | 07-2030 | 08-2030 | 12-2030
C24-047 | BayWa r.e Projects LLC. | Lincoln Park DG, LLC | 2024-08-01 | 150 | 150 | ES | 600 | 4 | Ulster | NY | G | Lincoln Park - East Kingston 115 kV | CHGE |  | 4 | 2025-03-31 |  |  | 07-2030 | 08-2030 | 12-2030
C24-048 | BPP NY Lansing BESS I LLC | BPP NY Lansing BESS I | 2024-08-01 | 200 | 200 | ES | 800 | 4 | Tompkins | NY | C | Milliken 115kV (aka Cayuga 115kV) | NYSEG |  | 4 | 2025-05-31 |  |  | 05-2028 | 06-2028 | 07-2028
C24-049 | BayWa r.e Projects LLC. | North Catskill DG LLC | 2024-08-01 | 100 | 100 | ES | 400 | 4 | Greene | NY | G | North Catskill -Churchtown 115 kV | CHGE | Transco | 4 | 2025-03-31 |  |  | 07-2030 | 08-2030 | 12-2030
C24-050 | Grateful Storage, LLC | Grateful Storage, LLC | 2024-08-01 | 250 | 250 | ES | 1110 | 4.44 | Orange | NY | G | Rock Tavern - Roseton 345 kV | CHGE |  | 4 | 2025-02-28 |  |  | 02-2030 | 03-2030 | 05-2030
C24-052-001 | Liberty Renewables Inc. | Hemlock Hollow Wind | 2024-08-01 | 95 | 95 | W |  |  | Cattaraugus | NY | A | Dugan - Homer Hill 115kV, Line #155 | NM-NG |  | 4 | 2025-02-28 |  |  | 07-2029 | 08-2029 | 09-2029
C24-056 | BGTF US Development Holdings LLC | Naples Energy Storage | 2024-08-01 | 120 | 120 | ES | 480 | 4 | Steuben | NY | C | Eelpot Road 115 kV | NYSEG |  | 4 | 2025-02-28 |  |  | 10-2028 | 11-2028 | 12-2028
C24-057 | Empire Reserve Energy, LLC | Highland BESS | 2024-08-01 | 79 | 79 | ES | 316 | 4 | Orange County | NY | G | Sugarloaf 138kV | O&R | Transco, ConEd, CHGE | 4 | 2025-02-28 |  |  | 12-2028 | 02-2029 | 06-2029
C24-058 | Mission Clean Energy Devco LLC | Slide Energy Center | 2024-08-01 | 79 | 79 | ES | 316 | 4 | Ulster | NY | G | Hurley Ave 115 kV substation | CHGE |  | 4 | 2025-03-31 |  |  | 08-2029 | 09-2029 | 11-2029
C24-059 | Empire Reserve Energy, LLC | Orchard BESS | 2024-08-01 | 100 | 100 | ES | 400 | 4 | Ulster County | NY | G | 115kV Modena Substation | CHGE |  | 4 | 2025-02-28 |  |  | 12-2028 | 02-2029 | 06-2029
C24-060 | Hanwha Q CELLS USA Corp. | Gemma Energy Storage | 2024-08-01 | 200 | 200 | ES | 800 | 4 | Steuben | NY | C | Stony Ridge 230kV | NYSEG |  | 4 | 2025-02-28 |  |  | 06-2027 | 06-2027 | 12-2027
C24-061 | Hanwha Q CELLS USA Corp. | Daphne Energy Storage | 2024-08-01 | 75 | 75 | ES | 300 | 4 | Suffolk County & Mastic City | NY | K | Moriches 69kV | LIPA |  | 4 | 2025-02-28 |  |  | 06-2027 | 06-2027 | 12-2027
C24-062 | Hanwha Q CELLS USA Corp. | Highbush Energy Storage | 2024-08-01 | 200 | 200 | ES | 800 | 4 | Dutchess | NY | G | Manchester 115 kV | CHGE |  | 4 | 2025-02-28 |  |  | 06-2027 | 06-2027 | 12-2027
C24-063 | Empire Reserve Energy, LLC | Heritage BESS | 2024-08-01 | 125 | 125 | ES | 500 | 4 | Orange County | NY | G | Shoemaker - Sugarloaf 138kV | O&R |  | 4 | 2025-03-31 |  |  | 12-2028 | 02-2029 | 06-2029
C24-064 | EDF Renewables Development, Inc. | Fraser Energy Storage | 2024-08-01 | 135 | 135 | ES | 540 | 4 | Delaware | NY | E | Fraser substation 115 kV | NYSEG |  | 4 | 2025-02-28 |  |  | 09-2028 | 07-2029 | 11-2029
C24-065 | Hanwha Q CELLS USA Corp. | Maplehurst Energy Park | 2024-08-01 | 75 | 75 | CR | 300 | 4.018 | Chautauqua | NY | A | Dunkirk - Falconer 115kV Line #160 | NM-NG |  | 4 | 2025-03-31 |  |  | 06-2027 | 06-2027 | 12-2027
C24-066 | Hanwha Q CELLS USA Corp. | Coral Energy Storage | 2024-08-01 | 100 | 100 | ES | 400 | 4 | Chemung | NY | C | Yawger 115kV Substation | NYSEG |  | 4 | 2025-02-28 |  |  | 06-2027 | 06-2027 | 12-2027
C24-067 | Empire Reserve Energy, LLC | Gala Grove BESS | 2024-08-01 | 125 | 125 | ES | 500 | 4 | Suffolk | NY | K | Wildwood - Riverhead 138 kV | LIPA |  | 4 | 2025-03-31 |  |  | 12-2028 | 02-2029 | 06-2029
C24-071 | Sweetwaters Energy Center LLC | Sweetwaters Energy Center | 2024-08-01 | 125 | 125 | ES | 500 | 4 | Suffolk | NY | K | Kings Substation 138kV | LIPA |  | 4 | 2025-02-28 |  |  | 12-2027 | 02-2028 | 05-2028
C24-072 | GCI Eastwater, LLC | Eastwater Energy Storage | 2024-08-02 | 100 | 100 | ES | 400 | 4 | Monroe | NY | B | Station 82 - Station 121 Line 23 115kV | NM-NG | RG&E | 4 | 2025-02-28 |  |  | 02-2027 | 03-2027 | 06-2027
C24-074 | GCI Lighthouse Energy Storage, LLC | Lighthouse Energy Storage | 2024-08-02 | 250 | 250 | ES | 1000 | 4 | Chautauqua | NY | A | Gardenville - Dunkirk Line 74 230 kV | NM-NG |  | 4 | 2025-02-28 |  |  | 02-2027 | 03-2027 | 06-2027
C24-076 | SUNXI LLC | Springbrooke | 2024-08-05 | 82.8 | 82.8 | S |  |  | Genesee | NY | B | Southeast Batavia-Golah Line 119 | NM-NG |  | 4 | 2025-04-30 |  |  | 04-2029 | 08-2029 | 12-2029
C24-077 | Abundant Solar Power Inc. | NY-5632 Turnpike Rd | 2024-08-06 | 19.94 | 19.94 | S |  |  | Steuben | NY | C | Bath - Howard 115 kV Line | NYSEG |  | 4 | 2025-02-28 |  |  | 09-2026 | 10-2026 | 11-2026
C24-078 | Abundant Solar Power Inc. | NY-MARKHAM HOLLOW RD | 2024-08-07 | 19.98 | 19.98 | S |  |  | Onondaga | NY | C | Tilden-Cortland Line 18 | NM-NG |  | 4 | 2025-02-28 |  |  | 09-2026 | 10-2026 | 11-2026
C24-079 | Maple Harvest Wind | Maple Harvest Wind | 2024-08-08 | 162 | 162 | W |  |  | Onondaga | NY | C | Tilden-Cortland Line 18. | NM-NG |  | 4 | 2025-02-28 |  |  | 10-2028 | 11-2028 | 12-2028
C24-080 | the New York Power Authority | Greenwood Heights Energy Storage | 2024-08-08 | 130 | 130 | ES | 520 | 4 | Kings | NY | J | Greenwood 138kV Substation | ConEd |  | 4 | 2025-03-31 |  |  | 10-2028 | 10-2028 | 12-2028
C24-081 | The New York Power Authority | Port Morris Energy Storage | 2024-08-08 | 130 | 130 | ES | 520 | 4 | Bronx | NY | J | Hell Gate Annex 138kV | NYPA | ConEd | 4 | 2025-03-31 |  |  | 10-2028 | 10-2028 | 12-2028
C24-085 | Terra-Gen Development Company, LLC | Arch 4 | 2024-08-09 | 150 | 150 | ES | 600 | 4 | Orange | NY | G | Rock Tavern 345kV Substation | CHGE |  | 4 | 2025-02-28 |  |  | 10-2028 | 10-2028 | 12-2028
C24-086 | Terra-Gen Development Company, LLC | Arch 1 | 2024-08-09 | 100 | 100 | ES | 400 | 4 | Orange | NY | G | Rock Tavern 345kV Substation | CHGE |  | 4 | 2025-02-28 |  |  | 10-2028 | 10-2028 | 10-2028
C24-087 | Terra-Gen Development Company, LLC | Arch 2 | 2024-08-09 | 150 | 150 | ES | 600 | 4 | Orange | NY | G | Rock Tavern 345kV Substation | CHGE | ConEd; NYPA; O&R | 4 | 2025-02-28 |  |  | 10-2028 | 10-2028 | 10-2028
C24-088 | Terra-Gen Development Company, LLC | Arch 3 | 2024-08-09 | 100 | 100 | ES | 480 | 4 | Orange | NY | G | Rock Tavern 345kV Substation | CHGE | ConEd / NYPA | 4 | 2025-02-28 |  |  | 10-2028 | 10-2028 | 12-2028
C24-089 | Braen Energy LLC | Braen Energy Storage Phase 1 | 2024-08-14 | 500 | 500 | ES | 2064.15 | 4 | Rockland | NY | G | Ramapo 345kV Substation | ConEd | O&R,CHGE | 4 | 2025-02-28 |  |  | 03-2028 | 04-2028 | 05-2028
C24-090 | Quantum DPI group | Cuba Solar Facility | 2024-08-15 | 22 | 22 | CR | 10 | 2.74 | Allegany | NY | A | HOMER HILL - ANDOVER 115kV line #157 | NM-NG | NYSEG | 4 | 2025-02-28 |  |  | 09-2028 | 10-2028 | 11-2028
C24-091 | BPP NY Somerset BESS I LLC | BPP NY Somerset BESS I LLC | 2024-08-19 | 199.5 | 199.5 | ES | 798 | 4 | Niagara | NY | A | Kintigh 345kV | NYSEG | NM-NG | 4 | 2025-05-31 |  |  | 06-2028 | 07-2028 | 08-2028
C24-092 | Quantum DPI Group | Scio Solar Facility | 2024-08-20 | 50 | 50 | CR | 20 | 2.74 | Allegany | NY | A | Homer Hill to ANDOVER 115kV Line 157 | NM-NG |  | 4 | 2025-02-28 |  |  | 06-2029 | 07-2029 | 09-2029
C24-093 | Terra-Gen Development Company, LLC | Alcazar 1 | 2024-08-22 | 100 | 100 | ES | 400 | 4 | Ulster | NY | G | Hurley 345kV Substation | CHGE |  | 4 | 2025-02-28 |  |  | 10-2028 | 10-2028 | 12-2028
C24-094 | Terra-Gen Development Company, LLC | Alcazar 2 | 2024-08-22 | 150 | 150 | ES | 600 | 4 | Ulster | NY | G | Hurley 345kV Substation | CHGE |  | 4 | 2025-02-28 |  |  | 10-2028 | 10-2028 | 12-2028
C24-095 | Westerlo Solar LLC | Westerlo Solar | 2024-08-23 | 40 | 40 | CR | 40 | 4.5 | Albany | NY | G | Westerlo-New Baltimore 69kV Line #NW | CHGE |  | 4 | 2025-02-28 |  |  | 04-2028 | 05-2028 | 07-2028
C24-097 | RWE Solar Development, LLC | Basecamp BESS | 2024-08-26 | 170 | 170 | ES | 680 | 4 | Chautauqua | NY | A | Laona Station 115kV | NM-NG |  | 4 | 2025-02-28 |  |  | 09-2028 | 10-2028 | 02-2029
C24-098 | RWE Solar Development, LLC | Farmhouse BESS | 2024-08-26 | 150 | 150 | ES | 600 | 4 | Orange | NY | G | Roseton 345 kV Substation | CHGE | NYPA | 4 | 2025-02-28 |  |  | 01-2029 | 02-2029 | 06-2029
C24-099 | Crown Point Solar LLC | Crown Point Solar | 2024-08-26 | 20 | 20 | CR | 20 | 4.5 | Essex | NY | F | Ticonderoga to Republic 115Kv Line 2 | NM-NG | NYSEG | 4 | 2025-02-28 |  |  | 04-2028 | 05-2028 | 07-2028
C24-101 | MN8 Energy Development Company LLC | Halo Energy Storage | 2024-08-26 | 100 | 100 | ES | 400 | 4 | Wyoming County | NY | C | South Perry Substation 230 kV | NYSEG |  | 4 | 2025-02-28 |  |  | 08-2028 | 09-2028 | 12-2028
C24-102 | ELP Rotterdam Solar LLC | ELP Rotterdam Solar | 2024-08-27 | 35 | 35 | CR | 36 | 4.5 | Schenectady | NY | F | Rotterdam-Maple Ave 115kV Line 10. | NM-NG |  | 4 | 2025-02-28 |  |  | 04-2028 | 05-2028 | 07-2028
C24-103 | Bath Solar LLC | Bath Solar | 2024-08-27 | 185 | 185 | CR | 184 | 4.5 | Steuben | NY | C | Avoca 230 kV - Stoney Ridge 230 kV Line #68 | NYSEG |  | 4 | 2025-02-28 |  |  | 04-2028 | 05-2028 | 07-2028
C24-104 | ACE DevCo NC, LLC | Horseblock Energy Storage | 2024-08-27 | 100 | 100 | ES | 400 | 4 | Suffolk | NY | K | West Yaphank 69kV Substation | LIPA |  | 4 | 2025-02-28 |  |  | 03-2028 | 04-2028 | 06-2028
C24-105 | ELP Clay Storage LLC | ELP Clay Storage | 2024-08-28 | 199 | 199 | ES | 796 | 4 | Onondaga | NY | C | Clay-Lighthouse Hill 115kV, Line #7 | NM-NG |  | 4 | 2025-02-28 |  |  | 04-2028 | 05-2028 | 07-2028
C24-108 | Boralex US Development LLC | NY125C - Little Salmon Solar | 2024-08-29 | 200 | 200 | S |  |  | Franklin | NY | D | 345kV Line HW1 Haverstock - WIllis | NYPA |  | 4 | 2025-02-28 |  |  | 11-2028 | 11-2028 | 12-2028
C24-109 | Falls Park Energy Storage Project, LLC | Falls Park Energy Storage | 2024-08-29 | 100 | 100 | ES | 400 | 4 | Columbia | NY | F | FALLS PARK 115 kV | NYSEG | Transco | 4 | 2025-02-28 |  |  | 09-2029 | 10-2029 | 12-2029
C24-111 | Fort Edward Solar LLC | Fort Edward Solar Farm (NY53) | 2024-08-29 | 100 | 100 | S |  |  | Washington | NY | F | Mohican to Battenkill 115 kV Line #15 | NM-NG |  | 4 | 2025-02-28 |  |  | 11-2027 | 11-2027 | 12-2027
C24-115 | Iris Bloom Solar Project, LLC | Iris Bloom Solar | 2024-08-30 | 150 | 150 | CR | 200 | 4.8 | Chautauqua | NY | A | Moon Road Sub 115 kV | NM-NG |  | 4 | 2025-02-28 |  |  | 09-2029 | 10-2029 | 12-2029
C24-118 | Rutland Center Solar 1, LLC | Rutland Center Solar | 2024-08-30 | 75 | 75 | S |  |  | Jefferson County | NY | E | Staplin Creek Station 115 kV | NM-NG |  | 4 | 2025-02-28 |  |  | 02-2030 | 05-2030 | 05-2030
C24-120 | Field Day Solar Project, LLC | Field Day Solar | 2024-09-03 | 300 | 300 | CR | 400 | 4.82 | Oneida | NY | E | Boonville to Rome 115KV Line 3 | NM-NG |  | 4 | 2025-02-28 |  |  | 09-2029 | 10-2029 | 12-2029
C24-121 | Beacon Harbor Solar Project, LLC | Beacon Harbor Solar | 2024-09-03 | 195 | 195 | CR | 300 | 4.82 | Jefferson | NY | E | Thousand Islands-Coffeen Line 4: Lyme Tap 115kV | NM-NG |  | 4 | 2025-02-28 |  |  | 09-2029 | 10-2029 | 12-2029
C24-122-002 | BGTF US Development Holdings LLC | Capital Energy Storage | 2024-09-04 | 190 | 190 | ES | 760 | 4 | Albany | NY | E | Marcy to New Scotland 345 kV line 18 | NM-NG | NYPA | 4 | 2025-02-28 |  |  | 10-2028 | 11-2028 | 12-2028
C24-124 | BGTF US Development Holdings LLC | Dunkirk Energy Storage | 2024-09-05 | 100 | 100 | ES | 400 | 4 | Chautauqua | NY | A | Dunkirk-Laona Line 162 115kV | NM-NG |  | 4 | 2025-02-28 |  |  | 10-2028 | 11-2028 | 12-2028
C24-125 | RWE Solar Development, LLC | Town Line Solar Phase II | 2024-09-05 | 60 | 60 | CR | 0 | 0 | Sullivan | NY | E | Coopers Corner to Middletown Tap 345 kV Line | NYPA | NYSEG, O&R | 4 | 2025-02-28 |  |  | 12-2029 | 01-2030 | 05-2030
C24-126 | BGTF US Development Holdings LLC | Pine Grove Energy Storage | 2024-09-05 | 150 | 150 | ES | 600 | 4 | Lewis | NY | E | Austin Road 345 kV | NM-NG |  | 4 | 2025-02-28 |  |  | 10-2028 | 11-2028 | 12-2028
C24-127 | BGTF US Development Holdings LLC | Crescent Energy Storage | 2024-09-05 | 75 | 75 | ES | 300 | 4 | Chautauqua | NY | A | Moons Road to Falconer 115 kV Line 175 | NM-NG |  | 4 | 2025-02-28 |  |  | 10-2028 | 11-2028 | 12-2028
C24-128 | Winner Solar, LLC | Winner Solar | 2024-09-05 | 120 | 120 | S |  |  | Clinton County | PA | C | Homer City - Mainesburg 345kV Line | NYSEG |  | 4 | 2025-02-28 |  |  | 06-2028 | 08-2028 | 10-2028
C24-129 | MN8 Energy Development Company LLC | Buffalo Road Energy Storage | 2024-09-05 | 100 | 100 | ES | 200 | 2 | Niagara | NY | A | Dupont to Packard 115 kV Line #184 | NM-NG |  | 4 | 2025-02-28 |  |  | 08-2028 | 09-2028 | 12-2028
C24-130 | Elevate Bethlehem, LLC | Elevate Bethlehem | 2024-09-05 | 120 | 120 | ES | 1200 | 10 | Albany | NY | F | Albany Steam 115 kV Substation | NM-NG |  | 4 | 2025-04-30 |  |  | 03-2028 | 04-2028 | 06-2028
C24-131 | Elevate Arthur Kill II, LLC | Elevate Arthur Kill II | 2024-09-05 | 180 | 180 | ES | 1800 | 10 | Richmond | NY | J | Fresh Kills 345 kV substation | ConED |  | 4 | 2025-04-30 |  |  | 03-2028 | 04-2028 | 06-2028
C24-132 | HW Power, LLC | Cross County Energy Storage | 2024-09-06 | 130 | 130 | ES | 520 | 4 | Westchester | NY | I | Eastview to Buchanan, 345 kV | ConEd |  | 4 | 2025-04-30 |  |  | 11-2028 | 12-2028 | 02-2029
C24-134 | MN8 Energy Development Company LLC | River Road Energy Storage | 2024-09-06 | 247.5 | 247.5 | ES | 495 | 2 | Erie | NY | A | Packard-Huntley 230 kV Line#78 | NM-NG |  | 4 | 2025-02-28 |  |  | 08-2028 | 09-2028 | 12-2028
C24-135 | Cayuga Lake Solar, LLC | Cayuga Solar | 2024-09-06 | 60 | 60 | S |  |  | Tompkins | NY | C | Milliken 115 kV Substation | NYSEG |  | 4 | 2025-02-28 |  |  | 09-2028 | 10-2028 | 12-2028
C24-136 | Emeren US, LLC | Marble River Storage | 2024-09-06 | 160 | 160 | ES | 640 | 4 | Clinton | NY | D | Ryan 230kV Substation | NYPA |  | 4 | 2025-02-28 |  |  | 10-2028 | 11-2028 | 12-2028
C24-137 | ACE DevCo NC, LLC | Gillie Brook | 2024-09-06 | 60 | 60 | S |  |  | Onondaga | NY | C | Elbridge 115 kV Substation | NM-NG | NYSEG; RG&E; | 4 | 2025-02-28 |  |  | 01-2029 | 02-2029 | 04-2029
C24-138 | Marathon Power | Marathon BESS | 2024-09-06 | 135 | 135 | ES | 540 | 4 | Suffolk | NY | K | Greenlawn 138kV | LIPA |  | 4 | 2025-05-31 |  |  | 12-2027 | 12-2027 | 02-2028
C24-139 | Emeren US, LLC | Valcour Storage | 2024-09-09 | 150 | 150 | ES | 600 | 4 | Clinton | NY | D | Patnode 230 kV substation | NYPA |  | 4 | 2025-02-28 |  |  | 10-2028 | 11-2028 | 12-2028
C24-148 | Emeren US, LLC | Willard Storage | 2024-09-10 | 300 | 300 | ES | 1200 | 4 | Rensselaer | NY | F | Eastover 115kV | NM-NG |  | 4 | 2025-02-28 |  |  | 10-2028 | 11-2028 | 12-2028
C24-149 | Manchester Solar NY LLC | Manchester Solar | 2024-09-11 | 20 | 20 | S |  |  | Ontario | NY | C | Station 127(Hooks Rd)-Elbridge Line 7 115kV | NM-NG | RG&E | 4 | 2025-05-31 |  |  | 07-2027 | 08-2027 | 09-2027
C24-150 | Kingbird Solar NY LLC | Kingbird Solar | 2024-09-11 | 20 | 20 | S |  |  | Chautauqua | NY | A | Gardenville to Dunkirk 115kV Line - Line #142 | NM-NG |  | 4 | 2025-05-31 |  |  | 07-2027 | 08-2027 | 09-2027
C24-152 | Hydrostor USA Holdings, Inc , a subsidiary of Hydrostor Inc | Antelope Energy Storage Center | 2024-09-11 | 500 | 500 | ES | 4000 | 8 | Croghan | NY | E | Adirondack 345kV substation | NYPA | NM-NG | 4 | 2025-02-28 |  |  | 10-2030 | 11-2030 | 12-2030
C24-154 | Sandlot Energy LLC | Sandlot IFB | 2024-09-11 | 50 | 50 | ES | 500 | 10 | Suffolk | NY | K | Deposit - Indian Head 69 kV Line | LIPA |  | 4 | 2025-05-31 |  |  | 12-2027 | 12-2027 | 02-2028
C24-155 | Zenobe Stockton LLC | Zenobe Stockton LLC | 2024-09-12 | 100 | 100 | ES | 400 | 4 | Chautauqua | NY | A | Moon Road 115kV | NM-NG |  | 4 | 2025-02-28 |  |  | 12-2027 | 04-2028 | 07-2028
C24-156 | Granada Solar, LLC | Grass River Solar | 2024-09-12 | 80 | 80 | S |  |  | St. Lawrence County | NY | E | N. Ogdensburg - Alcoa 115 kV Line (Line # 13) | NM-NG |  | 4 | 2025-02-28 |  |  | 06-2028 | 07-2028 | 08-2028
C24-158 | KCE NY 27, LLC | KCE NY 27 | 2024-09-12 | 50 | 50 | ES | 200 | 4 | Suffolk | NY | K | Quogue - Tiana 69kV | LIPA |  | 4 | 2025-02-28 |  |  | 09-2029 | 10-2029 | 12-2029
C24-159 | Viridity Energy Solutions | Cruiser BESS | 2024-09-12 | 100 | 100 | ES | 400 | 4 | Suffolk County | NY | K | Pulaski 69kV | LIPA |  | 4 | 2025-02-28 |  |  | 01-2028 | 02-2028 | 03-2028
C24-160 | Viridity Energy Solutions | Mustang BESS | 2024-09-12 | 95 | 95 | ES | 380 | 4 | Orange County | NY | G | Hartley 69 kV | O&R |  | 4 | 2025-02-28 |  |  | 01-2028 | 02-2028 | 03-2028
C24-162 | Ramadi LLC | Ramadi Utility Storage | 2024-09-13 | 140 | 140 | ES | 560 | 4 | Suffolk | NY | K | William Floyd to West Yaphank 69kV | LIPA |  | 4 | 2025-05-31 |  |  | 09-2027 | 01-2028 | 04-2028
C24-163 | BGTF US Development Holdings LLC | Porter Energy Storage | 2024-09-15 | 50 | 50 | ES | 200 | 4 | Essex | NY | F | Hague Road to Ticonderoga 115 kV line 4 | NM-NG |  | 4 | 2025-02-28 |  |  | 10-2028 | 11-2028 | 12-2028
C24-164 | KCE NY 28, LLC | KCE NY 28 | 2024-09-16 | 45 | 45 | ES | 180 | 4 | Suffolk | NY | K | Riverhead - Tuthill 69kV | LIPA |  | 4 | 2025-02-28 |  |  | 09-2029 | 10-2029 | 12-2029
C24-165 | KCE NY 38, LLC | KCE NY 38 | 2024-09-16 | 250 | 250 | ES | 1000 | 4 | Columbia | NY | F | Churchtown 115 kV Substation | Transco |  | 4 | 2025-02-28 |  |  | 09-2029 | 10-2029 | 12-2029
C24-167 | KCE NY 37, LLC | KCE NY 37 | 2024-09-16 | 150 | 150 | ES | 600 | 4 | Suffolk | NY | K | Sills Rd - Brookhaven 138 kV line | LIPA |  | 4 | 2025-02-28 |  |  | 09-2029 | 10-2029 | 12-2029
C24-168 | Northland Power U.S. Projects Inc | Ball Hill BESS | 2024-09-17 | 250 | 250 | ES | 1000 | 4 | Chautauqua | NY | A | Stebbins Road 230kV | NM-NG |  | 4 | 2025-02-28 |  |  | 12-2027 | 02-2028 | 05-2028
C24-169 | Endurance Power LLC | Endurance | 2024-09-17 | 75 | 75 | ES | 300 | 4 | Nassau | NY | K | Jericho- New Cassel 69kV | LIPA |  | 4 | 2025-05-31 |  |  | 12-2027 | 12-2027 | 02-2028
C24-173 | KCE NY 34, LLC | KCE NY 34 | 2024-09-17 | 100 | 100 | ES | 400 | 4 | Ulster | NY | G | Saugerties 69 kV | CHGE |  | 4 | 2025-02-28 |  |  | 09-2029 | 10-2029 | 12-2029
C24-175 | RWE Solar Development, LLC | Stargazer I | 2024-09-17 | 325 | 325 | CR | 340 | 4.66 | McKean | PA | A | Homer City to Pierce Brook 345 kV Line | NYSEG |  | 4 | 2025-02-28 |  |  | 01-2029 | 02-2029 | 07-2029
C24-176 | RWE Solar Development, LLC | Stargazer II | 2024-09-17 | 325 | 325 | CR | 340 | 4.66 | McKean | PA | A | Homer City to Pierce Brook 345 kV Line | NYSEG |  | 4 | 2025-02-28 |  |  | 01-2029 | 02-2029 | 07-2029
C24-177 | Jericho Power Station LLC | Commack(Jericho Power Station) | 2024-09-17 | 35 | 35 | ES | 140 | 4 | Suffolk | NY | K | Commack 69 kV Substation | LIPA |  | 4 | 2025-02-28 |  |  | 12-2027 | 02-2028 | 05-2028
C24-178 | Astoria Generating Company, L.P. | Gowanus Energy Storage | 2024-09-17 | 150 | 150 | ES | 1500 | 10 | Kings | NY | J | Gowanus 138kV Substation | ConEd |  | 4 | 2025-02-28 |  |  | 03-2028 | 04-2028 | 06-2028
C24-179 | Silverline Energy Center, LLC | Silverline Energy Center | 2024-09-17 | 150 | 150 | CR | 80 | 4.71 | Tompkins | NY | C | Miliken to Etna Line #974 115 kV line | NYSEG |  | 4 | 2025-02-28 |  |  | 10-2030 | 11-2030 | 12-2030
C24-182 | Southern Tier Energy Center, LLC | Southern Tier Energy Center | 2024-09-17 | 200 | 200 | ES | 800 | 4.0 | Tioga | NY | C | Oakdale 130755 - Watercure 130757 345 kV line | NYSEG |  | 4 | 2025-02-28 |  |  | 10-2029 | 11-2029 | 12-2029
C24-183 | East Setauket Energy Storage, LLC | East Setauket Storage II | 2024-09-17 | 248 | 248 | ES | 992 | 4 | Suffolk | NY | K | Holbrook - North Shore Beach 138kV | LIPA |  | 4 | 2025-02-28 |  |  | 09-2029 | 10-2029 | 12-2029
C24-184 | Tabletop Solar NY LLC | Tabletop Solar | 2024-09-18 | 80 | 80 | S |  |  | Fort Plain | NY | F | Clinton Tap off the Inghams-Meco-Marshviille Line 15 115kV | NM-NG |  | 4 | 2025-03-31 |  |  | 09-2028 | 10-2028 | 12-2028
C24-186 | Blue Stone Renewable III | THOR SOLAR | 2024-09-18 | 36.6 | 36.6 | S |  |  | RENSSELAER | NY | F | Schodack - Falls Park 115kV | Transco | NM-NG, NYSEG | 4 | 2025-02-28 |  |  | 04-2028 | 04-2028 | 08-2028
C24-188 | Wheelhouse Solar Energy Center, LLC | Wheelhouse Solar Energy Center | 2024-09-18 | 350 | 350 | CR | 80 | 4.71 | Herkimer, Oswego | NY | F | Edic 345 kV (137200) to Princetown 345 kV (148965) southern circuit #352 | NYPA | NM-NG, LS Power | 4 | 2025-02-28 |  |  | 10-2030 | 11-2030 | 12-2030
C24-189 | NY North Country, LLC | North Country Wind | 2024-09-18 | 380 | 380 | W |  |  | Franklin and Clinton | NY | D | Willis 230kV substation | NYPA |  | 4 | 2025-02-28 |  |  | 11-2028 | 12-2028 | 06-2029
C24-190 | NY North Country, LLC | North Country Wind II | 2024-09-18 | 380 | 380 | W |  |  | Franklin and Clinton | NY | D | Willis-Haverstock 345kV HW1 | NYPA |  | 4 | 2025-02-28 |  |  | 11-2028 | 12-2028 | 06-2029
C24-191 | Zenobe Rotterdam LLC | Zenobe Rotterdam LLC | 2024-09-19 | 100 | 100 | ES | 800 | 8 | Schenectady | NY | F | Rotterdam 115kV | NM-NG | LSPower | 4 | 2025-02-28 |  |  | 12-2027 | 04-2028 | 07-2028
C24-202 | Brusselville Solar, LLC | Brusselville Solar Energy Center | 2024-09-19 | 170 | 170 | CR | 80 | 4.71 | Genesee | NY | B | Dysinger-New Rochester 345kV Line (DH2) | NYPA | NYSEG,RG&E | 4 | 2025-02-28 |  |  | 10-2030 | 11-2030 | 12-2030
C24-204 | Declaration Energy Center, LLC | Declaration Energy Center | 2024-09-19 | 550 | 550 | CR | 80 | 0 | Seneca | NY | B | Clay - Pannell (Station 122), Line #1 345 kV line | NYPA | NM-NG, RG&E | 4 | 2025-02-28 |  |  | 10-2032 | 11-2032 | 12-2032
C24-205 | NEER Interconnection Holdings, LLC | Wheelhouse Energy Storage | 2024-09-19 | 200 | 200 | ES | 800 | 4.0 | Schoharie | NY | F | Planned Wheelhouse Solar switchyard looping Edic -Princetown #2 | NYPA | NM-NG; LSPower | 4 | 2025-02-28 |  |  | 10-2030 | 11-2030 | 12-2030
C24-207 | NextEra Energy Resources Interconnection Holdings, LLC | Trelina Energy Storage | 2024-09-19 | 120 | 120 | ES | 480 | 4.0 | Seneca, Ontario | NY | C | Planned Q720 Trelina Solar Switchyard on Border City to Station 168 115 kV line | NYSEG | NM-NG, RG&E | 4 | 2025-02-28 |  |  | 10-2030 | 11-2030 | 12-2030
C24-208 | Independence BESS LLC | Independence BESS | 2024-09-19 | 200 | 200 | ES | 800 | 4 | Oswego | NY | C | Independence 345 KV | NM-NG |  | 4 | 2025-02-28 |  |  | 03-2028 | 04-2028 | 06-2028
C24-209 | ACE DevCo NC LLC | Sidecar | 2024-09-20 | 50 | 50 | S |  |  | Tioga | NY | C | S Owego Substation to Goudey Substation tap line 115 kV | NYSEG |  | 4 | 2025-02-28 |  |  | 07-2029 | 08-2029 | 10-2029
C24-211 | The Commodore Storage, LLC | Marcy BESS 2 | 2024-09-20 | 195 | 195 | ES | 780 | 4 | Oneida | NY | E | Volney - Marcy 345 kV | NM-NG | NYPA | 4 | 2025-05-31 |  |  | 03-2028 | 07-2028 | 10-2028
C24-213 | Zenobe Lancaster LLC | Zenobe Lancaster LLC | 2024-09-20 | 100 | 100 | ES | 800 | 8 | Erie | NY | A | Pavement 115kV Substation | NYSEG |  | 4 | 2025-02-28 |  |  | 06-2028 | 10-2028 | 01-2029
C24-214 | Mulberry Energy Storage 1, LLC | Mulberry Energy Storage | 2024-09-20 | 130 | 130 | ES | 520 | 4 | Saratoga County | NY | F | Luther Forest-Eastover Rd 115kV Line 308 | NM-NG | NYSEG | 4 | 2025-05-31 |  |  | 01-2029 | 02-2029 | 03-2029
C24-215 | Mount Hope Stand Alone Storage 1, LLC | Mount Hope Storage | 2024-09-20 | 50 | 50 | ES | 200 | 4 | Orange County | NY | G | Cuddebackville-Shoemaker stations 69 kV Line #13 | O&R |  | 4 | 2025-02-28 |  |  | 01-2029 | 02-2029 | 03-2029
C24-216 | Zenobe Harmony LLC | Zenobe Harmony LLC | 2024-09-20 | 100 | 100 | ES | 400 | 4 | Chautauqua | NY | A | Dunkirk-Falconer Line 160 115kV | NM-NG |  | 4 | 2025-02-28 |  |  | 06-2028 | 10-2028 | 01-2029
C24-217 | Bay Breeze Solar, LLC | Bay Breeze solar | 2024-09-20 | 150 | 150 | S |  |  | Jefferson | NY | E | North Watertown (Lyme Junction)-Lyme Line 13 115 kV | NM-NG |  | 4 | 2025-02-28 |  |  | 09-2029 | 10-2029 | 12-2029
C24-218 | Poplar Energy Center | Poplar Energy Center, LLC | 2024-09-20 | 60 | 60 | ES | 240 | 4 | Suffolk | NY | K | Riverhead - Tuthill 69kV | LIPA |  | 4 | 2025-05-31 |  |  | 12-2028 | 01-2029 | 02-2029
C24-222 | Knickerbocker Energy Storage Project, LLC | Knickerbocker Energy Storage | 2024-09-20 | 300 | 300 | ES | 300 | 4 | Schodack Landing | NY | F | KNICKERBOCKER 345 kV | Transco | NM-NG | 4 | 2025-02-28 |  |  | 09-2030 | 10-2030 | 12-2030
C24-223 | Mission Clean Energy Devco, LLC | Queen Energy Center | 2024-09-20 | 140 | 140 | ES | 1400 | 10 | Tompkins | NY | C | Etna - Milliken 115 kV line | NYSEG |  | 4 | 2025-03-31 |  |  | 08-2029 | 09-2029 | 11-2029
C24-224 | ACE DevCo NC, LLC | Cohocton | 2024-09-20 | 130 | 130 | CR | 400 | 4.5 | Steuben | NY | C | Tap 115kV line from Bath 115 kV station to Spencer Hill (Howard) 115 kV Station | NYSEG |  | 4 | 2025-02-28 |  |  | 07-2029 | 08-2029 | 10-2029
C24-225 | Goldenrod Wind LLC | Goldenrod Wind | 2024-09-20 | 39 | 39 | W |  |  | Chautauqua | NY | A | Moon Road-Hartfield 115kV Line159 | NM-NG |  | 4 | 2025-02-28 |  |  | 06-2029 | 09-2029 | 12-2029
C24-227 | Lucy?s Energy Reserve LLC | South Dow 2 (Lucy's Energy Reserve 2) | 2024-09-20 | 125 | 125 | ES | 500 | 4 | Chautauqua | NY | A | Falconer-South Dow Line 154 115kV | NM-NG | NYSEG | 4 | 2025-02-28 |  |  | 12-2027 | 02-2028 | 05-2028
C24-229 | Buttercup Wind LLC | Buttercup Wind | 2024-09-21 | 49.9 | 49.9 | W |  |  | Chautauqua | NY | A | Dunkirk-Falconer Line 160 115kV | NM-NG |  | 4 | 2025-02-28 |  |  | 06-2029 | 09-2029 | 12-2029
C24-230 | Dewdrop Wind LLC | Dewdrop Wind | 2024-09-21 | 62 | 62 | W |  |  | Chautauqua | NY | A | South Ripley Substation -Dunkirk Substation 230kV | NM-NG |  | 4 | 2025-02-28 |  |  | 06-2029 | 09-2029 | 12-2029
C24-233 | Shallow Seam Energy Storage, LLC | Shallow Seam BESS | 2024-09-22 | 400 | 400 | ES | 1600 | 4 | Clearfield | PA | C | Homer City - Mainesburg 345kV Line (L47) | NYSEG |  | 4 | 2024-02-28 |  |  | 09-2028 | 12-2028 | 03-2029
C24-234 | RWE Solar Development, LLC | Zulu BESS | 2024-09-22 | 70 | 70 | ES | 280 | 4 | Orange | NY | G | Bethlehem Road 115kV | CHGE |  | 4 | 2025-02-28 |  |  | 09-2028 | 10-2028 | 02-2029
C24-235 | RWE Clean Energy Development, LLC | Champlain Solar Uprate | 2024-09-22 | 30 | 30 | S |  |  | Washington | NY | F | Mohican - Whitehall 115 kV Line 13 | NM-NG | NYSEG | 4 | 2025-02-28 |  |  | 05-2028 | 06-2028 | 12-2028
C24-236 | RWE Clean Energy Development, LLC | Champlain Solar | 2024-09-22 | 90 | 90 | S |  |  | Washington | NY | F | Mohican - Whitehall 115 kV Line 13 | NM-NG | NYSEG | 4 | 2025-02-28 |  |  | 05-2028 | 06-2028 | 12-2028
C24-237 | SBMT Energy Center, LLC | SBMT Energy Center, LLC | 2024-09-23 | 160 | 160 | ES | 640 | 4 | Kings County | NY | J | 345kV Gowanus Substation | ConEd |  | 4 | 2025-03-31 |  |  | 10-2028 | 11-2028 | 12-2028
C24-238 | Zenobe Americas Inc. | Zenobe Burns LLC | 2024-09-23 | 100 | 100 | ES | 400 | 4 | Allegany | NY | C | Moraine Rd 115kV Substation | NYSEG |  | 4 | 2025-02-28 |  |  | 12-2027 | 04-2028 | 07-2028
C24-244 | New York Power Authority | Utica Solar PV Project | 2024-09-23 | 20 | 20 | S |  |  | Oneida | NY | E | Deerfield - Schuyler 46kV Line 22 | NM-NG |  | 4 | 2025-03-31 |  |  | 09-2028 | 10-2028 | 11-2028
C24-245 | PA-Hockenberry LLC | PA-Hockenberry LLC | 2024-09-23 | 400 | 400 | S |  |  | Jefferson | PA | A | Tap on Homer City to Pierce Brook 345kV line | NYSEG |  | 4 | 2025-04-30 |  |  | 09-2029 | 10-2029 | 03-2030
C24-247 | Nexamp Solar LLC | Jerry Smith Energy Storage | 2024-09-23 | 34.9 | 34.9 | ES | 139.6 | 4 | Tompkins | NY | C | Milliken to Ludlowville 34.5kV Line#522 -on N.Lansing-Ludlowville 2.11mi section | NYSEG |  | 4 | 2025-02-28 |  |  | 09-2028 | 10-2028 | 01-2029
C24-248 | Dove Energy Storage | Dove Energy Storage | 2024-09-23 | 79.9 | 79.9 | ES | 319.6 | 4 | Montgomery | NY | F | St. Johnsville - Marshville, Line id #11 (CLCPA rebuild), 115 kV, | NM-NG |  | 4 | 2025-02-28 |  |  | 07-2028 | 08-2028 | 12-2028
C24-249 | Empire Solar LLC | Empire | 2024-09-23 | 60 | 60 | S |  |  | Chautaqua | NY | A | Dunkirk-South Ripley Line 68 230kV | NM-NG |  | 4 | 2025-02-28 |  |  | 11-2028 | 12-2028 | 02-2029
C24-250 | Honey Ridge Solar 1, LLC | Honey Ridge Solar | 2024-09-23 | 100 | 100 | S |  |  | Jefferson | NY | E | Black River - North Carthage 115 kV, Line #1 | NM-NG |  | 4 | 2025-02-28 |  |  | 01-2029 | 02-2029 | 03-2029
C24-251 | Vidal Blanc Storage 1, LLC | Vidal Blanc Storage | 2024-09-23 | 100 | 100 | ES | 400 | 4 | Ulster | NY | G | Galeville-Kerhonkson 115kV | CHGE |  | 4 | 2025-02-28 |  |  | 01-2029 | 02-2029 | 03-2029
C24-252 | Nexamp Solar LLC | Maple City Energy Storage | 2024-09-23 | 79 | 79 | ES | 316 | 4 | Steuben | NY | C | Bennett Substation 115kV | NYSEG |  | 4 | 2025-03-31 |  |  | 08-2029 | 09-2029 | 12-2029
C24-253 | Nexamp Solar LLC | Troy Heights Energy Storage | 2024-09-23 | 40 | 40 | ES | 160 | 4 | Tompkins | NY | C | Coddington Substation 34.5 kV | NYSEG |  | 4 | 2025-02-28 |  |  | 08-2028 | 09-2028 | 12-2028
C24-255 | Saltgrass Storage LLC | Saltgrass Storage | 2024-09-23 | 50 | 50 | ES | 200 | 4 | Nassau | NY | K | Line 33-222 and 33-317 LIPA 33kV | LIPA |  | 4 | 2025-03-31 |  |  | 06-2028 | 07-2028 | 08-2028
C24-256 | Springer Storage | Springer Storage | 2024-09-23 | 79.9 | 79.9 | ES | 319.6 | 4 | Washington | NY | F | Mohican-Whitehall Line 13 115kV | NM-NG |  | 4 | 2025-02-28 |  |  | 02-2028 | 03-2028 | 07-2028
C24-257 | Grapevine Storage LLC | Grapevine Storage | 2024-09-23 | 200 | 200 | ES | 800 | 4 | Fredonia | NY | A | Gardenville-Dunkirk Line 74 230kV | NM-NG |  | 4 | 2025-03-31 |  |  | 06-2028 | 07-2028 | 08-2028
C24-259 | Nexamp Solar LLC | Christmas Tree | 2024-09-23 | 25 | 25 | CR | 20 | 4 | Schuyler | NY | C | Cayuta to Ridge Road 34.5 kV Line# 501 | NYSEG |  | 4 | 2025-02-28 |  |  | 08-2027 | 09-2027 | 12-2027
C24-263 | Jefferson Energy Storage | Jefferson Energy Storage | 2024-09-23 | 100 | 100 | ES | 400 | 4 | Lewis | NY | E | Austin Rd. - Edic #11, 345 kV | NM-NG |  | 4 | 2025-02-28 |  |  | 02-2028 | 03-2028 | 07-2028
C24-264 | Berry Farm Storage 1, LLC | Berry Farm Storage | 2024-09-23 | 120 | 120 | ES | 480 | 4 | Chautauqua | NY | A | L160 115 kV line (Dunkirk and Falconer) | NM-NG |  | 4 | 2025-02-28 |  |  | 01-2029 | 02-2029 | 03-2029
C24-265 | Calpine Mid-Atlantic Development, LLC | Bethpage Battery Storage Project | 2024-09-23 | 44 | 44 | ES | 176 | 4 | Nassau | NY | K | LIPA Grumann B 69 kV Substation | LIPA |  | 4 | 2025-05-31 |  |  | 01-2027 | 02-2027 | 05-2027
C24-266 | Mission Clean Energy Devco, LLC | Summersweet Energy Center | 2024-09-23 | 199 | 199 | ES | 1990 | 10 | Orange county | NY | G | Sugarloaf - Sterling Forest 138 kV | O&R |  | 4 | 2025-03-31 |  |  | 08-2029 | 09-2029 | 11-2029
C24-268 | Arnold Energy Storage | Arnold Energy Storage | 2024-09-24 | 79.9 | 79.9 | ES | 319.6 | 4 | St. Lawrence | NY | D | Colton - Malone 115kV Line 3 | NM-NG |  | 4 | 2025-02-28 |  |  | 07-2028 | 08-2028 | 12-2028
C24-269 | Stonewall Solar LLC | Stonewall Solar | 2024-09-24 | 145 | 145 | CR | 290 | 4.3 | Delaware | NY | E | Fraser Tap-Colliers 115 kV line #951 | NYSEG |  | 4 | 2025-02-28 |  |  | 01-2028 | 02-2028 | 05-2028
C24-270 | Bassett Energy Storage | Bassett Energy Storage | 2024-09-24 | 79.9 | 79.9 | ES | 319.6 | 4 | Steuben | NY | C | Spencer Hill 115 kV Substation | NYSEG |  | 4 | 2025-02-28 |  |  | 02-2028 | 03-2028 | 07-2028
C24-273 | National Grid Generation LLC | Glenwood Power Station Battery Energy Storage System (BESS) | 2024-09-24 | 50 | 50 | ES | 200 | 4 | Nassau | NY | K | LIPA Glenwood 69kV Substation | LIPA |  | 4 | 2025-02-28 |  |  | 10-2028 | 10-2028 | 12-2028
C24-274 | National Grid Generation LLC | ? Southampton Power Station Battery Energy Storage System (BESS) | 2024-09-24 | 31.96 | 31.96 | ES | 120 | 4 | Suffolk | NY | K | Southampton 69kV | LIPA |  | 4 | 2025-02-28 |  |  | 10-2028 | 10-2028 | 12-2028
C24-278 | New York Power Authority | Sullivan-Woodbourne Solar Project | 2024-09-24 | 100 | 100 | S |  |  | Sullivan | NY | E | Mountaindale - Woodbourne 115 kV line | NYSEG |  | 4 | 2025-03-31 |  |  | 09-2028 | 10-2028 | 11-2028
C24-279 | New York Power Authority | Eastern Solar PV Project | 2024-09-24 | 30 | 30 | S |  |  | Ulster | NY | G | Kerhonkson to Honks Falls 69kV line | CHGE |  | 4 | 2025-03-31 |  |  | 09-2028 | 10-2028 | 11-2028
C24-280 | National Grid Generation LLC | Wading River Power Station Battery Energy Storage System (BESS) | 2024-09-24 | 50 | 50 | ES | 200 | 4 | Suffolk | NY | K | Wading River 138 kV Substation | LIPA |  | 4 | 2025-02-28 |  |  | 10-2028 | 10-2028 | 12-2028
C24-281 | the New York Power Authority | Brentwood Energy Storage | 2024-09-25 | 49.1 | 49.1 | ES | 196.4 | 4 | Suffolk | NY | K | Brentwood 69 kV Substation | LIPA |  | 4 | 2025-03-31 |  |  | 06-2028 | 07-2028 | 08-2028
C24-282 | 82 Shingle House Rd, LLC | Millwood Energy Storage | 2024-09-25 | 273.5 | 273.5 | ES | 1094 | 4 | Westchester | NY | H | Millwood West 345kV | ConEd |  | 4 | 2025-05-31 |  |  | 11-2028 | 11-2028 | 12-2028
C24-283 | Resilient New York Storage, LLC by Hanwha Energy USA Holdings Corporation, its Manager | Resilient New York Energy Storage | 2024-09-25 | 349 | 349 | ES | 1396 | 4 | Richmond | NY | J | Goethals 345 kV | ConEd |  | 4 | 2025-05-30 |  |  | 11-2028 | 11-2028 | 12-2028
C24-284 | Prologis Energy LLC | South Bronx Energy Storage | 2024-09-25 | 100 | 100 | ES | 400 | 4 | Bronx | NY | J | Hell Gate 138 kV Substation | NYPA | ConEd | 4 | 2025-02-28 |  |  | 07-2030 | 08-2030 | 12-2030
C24-288 | ACE DevCo NC, LLC | Mossy Bank Solar | 2024-09-27 | 200 | 200 | S |  |  | Steuben | NY | C | Prattsburgh Wind farm to Stony Ridge Line Tap 230 kV | NYSEG |  | 4 | 2025-02-28 |  |  | 09-2029 | 10-2029 | 12-2029
C24-289 | Genovia Storage LLC | Genovia Storage | 2024-09-27 | 300 | 300 | ES | 1200 | 4 | Genesee | NY | B | 345 kV Line 1 QP580_POI2 Substation to Q721_POI Substation | NYPA |  | 4 | 2025-03-31 |  |  | 06-2028 | 07-2028 | 08-2028
C24-292 | BayWa r.e Projects LLC. | Loganberry Energy Storage, LLC | 2024-09-27 | 150 | 150 | ES | 600 | 4 | Chautauqua | NY | A | Dunkirk to Falconer Line 160 115 kV | NM-NG |  | 4 | 2025-03-31 |  |  | 07-2030 | 08-2030 | 12-2030
C24-293 | Oswego Clean Energy Holdings | Oswego Clean Energy | 2024-09-27 | 24.9 | 24.9 | S |  |  | Oswego | NY | C | Oswego 115 kV Substation | NM-NG |  | 4 | 2025-05-31 |  |  | 11-2026 | 12-2026 | 12-2026
C24-294 | Birch Whistler, LLC | Birch-Whistler | 2024-09-27 | 100 | 100 | W |  |  | Delaware | NY | E | Line Tap Edic to Fraser Line, 345kV | NYPA | NM-NG, NYSEG | 4 | 2025-02-28 |  |  | 09-2029 | 11-2029 | 12-2029
C24-297 | Deer River Wind, LLC | Deer River Wind | 2024-09-27 | 100 | 100 | W |  |  | Lewis | NY | E | Black River-Lighthouse Hill Line 5 115kV | NM-NG |  | 4 | 2025-03-31 |  |  | 10-2029 | 11-2029 | 12-2029
C24-298 | Black Cherry Wind Power, LLC | Black Cherry Wind 1 | 2024-09-29 | 350 | 350 | W |  |  | Cameron & McKean | PA | A | Homer City - Piercebrook 345kV | NYSEG |  | 4 | 2025-02-28 |  |  | 05-2029 | 08-2029 | 12-2029
C24-299 | Black Cherry Wind Power, LLC | Black Cherry Wind 2 | 2024-09-29 | 150 | 150 | W |  |  | Cameron, Elk, and McKean | PA | A | Homer City - Piercebrook 345kV | NYSEG |  | 4 | 2025-02-28 |  |  | 05-2029 | 08-2029 | 12-2029
C24-300 | Kimberlite Solar Power, LLC | Kimberlite Solar | 2024-09-30 | 175 | 175 | S |  |  | Clearfield | PA | C | Homer City - Mainesburg 345kV Line (L47) | NYSEG |  | 4 | 2025-02-28 |  |  | 09-2028 | 12-2028 | 03-2029
C24-301 | Moonlight Flats Solar Power, LLC | Moonlight Flats Solar | 2024-09-30 | 250 | 250 | S |  |  | Clearfield | PA | C | Homer City 345 kV to Mainesburg 345 kV L47 | NYSEG |  | 4 | 2025-02-28 |  |  | 09-2028 | 12-2028 | 03-2029
C24-302 | McMullen Pond LLC | NY Oswego 200 Erie St Storage | 2024-09-30 | 142 | 142 | ES | 568 | 4 | Oswego | NY | C | Oswego - S Oswego 115kV circuit 3 | NM-NG |  | 4 | 2025-02-28 |  |  | 02-2028 | 03-2028 | 04-2028
C24-303 | Bergholtz Creek LLC | NY Niagara Falls 5800 Niagara Falls Blvd Storage | 2024-09-30 | 161 | 161 | ES | 644 | 4 | Niagara | NY | A | Packard - Huntley Line 77 230kV | NM-NG |  | 4 | 2025-02-28 |  |  | 02-2028 | 03-2028 | 04-2028
C24-304-004 | Chateauguay River, LLC | NY Chateaugay 0 Willis Rd Storage | 2024-10-01 | 150 | 150 | ES | 600 | 4 | Franklin | NY | D | Willis 230kV substation | NYPA |  | 4 | 2024-02-28 |  |  | 02-2028 | 03-2028 | 04-2028
C24-306 | Oriden | Lock 26 BESS | 2024-10-01 | 50 | 50 | ES | 200 | 4.0 | Wayne | NY | C | Clyde 115kV | RG&E | NYSEG, NM-NG | 4 | 2025-02-28 |  |  | 08-2028 | 10-2028 | 12-2028
C24-309 | Black Cherry Wind Power, LLC | Black Cherry BESS | 2024-10-01 | 400 | 400 | ES | 1600 | 4 | McKean | PA | A | Homer City to Piercebrook 345kV Line | NYSEG |  | 4 | 2025-02-28 |  |  | 05-2029 | 08-2029 | 12-2029
C24-312 | BW Solar Holding Inc. | St. Regis | 2024-10-02 | 58.5 | 58.5 | CR | 234 | 4.3 | St. Lawrence | NY | E | Dennison-Colton #5 115 kV Line. | NM-NG |  | 4 | 2025-03-31 |  |  | 01-2029 | 04-2029 | 06-2029
C24-313 | New York Power Authority | Southport Solar PV Project | 2024-10-02 | 42 | 42 | S |  |  | Chemung | NY | C | Caton Ave. 115 kV Station | NYSEG |  | 4 | 2025-03-31 |  |  | 09-2028 | 10-2028 | 11-2028
C24-317 | BGTF US Development Holdings LLC | Leo Energy Storage | 2024-10-03 | 75 | 75 | ES | 300 | 4 | Clinton | NY | D | Lyon Mountain 115 kV Substation | NYSEG | NYPA | 4 | 2025-02-28 |  |  | 10-2028 | 11-2028 | 12-2028
C24-318 | Nexamp Solar LLC | Sherburne Storage | 2024-10-04 | 40 | 40 | ES | 160 | 4 | Chenango | NY | E | County Line 46 kV Substation | NYSEG |  | 4 | 2025-02-28 |  |  | 08-2028 | 09-2028 | 12-2028
C24-319 | Ditch Creek Solar LLC | Ditch Creek | 2024-10-05 | 199.5 | 199.5 | CR | 400 | 4 | Madison | NY | C | CLAY to EDIC 345 kV Line #15 Circuit #2 | NYPA | NM-NG | 4 | 2025-02-28 |  |  | 08-2027 | 09-2027 | 12-2027
C24-320 | Nexamp Solar LLC | Boonville Standalone Storage | 2024-10-05 | 79 | 79 | ES | 316 | 4 | Lewis | NY | E | 115kV Boonville-Waters Road Line#8 (proposed as Boonville-Taylorville Line#6) | NM-NG |  | 4 | 2025-02-28 |  |  | 08-2028 | 09-2028 | 12-2028
C24-321 | Jericho Solar Park LLC | Jericho Solar | 2024-10-07 | 100 | 100 | S |  |  | Franklin | NY | D | NYPA's Willis Sub @115kV | NYPA |  | 4 | 2025-02-28 |  |  | 05-2029 | 07-2029 | 10-2029
C24-322 | Rolling Upland Wind Farm LLC | Rolling Upland Wind Farm | 2024-10-07 | 79.8 | 79.8 | W |  |  | Madison and Oneida County | NY | E | County Line-Brothertown 115kV | NYSEG |  | 4 | 2025-02-28 |  |  | 05-2029 | 07-2029 | 10-2029
C24-323 | Echo Lake Solar LLC | Echo Lake | 2024-10-07 | 79.9 | 79.9 | CR | 160 | 4.22 | Oneida | NY | E | 115 kV Boonville Village - Porter Line #1, Circuit #1 | NM-NG |  | 4 | 2025-02-28 |  |  | 03-2028 | 04-2028 | 07-2028
C24-324 | Origis Development LLC | Overlook Storage | 2024-10-08 | 199 | 199 | ES | 796 | 4 | Dutchess | NY | G | Pleasant Valley - Todd Hill 115 kV | CHGE |  | 4 | 2025-03-31 |  |  | 09-2028 | 10-2028 | 12-2028
C24-325 | Origis Development LLC | Van Buren Storage | 2024-10-08 | 150 | 150 | ES | 600 | 4 | Chautauqua | NY | A | Dunkirk to Falconer 115kV Line 160 | NM-NG |  | 4 | 2025-03-31 |  |  | 09-2028 | 10-2028 | 12-2028
C24-326 | Origis Development LLC | Lockport Storage | 2024-10-08 | 180 | 180 | ES | 720 | 4 | Niagara | NY | A | Robinson Road 230 kV | NYSEG |  | 4 | 2025-05-31 |  |  | 09-2028 | 10-2028 | 12-2028
C24-327 | North Creek Solar LLC | North Creek | 2024-10-08 | 199.5 | 199.5 | CR | 400 | 4 | Oneida | NY | E | EDIC to GORDON ROAD 345kV, Line #14 | NM-NG | LSPower | 4 | 2025-02-28 |  |  | 08-2027 | 09-2027 | 12-2027
C24-331 | the New York Power Authority | Hell Gate Energy Storage | 2024-10-09 | 90 | 90 | ES | 360 | 4 | Bronx | NY | J | Hell Gate Bus Section 2 - 138kV | NYPA | ConEd | 4 | 2025-03-31 |  |  | 10-2028 | 10-2028 | 12-2028
C24-332 | Granada Solar, LLC | Stoner Trail Storage | 2024-10-09 | 100 | 100 | ES | 400 | 4 | Fulton | NY | F | Inghams-Stoner 115kV line 9 and Meco-Maple Ave 115kV line 22 | NM-NG |  | 4 | 2025-02-28 |  |  | 06-2028 | 07-2028 | 08-2028
C24-333 | the New York Power Authority | Pouch Energy Storage System | 2024-10-09 | 47.1 | 47.1 | ES | 188.4 | 4 | Kings | NY | J | Fox Hills 138kV Substation | ConEd |  | 4 | 2025-03-31 |  |  | 10-2028 | 10-2028 | 12-2028
C24-334 | the New York Power Authority | Flynn Energy Storage | 2024-10-09 | 170 | 170 | ES | 680 | 4 | Suffolk | NY | K | West Bus - 138kV | LIPA |  | 4 | 2025-03-31 |  |  | 10-2030 | 11-2030 | 12-2030
C24-335 | PA-Fritz Kiln LLC | PA-Fritz Kiln LLC | 2024-10-09 | 300 | 300 | S |  |  | Elk | PA | A | Tap on Homer City - Pierce Rd 345kV line | NYSEG |  | 4 | 2025-04-30 |  |  | 09-2029 | 10-2029 | 03-2030
C24-336 | ConnectGen Montgomery County LLC | Mill Point Solar II | 2024-10-10 | 100 | 100 | CR |  |  | Montgomery | NY | E | Marcy - New Scotland 345kV, Line 18 | NM-NG | NYPA | 4 | 2025-02-28 |  |  | 07-2028 | 09-2028 | 12-2028
C24-337 | Terra-Gen Development Company, LLC | Aria Storage 1 | 2024-10-10 | 100 | 100 | ES | 400 | 4 | Dutchess | NY | H | East Fishkill 345 kV substation | ConEd |  | 4 | 2025-02-28 |  |  | 10-2028 | 10-2028 | 12-2028
C24-338 | Terra-Gen Development Company, LLC | Aria Storage 2 | 2024-10-10 | 150 | 150 | ES | 600 | 4 | Dutchess | NY | H | East Fishkill 345 kV | ConEd |  | 4 | 2025-02-28 |  |  | 10-2028 | 12-2028 | 12-2028
C24-341 | Origis Development LLC | Marlboro Storage | 2024-10-10 | 100 | 100 | ES | 400 | 4 | Ulster | NY | G | Marlboro 115kV Substation | CHGE |  | 4 | 2025-03-31 |  |  | 09-2028 | 10-2028 | 12-2028
C24-342 | Beacon Wind Land LLC | AGRE Storage | 2024-10-11 | 125 | 125 | ES | 500 | 4 | Queens | NY | J | Astoria West 138 kV | ConEd |  | 4 | 2025-03-31 |  |  | 01-2029 | 03-2029 | 05-2029
C24-344 | Deerpark Energy Storage, LLC | Deerpark Energy Storage | 2024-10-11 | 50 | 50 | ES | 200 | 4 | Orange | NY | G | Cuddebackville 69kV Substation | O&R |  | 4 | 2025-02-28 |  |  | 12-2028 | 02-2029 | 06-2029
C24-347 | Hodson Energy Little Falls LLC | Little Falls Solar | 2024-10-14 | 78 | 78 | S |  |  | Herkimer | NY | E | Watkins Road-Inghams Line 2 115kV | NM-NG | NYPA | 4 | 2025-03-31 |  |  | 11-2027 | 01-2028 | 02-2028
C24-348 | ConnectGen Cayuga County LLC | Harvest Hills Solar | 2024-10-14 | 200 | 200 | S |  |  | Cayuga | NY | C | Wright Avenue - Milliken 115kV Line 973 | NYSEG |  | 4 | 2025-02-28 |  |  | 07-2029 | 09-2029 | 12-2029
C24-349-005 | RIC Development, LLC | Richland III Solar | 2024-10-14 | 79.9 | 79.9 | S |  |  | Oswego | NY | C | Indeck Oswego - Tar Hill Line 2 115kV | NM-NG |  | 4 | 2025-02-28 |  |  | 08-2028 | 11-2028 | 02-2029
C24-350 | Hickling Storage, LLC | Hickling Storage, LLC | 2024-10-14 | 90 | 90 | ES | 180 | 2 | Steuben | NY | C | 115kV Hickling Substation | NYSEG |  | 4 | 2025-03-31 |  |  | 09-2027 | 10-2027 | 12-2027
C24-352 | CEDAR HOLDCO LLC | Swiss Valley Energy Storage | 2024-10-15 | 300 | 300 | ES | 1200 | 4 | Wyoming | NY | C | Wethersfield 230 kV Substation | NYSEG |  | 4 | 2025-02-28 |  |  | 09-2029 | 10-2029 | 12-2029
C24-357 | Glove City Energy Center, LLC | Glove City Solar | 2024-10-15 | 100 | 100 | S |  |  | Montgomery | NY | F | Stoner (137906) to Inghams (137228) 115kV line | NM-NG |  | 4 | 2025-04-30 |  |  | 10-2029 | 11-2029 | 12-2029
C24-358 | CEDAR HOLDCO LLC | Sugar Loaf Energy Storage I | 2024-10-15 | 300 | 300 | ES | 1200 | 4 | Orange | NY | G | Sugarloaf 138 kV Substation | O&R | Transco, ConEd | 4 | 2025-02-28 |  |  | 09-2029 | 10-2029 | 12-2029
C24-359 | CEDAR HOLDCO LLC | Sugar Loaf Energy Storage II | 2024-10-15 | 300 | 300 | ES | 1200 | 4 | Orange | NY | G | Sugarloaf 138 kV Substation | O&R | ConEd, Transco | 4 | 2025-02-28 |  |  | 09-2029 | 10-2029 | 12-2029
C24-361 | Cherry Valley Energy Center, LLC | Cherry Valley Solar | 2024-10-15 | 125 | 125 | S |  |  | Montgomery | NY | F | Edic to Princetown Line #351, 345 kV | NYPA | LS Power; NM-NG | 4 | 2025-03-31 |  |  | 10-2029 | 11-2029 | 12-2029
C24-362 | RWE Solar Development, LLC | Amsterdam Solar | 2024-10-15 | 150 | 150 | S |  |  | Montgomery | NY | E | Edic - Gordon Road 345 kV, Line 14 | NM-NG | NYPA, LSpower | 4 | 2025-04-30 |  |  | 05-2028 | 06-2028 | 07-2028
C24-363 | RWE Solar Development, LLC | Town Line Solar CSR Phase I | 2024-10-15 | 240 | 240 | CR | 400 | 4.66 | Sullivan | NY | E | Coopers Corner to Middletown Tap 345 kV Line | NYPA | NYSEG, O&R | 4 | 2025-04-30 |  |  | 12-2029 | 01-2030 | 05-2030
C24-364 | RWE Solar Development, LLC | Erie Canal BESS | 2024-10-15 | 230 | 230 | ES | 920 | 4 | Niagara | NY | A | Robinson Road 115 kV | NYSEG |  | 4 | 2025-02-28 |  |  | 09-2028 | 10-2028 | 02-2029
C24-366 | Azalea Wind LLC | Azalea Wind 1 | 2024-10-15 | 50 | 50 | W |  |  | Schuyler | NY | C | Montour Falls to Coddington Road 115kV | NYSEG |  | 4 | 2025-02-28 |  |  | 06-2029 | 09-2029 | 12-2029
C24-367 | Lewis Wind, LLC | Lewis Wind | 2024-10-15 | 100 | 100 | W |  |  | Lewis | NY | E | Volney-Marcy Line 19 345kV line | NM-NG | NYPA | 4 | 2025-03-31 |  |  | 10-2030 | 11-2030 | 12-2030
C24-370 | Azalea Wind LLC | Azalea Wind 2 | 2024-10-15 | 50 | 50 | W |  |  | Schuyler | NY | C | Montour Falls to Coddington Road 115kV | NYSEG |  | 4 | 2025-02-28 |  |  | 06-2029 | 09-2029 | 12-2029
CR24-1002 | National Grid Generation, LLC | West Babylon Internal Combustion (IC), Unit 4 | 2024-09-27 |  |  | O |  |  | Suffolk | NY | K | West Babylon 13.8 kV | LIPA |  | 4 | 2025-02-28 |  |  | TBD | TBD | TBD
CR24-1003 | GB II New York LLC | Bethlehem Energy Center Uprate | 2024-10-04 |  |  | NG |  |  | Albany | NY | F | Albany Steam 115 kV | NM-NG |  | 4 | 2025-05-31 |  |  | 06-2026 | 06-2026 | 06-2026
CR24-1004 | Arthur Kill Power LLC | Arthur Kill Unit 2 Uprate | 2024-10-04 |  |  | NG |  |  | Richmond | NY | J | Freshkills 138kV | ConEd |  | 4 | 2025-05-31 |  |  | TBD | TBD | TBD
NOTES: | ● The column labeled 'SP' refers to the maximum summer megawatt electrical output. The column labeled 'WP' refers to the maximum winter megawatt electrical output.
● Type / Fuel Key: ST=Steam Turbine, CT=Combustion Turbine, CC, CS= Steam Turbine & Combustion Turbine, H=Hydro, PS=Pumped Storage, W=Wind, OSW= Off-Shore Wind, NU=Nuclear, NG=Natural Gas, M=Methane, SW=Solid Waste, S=Solar, Wo=Wood, F=Flywheel ES=Energy Storage, O=Oil, C=Coal, D=Dual Fuel, AC,
DC, L=Load, FC=Fuel Cell,CW=CSR - ES + Wind, CR=CSR - ES + Solar
● The column labeled 'Z' refers to the zone
● The column labeled 'S' refers to the status of the project in the NYISO's LFIP. Key: 1C = IR Validated/ Scoping Meeting Pending, 2C = Customer Engagement Window, 3C = Phase 1 Entry Decision Period, 4C = Phase 1 Study, 5C = Phase 2 Entry Decision Period, 6C = Phase 2 Study, 7C = Final Decision Period, 10C = Accepted Cost Allocation/ IA in Progress, 11C = IA Completed, 12C = Under Construction, 13C = In Service for Test, 14C = In Service Commercial, 15C =Partially In-Service/ Partially under construction
● Proposed In-Service Dates, Proposed Initial Synchronization Dates and Commercial Operation Dates (COD) are shown in format Year/Qualifier, where Qualifier may indicate the month, season, or quarter.

## Affected System Studies
Queue Pos. | Developer/Interconnection Customer | Project Name | Date of IR | SP (MW) | WP (MW) | Type/ Fuel | County | State | Zone | Points of Interconnection | Utility | Affected Transmission Owner (ATO) | S | Last Updated Date | Availability of Studies | IA Tender Date | CY/FS Complete Date | Proposed In-Service/Initial Backfeed Date | Proposed Sync Date | Proposed COD
1718 | Seven Creek Energy, LLC | Erie East BESS | 2024-09-10 |  |  | AC | Erie | PA | A | Erie East 230kV (First Energy, Erie PA) | PJM | NM-NG | 1 | 2025-04-30 |  |  |  | 06-2027
1734 | Mid-Atlantic Interstate Transmission, LLC | Fairbanks Run Mod Sub | 2025-04-09 |  |  | AC | Warren | PA | A | Tapping the National Grid Falconer to MAIT Warren line on the Pennsylvania side of the line. | PJM | NM-NG | 1 | 2025-04-30 |  |  |  | 04-2028

## Withdrawn
Queue Pos. | Owner/Developer | Project Name | Date of IR | SP (MW) | WP (MW) | Type/ Fuel | County | State | Z | Interconnection Point | Utility | S | Last Update
0005 | Sithe Energies | Torne Valley Station | 1999-01-28 | 860 | [5 empty] | Ramapo | CONED | 0
0006 | Sunset Energy Fleet LLC | Sunset Energy Fleet | 1999-02-17 | 520 | [5 empty] | Gowanus | CONED | 0
0007 | American National Power | Ramapo Energy | 1999-02-23 | 1100 | [5 empty] | Ramapo | CONED | 0
0008 | Columbia Electric Corp. | Grassy Point | 1999-02-23 | 1100 | [5 empty] | West Haverstraw | CONED | 0
0009 | Millennium Power Gen Co. LLC | Millennium 1 | 1999-02-23 | 160 | [5 empty] | Hell Gate/Bruckner | CONED | 0
0010 | Millennium Power Gen Co. LLC | Millennium 2 | 1999-02-23 | 320 | [5 empty] | Hell Gate/Bruckner | CONED | 0
0012 | East Coast Power, LLC | East Coast Power Linden | 1999-03-25 | 70 |  | ST | Richmond-NJ | NY | J | Goethals 345kV | CONED | 0 | 2008-07-10
0013 | East Coast Power, LLC | Linden 7 | 1999-03-25 | 100 |  | ST | Richmond-NJ | NY | J | Goethals 345kV | CONED | 0 | 2008-07-10
0014 | East Coast Power, LLC | Linden Plant Improvement | 1999-03-25 | 20 |  | ST | Richmond-NJ | NY | J | Goethals 345kV | CONED | 0 | 2008-07-10
0015 | AEP Resources Service Corp. | CT-LI AC Tie-line | 1999-04-13 | 600 | [5 empty] | Shoreham, Long Island | LIPA | 0
0016 | Oak Point Property, LLC | Oak Point Yard | 1999-04-15 | 500 |  | CC | Bronx | NY | J | Hell Gate/Bruckner 138kV | CONED | 0 | 2008-07-10
0019 | NYC Energy LLC | NYC Energy LLC | 1999-05-07 | 79.9 |  | CT | Kings | NY | J | Kent Ave 138kV | CONED | 0 | 2010-09-30
0020 | KeySpan Energy, Inc. | Spagnoli Road CC Unit | 1999-05-17 | 250 |  | CC | Suffolk | NY | K | Spagnoli Road 138kV | LIPA | 0 | 2012-03-01
0021 | KeySpan Energy, Inc. | Shoreham Gen Station | 1999-05-17 | 250 | [5 empty] | Shoreham | LIPA | 0
0022 | Calpine Eastern Corporation | Wawayanda Energy Center | 1999-06-10 | 500 |  | CC | Orange | NY |  | Coop Corn-Rock Tav Lines 345kV | NYPA | 0 | 2006-06-26
0023 | Calpine Eastern Corporation | Sullivan County Power Project | 1999-06-25 | 1080 |  | CC | Sullivan | NY |  | Coop Corn-Rock Tav Lines 345kV | NYPA | 0 | 2006-03-31
0024 | Reliant Energy | Astoria Repowering-Phase 1 | 1999-07-13 | 367 |  | CC | Queens | NY |  | Astoria 138kV | CONED | 0 | 2006-08-09
0026 | Twin Tier Power, LLC | Twin Tier Power | 1999-08-20 | 520 | [5 empty] | Watercure-Oakdale 31 Line | NYSEG | 0
0027 | ENRON | Far Rockaway Barge | 1999-09-08 | 60 | [5 empty] | Far Rockaway | LIPA | 0
0028 | KeySpan Energy, Inc. | Spagnoli Road GT Unit | 1999-09-08 | 79.9 | [5 empty] | Spagnoli Road | LIPA | 0
0029 | Mirant | Bowline Point Unit 3 | 1999-10-13 | 750 |  | CC | Rockland | NY |  | W. Haverstraw 345kV | CONED | 0 | 2006-07-10
0030 | Sithe Energies | Heritage Station | 1999-10-29 | 800 | [5 empty] | Independence (Oswego) | NM-NG | 0
0031 | SCS Energy, LLC | Astoria Energy - Phase 2 | 1999-11-16 | 500 |  | NG | Queens | NY | J | Astoria 138kV | CONED | 0 | 2023-05-31
0032 | American National Power | Brookhaven Energy | 1999-11-22 | 580 |  | CC | Suffolk | NY |  | Holbrook-Brookhaven 138kV | LIPA | 0
0033 | Glenville Energy Park, LLC | Glenville Energy Park | 1999-11-30 | 540 |  | CC | Schenectady | NY | F | Rotterdam 230kV | NM-NG | 0 | 2008-07-10
0034 | York Research Corp. | North First Street | 2000-01-11 | 500 | [5 empty] | Con Ed System | CONED | 0
0035 | Gotham Power Zerega, LLC | Gotham Power - Bronx I | 2000-01-12 | 79.9 |  | CT | Bronx | NY | J | Parkchester/Tremont 138kV | CONED | 0 | 2008-07-10
0036 | Boundless Energy, LLC | Project Neptune DC NB-NYC | 2000-01-21 | 1200 |  | DC | Kings | NY | J | Farragut 345kV | CONED | 0 | 2008-07-10
0037 | Caithness Energy, LLC | Kitchen | 2000-01-28 | 750 | [5 empty] | Riverh'd-Brookh'n-Holb'k | LIPA | 0
0038 | KeySpan Energy, Inc. | Far Rochaway Gen Ext. | 2000-02-01 | 79 | [5 empty] | Far Rockaway | LIPA | 0
0039 | KeySpan Energy, Inc. | E. F. Barrett Gen Ext | 2000-02-01 | 79 | [5 empty] | Barrett | LIPA | 0
0040 | KeySpan Energy, Inc. | Riverhead Gen Station | 2000-02-01 | 79 | [5 empty] | Riverhead | LIPA | 0
0041 | KeySpan Energy, Inc. | Southampton Gen Ext. | 2000-02-01 | 79 | [5 empty] | Southampton | LIPA | 0
0042 | PP&L Global, Inc. | Holbrook Energy | 2000-02-01 | 300 | [5 empty] | Holbrook | LIPA | 0
0043 | PP&L Global, Inc. | PPL Kings Park | 2000-02-01 | 300 | [5 empty] | Pilgrim | LIPA | 0
0044 | PP&L Global, Inc. | Ruland Energy | 2000-02-01 | 300 | [5 empty] | Ruland Road | LIPA | 0
0045 | PP&L Global, Inc. | Freeport Energy | 2000-02-01 | 100 | [5 empty] | Freeport | LIPA | 0
0046 | PP&L Global, Inc. | Brookhaven Energy | 2000-02-03 | 300 | [5 empty] | Brookhaven | LIPA | 0
0047 | GenPower, LLC | GenPower DC Tie-line | 2000-02-09 | 800 | [5 empty] | West 49th Sreet | CONED | 0
0048 | PP&L Global, Inc. | PPL Kings Park Ext. | 2000-02-10 | 300 | [5 empty] | Pilgrim | LIPA | 0
0049 | PP&L Global, Inc. | Brookhaven Energy Ext. | 2000-02-10 | 300 | [5 empty] | Brookhaven | LIPA | 0
0050 | AES Long Island, LLC | AES Smithtown Gen | 2000-02-10 | 510 | [5 empty] | LIPA System | LIPA | 0
0051 | KeySpan Energy, Inc. | Wading River Gen Ext. | 2000-02-15 | 150 | [5 empty] | Wading River | LIPA | 0
0052 | NIMO/Black River Power | Fort Drum Gen Exp. | 2000-03-06 | 50 | [5 empty] | Fort Drum | NM-NG | 0
0053 | TransEnergie US, Ltd | CT-Ruland, LI DC Tie | 2000-03-07 | 300 | [5 empty] | Ruland Road | LIPA | 0
0054 | TransEnergie US, Ltd | CT-Pilgrim, LI DC Tie | 2000-03-07 | 300 | [5 empty] | Pilgrim | LIPA | 0
0056 | 1st Rochdale Coop Group | Gotham Power/Brooklyn | 2000-03-17 | 79 | [5 empty] | Kent Ave | CONED | 0
0057 | Flat Rock Windpower, LLC | Flat Rock Windpower | 2000-03-21 | 100 |  | W |  |  |  | Lowville-Boonville | NM-NG | 0
0058 | Mirant | Lovett #3 Repowering | 2000-03-23 | 180 | [5 empty] | Lovett | CONED | 0
0059 | Mirant | Hillburn Unit #2 | 2000-03-23 | 79.9 | [5 empty] | Hillburn | CONED | 0
0060 | Mirant | Hillburn #2 Conversion | 2000-03-23 | 40 | [5 empty] | Hillburn | CONED | 0
0061 | GTM Energy, LLC | Greenpoint Energy Park | 2000-04-19 | 500 | [5 empty] | Rainey-Farragut Lines | CONED | 0
0062 | Project Orange Associates, LP | Project Orange | 2000-05-08 | 420 | [5 empty] | Temple St. | NM-NG | 0
0063 | Lewis Staley Associates, Inc. | LSA Station A | 2000-05-11 | 650 | [5 empty] | Homer City-Stolle Rd Line | NYSEG | 0
0064 | Lewis Staley Associates, Inc. | LSA Station B | 2000-05-12 | 600 | [5 empty] | Dunkirk-Gardenville Line | NM-NG | 0
0065 | Fortistar-Lockport Merchant | Lockport II Gen Station | 2000-05-15 | 79.9 |  | CT | Niagara | NY | A | Harrison Station 115kV | NYSEG | 0 | 2008-07-10
0067 | Titan Development, LLC | Wallkill Energy | 2000-06-21 | 1080 | [5 empty] | Coop Corn-Rock Tav Lines | NYPA | 0
0068 | PP&L Global, Inc. | Ruland Energy Ext. | 2000-06-23 | 300 | [5 empty] | Ruland Road | LIPA | 0
0070 | Reliant Energy | Astoria Repowering-Phase 2 | 2000-08-18 | 173 |  | CT | Queens | NY |  | Astoria 138kV | CONED | 0 | 2006-08-09
0071 | Mill Creek Wind Plant, LLC | Mill Creek Wind Plant | 2000-09-08 | 50 | [5 empty] | Lowville | NM-NG | 0
0072 | Fortistar Power Marketing, LLC | Island Gen. Station | 2000-09-08 | 79.9 | [5 empty] | Fresh Kills | CONED | 0
0073 | Fortistar Power Marketing, LLC | Island Gen. Station #2 | 2000-09-08 | 500 | [5 empty] | Fresh Kills | CONED | 0
0074 | FPL Energy, LLC | Oceanside Energy Center | 2000-10-10 | 330 | [5 empty] | Barrett | LIPA | 0
0075 | 1st Rochdale Coop Group | Gotham Power - Bronx II | 2000-10-17 | 79 | [5 empty] | Hell Gate/Bruckner | CONED | 0
0076 | Calpine Eastern Corporation | Waterford | 2000-10-30 | 530 |  | CT | Saratoga | NY |  | NM-NG 230 or 115 kV | NM-NG | 0 | 2019-03-06
0077 | Titan Development, LLC | Dover Energy | 2000-11-17 | 1000 | [5 empty] | Pl. Valley-Long Mt. Tie-Line | CONED | 0
0078 | KeySpan Ravenswood | Ravenswood Repower Ph I | 2000-12-04 | 440 | [5 empty] | Vernon | CONED | 0
0086 | NRG/ Berrians I GT Power, LLC | Berrians GT Replacement | 2001-01-15 | 79.9 | [5 empty] | Astoria | CONED | 0
0087 | Titan Development, LLC | Buchanan Energy | 2001-02-26 | 500 | [5 empty] | Buchanan | CONED | 0
0088 | Titan Development, LLC | Halfmoon Energy | 2001-02-26 | 500 | [5 empty] | Rotterdam-Bear Swamp line | NM-NG | 0
0089A | Atlantic Energy, LLC | Neptune DC PJM-NYC | 2001-03-15 | 600 | [5 empty] | W49th St | CONED | 0
0089B | Atlantic Energy, LLC | Neptune DC PJM-NYC | 2001-03-15 | 600 | [5 empty] | W49th St | CONED | 0
0090 | Fortistar, LLC | Fortistar VP | 2001-03-20 | 79.9 |  | CT | Richmond | NY | J | Fresh Kills 138kV | CONED | 0 | 2009-05-27
0091 | Fortistar, LLC | Fortistar VAN | 2001-03-20 | 79.9 |  | CT | Richmond | NY | J | Goethals/Fresh Kills 138kV | CONED | 0 | 2009-05-27
0092 | Amerada Hess Corp. | Redhook Energy | 2001-05-01 | 79.9 | [5 empty] | ConEd 138 kV (tbd) | CONED | 0
0093 | In-City I, LLC | Cross Hudson Project | 2001-05-11 | 550 |  | CC | NY | NY |  | W49th Street 345kV | CONED | 0 | 2007-08-23
0096 | Calpine Eastern Corporation | CPN 3rd Turbine, Inc. (JFK) | 2001-05-29 | 45 |  | CT | Queens | NY | J | Jamaica 138kV | CONED | 0 | 2008-07-10
0097 | NYSEG Solutions | South Glens Falls Expansion | 2001-06-15 | 40 | [5 empty] | Mohican-Butler#18 line | NM-NG | 0
0098 | TransEnergie US Ltd. | PJM-NY City HVDC | 2001-06-22 | 990 | [5 empty] | W49th St and/or Farragut | CONED | 0
0100 | Titan Development, LLC | Blooming Grove Power | 2001-07-02 | 500 | [5 empty] | Rock Tavern-Ramapo line | CONED | 0
0101 | Northeast Utilities Service Co. | NU CT-LI HVDC Cable | 2001-07-13 | 660 | [5 empty] | Shore Road | LIPA | 0
0102 | Entergy Power Gen. Corp. | Indian Point Energy Center | 2001-07-23 | 400 |  | CT | Westchester | NY |  | Buchanan 345kV | CONED | 0
0103 | Pegasus Trans. Co., Ltd. | Niagara Reinforcement Inter. | 2001-08-15 | 1200 |  | DC | Oneida-NY | NY |  | Marcy,Edic,Porter - W49th St. | NYPA/NM/CE | 0
0104 | PG&E/Liberty Gen. Co., LLC | Jupiter PJM-NYC Cable | 2001-08-24 | 1200 | [5 empty] | W49th St or Farragut | CONED | 0
0105 | Calpine Eastern Corporation | Titan Smith Street | 2001-10-05 | 79.9 |  | CT | Kings | NY |  | Gowanus 138 or 345 kV | CONED | 0 | 2019-03-06
0106 | TransGas Energy, LLC | TransGas Energy | 2001-10-05 | 1100 |  | CC | Kings | NY | J | E13St, Rainey, or Farragut-345kV | CONED | 0 | 2012-03-01
0108 | Sempra Generation | SE Long Island | 2001-11-29 | 575 |  | CT | Suffolk | NY |  | Shoreham-Holbrook lines 138kV | LIPA | 0
0109 | Calpine Eastern Corporation | Maspeth | 2002-01-25 | 79.9 | [5 empty] | Vernon-Glendale line | CONED | 0
0110 | PG&E/Liberty Gen. Co., LLC | Liberty Generation | 2002-02-04 | 400 |  | CT | Richmond-NJ | NY |  | Goethals 345kV | CONED | 0 | 2019-03-06
0111 | River Hill Power Co., LLC | River Hill Project | 2002-02-05 | 290 |  | CT | Chemung-PA | NY | C | Homer City-Watercure 345kV | NYSEG | 0 | 2008-07-10
0112 | TransEnergie US Ltd. | PJM-Rainey HVDC | 2002-04-09 | 660 |  | DC | Queens-NJ | NY |  | Rainey 345kV | CONED | 0 | 2006-05-31
0113 | Windfarm Prattsburgh, LLC | Prattsburgh Wind Park | 2002-04-22 | 55.5 |  | W | Yates | NY | C | Eelpot Rd-Flat St. 115kV | NYSEG | 0 | 2010-03-31
0114 | Global Winds Harvest, Inc. | Cherry Valley Wind Park | 2002-04-22 | 40.5 | [5 empty] | East Springfield | NYSEG | 0
0116 | PG&E/Liberty Gen. Co., LLC | Liberty Gen Co, LLC | 2002-04-29 | 600 | [5 empty] | Goethals | CONED | 0
0117 | Chautauqua Windpower, LLC | Chautauqua Windpower | 2002-05-14 | 50 |  | W | Chautauqua | NY |  | Dunkirk-S. Ripley 230kV | NM-NG | 0 | 2007-03-27
0118 | Global Winds Harvest, Inc. | Prattsburgh Wind Park II | 2002-05-15 | 75 | [5 empty] | Eelpot Rd-Flat St. line | NYSEG | 0
0119 | ECOGEN, LLC | Prattsburgh Wind Farm | 2002-05-20 | 78.2 |  | W | Yates | NY | C | Eelpot Rd-Flat St. 115kV | NYSEG | 0 | 2013-10-31
0120 | ECOGEN, LLC | Springwater Wind Farm | 2002-05-20 | 79.5 | [5 empty] | Eelpot Rd | NYSEG | 0
0124 | Bay Energy, LLC | Bay Energy Project | 2002-07-01 | 79.9 |  | CT | Kings | NY |  | Gowanus 138kV | CONED | 0
0126 | TransEnergie US Ltd. | PJM-Newbridge Rd HVDC | 2002-09-10 | 350 |  | DC |  |  |  | Newbridge Road 138kV | LIPA | 0 | 2006-05-31
0127 | KeySpan Energy for LIPA | Northport-Norwalk Upgrade | 2002-09-19 | 150 | [5 empty] | Northport | LIPA | 0
0127A | Airtricity Munnsville Wind Farm, LLC | Munnsville - Phase 2 | 2002-10-09 | 5.5 |  | W | Madison | NY | E | 46kV line | NYSEG | 0 | 2023-05-31
0128 | Flat Rock Wind Power, LLC | Flat Rock Wind Power 230 kV | 2002-11-20 | 240 |  | W |  |  |  | Adirondack-Porter line | NM-NG | 0
0129 | Conjunction, LLC | Empire Connection | 2002-12-10 | 2000 |  | DC |  |  |  | New Scotland / ConEd | NM-NG/CONED | 0
0130 | Electrotek Concepts, Inc. | Grace Corona Generation | 2003-01-14 | 79.9 | [5 empty] | Corona | CONED | 0
0131 | Green Power Energy, LLC | Cody Road Wind Farm | 2003-03-05 | 10.5 |  | W |  |  |  | Oneida-Cortland line | NM-NG | 0
0132 | Airtricity Developments, LLC | Munnsville Windpower | 2003-05-11 | 40 |  | W |  |  |  | NYSEG Ckt 806 | NYSEG | 0
0134 | TransEnergie US Ltd. | PJM-Barrett HVDC | 2003-05-21 | 650 | [5 empty] | Barrett 138 kV | LIPA | 0
0137 | Conjunction, LLC | Empire Connection DC | 2003-06-16 | 2000 | [5 empty] | N. Scotland/Leeds, ConEd | NM/CONED | 0
0140 | National Grid | Leeds-PV Reconductoring | 2003-08-26 | N/A |  | AC | Greene-Dutchess | NY | G | Leeds/Athens-Pl. Valley 345kV | NM-NG | 0 | 2008-07-10
0141A | Atlantic Renewable Energy Corp. | Bishop | 2003-09-09 | 23.1 |  | W | Livingston | NY |  | Springwater 34.5kV line | NYSEG | 0
0142 | EC&R Northeast, LLC | Steuben Wind | 2003-10-30 | 50 |  | W | Steuben | NY | C | Bennett-Palmiter 115kV line | NYSEG | 0 | 2010-06-04
0147 | NY Windpower, LLC | West Hill Windfarm | 2004-04-16 | 31.5 |  | W | Madison | NY | C | Oneida-Fenner 115kV | NM-NG | 0 | 2012-08-31
0148 | Trigen Nassau Gen Co., LLC | Trigen-Nassau | 2004-05-18 | 79.9 | [5 empty] | Uniondale Substation | LIPA | 0
0150 | Reunion Power, LLC | Cherry Valley Wind Power | 2004-06-17 | 70 |  | W | Ostego | NY | E | Marshville - Sharon 69kV | NM-NG | 0 | 2010-03-31
0151 | Con Edison | West Side Switching Station | 2004-06-30 | N/A |  | AC | NY | NY | J | West 49th St & Farragut 345kV | CONED | 0 | 2011-03-31
0152 | Moresville Energy LLC | Moresville Energy Center | 2004-07-23 | 99 | 99 | W | Delaware | NY | E | Axtell Road-Grand Gorge 115kV | NYSEG | 0 | 2011-06-30
0154 | KeySpan Energy for LIPA | Holtsville-Brentwood-Pilgrim | 2004-08-19 | N/A | N/A | AC | Suffolk | NY | K | Holtsville & Pilgrim 138kV | LIPA | 0 | 2017-02-28
0155 | Invenergy NY, LLC | Canisteo Hills Windfarm | 2004-09-17 | 148.5 |  | W | Steuben | NY | C | Bennett-Bath 115kV | NYSEG | 0 | 2012-03-01
0157 | BP Alternative Energy NA, Inc. | Orion Energy NY I | 2004-10-12 | 100 | 100 | W | Herkimer | NY | E | Watkins Rd.-Inghams 115kV | NM-NG | 0 | 2012-03-01
0158 | Orion Energy, LLC | Orion Energy NY II | 2004-10-12 | 100 | 100 | W | Montgomery | NY |  | Inghams-Meco 115kV | NM-NG | 0 | 2019-01-06
0159 | Orion Energy, LLC | Orion Energy NY III | 2004-10-12 | 150 |  |  | Clinton | NY |  | TBD | NYSEG | 0
0160 | Jericho Rise Wind Farm, LLC | Jericho Rise Wind Farm | 2004-10-12 | 79.2 | 79.2 | W | Franklin | NY | D | Willis 115 kV | NYPA | 0 | 2011-04-30
0162 | AES Somerset, LLC | Niagara Windpower | 2004-12-15 | 70 |  | W | Niagara | NY |  | Somerset Switch Yard | NYSEG | 0 | 2019-08-05
0163 | Clipper Windpower Dev. Co. Inc. | Paragon I Wind Generation | 2005-01-13 | 100 | 100 | W | Steuben | NY | C | Bath-Montour Falls 115kV | NYSEG | 0 | 2008-08-19
0164 | FPL Energy | Long Island Offshore Wind | 2005-01-28 | 140 | 140 | W | Suffolk | NY |  | Sterling Substation | LIPA | 0 | 2008-02-26
0165 | UPC Wind Management, LLC | Genesee Wind Farm | 2005-01-31 | 500 | 500 | W | Genesee | NY |  | Batavia Substation 115kV | NM-NG | 0 | 2019-11-05
0166 | Cape Vincent Wind Power, LLC | St. Lawrence Wind Farm | 2005-02-08 | 75.9 | 75.9 | W | Jefferson | NY | E | Rockledge Substation 115kV | NM-NG | 0 | 2014-02-28
0167 | AES NY Wind, LLC | St. Lawrence Wind Farm II | 2005-02-08 | 80 |  | W | Jefferson | NY |  | Lyme Substation | NM-NG | 0 | 2019-06-05
0168 | Dairy Hills Wind Farm, LLC | Dairy Hills Wind Farm | 2005-02-08 | 120 | 120 | W | Wyoming | NY | C | Stolle Rd.-Meyer 230kV | NYSEG | 0 | 2012-03-01
0169 | Alabama Ledge Wind Farm, LLC | Alabama Ledge Wind Farm | 2005-02-08 | 79.8 | 79.8 | W | Genesee | NY | B | Oakfield-Lockport 115kV | NM-NG | 0 | 2012-06-01
0170 | Machias Wind Farm, LLC | Machias Wind Farm | 2005-02-08 | 90 | 90 | W | Cattaraugus | NY |  | Homer Hill-Gardenville 115kV | NM-NG | 0 | 2006-10-11
0176 | Noble Environmental Power, LLC | Wethersfield Windfield 115kV | 2005-02-14 | 129 | 129 | W | Wyoming | NY |  | Arcade Substation 115kV | Village of Arcade | 0 | 2006-07-18
0178 | Noble Allegany Windpark, LLC | Allegany Windpark | 2005-02-14 | 100.5 | 100.5 | W | Cattaraugus | NY | A | Freedom Substation 115kV | Village of Arcade | 0 | 2010-06-28
0179 | Noble Environmental Power, LLC | Cherry Hill Windpark | 2005-02-14 | 102 | 102 | W | Franklin | NY | E | Nicholville-Malone 115kV | NYSEG | 0 | 2009-02-05
0180 | Invenergy Wind, LLC | Buffalo Rd. Wind Farm | 2005-02-23 | 165 | 165 | W | Wyoming | NY |  | Stolle Rd.-Meyer 230kV | NYSEG | 0 | 2007-01-09
0180A | Green Power | Cody Rd | 2005-03-17 | 10 | 10 | W | Madison | NY | C | Fenner - Cortland 115kV | NM-NG | 0 | 2017-02-28
0181 | Everpower Global | Cold Spring Wind | 2005-03-21 | 69.3 |  | W | Cattaraugus | NY |  | Falconer-Homer Hill 115kV | NM-NG | 0 | 2019-09-05
0183 | Invenergy Wind, LLC | Buffalo Rd. Wind Farm II | 2005-03-28 | 165 | 165 | W | Wyoming | NY |  | Batavia 115kV | NYSEG/NM-NG | 0 | 2019-12-05
0184 | Invenergy Wind, LLC | Ripley Hill | 2005-03-28 | 75.9 |  | W | Onondaga | NY |  | Town of Spafford | NYSEG/NM-NG | 0 | 2019-08-05
0186 | Jordanville Wind, LLC | Jordanville Wind | 2005-04-01 | 80 | 80 | W | Herkimer | NY | E | Porter-Rotterdam 230kV | NM-NG | 0 | 2011-09-30
0187 | North Slope Wind Farm, LLC | North Slope Wind | 2005-04-05 | 109.5 | 109.5 | W | Clinton | NY | D | Willis-Plattsburgh 230kV | NYPA | 0 | 2009-02-05
0188 | NY Windpower, LLC | Orangeville Wind | 2005-04-05 | 96 |  | W | Wyoming | NY |  | 115kV | NYSEG | 0 | 2019-08-05
0189 | Atlantic Wind, LLC | Horse Creek Wind | 2005-04-08 | 126 | 126 | W | Jefferson | NY | E | Coffeen St-Thousand Island 115kV | NM-NG | 0 | 2014-04-30
0190 | PPM Energy, Inc. | Mixer Road Wind | 2005-04-08 | 66 | 66 | W | Jefferson | NY |  | West Adams 115kV | NM-NG | 0 | 2006-10-11
0191 | NY Regional | NY Regional | 2005-05-13 | 1200 | 1200 | DC | Oneida-Orange | NY | E, G | Edic - Rock Tavern | NM-NG/CH | 0 | 2009-04-08
0192 | Orion Energy, LLC | Orion Livingston | 2005-05-17 | 75 | 75 | W | Livingston | NY |  | Stolle Rd.-Meyer 230kV | NYSEG | 0 | 2019-01-06
0193 | Orion Energy, LLC | Orion Wyoming | 2005-05-17 | 60 | 60 | W | Wyoming | NY |  | South Perry 115kV | NYSEG | 0 | 2007-01-09
0194 | Calpine Energy Services | Bayonne | 2005-05-26 | 300 | 300 | ST | NY | NY |  | World Trade Center 138kV | CONED | 0 | 2019-02-06
0195 | Brookfield Power US | Harbor Cable Project II | 2005-06-14 | 200 | 200 | DC | Richmond | NY | J | Goethal 345kV | CONED | 0 | 2009-07-31
0196 | Roaring Brook Windpower, LLC | Roaring Brook | 2005-07-01 | 79.9 | 79.8 | W | Lewis | NY |  | Adirondak-Porter 230kV | NM-NG | 0 | 2006-07-10
0197 | PPM Roaring Brook, LLC / PPM | Roaring Brook Wind | 2005-07-01 | 78 | 78 | W | Lewis | NY | E | Boonville-Lowville 115kV | NM-NG | 0 | 2016-04-30
0198 | Arkwright Summit Wind Farm, LLC | Arkwright Summit Wind Farm | 2005-07-21 | 79.8 | 79.8 | W | Chautauqua | NY | A | Dunkirk-Falconer 115kV | NM-NG | 0 | 2013-09-30
0200 | Cavallo Power | Linden Power I | 2005-08-16 | 845 | 915 | CC | NY-NJ | NY |  | Goethal Substation | CONED | 0 | 2019-02-06
0201 | NRG Energy | Berrians GT | 2005-08-17 | 200 | 200 | CC | Queens | NY | J | Astoria West Substation 138kV | CONED | 0 | 2015-07-31
0202 | Liberty Generating Co. | 130 MW Uprate | 2005-08-25 | 130 | 130 | CT | NY-NJ | NY |  | Goethal 345kV | CONED | 0 | 2019-03-06
0203 | GenWy Wind, LLC | GenWy Wind Farm | 2005-10-21 | 478.5 | 478.5 | W | Genesee | NY | A | Stolle Rd - Homer City 345kV | NYSEG | 0 | 2010-03-31
0204 | Clipper Windpower Dev. Co. Inc. | Paragon II Wind Generation | 2005-10-27 | 150 | 150 | W | Steuben | NY | C | Avoca - Hillside 230kV | NYSEG | 0 | 2008-08-19
0204A | Duer's Patent Project, LLC | Beekmantown Windfarm | 2005-10-31 | 19.5 | 19.5 | W | Clinton | NY | D | Kents Falls - Sciota 115kV | NYSEG | 0 | 2013-03-31
0207 | Cape Vincent Wind Power, LLC | Cape Vincent | 2006-01-12 | 209.3 | 209.3 | W | Jefferson | NY | E | Rockledge Substation 115kV | NM-NG | 0 | 2014-02-28
0208 | CRC Development, LLC | Roundhouse Renewable | 2006-01-17 | 35 | 36 | ST | Otsego | NY |  | City of Oneonta | NYSEG | 0 | 2006-09-25
0209 | SUEZ Energy Generating NA, Inc | Nassau Generating | 2006-02-10 | 88 | 100 | CT | Nassau | NY |  | Garden City Substation 138kV | LIPA | 0 | 2007-07-10
0210 | Canadian Niagara Power, Inc. | Fortran | 2006-03-14 | 150 | 150 | AC | Niagara | NY | A | Huntley Station 115kV | NM-NG | 0 | 2010-03-31
0213 | Noble Environmental Power, LLC | Ellenburg II Windfield | 2006-04-03 | 21 | 21 | W | Clinton | NY | D | Willis-Plattsburgh WP-2 230kV | NYPA | 0 | 2013-04-30
0215 | Noble Burke Windpark, LLC | Noble Burke Windpark | 2006-04-03 | 120 | 120 | W | Franklin-Clinton | NY | D | Willis Substation 230kV | NYPA | 0 | 2009-02-05
0217 | AES Keystone Wind, LLC | Cherry Flats | 2006-06-06 | 90 | 90 | W | Tioga | PA | C | Homer City-Watercure 345kV | NYSEG | 0 | 2008-12-22
0218 | Gamesa Energy USA | Endless Mountain Wind | 2006-07-03 | 150 | 150 | W | Tioga - Bradford | PA |  | Homer City-Watercure 345kV | NYSEG | 0 | 2006-07-27
0219 | NRG Energy, Inc. | Huntley | 2006-07-12 | 752 | 752 | CC | Niagara | NY | A | Tonawanda | NM-NG | 0 | 2008-12-22
0220 | AES Keystone Wind, LLC | Armenia Mountain I | 2006-07-19 | 175 | 175 | W | Bradford | PA | C | Homer City-Watercure 345kV | NYSEG | 0 | 2008-08-19
0221 | AES Keystone Wind, LLC | Armenia Mountain II | 2006-07-19 | 75 | 75 | W | Bradford | PA | C | Homer City-Watercure 345kV | NYSEG | 0 | 2009-04-08
0222 | Ball Hill Windpark, LLC | Ball Hill Windpark | 2006-07-21 | 90 | 90 | W | Chautauqua | NY | A | Dunkirk-Gardenville 230kV | NM-NG | 0 | 2013-11-30
0223 | Noble Environmental Power, LLC | Arkwright Windpark | 2006-07-21 | 99 | 99 | W | Chautauqua | NY |  | Dunkirk-Falconer 115kV | NM-NG | 0 | 2007-03-12
0224 | NRG Energy, Inc. | Berrians GT II | 2006-08-23 | 50 | 90 | CC | Queens | NY | J | Astoria West Substation 138kV | CONED | 0 | 2015-07-31
0224B | Casella Waste Systems | Chemung Landfill | 2006-09-05 | 6.4 | 6.4 | M | Chemung | NY | C | 115kV | NYSEG | 0 | 2008-04-15
0225A | Schenectady International, Inc. | SII Rotterdam Junction | 2006-09-08 | 9.3 | 9.3 | Wo | Rotterdam | NY | F | 69kV | NM-NG | 0 | 2010-08-31
0225B | Burrstone Energy | Faxton/ St. Luke | 2006-09-15 | 2.2 | 2.2 | NG | Herkimer | NY | E | TBD | NM-NG | 0 | 2008-07-10
0226 | Cavallo Power | Linden | 2006-09-08 | 1200 | 1200 | CC | NY-NJ | NY |  | East 13th, West 49th | CONED | 0 | 2006-11-14
0227 | EC&R Northeast, LLC | Orleans Wind | 2006-09-28 | 120 | 120 | W | Orleans | NY | A | Shelby Substation - 115kV | NM-NG | 0 | 2008-10-14
0227A | Laidlaw Energy Group Inc. | Laidlaw Energy & Env. | 2006-10-30 | 7 | 7 | Wo | Cattaraugus | NY | A | 13.2kV | NM-NG | 0 | 2013-05-31
0228 | AES Bainbridge, LLC | Jennison | 2006-10-30 | 516 | 536 | C | Chenango | NY |  | TBD | NYSEG | 0 | 2007-04-24
0229 | AES Somerset 2, LLC | Somerset | 2006-11-01 | 687 | 706 | C | Niagara | NY |  | Somerset Substation 345kV | NYSEG | 0 | 2007-03-27
0230 | Cornell University | Cornell CHPP | 2006-11-02 | 30 | 30 | NG |  |  |  | Maple Ave. Substation 115kV |  | 0 | 2006-11-21
0231 | Seneca Energy II, LLC | Seneca | 2006-11-02 | 6.4 | 6.4 | M | Seneca | NY | C | Goulds Substation 34.5kV | NYSEG | 0 | 2012-04-30
0235 | Gamesa Energy USA, LLC | Canfield Wind | 2006-12-12 | 120 | 120 | W | Tioga - Bradford | PA |  | Homer City-Watercure 345kV | NYSEG | 0 | 2007-10-16
0236 | Gamesa Energy USA, LLC | Dean Wind | 2006-12-14 | 150 | 150 | W | Tioga - Schuyler | NY | C | Watercure-Oakdale 345kV | NYSEG | 0 | 2011-04-30
0237 | Allegany Wind, LLC | Allegany Wind | 2007-01-09 | 72.5 | 72.5 | W | Cattaraugus | NY | A | Homer Hill Ð Dugan Rd. 115kV | NM-NG | 0 | 2015-02-28
0238 | Tonawanda Creek Wind, LLC | Tonawanda Creek Wind | 2007-01-30 | 75 | 75 | W | Genesee | NY | A | Lockport Ð Batavia 115kV | NM-NG | 0 | 2009-07-31
0239 | Western Door Wind, LLC | Western Door Wind | 2007-01-30 | 100 | 100 | W | Yates | NY | C | Greenidge Ð Haley Rd. 115kV | NYSEG | 0 | 2012-01-30
0239A | Innovative Energy System, Inc. | Modern Innovative Plant | 2007-01-31 | 6.4 | 6.4 | M | Niagara | NY | A | Youngstown Ð Sanborn 34.5kV | NM-NG | 0 | 2013-04-30
0240 | Noble Environmental Power, LLC | Farmersville Windpark | 2007-02-26 | 100 | 100 | W | Cattaraugus-PA | NY | A | Stolle Rd - Farmer's Valley 345kV | NM-NG | 0 | 2009-07-31
0241 | Noble Chateaugay Windpark II, LLC | Chateaugay II Windpark | 2007-03-15 | 19.5 | 19.5 | W | Franklin | NY | D | Chateaugay Substation 34.5kV | NYSEG | 0 | 2012-08-31
0242 | RG&E | Brown's Race Uprate | 2007-04-09 | 6 | 6 | H | Monroe | NY |  | Brown's Race Substation | NYSEG | 0 | 2007-06-05
0243 | Astoria Energy, LLC | Astoria Uprate | 2007-04-12 | 100 | 230 | CC | Queens | NY | J | Astoria East Substation 138kV | ConEd | 0 | 2010-03-31
0244 | AES Bainbridge, LLC | Jennison | 2007-04-13 | 650 | 650 | C | Chenango | NY |  | Oakdale Ð Fraser 345kV | NYSEG | 0 | 2008-03-20
0246 | PPM Energy, Inc | Dutch Gap Wind | 2007-06-01 | 250 | 250 | W | Jefferson | NY | E | Indian River - Black Rive 115kV | NM-NG | 0 | 2012-03-01
0247 | RG&E | Russell Station | 2007-06-11 | 300 | 325 | CC | Monroe | NY | B | Russell Station 115kV | RG&E | 0 | 2012-04-30
0248 | RG&E | Russell Station II | 2007-06-11 | 300 | 300 | C | Monroe | NY |  | Russell Station 115kV | NYSEG | 0 | 2007-10-02
0249 | Hess Corporation | Bayone Energy Center II | 2007-06-20 | 250 | 250 | D | Bayonne | NJ |  | Gowanus Substation 138kV | ConEd | 0 | 2007-10-02
0252 | Brookfield Power | Manhattan Cable | 2007-08-01 | 350 | 350 | DC | NY | NY | J | World Trade Center 138 kV | ConEd | 0 | 2008-07-10
0253 | Marble River, LLC | Marble River SPS | 2007-08-13 | TBD | TBD | AC | Clinton | NY | D | Moses-Willis-Plattsburgh 230kV | NYPA | 0 | 2012-06-30
0254 | Ripley-Westfield Wind LLC | Ripley-Westfield Wind | 2007-08-14 | 124.2 | 124.2 | W | Cahatauqua | NY | A | Ripley - Dunkirk 230kV | NM-NG | 0 | 2012-03-01
0255 | In-City, LLC | Cross Hudson | 2007-08-23 | 550 | 550 | CC | NY-NJ | NY | J | W49th Street 345kV | ConEd | 0 | 2008-07-01
0256 | Niagara Shore Winds, LLC | Niagara Shore Wind | 2007-09-04 | 70.5 | 70.5 | W | Niagara | NY | A | Somerset Switch Yard 345kV | NYSEG | 0 | 2010-03-31
0257 | RG&E | Brown's Race Uprate | 2007-09-12 | 2 | 2 | H | Monroe | NY | B | Beebee Station 34kV | RG&E | 0 | 2011-03-31
0258 | Babcock & Brown, LP | Ripley-Westfield Wind II | 2007-09-24 | 124.8 | 124.8 | W | Chautauqua | NY |  | Ripley - Dunkirk 230kV | NM-NG | 0 | 2007-10-16
0259 | Delaware County Electric | Delaware County Landfill | 2007-09-24 | 1 | 1 | M | Delaware | NY |  | TBD | NYSEG | 0 | 2008-01-29
0261 | Astoria Generating Company | South Pier Improvement | 2007-10-02 | 105 | 108 | CT | Kings | NY | J | Gowanus 138kV | ConEd | 0 | 2012-03-01
0262 | RP Wind NY, LLC | Schoharie Highlands | 2007-10-05 | 70 | 70 | W | Schoharie | NY | F | 69kV | NM-NG | 0 | 2009-05-12
0264 | RG&E | Seth Green | 2007-10-23 | 2.8 | 2.8 | H | Monroe | NY | B | 11kV | RG&E | 0 | 2014-03-31
0265 | CityGreen Transmission | CityGreen | 2007-11-16 | 1100 | 1100 | DC | Westchester-Queens | NY | H, J | Millwood - Farragut/Rainey 345kV | ConEd | 0 | 2010-03-31
0266 | NRG Energy, Inc. | Berrians GT III | 2007-11-28 | 250 | 290 | CC | Queens | NY | J | Astoria Annex 345kV | NYPA | 0 | 2015-06-30
0267 | Winergy Power, LLC | Winergy NYC Wind Farm | 2007-11-30 | 600 | 600 | W | NY | NY | J | Gowanus Substation 345kV | ConEd | 0 | 2012-07-31
0268 | NRG Energy, Inc. | Arthur Kill | 2007-12-07 | 800 | 800 | CC | NY | NY | J | Gowanus Substation | ConEd | 0 | 2008-07-10
0269 | WM Renewable Energy, LLC | Madison County Landfill | 2007-12-10 | 2 | 2 | M | Madison | NY |  | Canastota | NM-NG | 0 | 2008-01-29
0270 | Wind Development Contract Co LLC | Hounsfield Wind | 2007-12-13 | 244.8 | 244.8 | W | Jefferson | NY | E | Fitzpatrick - Edic 345kV | NYPA | 0 | 2016-07-31
0271 | State Line Wind Power LLC | State Line Wind | 2007-12-20 | 124.8 | 124.8 | W | Chautauqua | NY | A | South Ripley - Dunkirk 230kV | NM-NG | 0 | 2011-10-31
0272 | NYPA | Benchmark Generator | 2007-12-20 | 900 | 1080 | CT | Queens | NY | J | Astoria 345kV | NYPA | 0 | 2009-04-08
0273 | Winergy Power, LLC | Winergy Long Island Wind | 2007-12-21 | 299 | 299 | W | Suffolk | NY | K | Sterling Substation | LIPA | 0 | 2008-07-10
0274 | In City I, LLC | PSEG Fossil Bergen Unit 2 | 2008-01-23 | 100 | 100 | CC | NY-NJ | NY | J | W49th Street 345kV | ConEd | 0 | 2008-07-10
0275 | Shell Wind Energy Inc. | Cayuga County Wind | 2008-01-24 | 120 | 120 | W | Cayuga | NY | C | Milliken - Wright Ave. 115kV | NYSEG | 0 | 2009-04-08
0277 | UniStar Nuclear Energy | Nine Mile Point Station Unit #3 | 2008-02-04 | 1640 | 1660 | NU | Oswego | NY | C | Scriba Substation 345kV | NM-NG | 0 | 2009-12-22
0278 | Riverbank Power Corporation | Riverbank Power A | 2008-02-20 | 1000 | 1000 | PS | Niagara | NY | A | Niagara - Rochester 345kV | NYPA | 0 | 2009-06-24
0279 | Riverbank Power Corporation | Riverbank Power D1 | 2008-02-20 | 1000 | 1000 | PS | St. Lawrence | NY | E | Massena 765kV | NYPA | 0 | 2010-03-31
0280 | Riverbank Power Corporation | Riverbank Power D2 | 2008-02-20 | 1000 | 1000 | H | St. Lawrence | NY | E | Massena 765kV | NYPA | 0 | 2008-10-14
0281 | Riverbank Power Corporation | Riverbank Power G | 2008-02-20 | 1000 | 1000 | PS | Rockland | NY | G | West Haverstraw 345kV | ConEd/O&R | 0 | 2010-11-30
0282 | Concord Wind Power LLC | Concord Wind | 2008-02-28 | 101.2 | 101.2 | W | Chautauqua | NY | A | Dunkirk - South Ripley 230kV | NM-NG | 0 | 2011-05-31
0283 | Riverbank Power Corporation | Riverbank Power J | 2008-03-03 | 1000 | 1000 | H | Queens | NY | J | Poletti Substation 345kV | NYPA | 0 | 2008-04-15
0285 | Machias Wind Farm, LLC | Machias I | 2008-03-27 | 79.2 | 79.2 | W | Cattaraugus | NY | A | Gardenville - Homer Hill 115kV | NM-NG | 0 | 2012-06-30
0286 | Machias Wind Farm, LLC | Machias II | 2008-03-27 | 199.5 | 199.5 | W | Cattaraugus | NY | A | 345kV | NYSEG | 0 | 2009-04-08
0287 | Horizon Wind Energy, LLC | Pomfret | 2008-03-27 | 73.5 | 73.5 | W | Chautauqua | NY | A | Dunkirk - Falconer 115kV | NM-NG | 0 | 2010-09-30
0288 | Chateaugay River Wind Farm, LLC | Chateaugay River | 2008-03-31 | 120 | 120 | W | Franklin | NY | E | Willis Substation 230kV | NYPA | 0 | 2009-02-05
0290 | National Grid | Paradise | 2008-04-03 | N/A | N/A | AC | Niagara | NY | A | Paradise Station 115kV | NM-NG | 0 | 2011-03-31
0291 | Long Island Cable, LLC | LI Cable - Phase 1 | 2008-04-14 | 440 | 440 | W | Suffolk | NY | K | Ruland Road 138kV | LIPA | 0 | 2012-07-31
0292 | Long Island Cable, LLC | LI Cable - Phase 2a | 2008-04-14 | 220 | 220 | W | Suffolk | NY | K | Ruland Road 138kV | LIPA | 0 | 2012-07-31
0293 | Long Island Cable, LLC | LI Cable - Phase 2b | 2008-04-14 | 280 | 280 | W | Suffolk | NY | K | Ruland Road 138kV | LIPA | 0 | 2008-12-22
0295 | CCH Holdings Group, LLC | Cross Hudson II | 2008-05-06 | 800 | 800 | AC | NY-NJ | NY | J | West 49th St. Substation 345kV | ConEd | 0 | 2012-06-01
0296 | Noble Environmental Power, LLC | Harrigan Hill Wind | 2008-05-12 | 100.5 | 100.5 | W | Clinton-Ellenburg | NY | D | Lyon Mt - Willis 115kV | NYSEG | 0 | 2009-07-31
0297 | Ashford Wind Farm, LLC | Ashford Wind | 2008-05-16 | 19.9 | 19.9 | W | Cattaraugus | NY | A | Otto-West Valley 34.5kV | NM-NG | 0 | 2010-03-31
0298 | TCI Renewable, LLC | Leicester Wind | 2008-05-22 | 57 | 57 | W | Livingston | NY | A | Highbank - Mortimer 115kV | NYSEG | 0 | 2010-08-31
0299 | Erie Boulevard Hydropower | Great Bend | 2008-06-03 | 14.4 | 14.4 | H | Jefferson | NY | E | Deferiet 115 kV substation | NM-NG | 0 | 2009-04-08
0300 | Auburn Public Power Agency | Auburn Sewage Treatment | 2008-06-26 | 3 | 3 |  | Onondaga | NY | C | Auburn, NY | NYSEG | 0 | 2008-10-14
0301 | Hamlin Wind, LLC | Hamlin Wind Farm | 2008-07-15 | 80 | 80 | W | Monroe | NY | A | West Hamlin 115kV | NM-NG | 0 | 2010-03-31
0302 | Barre Wind, LLC | Barre Wind Farm | 2008-07-15 | 120 | 120 | W | Orleans | NY | A | Lockport - Mortimer 115 KV | NM-NG | 0 | 2008-12-22
0303 | Invenergy Thermal Devel., LLC | Tioga County Energy | 2008-07-17 | 620 | 700 | CT | Tioga | NY | C | Oakdale - Watercure 345kV | NYSEG | 0 | 2009-04-08
0304 | Transmission Developers Inc. | Clay HVDC | 2008-07-18 | 2000 | 2000 | DC | NY | NY | J | Clay to Farragut 345kV | NM-NG/ConEd | 0 | 2008-08-28
0305 | TDI-USA Holdings Corporation | Champlain Hudson Power Express | 2008-07-18 | 1000 | 1000 | DC | Quebec - NY | NY | J | Astoria Annex Substation 345kV | NYPA | 0 | 2017-01-31
0306 | Transmission Developers Inc. | Clay HVDC | 2008-07-18 | 2000 | 2000 | DC | Onondaga/NY | NY | C, J | Clay 345kV - Sherman Creek 138 kV | NM-NG/ConEd | 0 | 2011-11-30
0307 | NY Wire, LLC | NY Wire-Phase 1 | 2008-07-29 | 550 | 550 | DC | NJ-Kings | NY | J | Gowanus Substation 345kV | ConEd | 0 | 2012-07-31
0309 | AP Dutchess Properties Inc. | Wingdale Energy Center | 2008-09-11 | 650 | 650 | CC | Dutchess | NY | G | Pleasant Valley - Long Mt. | ConEd | 0 | 2009-05-12
0310 | Cricket Valley Energy Center, LLC | Cricket Valley Energy Center | 2008-09-22 | 1019.9 | 1136 | CC | Dutchess | NY | G | Pleasant Valley - Long Mt. 345kV | ConEd | 0 | 2014-12-31
0311 | NY State Electric & Gas | Concord Casino | 2008-09-24 | 48 | 48 | L | Sullivan | NY | E | Coopers Corner - Rock Hill | NYSEG | 0 | 2013-04-30
0312 | RP Wind NY, LLC | Gateway Wind Energy | 2008-09-25 | 79.2 | 79.2 | W | Schenectady | NY | F | Princetown - Rotterdam | NM-NG | 0 | 2009-04-08
0313 | Atlantic Wind, LLC | Stone Church Wind | 2008-09-30 | 150 | 150 | W | St. Lawrence | NY | E | Mc Intyre Substation 115 kV | NM-NG | 0 | 2011-03-31
0314 | Riverbank Power Corporation | Oswego | 2008-10-07 | 1000 | 1000 | PS | Oswego | NY | C | Oswego complex 345kV | NM-NG | 0 | 2009-06-24
0315 | CRC Renewables, LLC | Onondaga Renewables | 2008-10-23 | 47 | 47 | Wo | Onondaga | NY | C | Geres Lock 115kV | NM-NG | 0 | 2012-01-30
0316 | State Line Wind Power, LLC | State Line Wind II | 2008-10-31 | 124.8 | 124.8 | W | Chautauqua | NY | A | Dunkirk - South Ripley 230kV | NM-NG | 0 | 2009-10-28
0317 | CityGreen Transmission Inc. | CityGreen AC | 2008-11-05 | 1100 | 1100 | AC | Wsch'r/Bkln/Qns | NY | H, J | Millwood 345kV - Farragut/Rainey | ConEd | 0 | 9/30/09
0319 | AES Energy Storage, LLC | Cayuga Energy Storage | 2008-12-03 | 20 | 20 | ES | Onondaga | NY | C | Milliken 115kV | NYSEG | 0 | 2012-06-01
0320 | AES Energy Storage, LLC | Somerset Energy Storage | 2008-12-03 | 20 | 20 | ES | Niagara | NY | A | Somerset 69kV | NYSEG | 0 | 2012-06-01
0321 | Monroe County | Monroe County Landfill | 2009-01-02 | 6.4 | 6.4 | M | Monroe | NY | B | Sanford Rd. | NM-NG | 0 | 2009-09-30
0322 | Rolling Upland Wind Farm, LLC | Rolling Upland Wind | 2009-01-13 | 59.9 | 59.9 | W | Madison | NY | E | County Line - Brothertown 115kV | NYSEG | 0 | 2014-08-31
0323 | Riverbank Power Corporation | Verplanck | 2009-01-23 | 1000 | 1000 | PS | Westchester | NY | H | Indian Point 345kV | ConEd/O&R | 0 | 2009-06-24
0324 | Belltown Biogas, LLC | Belltown Bio | 2009-03-06 | 2 | 2 | M | Cayuga | NY | C | King Ferry | NYSEG | 0 | 2009-04-08
0325 | Synergy Biogas, LKc | Synergy Bio | 2009-03-06 | 2 | 2 | M | Wyoming | NY | A | Wyoming | NM-NG | 0 | 2009-04-08
0327 | Con Edison | Offshore Wind | 2009-03-20 | 700 | 700 | W | NY-Suffolk | NY | J, K | Far Rockaway 69kV | LIPA | 0 | 2011-06-30
0328 | Steuben Rural | Steuben County Landfill | 2009-03-23 | 4.8 | 4.8 | M | Steuben | NY | C | Quarry - Bath 34.5 | NYSEG | 0 | 2009-05-27
0329 | Horizon Wind Energy, LLC | Madison Wind Expansion | 2009-03-23 | 8.3 | 8.3 | W | Madison | NY | E | County Line - Brothertown 115kV | NYSEG | 0 | 2009-05-27
0332 | FitzPatrick Nuclear Station | FitzPatrick Nuclear Uprate | 2009-05-01 | 112 | 112 | NU | Oswego | NY | C | FitzPatrick Substation | NYPA | 0 | 2009-06-24
0334 | Atlantic Wind, LLC | Sangerfield Wind | 2009-05-28 | 46 | 46 | W | Onieda | NY | E | TBD | NM-NG/NYSEG | 0 | 2009-07-31
0335 | NextEra Energy Resources, LLC | Cold Creek Spring Wind | 2009-06-09 | 150.7 | 150.7 | W | Cattaraugus | NY | A | Carrs Corners - Salamanca 115kV | NM-NG | 0 | 2012-08-31
0336 | Enfield Energy, LLC | Black Oak Wind | 2009-06-29 | 50 | 50 | W | Thompkins | NY | C | Black Oak Rd 115kV | NYSEG | 0 | 2012-06-30
0338 | RG&E | Brown's Race II | 2009-08-11 | 6.3 | 6.3 | H | Monroe | NY | B | Station 137 11kV | RG&E | 0 | 2019-12-31
0341 | Covanta Energy | Hempstead Expansion | 2009-09-02 | 37 | 39 | ST | Nassau | NY | K | Hempstead 138kV | LIPA | 0 | 2010-08-31
0343 | Champlain Wind Link, LLC | Champlain Wind Link I | 2009-09-29 | 600 | 600 | AC | Clinton | NY | D | Plattsburgh - New Haven, VT 230kV | NYPA | 0 | 2012-07-31
0344 | Champlain Wind Link, LLC | Champlain Wind Link II | 2009-09-29 | 600 | 600 | AC | Clinton | NY | D | Plattsburgh - New Haven, VT 345kV | NYPA | 0 | 2012-04-30
0345 | St. Elizabeth Medical Center | St. Elizabeth Medical Center | 2009-11-02 | 2.3 | 2.3 | NG | Herkimer | NY | E |  | NM-NG | 0 | 2009-11-30
0346 | Beacon Power | Scotia Industrial Park | 2009-11-24 | 20 | 20 | F | Schenectady | NY | F | Spier - Rotterdam | NM-NG | 0 | 2012-08-31
0347 | Franklin Wind Farm, LLC | Franklin Wind | 2009-12-02 | 50.4 | 50.4 | W | Delaware | NY | E | Oakdale - Delhi 115kV | NYSEG | 0 | 2019-01-31
0348 | Casella Waste Systems | Hyland Landfill | 2009-12-02 | 0.8 | 0.8 | M | Allegany | NY | B | Station 249 | RG&E | 0 | 2010-04-30
0349 | Taylor Biomass Energy-Montgomery, LLC | Taylor Biomass | 2009-12-30 | 19 | 22.5 | SW | Orange | NY | G | Maybrook - Rock Tavern 69kV | CHGE | 0 | 2021-06-30
0350 | Lake Erie Wind, LLC | Lake Erie Wind | 2010-02-16 | 810 | 810 | W | Chautauqua | NY | A | Dunkirk - Gardenville 230kV | NM-NG | 0 | 2012-01-30
0351 | Linden VFT, LLC | Linden VFT Uprate | 2010-03-02 | 15 | 15 | AC | Richmond | NY | J | Goethals 345kV | CONED | 0 | 2013-02-28
0352 | WM Renewable Energy | Oneida-Herkimer Landfill | 2010-04-08 | 3.2 | 3.2 | M | Oneida | NY | E |  |  | 0 | 2010-06-04
0354 | Atlantic Wind, LLC | North Ridge Wind | 2010-05-13 | 100 | 100 | W | St. Lawrence | NY | E | Nicholville - Parishville 115kV | NM-NG | 0 | 2015-01-31
0356 | Pattern Renewables | Hounsfield Wind | 2010-09-07 | 249.4 | 249.4 | W | Jefferson | NY | E | Oswego Substation 345kV | NYPA | 0 | 2010-11-30
0357 | West Point Partners, LLC | NY Power Pathway | 2010-09-10 | 1000 | 1000 | DC | Albany-Westchester | NY | F, H | New Scotland - Buchanan South 345kV | NM-NG/Coned | 0 | 2013-02-28
0358 | West Point Partners, LLC | West Point Transmission | 2010-09-13 | 1000 | 1000 | DC | Greene, Westchester | NY | F, H | Leeds - Buchanan North 345kV | NM-NG/ConEd | 0 | 2018-01-31
0359 | National Grid | Verizon - Project Oasis | 2010-12-20 | 75 | 75 | L | Niagara | NY | A | Somerset - Kintigh 345kV | NYSEG | 0 | 2011-02-28
0360 | NextEra Energy Resources, LLC | Watkins Glen Wind | 2010-12-22 | 122.4 | 122.4 | W | Schuyler | NY | C | Bath - Montour Falls 115 kV | NYSEG | 0 | 2015-05-31
0361 | US PowerGen Co. | Luyster Creek Energy | 2011-02-15 | 401 | 444 | D | Queens | NY | J | Astoria West Substation 138kV | CONED | 0 | 2020-02-29
0362 | Monticello Hills Wind, LLC | Monticello Hills Wind | 2011-03-07 | 19.8 | 19.8 | W | Ostego | NY | E | W. Winfield - Richfield Spring 46kV | NYSEG | 0 | 2017-04-30
0363 | Anbaric Development Partners, LLC | Poseidon Offshore | 2011-04-27 | 500 | 500 | W | NY - Suffolk | NY | K | Ruland Rd. 138kV | LIPA | 0 | 2020-07-31
0364 | Bruce Hill Wind, LLC | Bruce Hill Wind | 2011-05-04 | 18 | 18 | W | Delaware | NY | E | Axtell Road Substation 115 kV | NYSEG | 0 | 2012-09-30
0365 | Transmission Developers Inc. | Champlain Hudson SPS | 2011-07-15 | TBD | TBD | AC | Queens | NY | J | Astoria and Farragut Subsations | ConEd/NYPA | 0 | 2012-12-31
0366 | NextEra Energy Resources, LLC | Watkins Glen East | 2011-08-02 | 150.6 | 150.6 | W | Schuyler | NY | C | Montour Falls Substation | NYSEG | 0 | 2012-10-31
0367 | Orange & Rockland | North Rockland Transformer | 2011-09-14 | N/A | N/A | AC | Rockland | NY | G | Line Y94 345kV | ConEd | 0 | 2018-07-31
0369 | Clover Leaf Power, LLC | Clover Leaf Hollers Ave | 2011-10-24 | 173.9 | 192.8 | CT | Bronx | NY | J | E 179th St. Subsation 138kV | ConEd | 0 | 2013-12-31
0370 | Smokey Avenue Wind, LLC | Smokey Avenue Wind | 2011-10-28 | 18 | 18 | W | Otsego | NY | F | Worcester - Schenevus 23kV | NM-NG | 0 | 2014-01-31
0371 | South Mountain Wind, LLC | South Mountain Wind | 2011-10-31 | 18 | 18 | W | Delaware | NY | E | River Rd Substation 46kV | NYSEG | 0 | 2018-01-31
0372 | Dry Lots Wind, LLC | Dry Lots Wind | 2011-10-31 | 33 | 33 | W | Herkimer | NY | E | Schuyler - Whitesboro 46kV | NM-NG | 0 | 2021-02-28
0374 | CPV Valley, LLC | CPV Valley II | 2012-02-21 | 820 | 820 | CC | Wawayanda | NY | G | Rock Tavern-Coopers Corners 345kV | NYPA | 0 | 2015-09-30
0376 | Ridgeline Energy, LLC | Troups Creek Wind | 2012-03-07 | 32 | 32 | W | Steuben | NY | C | Troupsburg Substation | NYSEG | 0 | 2012-04-30
0376A | Atlantic Development, LLC | Atlantice Development | 2012-03-15 | N/A | N/A | W | N/A |  | N/A | N/A | N/A | 0 | 2009-07-31
0377 | Monroe County | Monroe County Mill Seat | 2012-03-16 | 3.2 | 3.2 | M | Monroe | NY | B | Sanford Rd. 34.5kV | NM-NG | 0 | 2016-04-30
0379 | Seneca Energy II, LLC | Seneca II Expansion | 2012-04-24 | 6.4 | 6.4 | M | Seneca | NY | C | Seneca - Waterloo 34.5kV | NYSEG | 0 | 2013-05-31
0381 | Clipper Wind Power Development | Paragon Wind | 2012-05-15 | 79.9 | 79.9 | W | Steuben-Schuyler | NY | C | Stony Ridge - Hillside 230kV | NYSEG | 0 | 2012-10-31
0382 | Astoria Generating Co. | South Pier Improvement | 2012-05-30 | 91.2 | 95.5 | CT | Kings | NY | J | Gowanus Substation 138kV | ConEd | 0 | 2018-03-31
0383 | NRG Energy, Inc. | Bowline Gen. Station Unit #3 | 2012-05-30 | 775 | 814 | CC | Rockland | NY | G | Ladentown Substation 345kV | O&R | 0 | 2019-07-31
0384 | National Grid | Knickerbocker Pleasant Valley | 2012-06-15 | TBD | TBD | AC | Columbia-Dutchess | NY | F, G | Knickerbocker - P. Valley 345kV | NM-NG/ConEd | 0 | 2016-05-31
0385 | National Grid | Hudson Valley Reinforcement | 2012-06-15 | TBD | TBD | AC | Alb.-Col.-Dutch. | NY | F, G | N. Scotland-Leeds-P. Valley 345kV | NM-NG/ConEd | 0 | 2015-02-28
0386 | Vermont Green Line Devco, LLC | Grand Isle Intertie | 2012-06-28 | 400 | 400 | DC | Clinton | NY | D | Plattsburgh 230kV-New Haven, VT 345kV | NYPA | 0 | 2022-10-31
0388 | Enel Green Power North America | Dexter Solar | 2012-07-24 | 17 | 17 | S | Jefferson | NY | E | Dexter Stubstation | NM-NG | 0 | 2012-09-30
0389 | GUSC Energy, Inc. | Griffiss Technology Park | 2012-08-14 | 0.9 | 0.9 | ST | Oneida | NY | E | Boonville - Rome 115kV | NM-NG | 0 | 2012-09-30
0391 | North America Transmission, LLC | Edic - Fraser #2 | 2012-09-21 | TBD | TBD | AC | Oneida-Delaware | NY | E | Edic - Fraser 345kV | NM-NG/NYSEG | 0 | 2016-01-31
0392 | Exelon Corporation | Scriba-Volney | 2012-10-05 | TBD | TBD | AC | Oswego | NY | C | Scriba - Volney 345kV | NM-NG/NYSEG | 0 | 2016-05-31
0393 | NRG Berrians East Development, LLC | Berrians East Replacement | 2012-10-16 | 94.2 | 57 | D | Queens | NY | J | Astoria East 138kV Substation | CONED | 0 | 2023-01-31
0398 | Black Oak Wind Farm, LLC | Black Oak Wind | 2013-01-10 | 12.5 | 12.5 | W | Thompkins | NY | C | Montour - Coddington 115kV | NYSEG | 0 | 2017-08-31
0399 | American Electric Power | Mohawk Valley HVDC | 2013-02-27 | 1000 | 1000 | DC | Oneida-Bronx | NY | E, J | Marcy - Mott Haven 345kV | NYPA/ConEd | 0 | 2013-06-30
0400 | East Coast Power LLC | Linden Cogen Uprate | 2013-03-04 | 208 | 204 | CT | Linden | NJ | J | Linden Cogen 345kV | ConEd | 0 | 2015-10-31
0401 | Caithness Long Island II, LLC | Caithness Long Island II | 2013-03-22 | 599 | 632 | D | Suffolk | NY | K | Sills Road Substation 138kV | LIPA | 0 | 2018-09-30
0402 | NextEra Energy Transmission | Marcy - PV 345 | 2013-05-17 | TBD | TBD | AC | Oneida-Dutchess | NY | E-G | Marcy - P. Valley 345kV | NM-NG/NYPA/ ConEd | 0 | 2015-02-28
0404 | NextEra Energy Transmission | Princetown - Rotterdam 230 | 2013-06-04 | TBD | TBD | AC | Schenectady | NY | F | Princetown - Rotterdam 230kV | NM-NG | 0 | 2016-05-31
0405 | NextEra Energy Transmission | Oakdale - Fraser 345 | 2013-06-21 | TBD | TBD | AC | Broome-Delaware | NY | C, E | Oakdale - Fraser 345kV | NYSEG | 0 | 2015-12-31
0406 | NextEra Energy Transmission | Marcy - KB - PV 345 | 2013-06-21 | TBD | TBD | AC | Oneida-Dutchess | NY | E-G | Marcy - P. Valley 345kV | NM-NG/NYPA/ ConEd | 0 | 2015-02-28
0407 | National Grid | Edic-N.Scotland-Leed-PV | 2013-07-01 | TBD | TBD | AC | Oneida-Dutchess | NY | E-G | Edic - Pleasant Valley 345kV | NM-NG | 0 | 2015-02-28
0408 | National Grid | Edic-Princetown-N.Scotland-Leeds-PV | 2013-07-01 | TBD | TBD | AC | Oneida-Dutchess | NY | E, G | Edic - Pleasant Valley 345kV | NM-NG | 0 | 2015-02-28
0409 | National Grid | Edic-Knickerbocker-PV | 2013-07-01 | TBD | TBD | AC | Oneida-Dutchess | NY | E, G | Edic - Pleasant Valley 345kV | NM-NG | 0 | 2015-02-28
0410 | National Grid | Edic-Princetown-Knickerbocker-PV | 2013-07-01 | TBD | TBD | AC | Oneida-Dutchess | NY | E, G | Edic - Pleasant Valley 345kV | NM-NG | 0 | 2015-02-28
0411 | BCDC Transmission LLC | BCDC Transmission | 2013-07-01 | 400 | 400 | AC | NY | NY | J | NJ - Farragut Substation 345kV | ConEd | 0 | 2013-12-31
0412 | NY State Electric & Gas | Oakdale - Fraser 345 | 2013-08-20 | N/A | N/A | AC | Broome-Delaware | NY | C, E | Oakdale - Fraser 345kV | NYSEG | 0 | 2016-07-31
0413 | National Grid | Edic-Prince.-N.Scotland-Knick.-PV | 2013-08-21 | TBD | TBD | AC | Oneida-Dutchess | NY | E, G | Edic - Pleasant Valley 345kV | NM-NG | 0 | 2015-02-28
0414 | North America Transmission, LLC | Segment B Enhanced | 2013-09-05 | N/A | N/A | AC | Albany-Dutchess | NY | F, G | New Scotland - P. Valley 345kV | NM-NG/ConEd/ O&R/CHGE | 0 | 2019-04-30
0415 | Iberdrola USA | Connect NY | 2013-09-06 | 1000 | 1000 | DC | Albany-Dutchess | NY | F, G | New Scotland - Hurley Ave 345kV | NM-NG/Cen Hud | 0 | 2014-10-31
0416 | NextEra Energy Transmission | Marcy - KB - PV 345 (2) | 2013-09-09 | TBD | TBD | AC | Oneida-Dutchess | NY | E, G | Marcy - P. Valley 345kV | NM-NG/NYPA/ ConEd | 0 | 2015-02-28
0417 | NextEra Energy Transmission | Marcy - KB - PV 345 (3) | 2013-09-09 | TBD | TBD | AC | Oneida-Dutchess | NY | E, G | Marcy - P. Valley 345kV | NM-NG/NYPA/ ConEd | 0 | 2016-05-31
0418 | NextEra Energy Transmission | Marcy - NS - PV 345 | 2013-09-09 | TBD | TBD | AC | Oneida-Dutchess | NY | E, G | Marcy - P. Valley 345kV | NM-NG/NYPA/ ConEd | 0 | 2015-03-31
0419 | NextEra Energy Transmission | Marcy - NS - KB - PV 345 | 2013-09-16 | TBD | TBD | AC | Oneida-Dutchess | NY | E, G | Marcy - P. Valley 345kV | NM-NG/NYPA/ ConEd | 0 | 2016-05-31
0420 | NextEra Energy Transmission | Marcy - KB - PV 345 (4) | 2013-09-16 | TBD | TBD | AC | Oneida-Dutchess | NY | E, G | Marcy - P. Valley 345kV | NM-NG/NYPA/ ConEd | 0 | 2015-02-28
0423 | Rochester Gas & Electric | University of Rochester | 2013-11-17 | 25 | 25 | L | Monroe | NY | B | Station 251 | NYSEG | 0 | 2014-07-31
0424 | Boundless Energy NE, LLC | Leeds Path West | 2013-11-26 | N/A | N/A | AC | Greene-Westchester | NY | G-J | Leeds - Millwood 345kV | NM-NG/NYPA/ Cen Hud/ConEd/NYSEG | 0 | 2017-02-28
0425 | NextEra Energy Resources, LLC | Brookfield Wind Energy | 2013-12-11 | 100.3 | 100.3 | W | Chenango, Madison | NY | E | Chadwicks - Yahnundadis 115kV | NM-NG/NYSEG | 0 | 2015-05-31
0426 | North America Transmission, LLC | NS-Knickerbocker-PV | 2013-12-11 | TBD | TBD | AC | Albany-Dutchess | NY | F-G | New Scotland - P. Valley 345kV | NM-NG/ConEd | 0 | 2014-02-28
0427 | Island Park Energy Center, LLC | Island Park Energy Center CCPP | 2014-01-24 | 268 | 295 | CT | Nassau | NY | K | Barrett Power Station 138kV | LIPA | 0 | 2017-02-28
0428 | Island Park Energy Center, LLC | Island Park Energy Center SCPP | 2014-01-24 | 262 | 252 | CT | Nassau | NY | K | Barrett Power Station 138kV | LIPA | 0 | 2017-02-28
0433 | East Hampton Solar Farm, LLC | East Hampton - Phase 1 | 2014-04-21 | 20 | 20 | S | Suffolk | NY | K | Amagansett Substation 69KV | LIPA | 0 | 2014-05-31
0434 | East Hampton Solar Farm 2, LLC | East Hampton - Phase 2 | 2014-04-21 | 20 | 20 | S | Suffolk | NY | K | Amagansett Substation 69KV | LIPA | 0 | 2014-05-31
0435 | East Hampton Solar Farm 2, LLC | East Hampton - Phase 3 | 2014-04-21 | 20 | 20 | S | Suffolk | NY | K | Amagansett Substation 69KV | LIPA | 0 | 2014-05-31
0436 | East Hampton Solar Farm 2, LLC | Riverhead - Phase 1 | 2014-04-21 | 20 | 20 | S | Suffolk | NY | K | Edwards Substation 69KV | LIPA | 0 | 2014-05-31
0437 | East Hampton Solar Farm 2, LLC | Riverhead - Phase 2 | 2014-04-21 | 20 | 20 | S | Suffolk | NY | K | Edwards Substation 69KV | LIPA | 0 | 2014-05-31
0438 | East Hampton Solar Farm 2, LLC | Riverhead - Phase 3 | 2014-04-21 | 20 | 20 | S | Suffolk | NY | K | Edwards Substation 69KV | LIPA | 0 | 2014-05-31
0439 | Boston Energy Trading | East Garden City-Valley Stream | 2014-05-09 | TBD | TBD | AC | Nassau | NY | K | E. Garden City-Valley Stream 138kV | LIPA | 0 | 2016-04-30
0440 | Erie Power, LLC | Erie Power | 2014-06-02 | 79.4 | 88 | CC | Chautauqua | NY | A | South Ripley Substation 230kV | NM-NG | 0 | 2018-02-28
0441 | East Hampton Solar Farm, LLC | East Hampton Solar | 2014-06-09 | 60 | 60 | S | Suffolk | NY | K | Buell Substation 69kV | LIPA | 0 | 2015-01-31
0442 | Riverhead Solar Farm, LLC | Riverhead Solar | 2014-06-09 | 24 | 24 | S | Suffolk | NY | K | Edwards Substation 138kV | LIPA | 0 | 2015-05-31
0443 | Manorville Solar, LLC | Manorville Solar | 2014-06-09 | 16 | 16 | S | Suffolk | NY | K | Riverhead - Eastport 69kV | LIPA | 0 | 2015-04-30
0445 | Lighthouse Wind, LLC | Lighthouse Wind | 2014-06-30 | 201.3 | 201.3 | W | Niagara | NY | A | AES Somerset Substation 345kV | NYSEG | 0 | 2021-02-28
0446 | Solar Alliance Freedom, Inc. | Jockey Hill Solar | 2014-07-21 | 2 | 2 | S | Ulster | NY | G | Hurley Substation 345kV | CenHud | 0 | 2014-09-30
0447 | FTS Devco LLC | East Hampton Expansion | 2014-07-25 | 20 | 20 | S | Suffolk | NY | K | Amagansett Substation 69kV | LIPA | 0 | 2015-01-31
0448 | Alps Interconnector, LLC | Alps HVDC | 2014-08-12 | 600 | 600 | DC |  |  | F | Alps Substation 345kV | NM-NG | 0 | 2018-11-30
0449 | Stockbridge Wind, LLC | Stockbridge Wind | 2014-08-13 | 72.6 | 72.6 | W | Madison | NY | C | Whitman - Oneida 115kV | NM-NG | 0 | 2021-02-28
0450 | Stacy Solar Center, LLC | Stacy Solar | 2014-08-20 | 20 | 20 | S | Greene | NY | G | Coxsackie Substation 69kV | CenHud | 0 | 2015-02-28
0451 | Shortsville Solar Center, LLC | Shortsville Solar | 2014-08-20 | 20 | 20 | S | Ontario | NY | B | Substation #168 34.5kV | NYSEG | 0 | 2014-10-31
0452 | Taconic Solar Center, LLC | Taconic Solar | 2014-08-20 | 10 | 10 | S | Columbia | NY | F | Craryville Substation 34.5kV | NYSEG | 0 | 2014-10-31
0453 | Blue Hill Solar Center, LLC | Blue Hill Solar | 2014-08-20 | 20 | 20 | S | Columbia | NY | F | Blue Stores Substation 115kV | NM-NG | 0 | 2014-10-31
0454 | Sabin Solar Center, LLC | Sabin Solar | 2014-08-20 | 20 | 20 | S | Herkimer | NY | E | Salisbury Substation 115kV | NM-NG | 0 | 2014-10-31
0455 | Roseway Solar, LLC | Roseway Solar | 2014-08-21 | 19.9 | 19.9 | S | Sullivan | NY | E | 34.5kV | NYSEG | 0 | 2015-02-28
0456 | ESA Solar NY, LLC | Woodhull Solar | 2014-09-09 | 0.7 | 0.7 | S | Steuben | NY | C | Woodhull Substation | NYSEG | 0 | 2015-07-31
0457 | RES America Developments Inc. | Bellmont Wind | 2014-09-22 | 19.8 | 19.8 | W |  |  |  | Brainardsville, NY | NYSEG | 0 | 2014-12-31
0458 | TDI-USA Holdings, Inc. | CH Interconnection | 2014-10-24 | 1000 | 1000 | DC | Quebec-NY | NY | J | Astoria Annex Substation 345kV | NYPA | 0 | 2021-05-31
0459 | ESA Solar NY, LLC | Warsaw Solar | 2014-11-05 | 2 | 2 | S | Wyoming | NY | B | Wethersfield Substation 115kV | NYSEG | 0 | 2014-12-31
0460 | Dryden Solar, LLC | Dryden Solar | 2014-11-10 | 5 | 5 | S | Thompkins | NY | C |  | NYSEG | 0 | 2014-12-31
0463 | Long Island Clean Energy Project LLC | 62 Weeks Rd. Fuel Cell | 2014-12-05 | 19.9 | 19.9 |  | Suffolk | NY | K | 69kV | LIPA | 0 | 2015-01-31
0464 | Long Island Clean Energy Project LLC | Pulaski Rd. Fuel Cell | 2014-12-05 | 19.9 | 19.9 |  | Suffolk | NY | K | 138kV | LIPA | 0 | 2015-01-31
0465 | Hudson Transmission Partners | Hudson Transmission NY to PJM | 2014-12-15 | 675 | 675 | DC | NY | NY | J | W49th St 345kV - Bergen 230kV | ConEd | 0 | 2021-01-31
0466 | Atlantic Wind, LLC | Bone Run Wind | 2014-12-16 | 132 | 132 | W | Cattaraugus | NY | A | Falconer - Homer Hill 115kV | NM-NG | 0 | 2021-02-28
0468 | Apex Clean Energy LLC | Galloo Island Wind | 2014-12-30 | 110.4 | 110.4 | W | Oswego | NY | C | Hammermill - Wine Creek 115kV | NM-NG | 0 | 2021-02-28
0469 | NextEra Energy Transmission | Edic-PV 345 | 2015-01-06 | TBD | TBD | AC | Oneida-Dutchess | NY | E, G | Edic - Pleasant Valley 345kV | NM-NG/ConEd | 0 | 2015-05-31
0470 | NextEra Energy Transmission | Knickerbocker 115 | 2015-01-06 | TBD | TBD | AC | Columbia-Rensselaer | NY | F | Greenbush - Churchtown 115kV | NM-NG/NYSEG/ CHGE | 0 | 2016-05-31
0471 | NextEra Energy Transmission | Marcy-Princetown 345 | 2015-01-06 | TBD | TBD | AC | Oneida-Albany | NY | E, F | Marcy - Princetown 345kV | NM-NG/NYPA/ ConEd | 0 | 2016-05-31
0472 | NextEra Energy Transmission | Knickerbocker 345 | 2015-01-06 | TBD | TBD | AC | Rensselaer-Dutchess | NY | F | Knickerbocker - P. Valley 345kV | NM-NG/ConEd | 0 | 2016-05-31
0473 | Calverton Solar LLC | Calverton Solar | 2015-01-21 | 10 | 10 | S | Suffolk | NY | K | Riverhead - Wildwood 69kV | LIPA | 0 | 2019-02-28
0474 | EDP Renewables North America | North Slope Wind | 2015-01-30 | 200 | 200 | W | Franklin-Clinton | NY | D | Patnode 230kV | NYPA | 0 | 2021-02-28
0475 | OneEnergy Development, LLC | Windy Hill Solar | 2015-02-02 | 20 | 20 | W | Washington | NY | F | Battenkill Substation 115kV | NM-NG | 0 | 2015-07-31
0476 | NY State Electric & Gas | Edic-PV, Oakdale-Fraser | 2015-02-12 | N/A | N/A | AC | Oneida-Delaware | NY | E | Edic-PV, Oakdale-Fraser 345kV | NM-NG/NYSEG | 0 | 2016-07-31
0478 | Central Hudson Gas & Electric | Hurley Ave PARs | 2015-02-17 | TBD | TBD | AC | Dutchess | NY | G | Hurley Ave 345kV | CHGE/NM-NG/NYSEG | 0 | 2016-03-31
0479 | Central Hudson Gas & Electric | Edic-NS, Hurley PARs | 2015-02-17 | TBD | TBD | AC | Oneida-Dutchess | NY | E-G | Edic-NS, Hurley Ave 345kV | CHGE/NM-NG/NYSEG/NYPA | 0 | 2016-03-31
0480 | National Grid | Edic-NS, Knickerbocker-PV | 2015-02-20 | TBD | TBD | AC | Oneida-Dutchess | NY | E-G | Edic-NS, Knickerbocker-PV 345kV | NM-NG/ConEd | 0 | 2016-05-31
0481 | National Grid | Leeds - Pleasant Valley | 2015-02-20 | TBD | TBD | AC | Greene-Dutchess | NY | G | Leeds - P. Valley 345kV | NM-NG/ConEd | 0 | 2015-12-31
0482 | National Grid | Edic-NS, NS-Leeds-PV | 2015-02-20 | TBD | TBD | AC | Oneida-Dutchess | NY | E, G | Edic-NS, NS-Leeds-PV 345kV | NM-NG/ConEd | 0 | 2015-12-31
0483 | National Grid | NS-Leeds, Leeds-PV | 2015-02-20 | TBD | TBD | AC | Albany-Dutchess | NY | F, G | NS-Leeds, Leeds-PV 345kV | NM-NG/ConEd | 0 | 2015-12-31
0484 | National Grid | Edic-NS, NS-Leeds, Leeds-PV | 2015-02-20 | TBD | TBD | AC | Oneida-Dutchess | NY | E, G | Edic-NS, NS-Leeds, Leeds-PV 345kV | NM-NG/ConEd | 0 | 2015-12-31
0485 | National Grid | Knickerbocker-PV | 2015-03-04 | TBD | TBD | AC | Columbia-Dutchess | NY | F, G | Knickerbocker - P. Valley 345kV | NM-NG/ConEd | 0 | 2016-05-31
0486 | LI Energy Storage System | Buell Battery Storage | 2015-03-09 | 20 | 20 | ES | Suffolk | NY | K | East Hampton Substation 69kV | LIPA | 0 | 2015-10-31
0487 | LI Energy Storage System, LLC | Far Rockaway Battery Storage | 2015-03-09 | 20 | 20 | ES | Nassau | NY | K | Far Rockaway 69kV | LIPA | 0 | 2022-10-31
0488 | LI Energy Storage System | Glenwood Battery Storage | 2015-03-09 | 20 | 20 | ES | Suffolk | NY | K | Glenwood Substation 69kV | LIPA | 0 | 2017-04-30
0489 | LI Energy Storage System | Southampton Battery Storage | 2015-03-09 | 20 | 20 | ES | Suffolk | NY | K | Southampton 69kV | LIPA | 0 | 2015-10-31
0491 | Yaphank Fuel Cell Park, LLC | Yaphank Fuel Cell Park | 2015-03-23 | 19.6 | 19.6 | ES | Suffolk | NY | K | Yaphank Substation 69kV | LIPA | 0 | 2015-07-31
0492 | Setauket Fuel Cell Park, LLC | Setauket Fuel Cell Park | 2015-03-23 | 19.6 | 19.6 | FC | Suffolk | NY | K | Terryville Substation 69kV | LIPA | 0 | 2016-09-30
0493 | EPCAL Fuel Cell Park, LLC | EPCAL Fuel Cell Park | 2015-03-30 | 19.6 | 19.6 | FC | Suffolk | NY | K | Riverhead 69 kV | LIPA | 0 | 2016-01-31
0494 | Alabama Ledge Wind Farm LLC | Alabama Ledge Wind | 2015-03-31 | 79.8 | 79.8 | W | Genesee | NY | B | Lockport - Oakfield 115kV | NM-NG | 0 | 2020-01-31
0496 | Renovo Energy Center, LLC | Renovo Energy Center | 2015-04-13 | 480 | 504 | CC | Clinton | PA | C | Homer City - Mainsburg 345kV | NYSEG | 0 | 2021-02-28
0497 | Invenergy Wind Development LLC | Bull Run Wind | 2015-04-24 | 303.6 | 303.6 | W | Clinton | NY | D | Patnode 230kV | NYPA | 0 | 2023-01-31
0498 | ESC Tioga County Power, LLC | Tioga County Power | 2015-04-29 | 550 | 550 | CC | Tioga | PA | C | Homer City - Mainsburg 345kV | NYSEG | 0 | 2021-02-28
0499 | Sharon Solar LLC | Sharon Solar | 2015-05-07 | 19.6 | 19.6 | S | Schoharie | NY | F | Sharon Substation 69kV | NM-NG | 0 | 2015-10-31
0500 | Regeneron Solar LLC | Regeneron Solar | 2015-05-12 | 2 | 2 | S | Rensselaer | NY | F | East Greenbush, NY | NM-NG | 0 | 2015-08-31
0501 | Regeneron Solar LLC | Mariaville 2 Solar | 2015-05-12 | 2 | 2 | S | Schenectady | NY | F | Mariaville, NY | NM-NG | 0 | 2015-08-31
0502 | Lincoln Park DG LLC | Lincoln Park | 2015-05-22 | 18.3 | 18.3 |  | Dutchess | NY | F | Lincoln Park Substation | CHGE | 0 | 2015-06-30
0503 | East Kingstson DG LLC | East Kingston | 2015-05-22 | 18.3 | 18.3 |  | Dutchess | NY | F | East Kingston Substation | CHGE | 0 | 2015-06-30
0504 | NY DG Holding LLC | Saugerties | 2015-05-22 | 18.3 | 18.3 |  | Dutchess | NY | F | Saugerties Substation | CHGE | 0 | 2015-06-30
0505A | Central Hudson | Hurley Ave & Saugerties | 2015-06-05 | TBD | TBD | AC | Greene-Ulster | NY | G | Hurley Ave & Saugerties 69kV | CHGE | 0 | 2015-10-31
0506 | Empire State Connector Corp. | Empire State Connector | 2015-06-10 | 1000 | 1000 | DC | Onondaga | NY | E, J | Marcy - Gowanus 345kV | NYPA/ConEd | 0 | 2023-01-31
0507 | Erie Boulevard Hydropower, LP | Glens Falls Hydro | 2015-07-02 | 14.8 | 14.8 | H | Washington | NY | F | Henry St. - Glens Falls 34.5kV | NM-NG | 0 | 2016-12-31
0508 | Blue Circle DG LLC | Blue Circle | 2015-07-17 | 18.2 | 18.2 | FC | Greene | NY | G | LaFarge - PV 115 kV | NM-NG | 0 | 2016-02-29
0509 | North Catskill DG LLC | North Catskill | 2015-07-17 | 18.2 | 18.2 |  | Greene | NY | G | North Catskill Substation | CHGE | 0 | 2015-08-31
0511 | AG Energy, LP | Ogdensburg | 2015-09-04 | 79 | 90.1 | CC | St. Lawrence | NY | E | North Ogdensburg Substation | NM-NG | 0 | 2019-09-30
0512 | Northbrook Lyons Falls | Lyons Fills Mill Hydro | 2015-09-11 | 2.5 | 2.5 | H | Lewis | NY | E | Taylorville- Boonville 115 kV | NM-NG | 0 | 2019-06-30
0514 | RES Americas Developments Inc. | Empire Wind | 2015-10-01 | 120 | 120 | W | Rensselaer | NY | F | Stephentown - Greenbush 115kV | NM-NG | 0 | 2018-07-31
0515 | North Bergen Liberty Generation Center LLC | Liberty Generation | 2015-10-07 | 1000 | 1000 | CC | NY | NY | J | W49th St 345kV | ConEd | 0 | 2018-01-31
0516 | East Coast Power LLC | Linden Cogen Uprate | 2015-10-12 | 234.4 | 234.4 | CT | Union | NJ | J | Linden Cogen 345kV | ConEd | 0 | 2020-02-29
0518 | PPL Electric Utilities | Compass | 2015-10-27 | N/A | N/A | AC | Rockland | NY | G | Lackawanna - Ramapo 345kV | ConEd | 0 | 2021-05-31
0520 | EDP Renewables North America | Rolling Upland Wind | 2015-12-03 | 72.6 | 72.6 | W | Madison | NY | E | County Line - Brothertown 115kV | NYSEG | 0 | 2023-01-31
0523 | Dunkirk Power LLC | Dunkirk Unit 2 | 2015-12-17 | 75 | 75 | ST | Chautauqua | NY | A | Dunkirk 115kV | NM-NG | 0 | 2020-06-30
0524 | Dunkirk Power LLC | Dunkirk Unit 3 & 4 | 2015-12-17 | 370 | 370 | ST | Chautauqua | NY | A | Dunkirk 230kV | NM-NG | 0 | 2020-06-30
0525 | NY Power Authority | Western NY Energy Link | 2015-12-18 | N/A | N/A | AC | Niagara | NY | A | Niagara - Stolle - Gardenville | NYPA/NYSEG | 0 | 2018-02-28
0526 | Atlantic Wind, LLC | North Ridge Wind | 2015-12-23 | 100 | 100 | W | St. Lawrence | NY | D | Malone - Colton 115kV | NM-NG | 0 | 2023-01-31
0527 | Atlantic Wind, LLC | Horse Creek Wind | 2015-12-23 | 250 | 250 | W | Jefferson | NY | E | Indian River 115kV | NM-NG | 0 | 2017-07-31
0528 | National Grid | Moderate Power Transfer | 2015-12-30 | N/A | N/A | AC | Niagara-Erie | NY | A | Niagara, Erie, Stolle, Gardenville | NM-NG | 0 | 2017-09-30
0529 | National Grid | High Power Transfer | 2015-12-30 | N/A | N/A | AC | Niagara-Erie | NY | A | Niagara, Erie, Stolle, Gardenville | NM-NG | 0 | 2017-09-30
0530 | NextEra Energy Transmission NY, Inc. | Empire State Line | 2016-01-04 | N/A | N/A | AC | Niagara-Erie | NY | A | Dysinger - Stolle 345kV | NYPA/NYSEG | 0 | 2018-01-31
0532 | Invenergy Wind Development LLC | Allegany Wind | 2016-02-01 | 100 | 100 | W | Allegany | NY | B | Freedom Substation | Village of Arcade | 0 | 2019-03-31
0533 | Delano Management LLC | Empire Interconnection | 2016-02-03 | 275 | 275 | DC | Nassau | NY | K | Far Rockaway Substation 69kV | LIPA | 0 | 2017-11-30
0534 | OneEnergy Development, LLC | Great Valley Solar | 2016-02-03 | 20 | 20 | S | Washington | NY | F | Battenkill 34.5kV Substation | NM-NG | 0 | 2019-07-31
0536 | Empire Interconnection LLC | Glenwood | 2016-04-19 | 275 | 275 | AC | Suffolk | NY | K | Glenwood/Far Rockaway Station 69kV | LIPA | 0 | 2017-11-30
0537 | NextEra Energy Transmission NY, Inc. | Segment A | 2016-04-25 | N/A | N/A | AC | Oneida-Albany | NY | E, F | Edic - New Scotland 345kV | NM-NG/NYPA | 0 | 2018-01-31
0538 | NextEra Energy Transmission NY, Inc. | Segment B | 2016-04-25 | N/A | N/A | AC | Albany-Dutchess | NY | F, G | Greenbush - PV 345kV | NM-NG/NYSEG/ CHGE/ConEd | 0 | 2018-10-31
0539 | NextEra Energy Transmission NY, Inc. | Segment B Alt | 2016-04-25 | N/A | N/A | AC | Albany-Dutchess | NY | F, G | Greenbush - PV 345kV | NM-NG/NYSEG/ CHGE/ConEd | 0 | 2018-10-31
0540 | AVANGRID | Connect NY Edic - PV | 2016-04-28 | 1000 | 1000 | DC | Oneida-Dutchess | NY | E, G | Edic - PV 345kV | NM-NG/ ConEd | 0 | 2022-10-31
0541 | AVANGRID | Connect NY Edic - Ramapo | 2016-04-28 | 1000 | 1000 | DC | Oneida-Dutchess | NY | E, G | Edic - Ramapo 345kV | NM-NG/ ConEd | 0 | 2022-10-31
0542 | National Grid | Segment A Edic-New Scotland | 2016-05-04 | N/A | N/A | AC | Oneida-Albany | NY | E, F | Edic - New Scotland 345kV | NM-NG | 0 | 2018-01-31
0544 | Invenergy Wind Development LLC | Alle Catt Wind | 2016-05-04 | 100.5 | 100.5 | W | Cattaraugus | NY | A | Freedom Substation 115kV | Village of Arcade | 0 | 2017-08-31
0547 | North America Transmission, LLC | Dysinger-Stolle | 2016-05-25 | N/A | N/A | AC | Niagara-Erie | NY | A | Dysinger - Stolle 345kV | NYPA/NYSEG/ NM-NG | 0 | 2019-04-30
0548 | North America Transmission, LLC | Dysinger-Stolle-Gardenville | 2016-05-25 | N/A | N/A | AC | Niagara-Erie | NY | A | Dysinger - Gardenville 345kV | NYPA/NYSEG/ NM-NG | 0 | 2017-10-31
0549 | North America Transmission, LLC | Niagara-Dysinger-Stolle-Gardenville | 2016-05-25 | N/A | N/A | AC | Niagara-Erie | NY | A | Niagara - Gardenville 345kV | NYPA/NYSEG/ NM-NG | 0 | 2017-10-31
0550 | North America Transmission, LLC | Dysinger-Stolle-Gardenville II | 2016-06-02 | N/A | N/A | AC | Niagara-Erie | NY | A | Dysinger - Gardenville 345kV | NYPA/NYSEG/ NM-NG | 0 | 2017-10-31
0551 | OneEnergy Development, LLC | Caprock Solar | 2016-06-24 | 20 | 20 | S | Monroe | NY | B | South Union - Sweden 115kV | NM-NG | 0 | 2017-08-31
0552 | OneEnergy Development, LLC | Flotilla Solar | 2016-06-24 | 20 | 20 | S | Monroe | NY | B | Brockport - Hamlin 115kV | NM-NG | 0 | 2017-08-31
0553 | OneEnergy Development, LLC | Caspian Solar | 2016-06-24 | 20 | 20 | S | Monroe | NY | B | Sweden - South Union 115kV | NM-NG | 0 | 2016-08-31
0554 | Lookheed Martin | Lockheed Matin MST Syracuse | 2016-06-27 | [6 empty] | Lockheed Martin switch 13.8kV | NM-NG | 0 | 2016-07-31
0555 | North America Transmission, LLC | Segment A Base | 2016-07-06 | N/A | N/A | AC | Oneida-Albany | NY | E, F | Edic - New Scotland 345kV | NM-NG | 0 | 2019-04-30
0557 | North America Transmission, LLC | Segment A Enhanced | 2016-07-06 | N/A | N/A | AC | Oneida-Albany | NY | E, F | Edic - New Scotland 345kV | NM-NG | 0 | 2019-04-30
0558 | North America Transmission, LLC | Segment A 765 | 2016-07-06 | N/A | N/A | AC | Oneida-Albany | NY | E, F | Edic - New Scotland 345kV | NM-NG/ NYPA | 0 | 2019-04-30
0559 | North America Transmission, LLC | Segment B Base | 2016-07-06 | N/A | N/A | AC | Oneida-Albany | NY | E, F | Knickerbocker - PV 345kV | NM-NG/O&R CHGE/ConEd | 0 | 2019-04-30
0560 | Deer River Wind, LLC | Deer River Wind | 2016-07-08 | 100 | 100 | W | Lewis | NY | E | Black River-Lighthouse Hill 115kV | NM-NG | 0 | 2024-12-31
0561 | Astoria Generating Company LP | Astoria Generating Unit 4 | 2016-07-18 | 385 | 385 | ST | NY | NY | J | Astoria West Substation 138 kV | ConEd | 0 | 2020-02-29
0562 | OneEnergy Development, LLC | Hidden Meadow Solar | 2016-07-22 | 20 | 20 | S | Columbia-Dutchess | NY | F, G | Milan - Churchtown 115kV | NM-NG | 0 | 2017-03-31
0563 | Double Lock Solar, LLC | Double Lock Solar | 2016-07-25 | 20 | 20 | S | Herkimer | NY | E | St. Johnsville - Marshville 115kV | NM-NG | 0 | 2019-07-31
0567 | Tribes Hill Solar, LLC | Tribes Hill Solar | 2016-08-10 | 20 | 20 | S | Montgomery | NY | F | Ephrata - Florida 69KV | NM-NG | 0 | 2018-06-30
0568 | Turkey Hollow Solar, LLC | Turkey Hollow Solar | 2016-08-16 | 20 | 20 | S | Delaware | NY | F | Grand Gorge - Axtell Road 115kV | NYSEG | 0 | 2018-01-31
0569 | Hecate Energy, LLC | Greene County | 2016-08-17 | 50 | 50 | S | Greene | NY | G |  | CHGE | 0 | 2016-09-30
0574 | Atlantic Wind, LLC | Mad River Wind | 2016-09-16 | 450 | 450 | W | Jefferson-Oswego | NY | E | Volney - Marcy 345kV | NM-NG | 0 | 2023-01-31
0576 | Astoria Generating Company LP | Astoria Generating Unit 4 | 2016-09-16 | 385 | 385 | ST | NY | NY | J | Astoria East Substation 138kV | ConEd | 0 | 2020-02-29
0577 | Greene County Energy Properties, LLC | Greene County Energy | 2016-09-20 | 20 | 20 | S | Greene | NY | G | New Baltimore - Coxsackie 69 kV | CHG&E | 0 | 2024-05-31
0578 | Sharon Solar LLC | Sharon Solar | 2016-09-20 | 20 | 20 | S | Schoharie | NY | F | Sharon Substation 69kV | NM-NG | 0 | 2017-06-30
0582 | Sunny Knoll Solar LLC | Sunny Knoll Solar | 2016-10-18 | 20 | 20 | S | Schoharie | NY | F | Cobleskill - Schoharie 69kV | NM-NG | 0 | 2019-05-31
0585 | Caledonia Solar LLC | Caledonia I Solar | 2016-11-07 | 20 | 20 | S | Livingston | NY | A | Golah - South Perry 69kV | NM-NG | 0 | 2018-06-30
0587 | Fork Valley Solar LLC | Fork Valley Solar | 2016-11-08 | 20 | 20 | S | Steuben | NY | C | Eelpot Rd 345.5kV Substation | NYSEG | 0 | 2018-07-31
0588 | Exelon Transmission Co., LLC | Niagara Transmission Expansion | 2016-11-15 | N/A | N/A | AC | Niagara-Erie | NY | A | Niagara - Gardenville | NYPA/NYSEG/ NM-NG | 0 | 2017-09-30
0589 | Duke Energy Renewables Solar, LLC | North Country Solar | 2016-12-02 | 15 | 15 | S | Lewis | NY | E | Boonville 46kV | NM-NG | 0 | 2022-03-31
0593 | OneEnergy Development, LLC | Raceway Solar | 2016-12-28 | 20 | 20 | S | Rensselaer | NY | F | Cobb Hill Substation | NYSEG | 0 | 2017-04-30
0594 | North Park Energy, LLC | NW Energy | 2016-12-29 | 60 | 60 | ES | Wyoming | NY | C | Wethersfield Substation 230kV | NYSEG | 0 | 2023-01-31
0595 | North Park Energy, LLC | SW Energy | 2016-12-29 | 100 | 100 | ES | Cattaraugus | NY | A | Five Mile Rd Substation 115kV | NM-NG | 0 | 2021-08-31
0597 | Hecate Energy Greene County 3 LLC | Greene County 3 | 2017-01-10 | 20.0 | 20.0 | S | Greene | NY | G | North Catskill - Coxsackie 69kV | CHG&E | 0 | 2024-05-31
0599 | LeRoy, LLC | LeRoy Solar | 2017-01-11 | 20 | 20 | S | Genesee | NY | B | LeRoy Substation 115kV | NGrid | 0 | 2017-04-30
0600 | Conti Enterprises, Inc. | Darby Solar | 2017-01-12 | 20 | 20 | S | Washington | NY | G | Mechanicville - Schaghticoke 34.5kV | NM-NG | 0 | 2019-04-30
0601 | HP Hood LLC | Hood Cogen | 2017-01-20 | 4 | 4 | CT | Madison | NY | C | Oneida - Fenner 115kV | NGrid | 0 | 2018-12-31
0602 | Cypress Creek Renewables | Keesog Solar | 2017-01-30 | 50 | 50 | S | Franklin | NY | D | Moses - Willis 230kV | NYPA | 0 | 2017-05-31
0603 | Hecate Energy Riverhead, LLC | Riverhead | 2017-02-03 | 7.5 | 7.5 | S | Suffolk | NY | K | Wildwood - Riverhead 69kV | LIPA | 0 | 2018-05-31
0604 | Hecate Energy Columbia County 1, LLC | Columbia County 1 | 2017-02-07 | 20 | 20 | S | Columbia | NY | G | Craryville Substation 34.5kV | NYSEG | 0 | 2017-07-31
0605 | Hecate Energy Columbia County 2, LLC | Columbia County 2 | 2017-02-07 | 20 | 20 | S | Columbia | NY | G | Craryville Substation 34.5kV | NYSEG | 0 | 2017-07-31
0606 | Hecate Energy Craryville 3, LLC | Columbia County 3 | 2017-02-07 | 10 | 10 | S | Columbia | NY | G | Craryville Substation 34.5kV | NYSEG | 0 | 2017-07-31
0607 | Empire State Connector Corporation | Empire State Connector II | 2017-02-08 | 1000 | 1000 | DC | Oneida-NY | NY | E, J | Marcy - Astoria 345kV | NYPA/NM-NG/ ConEd | 0 | 2017-03-31
0608 | ITC NY Development, LLC | Segment A | 2017-02-08 | N/A | N/A | AC | Oneida-Albany | NY | E, F | Edic - New Scotland 345kV | NM-NG | 0 | 2019-04-30
0609 | ITC NY Development, LLC | Segment B | 2017-02-08 | N/A | N/A | AC | Oneida-Albany | NY | E, F | Knickerbocker - PV 345kV | NM-NG/NYSEG/ CHGE/ConEd | 0 | 2019-04-30
0610 | Woodruff Solar, LLC | Woodruff Solar | 2017-02-10 | 20 | 20 | S | Livingston | NY | A | Golah - N. Lakeville 34.5KV | NM-NG | 0 | 2019-06-30
0611 | Badra Solar, LLC | Badra Solar | 2017-02-10 | 20 | 20 | S | Franklin | NY | D | Nicholville - Malone 115kV | NM-NG | 0 | 2017-03-31
0613 | OneEnergy Development, LLC | Sugar Maple Solar | 2017-02-17 | 20 | 20 | S | Herkimer | NY | E | Trenton Falls - Poland 46kV | NM-NG | 0 | 2019-06-30
0614 | Sabertooth Solar, LLC | Sabertooth Solar | 2017-02-22 | 20 | 20 | S | Cortland | NY | B | Willett - Lapeer 115kV | NYSEG | 0 | 2017-06-30
0615 | West Point Partners, LLC | West Point II HVDC | 2017-03-02 | 1000 | 1000 | DC | Albany-Westchester | NY | F, H | New Scotland - Buchanan South 345kV | NM-NG/ConEd | 0 | 2019-02-28
0616 | Heelstone Development, LLC | Mohawk Solar | 2017-03-23 | 20 | 20 | S | Herkimer | NY | E | Watkins Rd - Ilion 115kV | NM-NG | 0 | 2019-04-30
0621 | Blue Stone Solar Energy, LLC | Saugerties Solar | 2017-03-27 | 20 | 20 | S | Ulster | NY | G | Saugerties - Woodstock 69kV | CHGE | 0 | 2020-10-31
0622 | Geronimo Solar Energy, LLC | Alcoa Solar | 2017-03-27 | 20 | 20 | S | St. Lawrence | NY | E | 13.8kV | NM-NG | 0 | 2017-06-30
0623 | Conti Enterprises, Inc. | Puckett Solar | 2017-04-05 | 20 | 20 | S | Chenango | NY | C | Chenango Forks 34.5kV Substation | NYSEG | 0 | 2017-06-30
0624 | Franklin Solar, LLC | Franklin Solar | 2017-04-11 | 150 | 150 | S | Franklin | NY | D | Malone 115kV Substation | NM-NG | 0 | 2023-01-31
0625 | Whitehart Solar, LLC | Whitehart Solar | 2017-04-13 | 20 | 20 | S | Sullivan | NY | E | Hyatt Rd.- Border City 115kV | NYSEG | 0 | 2018-09-30
0626 | KCE NY 1, LLC | KCE NY 1 | 2017-04-14 | 20 | 20 |  | Saratoga | NY | F | Luther Forest 34.5kV Substation | NM-NG | 0 | 2017-06-30
0627 | OneEnergy Development, LLC | Southtown 2 Solar | 2017-04-17 | 20 | 20 | S |  |  |  | North Angola 34.5kV Substation | NM-NG | 0 | 2017-06-30
0628 | OneEnergy Development, LLC | Slingshot 2 Solar | 2017-04-17 | 20 | 20 | S | Steuben | NY | C | Hammondsport 34.5 kV Substation | NYSEG | 0 | 2017-08-31
0629 | Silver Lake Solar, LLC | Silver Lake Solar | 2017-04-27 | 24.9 | 24.9 | S | Wyoming | NY |  | South Perry 34.5kV | NYSEG | 0 | 2023-08-31
0630 | Cayuga Operating Co. | Cayuga Solar | 2017-04-27 | 20 | 20 | S | Lansing | NY | C | Milliken 34.5 Substation | NYSEG | 0 | 2018-01-31
0632 | GridAmerica Holdings Inc. | Alps - Berkshire | 2017-05-04 | N/A | N/A | AC | Rensselaer | NY | F | Alps - Berkshire 345kV | NM-NG | 0 | 2022-10-31
0633 | Conti Enterprises, Inc. | Janis Solar | 2017-05-15 | 20 | 20 | S |  |  | B | Willet - Tarbell 34.5 kV | NYSEG | 0 | 2017-06-30
0634 | Champagne Storage, LLC | Champagne Storage | 2017-05-18 | 20 | 20 | ES | Madison | NY | E | Oneida - Cortland 115kV | NM-NG | 0 | 2018-01-31
0635 | Rising Solar, LLC | Rising Solar | 2017-06-14 | 20 | 20 | S | Orange | NY | G | Sugarloaf - Wisner 69kV | O&R | 0 | 2018-12-31
0636 | Daybreak Solar, LLC | Daybreak Solar | 2017-06-15 | 25 | 25 | S | Ulster | NY | G | East Walden Substation 69kV | CHGE | 0 | 2019-01-31
0639 | Owego Solar LLC | Owego Solar | 2017-07-19 | 20 | 20 | S | Tioga | NY | C | South Owego - Stagecoach 115kV | NYSEG | 0 | 2017-11-30
0640 | Granada Solar, LLC | Grissom Solar | 2017-07-19 | 20 | 20 | S | Fulton | NY | F | Vail Mills Substation 69kV | NM-NG | 0 | 2017-11-30
0641 | AVANGRID | Oakdale - Lafayette | 2017-07-24 | N/A | N/A | AC | Broome-Onondaga | NY | C | Oakdale - Lafayette | NM-NG/NYSEG | 0 | 2019-10-04
0642 | AVANGRID | Jennison - Edic | 2017-07-24 | N/A | N/A | AC | Chenango - Oneida | NY | E | Jennison - Edic | NM-NG/NYSEG | 0 | 2019-10-04
0643 | AVANGRID | Multiple Areas | 2017-07-24 | N/A | N/A | AC | Steuben - Otsego | NY | C, E | Transmission Reinforcements | NM-NG/NYSEG | 0 | 2019-10-04
0645 | Oya Solar NY LP | Manny Corner Solar | 2017-08-01 | 20 | 20 | S | Montgomery | NY | F | Meco - Rotterdam 115kV | NM-NG | 0 | 2018-03-31
0646 | Oya Solar NY LP | Shaw Solar | 2017-08-01 | 20 | 20 | S | Jefferson | NY | E | Thousand Island 115kV | NM-NG | 0 | 2017-12-31
0647 | Oya Solar NY LP | Robinson Solar | 2017-08-01 | 20 | 20 | S | Jefferson | NY | E | Thousand Island 115kV | NM-NG | 0 | 2018-03-31
0648 | Oya Solar NY LP | Black Creek Solar | 2017-08-01 | 20 | 20 | S | Jefferson | NY | E | Thousand Island - Coffeen 115kV | NM-NG | 0 | 2017-12-31
0649 | CR Fuel Cell, LLC | Clare Rose | 2017-08-03 | 13.9 | 13.9 | FC | Suffolk | NY | K | William Floyd 69kV | LIPA | 0 | 2021-12-31
0650 | BRT Fuel Cell, LLC | Brookhaven Rail Terminal | 2017-08-03 | 18.5 | 18.5 | FC | Suffolk | NY | K | W. Yaphank - Yaphank 69kV | LIPA | 0 | 2021-12-31
0651 | Yaphank Fuel Cell Park, LLC | Yaphank Solid Waste Management | 2017-08-04 | 7.4 | 7.4 | FC | Suffolk | NY | K | W. Yaphank - North Bellport 69kV | LIPA | 0 | 2018-10-31
0652 | Somerset Operating Company LLC | Somerset Solar | 2017-08-04 | 19.9 | 19.9 | S | Monroe | NY | B | Kintigh Switchyard 69kV | NYSEG | 0 | 2018-02-01
0653 | Plattsburgh Solar, LLC | Moffitt Solar | 2017-08-07 | 20 | 20 | S | Clinton | NY | D | Northend - Woodruff Pond 46kV | NYSEG | 0 | 2018-09-30
0654 | Renovo Energy Center LLC | Renovo Energy Center | 8/11/2017 | N/A | N/A | AC | Clinton | PA | C | Homer City - Mainsburg 345kV | NYSEG | 0 | 2023-04-30
0655 | Admiral Wind LLC | Admiral Wind LLC | 2017-08-11 | 20 | 20 | W | Madison | NY | C | Fenner - Oneida 115kV | NM-NG | 0 | 2019-09-30
0656 | Taku Wind LLC | Taku Wind | 2017-08-11 | 20 | 20 | W | Genesee | NY | A | Akron - Attica 34.5kV | NM-NG | 0 | 2018-01-31
0657 | Mistral Wind LLC | Mistral Wind LLC | 2017-08-11 | 20 | 20 | W | Genesee | NY | B | Lockport - Batavia 115kV | NM-NG | 0 | 2018-11-30
0658 | CVE North America, Inc. | Volney Solar Park | 2017-08-29 | 19.8 | 19.8 | S | Fulton | NY | F | South Oswego - Clay 115kV | NM-NG | 0 | 2018-01-31
0659 | Solar Liberty Energy Systems, Inc. | Westwood Rd | 2017-09-19 | 10.1 | 11.3 | S | Erie | NY | A | Erie St - Alden 34.5kV | NYSEG | 0 | 2018-03-31
0660 | Solar Liberty Energy Systems, Inc. | Liberty Dr | 2017-09-07 | 7.4 | 7.4 | S | Niagara Falls | NY | A | Packard - Erie St 115 kV | NM-NG | 0 | 2018-03-31
0661 | Solar Liberty Energy Systems, Inc. | Eden Evans Rd | 2017-09-07 | 18 | 18 | S | Erie | NY | A | Shelton - Angola 34.5kV | NM-NG | 0 | 2018-03-31
0662 | EDP Renewables North America LLC | Coldwater Solar | 2017-09-07 | 80 | 80 | S | Chautauqua | NY | A | Dunkirk - Gardenville 115kV | NM-NG | 0 | 2019-04-30
0663 | Solar Liberty Energy Systems, Inc. | Main St | 2017-09-08 | 10.8 | 10.8 | S | York | NY | A | Golah - South Perry 69 kV | NM-NG/NYSEG | 0 | 2018-03-31
0664 | South Cooper Solar LLC | South Cooper Solar | 2017-09-14 | 20 | 20 | S | Cattaraugus | NY | A | Five Mile - Gardenville 115 kV | NM-NG | 0 | 2018-05-31
0665 | Forest Glen Solar LLC | Forest Glen Solar | 2017-09-14 | 20 | 20 | S | Allagany | NY | A | Five Mile - Homer Hill 115kV | NM-NG | 0 | 2018-03-31
0666 | Martin Rd Solar LLC | Martin Rd Solar | 2017-09-14 | 20.0 | 20.0 | Solar | Machias | NY | A | Arcade - Five Mile 115kV | NM-NG | 0 | 2024-04-30
0667 | Bakerstand Solar LLC | Bakerstand Solar | 2017-09-14 | 20 | 20 | Solar | Cattaraugus | NY | A | Machias - Maplehurst 34.5kV | NM-NG | 0 | 2024-04-30
0668 | North Bergen Liberty Generating, LLC | Liberty Generating Alternative | 2017-09-15 | 1171 | 1172 | CC | NY | NY | J | West 49th St 345kV | ConEd | 0 | 2023-05-31
0669 | SED NY Holdings LLC | Clay Solar | 2017-09-21 | 20 | 20 | S | Clay | NY | C | Clay - Lockheed 115kV | NM-NG | 0 | 2021-05-31
0671 | East Coast Power LLC | Linden Cogen Uprate | 2017-09-25 | 32 | 23 | CT | Union | NJ | J | Linden Cogen 345kV | ConEd | 0 | 2020-11-30
0672 | LS Power Development, LLC | Helix Ravenswood I | 2017-10-06 | 30.2 | 30.2 | CT | NY | NY | J | Rainey Substation 345kV | ConEd | 0 | 2018-09-30
0673 | LS Power Development, LLC | Helix Ravenswood II | 2017-10-06 | 72.4 | 72.4 | CT | NY | NY | J | Rainey Substation 345kV | ConEd | 0 | 2018-09-30
0674 | Helix Ravenswood, LLC | Vernon Battery Storage I | 2017-10-24 | 10 | 10 | ES | Queens | NY | J | Vernon Substation | ConEd | 0 | 2018-08-31
0675 | Helix Ravenswood, LLC | Vernon Battery Storage II | 2017-10-24 | 10 | 10 | ES | Queens | NY | J | Vernon Substation | ConEd | 0 | 2018-08-31
0676 | Granada Solar, LLC | Regan Solar | 2017-10-25 | 20 | 20 | S | Chenango | NY | C | Guilford 46kV | NYSEG | 0 | 2018-03-31
0677 | Granada Solar, LLC | Grange Solar | 2017-10-25 | 20 | 20 | S | Broome | NY | C | Vincent Cors 34.5kV | NYSEG | 0 | 2018-01-31
0679 | Anbaric Development Partners, LLC, NY OceanGrid, LLC | NY City Offshore Wind | 2017-11-07 | 1200 | 1200 | DC | Kings | NY | J | Gowanus 345kV | ConEd | 0 | 2024-05-31
0680 | Anbaric Development Partners, LLC | Juno Power Express | 2017-11-07 | 1200 | 1200 | DC | Suffolk | NY | K | Ruland Rd. 138kV | LIPA | 0 | 2024-11-30
0681 | Granada Solar, LLC | Magruder Solar | 2018-01-02 | 20 | 20 | S | Ulster | NY | G | Modena - Galeville 115kV | CHGE | 0 | 2018-02-28
0684 | ITC Lake Erie Connector, LLC | Lake Erie Connector | 2018-01-18 | N/A | N/A | AC | Chautauqua | NY | A | S. Ripley 230kV | NM-NG | 0 | 2022-08-31
0685 | sPower Development Company, LLC | EPCAL 1 | 2018-01-19 | 20 | 20 | S | Suffolk | NY | K | Riverhead - Brookhaven 138kV | LIPA | 0 | 2018-04-30
0686 | Invenergy Solar Development North America LLC | Bull Run Solar Energy Center | 2018-01-26 | 125 | 125 | S | Clinton | NY | D | Patnode-Duley, Ryan-Plattsburgh 230kV | NYPA | 0 | 2024-06-30
0687 | sPower Development Company, LLC | EPCAL 2 | 2018-01-29 | 150 | 150 | S | Suffolk | NY | K | Edwards - Brookhaven 69kV | LIPA | 0 | 2018-06-30
0688 | EDF Renewable Development Inc. | East Walden Solar | 2018-02-02 | 20 | 20 | S | Orange | NY | G | East Waldon Sutbation | CHGE | 0 | 2018-03-31
0689 | EDF Renewable Development Inc. | Goshen Solar | 2018-02-02 | 20 | 20 | S | Orange | NY | G | Huntley Station 115kV | O&R | 0 | 2018-03-31
0690 | EDF Renewable Development Inc. | Slate Hill 1 Solar | 2018-02-02 | 20 | 20 | S | Orange | NY | G | Shoemaker - Westtown | O&R | 0 | 2018-03-31
0691 | EDF Renewable Development Inc. | Slate Hill 2 Solar | 2018-02-02 | 20 | 20 | S | Orange | NY | G | Shoemaker - Westtown | O&R | 0 | 2018-03-31
0692 | Consolidated Edison Company of NY, Inc. | Astoria Storage on Demand | 2018-02-07 | 15 | 15 | ES | Queens | NY | J | North Queens Substation | ConEd | 0 | 2018-03-31
0693 | Renovo Energy Center, LLC | Renovo Energy Center Uprate | 2018-02-13 | 515 | 548 | CC | Clinton | PA | C | Homer City - Mainesburg 345kV | NYSEG | 0 | 2023-01-31
0694 | Sunset Hill Solar, LLC | Sunset Hill Solar | 2018-02-16 | 20 | 20 | S | Albany | NY | G | New Baltimore - Westerlo NW 69 kV | CHG&E | 0 | 2024-05-31
0697 | Helix Ravenswood, LLC | Ravenswood Energy Storage 1 | 2018-03-09 | 129 | 129 | ES | Queens | NY | J | Rainey - Farragut 345kV | ConEd | 0 | 2023-01-31
0698 | Helix Ravenswood, LLC | Ravenswood Energy Storage 2 | 2018-03-09 | 129 | 129 | ES | Queens | NY | J | Vernon-Rainey 138kV | ConEd | 0 | 2023-01-31
0699 | Helix Ravenswood, LLC | Ravenswood Gas | 2018-03-09 | 238.5 | 243.8 | CT | Queens | NY | J | Rainey - Farragut 345kV | ConEd | 0 | 2023-01-31
0700 | Robinson Grid, LLC | Robinson Grid | 2018-03-13 | 300 | 300 | ES | Kings | NY | J | Gowanus 345kV | ConEd | 0 | 2024-12-31
0702 | Anbaric Development Partners, LLC | Long Island Offshore AC | 2018-03-15 | 800 | 800 | W | Suffolk | NY | K | Ruland Rd. 138kV | LIPA | 0 | 2020-05-31
0703 | Anbaric Development Partners, LLC | NY City Offshore AC | 2018-03-15 | 800 | 800 | W | Kings | NY | J | Farragut 345kV | ConEd | 0 | 2020-05-31
0705 | Oya Solar NY, LP | Chaumont Solar | 2018-04-10 | 160 | 160 | S | Sullivan | NY | G | Thousand Island - Coffeen 115kV | NM-NG | 0 | 2018-07-31
0707 | PSEG Power NY LLC | Bethlehem Battery | 2018-05-04 | 10 | 10 | ES | Albany | NY | F | Albany Substation 115kV | NM-NG | 0 | 2018-11-30
0708 | PSEG Power NY LLC | Bethlehem Solar | 2018-05-04 | 1 | 1 | S | Albany | NY | F | 13.2kV Substation | NM-NG | 0 | 2018-06-30
0709 | Alder Creek Solar, LLC | Alder Creek Solar | 2018-05-18 | 165 | 165 | S | Oneida | NY | E | Chases Lake - Porter 230kV | NM-NG | 0 | 2024-05-31
0711 | Somerset Solar Development LLC | Somerset Solar | 2018-05-31 | 19.9 | 19.9 | S | Monroe | NY | B | Kintigh Substation 345 kV | NYSEG | 0 | 2018-10-31
0712 | Cayuga Solar LLC | Cayuga Solar | 2018-05-31 | 19.9 | 19.9 | S | Thompkins | NY | C | Milliken Substation 34.5kV | NYSEG | 0 | 2018-11-30
0713 | EDF Renewables Development, Inc. | Edora B Solar Energy Center | 2018-06-01 | 20 | 20 | S | Orange | NY | G | Hartley Substation 69kV | O&R | 0 | 2020-05-31
0714 | EDF Renewables Development, Inc. | Edora C Solar Energy Center | 2018-06-01 | 20 | 20 | S | Orange | NY | G | Shoemaker-Westtown 69kV | O&R | 0 | 2019-07-31
0715 | EDF Renewables Development, Inc. | Suffragette Solar Energy Center | 2018-06-01 | 20 | 20 | S | Cayuga | NY | C | Hyatt Substation 34.5kV | NYSEG | 0 | 2021-05-31
0718 | Cortland Energy Center, LLC | Cortland Energy Center | 2018-06-07 | 50 | 50 | S | Cortland | NY | C | Cortland - SUNY 115 kV | NM-NG | 0 | 2023-01-31
0719 | East Light Energy Center, LLC | East Light Energy Center | 2018-06-07 | 40 | 40 | S | Montgomery | NY | F | Meco - Rotterdam 115 kV | NM-NG | 0 | 2023-01-31
0722 | SED NY Holdings LLC | Manchester Solar | 2018-06-07 | 20 | 20 | S | Ontario | NY | C | Station 168 34.5 kV line #704 | RG&E | 0 | 2021-02-28
0723 | Lyonsdale Biomass, LLC | Lyonsdale Solar | 2018-06-08 | 19.9 | 19.9 | S | Lewis | NY | E | Lyonsdale Substation 115kV | NM-NG | 0 | 2019-04-30
0724 | Brewster Solar, LLC | Brewster Solar | 2018-06-08 | 25 | 25 | S | Putnam | NY | G | Pawling - Croton Falls 115kV | NYSEG | 0 | 2018-11-30
0725 | York Solar, LLC | York Solar | 2018-06-08 | 24.9 | 24.9 | S | Livingston | NY | A | Line #863 - 69kV | NM-NG | 0 | 2018-11-30
0726 | Niagara Falls Solar, LLC | Niagara Falls Solar | 2018-06-08 | 24.9 | 24.9 | S | Niagara | NY | A | Line #181 - 115kV | NM-NG | 0 | 2018-09-30
0727 | Alden Solar, LLC | Alden Solar | 2018-06-11 | 24.9 | 24.9 | S | Erie | NY | A | Cold Springs - Pulteny 34.5kV | NYSEG | 0 | 2018-09-30
0728 | EDF Renewables Development, Inc. | Champlain Solar | 2018-06-11 | 20 | 20 | S | Clinton | NY | E | Mason Corners-Sciota Flatrock 115kV | NYSEG | 0 | 2018-07-31
0729 | EDF Renewables Development, Inc. | Quiet Meadows Solar | 2018-06-11 | 20 | 20 | S | Oneida | NY | E | Oneida - Oneida Energy 115kV | NM-NG | 0 | 2018-08-31
0732 | Machias Solar, LLC | Machias Solar | 2018-06-11 | 20 | 20 | S | Cattaraugus | NY | A | Fivemile - Gardenville 115kV | NM-NG | 0 | 2018-12-31
0733 | Arcade Solar, LLC | Arcade Solar | 2018-06-11 | 19.9 | 19.9 | S | Wyoming | NY | A | Arcade - Bliss 115kv | Village of Arcade | 0 | 2018-11-30
0736 | Empire State Solar, LLC | Meads Hill Solar | 2018-06-12 | 20 | 20 | S | Schuyler | NY | C | Montour Falls - Greenidge 115kV | NYSEG | 0 | 2018-11-30
0738 | Empire Offshore Wind LLC | El Melville | 2018-06-12 | 816 | 816 | W | Suffolk | NY | K | Ruland Rd. Substation 138kV | LIPA | 0 | 2023-01-31
0739 | Hecate Energy Cody Road LLC | Cody Road | 2018-06-12 | 19.9 | 19.9 | W | Madison | NY | C | Fenner - Cortland 115kV | NM-NG | 0 | 2019-07-31
0740 | Oakdale Battery Storage LLC | Oakdale Battery Storage | 2018-06-18 | 120 | 120 | ES | Broome | NY | C | Oakdale Substation 115kV | NYSEG | 0 | 2024-05-31
0741 | Bluestone Wind, LLC | Bluestone Battery Storage | 2018-07-02 | 10 | 10 | ES | Broome | NY | E | Afton - Stilesville 115kV | NYSEG | 0 | 2020-04-30
0742 | Consolidated Edison Co. of NY, Inc. | Astoria Storage on Demand | 2018-07-05 | 1.5 | 1.5 | ES | Queens | NY | J | North Queens 27kV | ConEd | 0 | 2022-01-31
0743 | Invenergy Solar Development North America LLC | Hornell Solar | 2018-07-16 | 20 | 20 | S | Steuben | NY | C | Bennett 34.5kV | NYSEG | 0 | 2019-10-31
0745 | Energy Storage Resources, LLC | Huckleberry Ridge Energy | 2018-07-25 | 100 | 100 | ES | Orange | NY | G | Shoemaker-Westtown 69kV line #11 and Shoemaker to Deerpark 69 kV #14 | O&R | 0 | 2024-05-31
0746 | Peconic River Energy Storage LLC d/b/a North Street Energy Storage | North Street Energy Storage | 2018-07-30 | 150 | 150 | ES | Suffolk | NY | K | Brookhaven - Sills 138kV | LIPA | 0 | 2023-05-31
0747 | White Creek Solar LLC | White Creek Solar | 2018-07-30 | 100 | 100 | S | Livingston | NY | A | Jones - Mortimer 115kV | NM-NG | 0 | 2018-10-31
0749 | KCE NY 11 LLC | KCE NY 11 | 2018-08-10 | 20 | 20 | ES | Orange | NY | G | Coldenham Substation 115kV | CHGE | 0 | 2019-02-28
0750 | Calpine Mid Atlantic Development, LLC | Bethpage Storage | 2018-08-14 | 50 | 50 | ES | Nassau | NY | K | Grumman Substation 69kV | LIPA | 0 | 2019-05-31
0751 | Calpine Mid Atlantic Development, LLC | Stony Brook Storage | 2018-08-14 | 24 | 24 | ES | Suffolk | NY | K | 8LR substation 69kV | LIPA | 0 | 8/31/21
0752 | Granada Solar, LLC (Conti) | Goldenrod Solar | 2018-08-15 | 90 | 90 | S | Herkimer | NY | E | Meco - Rotterdam 115 kV | NM-NG | 0 | 2018-10-31
0753 | Granada Solar, LLC (Conti) | Blue Star Solar | 2018-08-15 | 100 | 100 | S | Washington | NY | F | Mohican - Luther Forest 115kV | NM-NG | 0 | 2018-10-31
0754 | Anbaric Development Partners, LLC | NY Ocean Grid - Canal | 2018-08-20 | 800 | 800 | W | Suffolk | NY | K | Canal Substation 138kV | LIPA | 0 | 2020-08-31
0755 | Anbaric Development Partners, LLC | NY Ocean Grid - Shoreham | 2018-08-20 | 800 | 800 | W | Suffolk | NY | K | Shoreham Substation 138kV | LIPA | 0 | 2020-07-31
0756 | Rising Solar, LLC | Rising Solar II | 2018-08-24 | 20 | 20 | S | Orange | NY | G | Sugarloaf Substation - 69kV | O&R | 0 | 2021-01-31
0757 | Granada Solar, LLC | Monarda Solar | 2018-08-29 | 20 | 20 | S | Herkimer | NY | E | Meco - Rotterdam 115 kV | NM-NG | 0 | 2018-12-31
0760 | NY Power Authority | Moses-Adirondack | 2018-09-07 | N/A | N/A | AC | St. Lawrence-Lewis | NY | D, E | Moses - Adirondack 230kV | NYPA | 0 | 3/31/21
0761 | Invenergy Solar Development LLC | Athens Energy Center | 2018-09-17 | 100 | 100 |  | Greene | NY | G | New Scotland - North Catskill 115kV | NM-NG | 0 | 2018-10-31
0762 | Invenergy Storage Development LLC | Riverhead Storage Energy Center | 2018-09-17 | 75 | 75 | ES | Suffolk | NY | K | Brookhaven - Edwards Ave 138kV | LIPA | 0 | 2020-03-31
0763 | Invenergy Solar Development LLC | Cicero Storage | 2018-09-25 | 10 | 10 | ES | Onondaga | NY | C | Pine Grove Substation 13.2kV | NM-NG | 0 | 2020-01-31
0764 | Bay State Wind LLC | NY Wind Canal | 2018-09-28 | 440 | 440 | W | Suffolk | NY | K | Canal Substation 138kV | LIPA | 0 | 2020-10-31
0765 | Bay State Wind LLC | NY Wind Brookhaven | 2018-09-28 | 880 | 880 | W | Suffolk | NY | K | Brookhaven 138kV | LIPA | 0 | 2020-12-31
0767 | Bay State Wind LLC | NY Wind Gowanus | 2018-09-28 | 1200 | 1200 | W | NY | NY | J | Gowanus Substation 345kV | ConEd | 0 | 8/31/21
0770 | KCE NY8 LLC | KCE NY 8a | 2018-10-09 | 20 | 20 | ES | Greene | NY | G | South Cairo 13.2kV | CHG&E | 0 | 2024-12-31
0771 | Mistral Wind LLC | Mistral Wind Alternative | 2018-10-10 | 20 | 20 | W | Genesee | NY | B | N. Akron - Attica 34.5 kV | NM-NG | 0 | 2020-01-31
0772 | Hollyhock Solar, LLC | Hollyhock Solar | 2018-10-15 | 20 | 20 | S | Albany | NY | F | Leeds - New Scotland 115kV | NM-NG | 0 | 2018-12-31
0773 | Charboneau Solar, LLC | Charboneau Solar | 2018-10-15 | 20 | 20 | S | Essex | NY | F | Ticonderoga - Hague Road 115kV | NM-NG | 0 | 2019-04-30
0778 | Astoria Generating Company LP | Gowanus Gas Turbine Facility Repowering | 2018-11-08 | 549 | 588 | CT | Kings | NY | J | Gowanus Substation 345kV | ConEd | 0 | 2023-01-31
0779 | Hecate Energy Gedney Hill LLC | Gedney Hill Solar | 2018-11-09 | 20 | 20 | S | Albany | NY | G | New Baltimore - Westerlo 69kV | CHG&E | 0 | 2024-05-31
0780 | Hecate Energy Johnstown LLC | Johnstown Solar | 2018-11-09 | 20 | 20 | S | Schenectady | NY |  | Stoner - Rotterdam 115kV | NM-NG | 0 | 2023-08-31
0782 | Invenergy Solar Development North America LLC | Hornell Storage | 2018-12-04 | 20 | 20 | ES | Steuben | NY | C | Bennett 34.5kV | NYSEG | 0 | 2020-04-30
0784 | High Bridge Wind, LLC | High Bridge Battery | 2018-12-11 | 5 | 5 | ES | Chenango | NY | E | E. Norwich - Jennison 115kV | NYSEG | 0 | 2024-06-30
0785 | ConnectGen Erie-Wyoming LLC | Erie-Wyoming County Solar | 2018-12-12 | 175 | 175 | CR | Wyoming | NY | C | Stolle Road - High Sheldon 230kV | NYSEG | 0 | 2024-12-31
0786 | Ravenswood Development, LLC | Ravenswood Energy Storage | 2018-12-20 | 187 | 187 | ES | Queens | NY | J | Rainey - Farragut 345kV | ConEd | 0 | 2021-12-31
0788 | Atlantic Shores Offshore Wind Project 3, LLC | Atlantic Shores Offshore Wind 7 | 2019-01-14 | 880 | 880 | W | Nassau | NY | K | East Garden City 345kV Substation | NYPA | 0 | 2021-06-30
0789 | Atlantic Shores Offshore Wind Project 3, LLC | Atlantic Shores Offshore Wind 8 | 2019-01-14 | 880.0 | 880.0 | W | Kings | NY | J | Gowanus 345kV | ConEd | 0 | 2024-05-31
0790 | Atlantic Shores Offshore Wind Project 2, LLC | Atlantic Shores Offshore Wind 9 | 2019-01-14 | 880.0 | 880.0 | W | Richmond | NY | J | Fresh Kills 345kV | ConEd | 0 | 2024-05-31
0791 | Danskammer Energy LLC | Danskammer Energy Center | 2019-01-14 | 84.4 | 88.9 | CC | Orange | NY | G | Danskammer 115kV | CHGE | 0 | 2022-08-31
0792 | Anbaric Development Partners, LLC | Juno Power Express 2 | 2019-01-29 | 800.0 | 800.0 | DC | Suffolk | NY | K | Ruland Road 138kV | LIPA | 0 | 2024-05-31
0793 | esVolta, LP | Ladybug Energy Storage | 2019-02-06 | 75 | 75 | ES | Westchester | NY | I | Sprainbrook Substation | ConEd | 0 | 2019-07-31
0794 | esVolta, LP | Bluebird Energy Storage | 2019-02-06 | 40 | 40 | ES | Westchester | NY | I | Dunwoodie Substation | ConEd | 0 | 2019-07-31
0795 | esVolta, LP | Appleseed Energy Storage | 2019-02-06 | 50 | 50 | ES | Greene | NY | G | Leeds Substation | NM-NG | 0 | 2019-07-31
0802 | EDF Renewables Development, Inc. | Bunker Solar Energy Center | 2019-03-06 | 125 | 125 | ES | Franklin | NY | D | Willis - Lyon Mt 115kV | NYSEG | 0 | 2020-03-31
0803 | Yonkers Grid, LLC | Yonkers Grid, LLC | 2019-03-11 | 100 | 100 | ES | Westchester | NY | I | Dunwoodie - 138kV North Substation | ConEd | 0 | 2023-09-30
0806 | SED NY Holdings LLC | Limestone Solar | 2019-03-25 | 20.0 | 20.0 | S | Fulton | NY | F | Stoner - Rotterdam 115kV | NM-NG | 0 | 2024-05-31
0808 | Barrett Ridge Energy, LLC | Barrett Ridge Energy | 2019-04-01 | 107 | 107 | ES | Orange | NY | G | Sugar Loaf - Vernon 115kV | CHGE | 0 | 2021-04-20
0809 | Seven Creek Energy, LLC | Seven Creek Energy | 2019-04-01 | 240 | 240 | ES | Chautauqua | NY | A | South Ripley Substation 230kV | NM-NG | 0 | 2021-04-20
0812 | Diamond Generating Corporation | CWW 200 Wind | 2019-04-03 | 200 | 200 | W | Erie | NY | A | Harbor Front 115kV | NM-NG | 0 | 2021-03-31
0813 | Diamond Generating Corporation | CWW 300 Wind | 2019-04-03 | 300 | 300 | W | Erie | NY | A | Harbor Front 115kV | NM-NG | 0 | 2021-02-28
0814 | Diamond Generating Corporation | CWW 300 MW DUN | 2019-04-03 | 300 | 300 | W | Chautauqua | NY | A | Dunkirk Substation 230kV | NM-NG | 0 | 2021-02-28
0816 | LIPA | NNC TTC Increase | 2019-04-05 | N/A | N/A | AC | Suffolk | NY | K | Northport Substation 138kV | LIPA | 0 | 2021-06-30
0817 | Quogue Energy Storage, LLC | Quogue Energy Storage | 2019-04-12 | 20 | 20 | ES | Suffolk | NY | K | Quogue Substation 69kV | LIPA | 0 | 2019-06-30
0818 | Setauket Energy Storage, LLC | Port Jeff 1-Terryville Energy Storage | 2019-04-15 | 20 | 20 | ES | Suffolk | NY | K | Port Jefferson - Terryville 69kV | LIPA | 0 | 2019-06-30
0819 | Setauket Energy Storage, LLC | Port Jeff 2-Terryville Energy Storage | 2019-04-15 | 20 | 20 | ES | Suffolk | NY | K | Port Jefferson - Terryville 69kV | LIPA | 0 | 2019-06-30
0820 | Setauket Energy Storage, LLC | Port Jeff 2-Stony Brook Energy Storage | 2019-04-15 | 20 | 20 | ES | Suffolk | NY | K | Port Jefferson - Stony Brook 69kV | LIPA | 0 | 2019-06-30
0821 | Setauket Energy Storage, LLC | Port Jeff -Mt. Sinai Energy Storage | 2019-04-15 | 20 | 20 | ES | Suffolk | NY | K | Port Jefferson - Mt. Sinai 69kV | LIPA | 0 | 2019-06-30
0822 | Astoria Generating Company LP | Whale Square Energy Storage 1 | 2019-04-15 | 58.2 | 58.2 | ES | Kings | NY | J | Narrows Barge Feeder 23162 | ConEd | 0 | 2024-12-31
0823 | Wildwood Energy Storage, LLC | Wildwood Energy Storage | 2019-04-15 | 116.7 | 116.7 | ES | Suffolk | NY | K | Wildwood Substation 138kV | LIPA | 0 | 2020-04-30
0824 | Wildwood Energy Storage, LLC | Wildwood Shoreham Energy Storage | 2019-04-15 | 76.9 | 76.9 | ES | Suffolk | NY | K | Shoreham Substation 69kV | LIPA | 0 | 2020-04-30
0825 | Setauket Energy Storage, LLC | Setauket Energy Storage | 2019-04-15 | 65.3 | 65.3 | ES | Suffolk | NY | K | Port Jefferson - Terryville 69kV | LIPA | 0 | 2025-01-31
0826 | NRG Astoria Storage LLC | Astoria Energy Storage 1 | 2019-04-18 | 40 | 40 | ES | Queens | NY | J | North Queens 27kV Bus | ConEd | 0 | 2023-01-31
0829 | NRG Arthur Kill Storage LLC | Arthur Kill Energy Storage 2 | 2019-04-24 | 60 | 60 | ES | Richmond | NY | J | Arthur Kill 138kV | ConEd | 0 | 2020-01-31
0830 | NRG Astoria Storage LLC | Astoria Energy Storage 2 | 2019-04-26 | 79.9 | 79.9 | ES | Queens | NY | J | Astoria West 138kV Substation | ConEd | 0 | 2023-01-31
0831 | Dimension NY 1 LLC | NY-19-0002 Sheredy | 2019-04-29 | 10.2 | 10.2 | ES | Broome | NY | C | Northside Substation 34.5kV | NYSEG | 0 | 2020-01-31
0836 | Astoria Generating Company, LP | Dock Battery Energy Storage 2 | 2019-05-07 | 56.3 | 56.3 | ES | Queens | NY | J | Astoria East Substation 138kV | ConEd | 0 | 2020-02-29
0837 | Astoria Generating Company, LP | Parking Lot Battery Energy Storage 2 | 2019-05-07 | 79 | 79 | ES | Queens | NY | J | Astoria East Substation 138kV | ConEd | 0 | 2020-02-29
0838 | NRG Astoria Storage LLC | Astoria Energy Storage 3 | 2019-05-09 | 20 | 20 | ES | Queens | NY | J | North Queens 27kV Substation | ConEd | 0 | 2023-01-31
0839 | NRG Astoria Storage LLC | Astoria Energy Storage 4 | 2019-05-09 | 20 | 20 | ES | Queens | NY | J | Astoria West 138kV Substation | ConEd | 0 | 2020-02-29
0840 | Hecate Grid Swiftsure LLC | Swiftsure Energy Storage | 2019-05-09 | 650 | 650 | ES | Richmond | NY | J | Fresh Kills 345kV | ConEd | 0 | 2024-11-30
0841 | TJA Clean Energy, LLC | Sharon Springs Interconnection | 2019-05-10 | 20 | 20 | S | Schoharie | NY | F | Sharon - Cobleskill 69kV Substation | NM-NG | 0 | 2021-07-31
0842 | Mitsubishi Hitachi Power Systems Americas, Inc. | Comet Solar | 2019-05-17 | 20 | 20 | S | Monroe | NY | B | Mortimer - Golah 115kV | NM-NG | 0 | 2020-01-31
0844 | Boralex US Development, LLC | NY37 Energy Storage | 2019-05-17 | 4 | 4 | ES | Jefferson | NY | E | Coffeen - West Adams 115kV Substation | NM-NG | 0 | 2020-12-31
0845 | sPower Development Company, LLC | Bloom Energy Storage Center | 2019-05-20 | 120 | 120 | ES | Kings | NY | J | Farragut 345kV Substation | ConEd | 0 | 2020-03-31
0846 | sPower Development Company, LLC | Rescue Energy Storage Center | 2019-05-20 | 300 | 300 | ES | NY | NY | J | East 13th Street 138kV Substation | ConEd | 0 | 2020-04-30
0847 | sPower Development Company, LLC | Chelsea Energy Storage Center | 2019-05-20 | 300 | 300 | ES | NY | NY | J | West 49th St Substation 345kV | ConEd | 0 | 2020-04-30
0851 | ConnectGen Madison County LLC | Madison County Solar | 2019-05-23 | 20 | 20 | S | Madison | NY | E | Bouckville Substation | NYSEG | 0 | 2020-01-31
0852 | Niagara Dolomite Solar, LLC | Niagara Dolomite Solar | 2019-05-24 | 180 | 180 | S | Niagara | NY | A | Robinson Rd - Stolle Rd 230kV | NYSEG | 0 | 2024-12-31
0853 | Boralex US Development, LLC | NY16 Solar | 2019-05-24 | 20 | 20 | S | Washington | NY | F | Mohican - Schaghticoke 115kV | NM-NG | 0 | 2021-03-31
0854 | Boralex US Development, LLC | NY16 Energy Storage | 2019-05-24 | 4 | 4 | ES | Washington | NY | F | Battenkill - Mohican 115kV | NM-NG | 0 | 2019-10-04
0856 | Boralex US Development, LLC | NY13 Energy Storage | 2019-05-24 | 4 | 4 | ES | Washington | NY | F | Battenkill - Mohican 115kV | NM-NG | 0 | 2019-10-04
0857 | EDF Renewables Development, Inc. | Columbia Solar Energy Center | 2019-05-28 | 350 | 350 | S | Herkimer | NY | E | Edic - Fraser 345kV | NYPA | 0 | 2024-05-31
0858 | EDF Renewables Development, Inc. | Genesee Road Solar Energy Center | 2019-05-28 | 250 | 250 | S | Erie | NY | A | Stolle Rd - Five Mile Rd 345kV | NYSEG | 0 | 2024-12-31
0859 | EDF Renewables Development, Inc. | Ridge View Solar Energy Center | 2019-05-28 | 350 | 350 | S | Niagara | NY | A | Somerset - Dysinger 345kV | NYSEG | 0 | 2024-12-31
0860 | EDF Renewables Development, Inc. | Rosalen Solar Energy Center | 2019-05-28 | 200 | 200 | S | Steuben | NY | B | Clay - Pannell 345kV | NYPA | 0 | 2024-07-31
0861 | Mitsubishi Hitachi Power Systems Americas, Inc. | Tonawanda Solar | 2019-05-29 | 20 | 20 | S | Niagara | NY | B | Lockport - Batavia 115kV | NM-NG | 0 | 2020-12-31
0862 | Mitsubishi Hitachi Power Systems Americas, Inc. | Farwell Solar | 2019-05-29 | 20 | 20 | S | Orleans | NY | B | Lockport - Mortimer 115kV | NM-NG | 0 | 2021-02-28
0866 | NY North Country, LLC | North Country Wind | 2019-06-03 | 298.2 | 298.2 | W | Franklin | NY | D | Willis - Moses 230 kV MW1 | NYPA | 0 | 2024-12-31
0867 | Somerset Solar Development LLC | Somerset Solar Development LLC | 2019-06-03 | 20 | 20 | S | Niagara | NY | A | Kintigh 345kV | NYSEG | 0 | 2020-01-31
0868 | Cayuga Solar LLC | Cayuga Solar LLC | 2019-06-03 | 19.9 | 19.9 | S | Cayuga | NY | C | Milliken Substation | NYSEG | 0 | 2020-01-31
0869 | SunEast Tabletop Solar LLC | Tabletop Solar | 2019-06-04 | 80 | 80 | S | Montgomery | NY | F | Clinton - Clinton Tap 115 kV | NM-NG | 0 | 2024-12-31
0871 | Invenergy Solar Project Development LLC | Verona Solar Energy Center I | 2019-06-05 | 250 | 250 | S | Oneida | NY | C | Clay - Edic 345kV | NYPA | 0 | 2024-06-30
0872 | Invenergy Solar Project Development LLC | Taproot Solar Energy Energy | 2019-06-05 | 300 | 300 | S | Montgomery | NY | E | Porter - Rotterdam 230kV | NM-NG | 0 | 2019-12-31
0873 | Invenergy Solar Project Development LLC | Verona Solar Energy Center II | 2019-06-05 | 250.0 | 250.0 | S | Oneida | NY | C | Clay - Edic 345kV | NYPA | 0 | 2024-05-31
0875 | SL Portland, LLC | SL Portland Solar | 2019-06-06 | 19.9 | 19.9 | S | Chautauqua | NY | A | Dunkirk - Falconer 115 kV | NM-NG | 0 | 2020-04-30
0876 | SL Selkirk, LLC | SL Selkirk Solar | 2019-06-06 | 19.9 | 19.9 | S | Albany | NY | F | New Scotland - Alps 345kV | NM-NG | 0 | 2019-10-31
0877 | SL York, LLC | SL York Solar | 2019-06-06 | 19.9 | 19.9 | S | Livingston | NY | B | Golah - S. Perry 115 kV | NM-NG | 0 | 2020-04-30
0878 | Energy Storage Resources, LLC | Pirates Island | 2019-06-10 | 100 | 100 | ES | Erie | NY | A | Huntley - Gardenville 115kV | NM-NG | 0 | 2024-09-30
0879 | Empire Community Solar LLC | Holley Road Solar | 2019-06-10 | 19.9 | 19.9 | S | Orleans | NY | B | Lockport - Mortimer 115kV | NM-NG | 0 | 10/31/22
0881 | New Bremen Solar, LLC | New Bremen Solar | 2019-06-10 | 100 | 100 | S | Lewis | NY | E | Bremen - Lowville 115kV | NM-NG | 0 | 2023-12-31
0884 | Dimension NY 1 LLC | Blooming Farm LLC | 2019-06-12 | 10.2 | 10.2 | ES | Orange | NY | G | Blooming Grove Substation 69kV | O&R | 0 | 2019-10-04
0886 | Empire State Land Holdings, LLC | Turin Highlands Solar | 2019-06-12 | 20 | 20 | S | Oneida | NY | E | Taylorville - Boonville 115kV | NM-NG | 0 | 2019-07-31
0888 | Sky Solar Inc. | Hornell Center 16 | 2019-06-13 | 17.6 | 17.6 | S | Allegany | NY | C | Moraine Substation 115kV | NYSEG | 0 | 2019-10-31
0889 | Energy Storage Resources, LLC | Peconic River II | 2019-06-20 | 19.2 | 19.2 | ES | Suffolk | NY | K | 8RX Moriches | LIPA | 0 | 2019-08-31
0890 | Energy Storage Resources, LLC | Queen City | 2019-06-20 | 19.2 | 19.2 | ES | Dutchess | NY | K | Knapps Corners | CHGE | 0 | 2019-10-04
0891 | Energy Storage Resources, LLC | Meredith Woods | 2019-06-24 | 19.2 | 19.2 | ES | NY | NY | J | Baron Blvd | ConEd | 0 | 2019-10-04
0892 | FourGen LLC | Holtsville Fuel Cell | 2019-07-15 | 20 | 20 | FC | Suffolk | NY | K | Holtsville 69kV | LIPA | 0 | 2020-07-31
0893 | FourGen LLC | Setauket Fuel Cell | 2019-07-15 | 20 | 20 | FC | Suffolk | NY | K | Terryville Substation 69kV | LIPA | 0 | 2020-07-31
0894 | Montgomery Energy Storage 1, LLC | Montgomery Energy Storage | 2019-07-15 | 20 | 20 | ES | Orange | NY | G | Walden - Montgomery 69kV | CHG&E | 0 | 2020-05-31
0895 | Dimension NY 1 LLC | Road Property | 2019-07-15 | 19.9 | 19.9 | ES | Suffolk | NY | K | Central Islip 138kV | LIPA | 0 | 2020-01-31
0896 | Sky Solar Inc. | Hornell Center 16 BESS | 2019-07-18 | 8 | 8 | ES | Allegany | NY | C | Moraine Substation 115kV | NYSEG | 0 | 2019-10-31
0897 | Mitsubishi Hitachi Power Systems Americas, Inc. | Bluejay Solar | 2019-08-01 | 5 | 5 | S | Allegany | NY |  |  | RG&E | 0 | 2019-10-31
0898 | Mitsubishi Hitachi Power Systems Americas, Inc. | Oak Orchard Solar | 2019-08-01 | 5 | 5 | S | Orleans | NY | A, B | Shelby | NM-NG | 0 | 2019-12-31
0900 | Granada Solar, LLC | Fowler Solar | 2019-08-09 | 20 | 20 | S | Madison | NY | E | Fenner - Whitman 115kV | NM-NG | 0 | 2020-02-29
0901 | TJA Clean Energy, LLC | Lacona Solar | 2019-08-16 | 20 | 20 | S | Oswego | NY | E | Lighthouse Hill - Black River 115kV | NM-NG | 0 | 2021-12-31
0902 | sPower Development Company, LLC | Yacht Club Energy Storage | 2019-08-16 | 300 | 300 | ES | NY | NY | J | Gowanus 345kV | ConEd | 0 | 2021-04-30
0903 | sPower Development Company, LLC | Goethals Energy Storage | 2019-08-16 | 300 | 300 | ES | NY | NY | J | Goethals 345kV | ConEd | 0 | 2021-04-30
0904 | Agilitas Energy, LLC | South Conduit Avenue Energy Storage | 2019-08-20 | 10 | 10 | ES | NY | NY | J | South Conduit Ave | ConEd | 0 | 2019-10-31
0905 | Agilitas Energy, LLC | Liberty Avenue Energy Storage | 2019-08-20 | 10 | 10 | ES | NY | NY | J | Liberty Ave | ConEd | 0 | 2019-10-31
0906 | NRG Arthur Kill Storage LLC | Arthur Kill Energy Storage 2 | 2019-08-28 | 20 | 20 | ES | NY | NY | J | Fresh Kills Substation | ConEd | 0 | 2020-02-29
0908 | NRG Astoria Storage LLC | Astoria Energy Storage 5 | 2019-09-12 | 20 | 20 | ES | Queens | NY | J | North Queens Substation 27kV | ConEd | 0 | 2020-02-29
0909 | PetaWatt Holdings, Inc. | Massena Load | 2019-09-18 | 100 | 100 | L | St. Lawrence | NY | E | Dennison 115kV substation | NM-NG | 0 | 2021-04-30
0910 | Hartley Rd Energy Storage 1, LLC | 114 Hartley Rd-Goshen | 2019-09-24 | 10 | 10 | ES | Orange | NY | G | Hartley Substation 13.2kV | O&R | 0 | 2020-02-29
0911 | Dimension NY 1 LLC | Southold BESS | 2019-10-01 | 20 | 20 | ES | Suffolk | NY | K | Peconic - Southold 69kV | LIPA | 0 | 2022-04-30
0912 | Hecate Grid Intrepid 1 LLC | Intrepid Storage 69 | 2019-10-02 | 50 | 50 | ES | Nassau | NY | K | Barrett to Oil City 33-317 and 33-222 | LIPA | 0 | 2024-07-31
0913 | SED NY Holdings LLC | SunEast Manchester Solar LLC | 2019-10-04 | 20 | 20 | S | Ontario | NY | C | Station 127 (RGE)-Elbridge (NG) 115kV Line #7-983 | NM-NG | 0 | 2024-09-30
0914 | sPower Development Company, LLC | Loomis Creek Solar | 2019-10-07 | 100 | 100 | S | Columbia | NY | F | Churchtown Substation 115 kV | NYSEG | 0 | 2020-04-30
0915 | EDF Renewables Development, Inc. | Staten Island 1 Battery Storage | 2019-10-07 | 20 | 20 | ES | Richmond | NY | J | Fox Hills Substation 33kV | ConEd | 0 | 2020-09-30
0916 | EDF Renewables Development, Inc. | Hartley Battery Storage | 2019-10-07 | 20 | 20 | ES | Orange | NY | G | Hartley Road Substation 69kV | O&R | 0 | 2020-03-31
0917 | sPower Development Company, LLC | Loomis Creek ES | 2019-10-07 | 50 | 50 | ES | Columbia | NY | F | Churchtown Substation 115 kV | NYSEG | 0 | 2020-04-30
0918 | Hecate Grid Intrepid 1 LLC | Intrepid Storage 138 | 2019-10-09 | 250 | 250 | ES | Nassau | NY | K | Barrett to Valley Stream 138-291 & Barrett to Valley Stream 138-292 | LIPA | 0 | 2024-07-31
0919 | sPower Development Company, LLC | White Spring ES | 2019-10-10 | 100 | 100 | ES | Ontario | NY | C | Haley Road Substation 115 kV | NYSEG | 0 | 2021-06-30
0920 | sPower Development Company, LLC | White Spring Solar | 2019-10-10 | 200 | 200 | S | Ontario | NY | C | Haley Road Substation 115 kV | NYSEG | 0 | 2021-06-30
0921 | sPower Development Company, LLC | Line Creek ES | 2019-10-10 | 30 | 30 | ES | Schoharie | NY | F | Schoharie 69 kV | NM-NG | 0 | 2020-04-30
0922 | sPower Development Company, LLC | Line Creek Solar | 2019-10-10 | 50 | 50 | S | Schoharie | NY | F | Schoharie 69 kV | NM-NG | 0 | 2020-04-30
0923 | sPower Development Company, LLC | Far Rockaway Energy Storage Center | 2019-10-11 | 150 | 150 | ES | Queens | NY | K | Far Rockaway Substation 69 kV | LIPA | 0 | 2020-05-31
0924 | RICAL LLC | CBB | 2019-10-15 | 115 | 115 | ES | Dutchess | NY | G | Shenandoah Substation | CHGE | 0 | 2020-06-30
0925 | Hecate Grid Clermont 1 LLC | Clermont 1 | 2019-10-17 | 100 | 100 | ES | Suffolk | NY | K | West Babylon 69kV Substation | LIPA | 0 | 2023-05-31
0926 | Enel Energy Storage Holdings, LLC | Enel NYPA Astoria | 2019-10-18 | 100 | 100 | ES | Queens | NY | J | Astoria 138 kV substation | ConEd | 0 | 1/31/20
0927 | JERA Americas Inc. | Brunswick Energy Storage | 2019-10-21 | 100 | 100 | ES | Union | NJ | J | Goethals Substation 345kV | ConEd | 0 | 1/31/20
0928 | JERA Americas Inc. | Willow Bay Energy Storage | 2019-10-21 | 40 | 40 | ES | Richmond | NY | J | Fox Hills Substation 33kV | ConEd | 0 | 2020-03-31
0929 | EDF Renewables Development, Inc. | Morris Ridge Battery Storage | 2019-10-22 | 83 | 83 | ES | Livingston | NY | C | South Perry - Meyer 230 kV | NYSEG | 0 | 2024-05-31
0933 | Seven Creek Energy, LLC | Seven Creek Energy - Squab Hollow | 2019-10-31 | 290 | 290 | ES | Elk | PA | A | Homer City - Pierce Brook 345kV | NYSEG | 0 | 2021-04-30
0934 | Saturn Energy Storage LLC | Astoria BESS | 2019-10-31 | 70 | 68.6 | ES | Queens | NY | J | Astoria West Substation 138 kV | ConEd | 0 | 2020-04-30
0935 | SED NY Holdings LLC | Augustus Solar | 2019-11-01 | 20 | 20 | S | Oneida | NY | E | Brothertown - Oriskany Falls 46kV | NYSEG | 0 | 2024-11-30
0936 | AE - ESS Petracca, LLC | Petracca Place Energy Storage | 2019-11-01 | 10 | 10 | ES | Queens | NY | J | Corona 4kV | ConEd | 0 | 2020-05-31
0937 | Boralex US Development, LLC | NYSD Energy Storage | 2019-11-04 | 5.5 | 5.5 | ES | Saratoga | NY | F | Mechanicville 34.5 kV | NM-NG | 0 | 2020-03-31
0938 | KCE NY 12, LLC | KCE NY 12 | 2019-11-04 | 100 | 100 | ES | Suffolk | NY | K | Moriches Substation 69kV | LIPA | 0 | 2020-03-31
0939 | National Grid Generation LLC | Far Rockaway Power Station Battery Energy Storage System (BESS) | 2019-11-05 | 30 | 30 | ES | Queens | NY | K | Far Rockaway 69kV | LIPA | 0 | 2024-05-31
0940 | National Grid Generation LLC | Glenwood Power Station Battery Energy Storage System | 11/8/2019 | 50 | 50 | ES | Nassau | NY | K | Glenwood Substation (4YH) 138kV bus | LIPA | 0 | 2023-03-31
0941 | National Grid Generation LLC | Southampton Power Station Battery Energy Storage System (BESS) | 2019-11-08 | 30 | 30 | ES | Suffolk | NY | K | Southampton 69kV | LIPA | 0 | 2024-05-31
0942 | KCE NY 21, LLC | KCE NY 21 | 2019-11-08 | 60 | 60 | ES | Suffolk | NY | K | Pulaski 69kV | LIPA | 0 | 2024-05-31
0943 | Vistra Operations Company, LLC | Sithe Independence BESS | 2019-11-08 | 20 | 20 | ES | Oswego | NY | C | Sithe Independence 345kV | NM-NG | 0 | 2020-03-31
0944 | Invenergy Solar Development LLC | Verona Storage | 2019-11-12 | 100 | 100 | ES | Oneida | NY | C | Edic-Clay 345kV Line | NYPA | 0 | 2020-05-31
0945 | Niagara Grid I, LLC | Niagara Grid I | 2019-11-13 | 20 | 20 | ES | Erie | NY | A | Huntley - Praxair 115 kV Line #47 | NM-NG | 0 | 2024-06-30
0946 | Dimension NY 1 LLC | Helmer | 2019-11-14 | 21.3 | 21.3 | ES | Herkimer | NY | E | Old Forge - Raquette Lake 46 kV | NM-NG | 0 | 2020-01-31
0947 | Dimension NY 1 LLC | Livonia BESS | 2019-11-16 | 11.3 | 11.3 | ES | Livingston | NY | B | North Lakeville 34.5kV | NM-NG | 0 | 2022-10-31
0948 | Dimension NY 1 LLC | Webster BESS | 2019-11-18 | 8.8 | 8.8 | ES | Monroe | NY | B | 34.5 kV | RG&E | 0 | 2020-05-31
0949 | National Grid Generation LLC | Port Jefferson Power Station Battery Energy Storage System (BESS) | 2019-11-19 | 100 | 100 | ES | Suffolk | NY | K | Port Jefferson 138kV | LIPA | 0 | 2024-05-31
0951 | Cayuga Grid, LLC | Cayuga Grid, LLC | 2019-12-04 | 100 | 100 | ES | Erie | NY | A | New Gardenville 115kV Substation | NYSEG | 0 | 2023-04-30
0952 | Catskill Grid, LLC | Catskill Grid, LLC | 2019-12-04 | 100 | 100 | ES | Greene | NY | G | North Catskill - Milan 115kV | CHG&E | 0 | 2024-12-31
0954 | Empire Solar, LLC | Empire Solar | 2019-12-05 | 157.9 | 150 | S | Westfield | NY | A | South Ripley - Dunkirk 230 kV | NM-NG | 0 | 2024-05-31
0955 | VESI 26 LLC | Craillo Plaza | 2019-12-06 | 20 | 20 | ES | Rensselaer | NY | F | NGrid Rensselaer 34.5/ 13.2KV Substation | NM-NG | 0 | 2020-02-29
0957 | Holbrook Energy Storage, LLC | Holbrook Energy Storage | 2019-12-10 | 76.8 | 76.8 | ES | Suffolk | NY | K | Holtsville - Patchogue 69kV | LIPA | 0 | 2025-01-31
0958 | Empire Offshore Wind LLC | EI Oceanside | 2019-12-10 | 96 | 96 | W | Nassau | NY | K | Barrett - Valley Stream 138 kV Lines | LIPA | 0 | 2023-02-28
0959 | Empire Offshore Wind LLC | EI Oceanside 2 | 2019-12-11 | 1260 | 1260 | W | Nassau | NY | K | Barrett - Valley Stream 138 kV Lines | LIPA | 0 | 2024-04-30
0960 | SWEB Development USA, LLC | Cobleskill Solar | 2019-12-12 | 20 | 20 | S | Schoharie | NY | F | Cobleskill - Schoharie 69KV | NM-NG | 0 | 2023-10-31
0961 | Calpine Mid Atlantic Development, LLC | Bethpage Battery Energy Storage System | 2019-12-18 | 20 | 20 | ES | Nassau | NY | K | Grumman 69 kV | LIPA | 0 | 2024-10-31
0962 | Brookfield Power US Asset Management LLC | Beardslee Solar | 2019-12-19 | 20 | 20 | S | Herkimer | NY | E | St. Johnsville - Inghams 115kV | NM-NG | 0 | 11/30/22
0963 | Invenergy Storage Development LLC | Crooked Lake Storage | 2019-12-19 | 7 | 7 | ES | Yorktown | NY | H | Mohansic 13.2kV Substation | NYSEG | 0 | 2020-04-30
0964 | Invenergy Storage Development LLC | Berry Place Storage | 2019-12-20 | 10 | 10 | ES | Livingston | NY | A | Lakeville 34.5kV substation | NM-NG | 0 | 2020-01-31
0965 | Yaphank Energy Storage, LLC | Yaphank Energy Storage | 2019-12-21 | 76.8 | 77.6 | ES | Suffolk | NY | K | William Floyd - Brookhaven 69kV | LIPA | 0 | 2025-02-28
0966 | West Babylon Energy Storage, LLC | West Babylon Storage | 2019-12-21 | 40.3 | 40.3 | ES | Suffolk | NY | K | West Babylon - Lindenhurst 69kV | LIPA | 0 | 2024-05-31
0968 | SED NY Holdings LLC | Gouverneur Solar Project | 2020-01-09 | 20 | 20 | S | St. Lawrence | NY | E | North Gouverneur - Battle Hill 115kV | NM-NG | 0 | 2020-05-31
0969 | esVolta, LP | Modena Energy Storage I | 2020-01-09 | 6 | 6 | ES | Ulster | NY | G | Modena Substation | CHGE | 0 | 2020-02-29
0970 | esVolta, LP | Modena Energy Storage II | 2020-01-09 | 6 | 6 | ES | Ulster | NY | G | Modena Substation | CHGE | 0 | 2020-02-29
0972 | SWEB Development USA, LLC | Warner Hill Solar | 2020-01-10 | 20 | 20 | S | Schoharie | NY | F | Middleburg Tap - Middleburg 69kV | NM-NG | 0 | 2023-09-30
0973 | Wildwood Energy Storage, LLC | Wildwood-Riverhead Energy Storage | 2020-01-13 | 293.5 | 297.9 | ES | Suffolk | NY | K | Wildwood-Riverhead 138 kV | LIPA | 0 | 2021-08-30
0974 | KCE NY 19 LLC | KCE NY 19 | 2020-01-14 | 80 | 80 | ES | Orange | NY | G | Sugarloaf - Wisner 69kV | O&R | 0 | 2024-12-31
0975 | Dimension NY 1 LLC | Webb BESS | 2020-01-15 | 20 | 20 | ES | Herkimer | NY | E | Old Forge-Raquette Lake 46 kV | NM-NG | 0 | 2020-06-30
0976 | Invenergy Storage Development LLC | Esopus Valley Storage | 2020-01-16 | 10 | 10 | ES | Ulster | NY | G | Hurley Ave 34.5kV Substation | CHGE | 0 | 2020-04-30
0977 | Dimension NY 1 LLC | Dutchess BESS | 2020-01-16 | 6.6 | 6.6 | ES | Dutchess | NY | G | Pawling - Haviland Hollow 46kV | NYSEG | 0 | 2020-05-31
0978 | Hydroelectric Corporation | NY Hydro-Kinetic Project 1 | 2020-01-18 | 550 | 480 | H | Kings | NY |  | Sayreville Station 345kV |  | 0 | 2020-03-31
0980 | Invenergy Storage Development LLC | Heritage Storage | 2020-01-22 | 8 | 8 | ES | Erie | NY | A | Erie 34.5kV Substation | NYSEG | 0 | 2020-08-31
0981 | Invenergy Storage Development LLC | Oblong Storage | 2020-01-22 | 6 | 6 | ES | Dutchess | NY | G | Pawling 46kV Substation | NYSEG | 0 | 9/30/20
0982 | National Grid Generation LLC | West Babylon Power Station Battery Energy Storage System | 2020-01-22 | 50 | 50 | ES | Suffolk | NY | K | West Babylon 69kV | LIPA | 0 | 2024-05-31
0983 | JERA Americas Inc. | Winter Drive Energy Storage | 2020-01-28 | 8 | 8 | ES | Lancaster | NY | A | Erie Street Substation -34.5kV | NYSEG | 0 | 2020-05-31
0984 | JERA Americas Inc. | Empire Energy Storage | 2020-01-28 | 8 | 8 | ES | Monroe | NY | B | Station 55 34.5kV | RG&E | 0 | 2020-05-31
0985 | JERA Americas Inc. | Bristol Energy Storage | 2020-01-28 | 6 | 6 | ES | Ontario | NY | B | 34.5kV line | RG&E | 0 | 2020-05-31
0986 | JERA Americas Inc. | Pawling Energy Storage | 2020-01-29 | 6 | 6 | ES | Putnam | NY | G | 46kV line | NYSEG | 0 | 2020-05-31
0988 | Saturn Energy Storage LLC | Lancaster BESS | 2020-01-30 | 8 | 8 | ES | Erie | NY | A | Cemetery Rd - Erie St 34.5 kV | NYSEG | 0 | 2020-07-31
0989 | Saturn Energy Storage LLC | Pawling BESS | 2020-01-30 | 6 | 6 | ES | Dutchess | NY | H | Pawling-Corbin Rd 46 kV | NYSEG | 0 | 2020-07-31
0990 | Saturn Energy Storage LLC | Mohansic BESS | 2020-01-30 | 7 | 7 | ES | Westchester County | NY | H | The 13.2 kV 403 (1106340) line from Mohansic Substation running along Baldwin Rd | NYSEG | 0 | 2020-03-31
0991 | Saturn Energy Storage LLC | Bristol BESS | 2020-01-30 | 6 | 6 | ES | Ontario | NY | B | S Bristol-State Rt 28 34.5 kV | RG&E | 0 | 2020-07-31
0992 | KCE NY 25, LLC | KCE NY 25 | 2020-01-31 | 6 | 6 | ES | Ontario | NY | B | Station 146 34.5kV | RG&E | 0 | 2020-06-30
0993 | VESI 30 LLC | Empire Energy Storage | 2020-01-31 | 10 | 10 | ES | Monroe | NY | B | Station 55 - Station 73 34.5kV | RG&E | 0 | 2022-09-30
0994 | KCE NY 22, LLC | KCE NY 22 | 2020-02-12 | 90 | 90 | ES | Suffolk | NY | K | Holbrook - Sills Road 138kV | LIPA | 0 | 2024-05-31
0996 | SWEB Development USA, LLC | East Otto Solar Project | 2020-02-28 | 20 | 20 | S | Cattaraugus | NY | A | Line 803 near Snake Run Road | NM-NG | 0 | 2020-06-30
0997 | 212 Solar Development, LLC | 187 Finchville Turnpike, Mount Hope | 2020-03-05 | 20 | 20 | ES | Orange | NY | G | Cuddleback - Shoemaker 69kV | O&R | 0 | 9/30/20
0998 | 212 Solar Development, LLC | 0 Highland Lake Rd - Wallkill | 2020-03-05 | 20 | 20 | ES | Orange | NY | G | Cuddleback - Shoemaker 69kV | O&R | 0 | 2020-10-31
0999 | Suffolk BESS LLC | Suffolk BESS | 2020-03-06 | 79.7 | 79.7 | ES | Suffolk | NY | K | Port Jefferson 69 kV Substation | LIPA | 0 | 2020-09-30
1001 | Empire State Connector LLC | Empire State Connector II | 2020-03-20 | 1250 | 1250 | DC | Onondaga-NY | NY | E, J | Marcy - Rainey 345 kV | NYPA/ConEd | 0 | 2022-08-31
1002 | 212 Solar Development, LLC | 2143 Mount Hope Road | 2020-04-03 | 20 | 20 | ES | Orange | NY | G | Cuddleback - Shoemaker | O&R | 0 | 2020-10-31
1004 | Renewable Energy Aggregators, Inc. | Mifflin | 2020-04-13 | 300 | 300 | CR | Sullivan | NY | E | Coopers Corner 345 kV | NYSEG | 0 | 2024-05-31
1005 | sPower Development Company, LLC | East End Energy Storage Center | 2020-04-17 | 51.5 | 51.5 | ES | Suffolk | NY | K | Edwards Ave. 138 kV Substation | LIPA | 0 | 2020-09-30
1006 | NYC Energy | NYC Energy BNY Phase 1 | 2020-04-20 | 79.9 | 79.9 | ES | Kings | NY | J | Hudson Ave Substation | ConEd | 0 | 2020-12-31
1008 | KCE NY 26, LLC | KCE NY 26 | 2020-04-28 | 60 | 60 | ES | Suffolk | NY | K | Jamesport - Peconic 69kV | LIPA | 0 | 2024-05-31
1010 | OCS-A 0522, LLC | Vineyard Wind I | 2020-04-30 | 1403 | 1403 | W | Nassau | NY | K | East Garden City 345kV | NYPA | 0 | 2024-05-31
1011 | OCS-A 0522, LLC | Vineyard Wind II | 2020-04-30 | 1403 | 1403 | W | Suffolk | NY | K | Ruland Road 138kV | LIPA | 0 | 2024-05-31
1012 | Suffolk County Energy Storage II | Suffolk County Storage II | 2020-05-04 | 76.8 | 76.8 | ES | Suffolk | NY | K | Southold 69 kV | LIPA | 0 | 2025-01-31
1013 | Barrett Ridge Energy, LLC | Barrett Ridge Energy - PARs | 5/5/2020 | 168 | 168 | AC | Orange | NY | G | Sugarloaf 138 kV | O&R | 0 | 2023-04-30
1014 | ConnectGEN Chautauqua County LLC | South Ripley BESS | 2020-05-05 | 20 | 20 | ES | Chautauqua | NY | A | South Ripley 230kV substation | NM-NG | 0 | 5/31/21
1016 | Beacon Wind LLC | EI Steinway 1 | 2020-05-19 | 1300 | 1300 | W | Queens | NY | J | Mott Haven - Rainey 345 kV Circuits | ConEd | 0 | 2024-09-30
1017 | Beacon Wind LLC | EI Steinway 2 | 2020-05-19 | 1300 | 1300 | W | Queens | NY | J | Mott Haven - Rainey 345 kV Circuits | ConEd | 0 | 2024-09-30
1018 | Naturgy Candela DevCo LLC | Stone Mill Solar | 2020-05-21 | 20 | 20 | CR | Columbia | NY | F | Churchtown 115 kV | NYTransco | 0 | 2024-04-30
1019 | Naturgy Candela DevCo LLC | Marshville Solar | 2020-05-21 | 20 | 20 | CR | Montgomery | NY | F | Marshville 69 kV | NM-NG | 0 | 2023-10-31
1020 | Beacon Wind LLC | EI Fort Salonga | 2020-05-21 | 1300 | 1300 | W | Suffolk | NY | K | Northport 138 kV | LIPA | 0 | 2024-05-31
1021 | Beacon Wind LLC | EI East Shoreham | 2020-05-27 | 1300 | 1300 | W | Suffolk | NY | K | Shoreham 138 kV | LIPA | 0 | 2024-05-31
1022 | Beacon Wind LLC | EI Glenwood Landing | 2020-05-27 | 1300 | 1300 | W | Nassau | NY | K | Shore Road 345 kV | LIPA | 0 | 2024-05-31
1023 | KCE NY 27, LLC | KCE NY 27 | 2020-06-02 | 50 | 50 | ES | Suffolk | NY | K | Tiana - Quogue 69kV | LIPA | 0 | 2024-05-31
1024 | Renewable Energy Aggregators, Inc. | Cuomo Hydro 1 | 2020-06-03 | 300 | 300 | PS | Westchester | NY | H | Millwood 345kV Substation | ConEd | 0 | 2021-03-31
1025 | Renewable Energy Aggregators, Inc. | Cuomo Hydro 2 | 2020-06-03 | 300 | 300 | PS | Westchester | NY | I | Dunwoodie 345kV Substation | ConEd | 0 | 2021-03-31
1026 | Oriden LLC | Bonny Hill Solar | 2020-06-05 | 20 | 20 | S | Steuben | NY | C | Bath - Bath Muni 34.5 kV | NYSEG | 0 | 2020-09-30
1027 | Naturgy Candela DevCo LLC | Knickerbocker Solar | 2020-06-08 | 20 | 20 | CR | Rensselaer | NY | F | Schodack - Falls Park 115 kV Line #14 | NM-NG | 0 | 2024-05-31
1028 | Excelsior Reserve Energy | Raquette Lake Energy Storage | 2020-06-09 | 20 | 20 | ES | Hamilton | NY | E | Old Forge - Raquette Lake 46kV | NM-NG | 0 | 2022-06-30
1029 | Naturgy Candela DevCo LLC | Half Moon Solar | 2020-06-11 | 20 | 20 | CR | Rensselaer | NY | F | Valkin - Greenbush 115kV | NM-NG | 0 | 2024-05-31
1030 | Boralex US Development | NY109 Solar | 2020-06-15 | 20 | 20 | S | Fulton | NY | F | Stoner - Rotterdam 115kV | NM-NG | 0 | 2023-06-30
1032 | 212 Solar Development, LLC | 129 Round Hill Road | 2020-06-19 | 20 | 20 | ES | Orange | NY | G | Blooming Grove substation | O&R | 0 | 2020-10-31
1033 | 212 Solar Development, LLC | E Main Street, Wallkill | 2020-06-19 | 20 | 20 | ES | Ulster | NY | G | Shoemaker - E Wallkill line | O&R | 0 | 2020-10-31
1034 | 212 Solar Development, LLC | 30-35-90 Zwart Ln - Walden | 2020-06-19 | 20 | 20 | ES | Orange | NY | G | CHG&E WM Line | CHGE | 0 | 2020-08-31
1035 | Easton Solar LLC | NY08 Solar | 2020-06-22 | 20 | 20 | S | Washington | NY | F | Battenkill Substation 34.5kV | NM-NG | 0 | 2024-01-31
1036 | Juno Power Management LLC | Mainesburg ESS | 2020-06-22 | 130 | 130 | ES | Tioga | PA | C | Mainesburg - Watercure 345kV | NYSEG | 0 | 2024-10-31
1038 | ELP Rotterdam Solar LLC | ELP Rotterdam Solar | 2020-06-23 | 20 | 20 | S | Schenectady | NY | F | Rotterdam - Meco 115kV | NM-NG | 0 | 2024-03-31
1040 | Riverline Energy Center, LLC | Riverline Energy Center | 2020-06-24 | 200 | 200 | ES | St. Lawrence | NY | E | Moses - Adirondack 230kV | NYPA | 0 | 2024-05-31
1041 | Silverline Energy Center, LLC | Silverline Energy Center | 2020-06-25 | 150 | 150 | CR | Tompkins | NY | C | Miliken - Etna 115 kV lines 974 and 975 | NYSEG | 0 | 2024-05-31
1042 | Fort Edward Solar LLC | Fort Edward Solar Farm (NY53) | 2020-06-26 | 100 | 100 | S | Washington | NY | F | Mohican - Battenkill 115kV Line #15 | NM-NG | 0 | 2024-12-31
1043 | SL Portland, LLC | SL Portland Solar | 2020-06-30 | 19.8 | 19.8 | S | Chautauqua | NY | A | Dunkirk - Falconer 115kV | NM-NG | 0 | 2022-12-31
1044 | Delaware River Solar | Broadway Road | 2020-07-01 | 19.9 | 19.9 | S | Genesee | NY | A | Attica - Darien Lake 34.5kV | NM-NG | 0 | 2020-10-31
1045 | Sunrise Wind LCC | NY Wind Holbrook 2 Uprate | 2020-07-03 | 1050 | 1050 | W | Suffolk | NY | K | Holbrook 138kV | LIPA | 0 | 2024-05-31
1046 | Island Park Energy Center, LLC | Barrett Energy Storage Center | 2020-07-06 | 200.0 | 200 | ES | Nassau | NY | K | Barrett 138 kV | LIPA | 0 | 2024-05-31
1048 | Declaration Energy Center, LLC | Declaration Energy Center | 2020-07-14 | 300 | 300 | S | Seneca | NY | C | Border City 115 kV | NYSEG | 0 | 2024-05-31
1049 | Clean Energy Generation, LLC | Holbrook Energy Center | 2020-07-14 | 150 | 150 | ES | Suffolk | NY | K | Existing Holbrook (8D) 138 kV | LIPA | 0 | 2024-05-31
1050 | Clean Energy Generation, LLC | Holtsville Energy Center | 2020-07-14 | 150 | 150 | ES | Suffolk | NY | K | West Bus 138 kV | LIPA | 0 | 2024-05-31
1052 | Capital Power Solar Holdings LLC | Madison Solar | 2020-07-22 | 20 | 20 | S | Madison | NY | E | Teal-Oneida 115kV (Line#2) | NM-NG | 0 | 2024-02-29
1053 | Hydroelectric Corporation | NY Kinetic Plant 1 | 2020-07-22 | 141.9 | 144 | H | NY | NY | J | Con Edison Gowanus Substation | ConEd | 0 | 2020-08-31
1054 | Birdie Energy Storage, LLC | Birdie Energy Storage | 2020-07-23 | 83 | 83 | ES | Westchester | NY | I | Elmsford 138 kV Substation | ConEd | 0 | 2020-09-30
1055 | SWEB Development USA LLC | Addison Solar | 2020-07-23 | 120 | 120 | S | Steuben | NY | C | Stony Ridge - Sullivan Park 115 kV | NYSEG | 0 | 2024-05-31
1056 | Bay State Wind | NY Wind - Shore Road | 2020-07-27 | 1272 | 1272 | W | Nassau | NY | K | Shore Road 138kV | LIPA | 0 | 2024-05-31
1057 | Bay State Wind | NY Wind - New Bridge Road | 2020-07-27 | 1325 | 1325 | W | Nassau | NY | K | New Bridge Road 138kV | LIPA | 0 | 2020-10-31
1058 | Bay State Wind | NY Wind - Pilgrim | 2020-07-27 | 1276 | 1276 | W | Suffolk | NY | K | Pilgrim Substation 138 kV | LIPA | 0 | 2024-05-31
1059 | ACE DEVCO NC, LLC | Jaton | 2020-07-31 | 16.2 | 16.2 | S | Oswego | NY | C | South Oswego - Clay 115 kV | NM-NG | 0 | 2024-02-29
1060 | AES DE DEVCO NC LLC | Delight Farm | 2020-07-31 | 16.8 | 16.8 | S | Cayuga | NY | C | Union Springs - Aurora 34.5 kV | NYSEG | 0 | 2022-03-31
1061 | ACE DEVCO NC, LLC | Teele | 2020-07-31 | 19.8 | 19.8 | S | St. Lawrence | NY | E | Alcoa - N. Ogdensburg 115 kV | NM-NG | 0 | 2024-12-31
1062 | AES DE DEVCO NC LLC | Hounsfield | 2020-07-31 | 19.8 | 19.8 | S | Jefferson | NY | E | West Adams - Coffeen St 115 kV | NM-NG | 0 | 2022-11-30
1063 | ACE DEVCO NC, LLC | Morrow Farms LLC | 2020-07-31 | 19.8 | 19.8 | S | Jefferson | NY | E | Thousand Island - Coffeen St 115 kV | NM-NG | 0 | 2022-09-30
1064 | AES DE DEVCO NC LLC | K. High | 7/31/2020 | 19.8 | 19.8 | S | Wayne | NY | B | Station 218 - Station 181 34.5kV | RG&E | 0 | 2023-04-30
1065 | Delaware River Solar | Hance Road | 2020-08-03 | 19.9 | 19.9 | S | Wayne | NY | B | Station 13A - Station 121 115kV | RG&E | 0 | 2020-10-31
1066 | Bay State Wind | NY Wind - Mott Haven | 2020-08-04 | 1272 | 1272 | W | Bronx | NY | J | Mott Haven 345 kV | ConEd | 0 | 2024-05-31
1067 | Viridity Energy Solutions, Inc. | Hudson Valley Storage | 2020-08-05 | 20 | 20 | ES | Ulster | NY | G | E Kingston Substation | CHGE | 0 | 2020-10-31
1068 | Juno Power Management LLC | Buchanan Point BESS | 2020-08-05 | 300 | 300 | ES | Westchester | NY | H | Buchanan North Substation 345kV | ConEd | 0 | 2024-10-31
1069 | AES DE DEVCO NC LLC | Richardson Solar | 2020-08-05 | 24 | 22 | S | St. Lawrence | NY |  | Ogdensburg - McIntyre115 kV | NM-NG | 0 | 2021-02-28
1070 | Delaware River Solar | 311 Douglas Road | 2020-08-05 | 19.9 | 19.9 | S | Tompkins | NY | C | Montour Falls-Coddington 115kV | NYSEG | 0 | 2021-02-28
1071 | Delaware River Solar | Katrina Falls | 2020-08-06 | 19.9 | 19.9 | S | Sullivan | NY | E | Coopers Corners-Rock Tavern 345kV | NYPA | 0 | 2021-02-28
1072 | Delaware River Solar | Route 318 | 2020-08-06 | 19.9 | 19.9 | S | Seneca | NY | C | Hook Road - Elbridge 115 kV | NM-NG | 0 | 2021-02-28
1073 | AES DE DEVCO NC LLC | Forrence Orchards | 2020-08-07 | 19.8 | 19.8 | S | Clinton | NY | D | Hallock Hill - Kents Falls 115kV | NYSEG | 0 | 2021-11-30
1074 | Honey Ridge Solar 1 | Honey Ridge Solar | 2020-08-11 | 80 | 80 | S | Jefferson | NY | C, E | Black River 115kV Substation | NM-NG | 0 | 2020-10-31
1075 | Moss Ridge Solar 1 | Moss Ridge Solar | 2020-08-11 | 46 | 46 | S | St. Lawrence | NY | E | Colton - Battle Hill, 115 kV | NM-NG | 0 | 2020-09-30
1076 | Minisink Valley Solar 1, LLC | Minisink Valley Solar | 2020-08-28 | 15 | 15 | S | Orange | NY | G | Shoemaker - Westtown 69kV | O&R | 0 | 2020-10-31
1077 | Rutland Center Solar 1, LLC | Rutland Center Solar | 2020-08-14 | 110 | 110 | S | Jefferson | NY | E | Middle Rd 115 kV | NM-NG | 0 | 2023-04-30
1078 | sPower Development Company, LLC | Cayuga Solar | 2020-08-18 | 207 | 207 | S | Tompkins | NY | C | Milliken 115 kV | NYSEG | 0 | 2021-01-31
1081 | KCE NY 28, LLC | KCE NY 28 | 2020-08-27 | 45 | 45 | ES | Suffolk | NY | K | Riverhead-Tuthill 69kV | LIPA | 0 | 2024-05-31
1082 | CDG Owego 2 | CDG Owego 2, LLC | 2020-08-27 | 19.6 | 19.6 | S | Tioga | NY | C | Line 513 - 34.5KV | NYSEG | 0 | 2021-02-28
1083 | Juno Power Management LLC | Tremont BESS | 2020-08-28 | 300 | 300 | ES | Bronx | NY | J | Tremont 345kV | ConEd | 0 | 2022-07-31
1084 | Juno Power Management LLC | EGC BESS | 2020-08-28 | 300 | 300 | ES | Nassau | NY | K | EGC - Carle Place line #361 and EGC - Roslyn line #362, 138kV | LIPA | 0 | 2024-05-31
1085 | Juno Power Management LLC | Oyster Shore BESS | 2020-08-28 | 500 | 500 | ES | Nassau | NY | K | Shore Road 345kV | LIPA | 0 | 2024-05-31
1086 | Juno Power Management LLC | Buchanan Point BESS II | 2020-08-28 | 500 | 500 | ES | Westchester | NY | H | Buchanan South 345 kV | ConEd | 0 | 2024-05-31
1087 | Attentive Energy LLC | Attentive Energy | 8/31/2020 | 1200 | 1200 | W | Nassau & Kings | NY | K | East Garden City Substation 345kV | NYPA | 0 | 2023-04-30
1088 | ConnectGen Cayuga County LLC | Harvest Hills Solar | 2020-09-01 | 200 | 200 | CR | Cayuga | NY | C | Wright Avenue - Milliken 115kV | NYSEG | 0 | 2024-10-31
1090 | SED NY Holding LLC | Westmorland Solar | 2020-09-04 | 20 | 20 | S | Oneida | NY | E | Yahnundasis - Clinton 46 kV | NM-NG | 0 | 2024-03-31
1091 | ELP Middleburgh Solar LLC | ELP Middleburgh Solar | 2020-09-08 | 20 | 20 | S | Schoharie | NY | F | Middleburgh - Cobleskill 115kV | NM-NG | 0 | 2020-12-31
1092 | SED NY Holding LLC | Hampton Corners Solar | 2020-09-04 | 20 | 20 | S | Livingston | NY | B | Station 128 - Station 7325 115 kV Line #923 | RG&E | 0 | 2024-11-30
1093 | Con Edison Transmission, Inc. | Clean Path NY | 2020-09-10 | 1300 | 1300 | DC | Oneida | NY | E,J | Marcy - Rainey 345kV | ConEd/ NYSEG | 0 | 2021-08-30
1094 | SED NY Holdings LLC | Chase Mills Solar | 2020-09-14 | 20 | 20 | S | St. Lawrence | NY | D | 115kV Line Brady to Alcoa (5.82miles from Brady, 13.9 miles from Alcoa) | NM-NG | 0 | 12/31/20
1095 | Northland Power U.S. Projects | Chautauqua Solar | 2020-09-14 | 20 | 20 | S | Chautauqua | NY | A | Line 123975 | NM-NG | 0 | 2020-10-31
1096 | Northland Power U.S. Projects | Alfred Oaks Solar | 2020-09-14 | 100 | 100 | CR | Allegany | NY | C | Andover - Palmeter 115 kV, Line 932 | NYSEG | 0 | 2025-01-31
1097 | Juno Power Management LLC | Hicksville Storage | 2020-09-16 | 125 | 125 | ES | Nassau | NY | K | Newbridge Road 138kV | LIPA | 0 | 2021-03-31
1098 | SED NY Holdings LLC | Kingbird Solar | 2020-09-16 | 20 | 20 | S | Chatauqua | NY | A | Dunkirk - Silver Creek 115 kV (Line#142) | NM-NG | 0 | 2024-09-30
1099 | Brownfield Group, LLC | Canal Solar | 2020-09-17 | 20 | 20 | S | Madison | NY | E | Bouckville Substation 46kV | NYSEG | 0 | 2020-10-31
1100 | Granada Solar, LLC | Hosmer Solar, LLC | 2020-09-28 | 20 | 20 | S | Rensselaer | NY | F | Schodack - Falls Park 115 kV | NYTransco | 0 | 2024-06-30
1101 | Saturn Energy Storage LLC | Chestertown BESS | 2020-10-01 | 20 | 20 | ES | Warren | NY | F | Chestertown-Warrensburg #6 | NM-NG | 0 | 2021-04-30
1102 | SWEB Development USA | Troupsburg Solar | 2020-10-05 | 20 | 20 | Solar | Steuben | NY | C | Woodhull 34.5 kV | NYSEG | 0 | 2024-04-30
1103 | Cypress Creek Renewables, LLC | Thousand Island Solar | 2020-10-06 | 110 | 110 | S | Jefferson | NY | E | Coffeen Street - Thousand Island 115 KV | NM-NG | 0 | 2024-09-30
1104 | Saturn Energy Storage LLC | Brockport BESS | 2020-10-07 | 20 | 20 | ES | Monroe | NY | A | Brockport - Albion 34.5 kV Line #308 | NM-NG | 0 | 2023-02-28
1106 | Northland Power U.S. Projects | Allegany 2 Battery | 2020-10-16 | 10 | 10 | ES | Allegany | NY | C | Andover - Palmeter 115 kV line | NYSEG/NM-NG | 0 | 2021-02-28
1107 | Juno Power Management LLC | Buchanan Point BESS III | 2020-10-19 | 300 | 300 | ES | Westchester | NY | H | Buchanan 345kV | ConEd | 0 | 4/30/22
1108 | SWEB Development USA, LLC | Bangor Solar | 2020-10-26 | 106.9 | 106.9 | S | Franklin | NY | D | Malone - Nicholville 115kV | NYSEG, NM-NG | 0 | 2024-05-31
1109 | SWEB Development USA, LLC | Worth Wind | 2020-10-27 | 92 | 92 | W | Jefferson | NY | E | E. Watertown - Lighthouse Hill 115kV | NM-NG | 0 | 2024-05-31
1110 | Saturn Energy Storage LLC | Hurley BESS | 2020-10-27 | 20 | 20 | ES | Ulster | NY | G | Hurley Ave Substation, 69 kV | CHGE | 0 | 12/31/20
1111 | Saturn Energy Storage LLC | Kingston BESS | 2020-10-30 | 20 | 20 | ES | Ulster | NY | G | Boulevard Substation 69kV | CHGE | 0 | 12/31/20
1112 | Caithness LI Energy Storage, LLC | CLIES 10MW | 2020-11-18 | 10 | 10 | ES | Suffolk | NY | K | Sills Road 138kV | LIPA | 0 | 10/31/22
1114 | Clean Energy Generation, LLC | Wading River Energy Center | 2020-11-19 | 50 | 50 | ES | Suffolk | NY | K | Wading River 138 kV | LIPA | 0 | 2024-05-31
1116 | Liberty Renewables Inc. | Blue Hill Wind | 2020-11-24 | 25.4 | 27.0 | W | Madison | NY | E | Morrisville 46 kV | NYSEG | 0 | 2024-07-31
1118 | BWBP Origination, LLC | Lyonsdale Marmon Rd | 2020-12-04 | 19 | 19 | S | Lewis | NY | E | Lyonsdale Substation | NM-NG | 0 | 2021-03-31
1119 | Granada Solar, LLC | Fuller Storage | 2020-12-04 | 20 | 20 | ES | Orange | NY | G | East Walden 115kV | CHG&E | 0 | 2024-06-30
1120 | Ravenswood Development, LLC | Catskills Renewable Connector | 2020-12-11 | 1200 | 1200 | DC | Greene/Queens | NY | F, J | New Scotland-Leeds 345kV, Rainey-Farragut | NGrid/ConEd | 0 | 2022-06-30
1121 | Ravenswood Development, LLC | Werner - Ravenswood | 2020-12-11 | 1200 | 1200 | DC | PJM/Queens | NY | J | Rainey - Farragut 345kV | ConEd | 0 | 2022-06-30
1124 | Liberty Renewables | Smokey Ave Wind | 2020-12-22 | 18 | 18 | W | Otsego | NY |  | Worcester - Schenevus 23 kV |  | 0 | 2021-05-31
1126 | ACE DEVCO NC, LLC | Richardson | 2021-01-04 | 19.8 | 19.8 | S | St. Lawrence | NY | E | N. Ogdensburg - McIntyre 115 kV line | NM-NG | 0 | 2023-11-30
1127 | CBB PARK LLC | CBB PARK | 2021-01-20 | 50 | 50 | ES | Dutchess | NY | G | Pleasant Valley 115 kV | CHGE | 0 | 2021-07-31
1128 | Northland Power U.S. Projects | Allegany 2 Battery 2 | 2021-01-21 | 20 | 20 | ES | Allegany | NY | C | Andover-Palmeter 115 kV Line 101990 | NYSEG | 0 | 2023-01-31
1129 | Boundless Energy NY, LLC | Phoenix | 2021-01-21 | 2000 | 2000 | DC | Oneida-Manhattan & Bronx | NY | E, J | Edic & Marcy - W. 49 St & Farragut | NM-NG, NYPA, ConEd | 0 | 2021-07-31
1131 | Avangrid Networks, Inc. | Excelsior Connect - Edic to Rainey | 2021-01-28 | 1310 | 1310 | DC | Oneida-Queens | NY | E, J | Edic - Rainey 345kV | NM-NG, ConEd | 0 | 5/31/22
1132 | Avangrid Networks, Inc. | Excelsior Connect - Edic to Farragut | 2021-01-28 | 1310 | 1310 | DC | Oneida-Brooklyn | NY | E, J | Edic - Farragut 345kV | NM-NG, ConEd | 0 | 2022-03-31
1133 | EDF Renewables Development, Inc. | Moraine Storage | 2021-02-11 | 5 | 5 | ES | Allegany | NY | C | Moraine Road Substation 115 kV | NYSEG | 0 | 2024-01-31
1134 | EDF Renewables Development | Tracy Storage | 2021-02-11 | 5 | 5 | ES | Jefferson | NY | E | Thousand Island - Coffeen 115 kV Line #4 | NM-NG | 0 | 2024-01-31
1135 | EDF Renewables Development, Inc. | Homer Storage | 2021-02-11 | 5 | 5 | ES | Cortland | NY | C | Cortland - Fenner 115kV | NM-NG | 0 | 2023-09-30
1136 | Honey Ridge Solar 1, LLC | Honey Ridge Solar | 2021-02-15 | 125 | 125 | CR | Jefferson | NY | E | Black River 115 kV | NM-NG | 0 | 2024-09-30
1137 | Invenergy Wind Development North America LLC | Salt Rush Wind | 2021-02-16 | 75 | 75 | W | Wyoming | NY | C | Stony Creek 230kV | NYSEG | 0 | 2024-07-31
1138 | Invenergy Solar Project Development LLC | Wintergreen Solar | 2021-02-16 | 75 | 75 | S | Montgomery | NY | F | Marshville 115kV | NM-NG | 0 | 2024-05-31
1139 | Invenergy Solar Project Development LLC | Seventy-Seven Solar | 2021-02-16 | 100 | 100 | S | Wyoming | NY | C | High Sheldon 230kV | NYSEG | 0 | 2024-05-31
1140 | Invenergy Solar Project Development LLC | Taproot Solar | 2021-02-16 | 205 | 205 | S | Montgomery | NY | F | Edic - Princetown 345kV Line# 352 | LS Power/NYPA | 0 | 2024-05-31
1141 | Invenergy Solar Project Development LLC | Twinleaf Solar | 2021-02-16 | 75 | 75 | S | Lewis | NY | E | Coffeen St-Taylorville 115kV | NM-NG | 0 | 2024-06-30
1142 | Minerva Power Connection LLC | Minerva BESS I | 2021-02-16 | 300 | 300 | ES | Manhattan | NY | J | W49th St 345kV | ConEd | 0 | 2024-05-31
1143 | Minerva Power Connection LLC | Minerva BESS II | 2021-02-16 | 600 | 600 | ES | Manhattan | NY | J | W 49th st 345kV | ConEd | 0 | 6/30/21
1144 | Boundless Energy NY, LLC | HG-Phoenix | 2021-02-18 | 2000 | 2000 | DC | Erie, Onondaga,NY, KIngs | NY | A,E,J | Gardenville and Edic/Marcy - W49th St & Farragut | NM-NG/NYPA/ NYSEG/ConEd | 0 | 2021-12-31
1145 | EDF Renewables Development, Inc. | Oceanside Energy Storage | 2021-02-18 | 36 | 36 | ES | Nassau | NY | K | Barrett 138 kV | LIPA | 0 | 2022-10-31
1146 | RWE Clean Energy Development, LLC | Champlain Solar | 2021-02-19 | 100 | 100 | S | Washington | NY | F | Mohican - Whitehall 115 kV Line #13 | NM-NG | 0 | 2024-07-31
1147 | Wawayanda Solar 1, LLC | Wawayanda Solar | 2021-02-26 | 12.6 | 12.6 | S | Orange | NY | G | Westtown to Shoemaker 69 kV Line #11 | O&R | 0 | 2023-10-31
1149 | Con Edison Transmission, Inc. | Clean Path NY II | 2021-03-12 |  |  |  | Delaware/Queens | NY | E, J | Fraser 345kv and Mott Haven 345 kv | NYSEG/ ConEd | 0 | 2021-08-30
1150 | Moss Ridge Solar 1, LLC | Moss Ridge Solar | 2021-03-16 | 60 | 60 | S | St. Lawrence | NY | E | Corning - Battle Hill 115 kV line #4 | NM-NG | 0 | 2025-01-31
1152 | BWC Rexmere Lakes, LLC | Harpersfield Bruce Hill Rd. | 2021-03-18 | 19.9 | 19.9 | S | Delaware | NY | E | Axtell Rd. Substation | NYSEG | 0 | 2021-08-30
1153 | Wood Street Battery Storage LLC | Wood Street Battery Storage | 2021-03-22 | 110 | 110 | ES | Putnam | NY | H | Wood Street 115kV | NYSEG | 0 | 2023-02-28
1154 | OYA Solar CDG LLC | OYA Fort Plain Solar | 2021-03-29 | 115 | 115 | S | Montgomery | NY | F | Clinton Road substation 115 kV | NM-NG | 0 | 2021-07-31
1155 | CHPE LLC | New Scotland Interconnection | 2021-04-02 | 500 | 500 | DC | Albany | NY | F, J | New Scotland Substation | NYPA/ NM-NG | 0 | 4/30/22
1156 | Green Power Energy, LLC | Cody Road Wind Farm | 2021-04-08 | 19.9 | 19.9 | W | Madison | NY | C | Cortland - Fenner Line #3 115 kV | NM-NG | 0 | 1/31/25
1157 | Minerva Power Connection LLC | Minerva Transmission | 2021-04-09 | 1200 | 1200 | DC | Manhattan | NY | J | W 49th St 345kV | ConEd | 0 | 10/31/21
1158 | Tyre Solar Energy Center | Gravel Road Solar | 2021-04-09 | 125.6 | 125 | S | Seneca | NY | C | Elbridge - Hook Rd 115kV | NM-NG/ NYSEG | 0 | 2022-01-31
1159 | Innisfree Storage LLC | Innisfree Storage | 2021-04-14 | 50 | 52.5 | ES | Suffolk | NY | K | Port Jefferson - Mt. Sinai 69 kV | LIPA | 0 | 2024-09-30
1160 | Arcade Solar, LLC | Arcade Solar | 2021-04-16 | 75 | 75 | S | Wyoming | NY | A | Village of Arcade Freedom 115 kV Substation | Village of Arcade | 0 | 2023-12-31
1161 | Garnet Energy Center, LLC, | Garnett Battery Storage | 2021-04-20 | 20 | 20 | ES | Cayuga | NY | B | Pannel - Clay 345 KV | NYPA | 0 | 2022-07-31
1162 | Ontario Valley Solar 1, LLC | Ontario Valley Solar | 4/26/2021 | 135 | 135 | CR | Jefferson | NY | E | Lyme Tap line off the Thousand Island – Coffeen 115 kV Line #4 | NM-NG | 0 | 2023-03-31
1163 | QMB2 Energy Storage, LLC | QMB2 Energy Storage, LLC | 2021-04-27 | 200 | 200 | ES | Queens | NY | J | Jamaica - Valley Stream 138kV | ConEd | 0 | 2024-05-31
1164 | Juno Power Management LLC | Glenwood BESS | 2021-05-05 | 75 | 75 | ES | Nassau | NY | K | Glenwood 4ZH 69kV | LIPA | 0 | 2024-07-31
1165 | West River Solar | West River Solar | 2021-05-07 | 20 | 20 | S | Saratoga | NY | F | Battenkill to Mohican 115kV line#15 | NM-NG | 0 | 2023-06-30
1167 | Clean Path NY LLC | CPNY | 2021-05-11 | 1300 | 1300 | DC | Delaware Queens | NY | E,J | Fraser 345kV sending Rainey 345kV receiving | NYSEG, ConEd | 0 | 2023-05-31
1168 | Invenergy Transmission LLC | CPNY-MH | 2021-05-11 | 1300 | 1300 | DC | Delaware, Bronx | NY | E, J | Fraser - Mott Haven 345kV | NYSEG/ ConEd | 0 | 12/31/21
1169 | Excelsior Energy Center, LLC | Excelsior Battery Storage | 2021-05-11 | 20 | 20 | ES | Genesee | NY | B | Byron 345 kV substation | NYPA | 0 | 2024-04-30
1170 | Tier Four Connector, LLC | Bowline to West 49th Street | 2021-05-12 | 1228 | 1228 | AC | Rockland/NY | NY | G, J | Bowline - West 49th St 345 kV | O&R/ConEd | 0 | 2022-01-31
1171 | ELP Stuyvesant Solar LLC | ELP Stuyvesant Solar | 2021-05-14 | 20 | 20 | S | Columbia | NY | F | Valkin - Falls Park 115 kV line #19 | Transco | 0 | 2024-01-31
1172 | Northland Power US Projects | Cowens Corners Solar | 2021-05-17 | 20 | 20 | CR | Cattaraugus | NY | A | Ellington - Randolph 34.5 kV | NYSEG | 0 | 2021-08-30
1173 | Northland Power US Projects | Christmiller Solar | 2021-05-17 | 20 | 20 | CR | Cattaraugus | NY | A | Dake Hill – Machias 34.5kV | NM-NG | 0 | 12/31/22
1174 | Boralex US Development | NY48 - Diamond Solar | 2021-05-17 | 60 | 60 | S | Herkimer | NY | E | Porter - Valley 115kV | NM-NG | 0 | 2024-12-31
1175 | OW Ocean Winds East, LLC | OW Ocean Winds East 1 | 2021-05-18 | 1200 | 1200 | W | Nassau | NY | K | Ruland Rd 138 kV | LIPA | 0 | 2024-07-31
1176 | OW Ocean Winds East, LLC | OW Ocean Winds East 2 | 2021-05-18 | 1200 | 1200 | W | Nassau | NY | K | Valley Stream 138 kV | LIPA | 0 | 2024-07-31
1177 | Southern Tier Energy Center, LLC | Southern Tier Energy Center | 2022-08-16 | 200 | 200 | ES | Tioga | NY | C | Oakdale to Watercure 345 kV L31 line | NYSEG | 0 | 2024-05-31
1178 | Newport Deerfield Solar LLC | NY115 - Newport Solar | 2021-05-19 | 130 | 130 | S | Oneida | NY | E | Porter - Deerfield 115 kV (Line#9) | NM-NG | 0 | 2024-12-31
1179 | Boralex US Development, LLC | NY38 B Solar | 2021-05-19 | 20 | 20 | S | Jefferson | NY | E | Coffeen - West Adams 115 kV | NM-NG | 0 | 2021-08-31
1180 | Union Energy Center, LLC | Union Energy Center, LLC | 2021-05-20 | 116 | 116 | ES | Putnam | NY | H | Union Valley - Croton Falls 115 kV line #991 | NYSEG | 0 | 2024-12-31
1181 | Northline Energy Center, LLC | Northline Energy Center | 2021-05-20 | 200 | 200 | ES | Clinton | NY | D | Pathnode-Duley 230 kV line | NYPA | 0 | 2024-05-31
1182 | Foothills Solar LLC | NY128 - Foothills Solar | 2021-05-20 | 40 | 40 | S | Fulton | NY | F | Mayfeild-Northville 69kV #8 | NM-NG | 0 | 2024-12-31
1185 | Empire Offshore Wind LLC | EI Empire ESS I | 2021-05-21 | 96 | 96 | ES | Nassau | NY | K | Barrett 138 kV Substation | LIPA | 0 | 2023-09-30
1186 | Empire Offshore Wind LLC | EI Empire ESS II | 2021-05-21 | 1440 | 1440 | CW | Nassau | NY | K | Barrett 138 kV Substation | LIPA | 0 | 6/30/21
1187 | Northland Power US Projects | Balcom Corners | 2021-05-27 | 20 | 20 | CR | Chautauqua | NY | A | Ellington - Frog Valley 34.5 kV | NYSEG | 0 | 2021-09-30
1189 | OW Ocean Winds East, LLC | OW Ocean Winds East 3 | 2021-05-27 | 1600 | 1600 | W | Nassau | NY | K | East Garden City 345 kV | NYPA | 0 | 2024-07-31
1190 | Bluepoint Wind, LLC. | OW Ocean Winds East 4 | 2021-05-28 | 1600 | 1600 | W | Brooklyn | NY | J | Brooklyn Clean Energy Hub 345 kV | ConEd | 0 | 2024-07-31
1191 | Northland Power U.S. Projects | Gunns Corners Solar | 2021-05-31 | 100 | 100 | CR | Jefferson | NY | E | Thousand Islands - Coffeen St. #4 115kV | NM-NG | 0 | 2024-05-31
1192 | OW Ocean Winds East, LLC | OW Ocean Winds East 6 | 2021-06-02 | 1600 | 1600 | W | Manhattan | NY | J | West 49th Street 345 kV | ConEd | 0 | 2024-05-31
1193 | OW Ocean Winds East, LLC | OW Ocean Winds East 5 | 2021-06-02 | 1600 | 1600 | W | Queens | NY | J | Rainey 345 kV | ConEd | 0 | 2024-05-31
1194 | Crane Brook Solar Project | Crane Brook Solar Project, LLC | 2021-06-03 | 130 | 130 | S | Cayuga | NY | C | State St - Clinton Corn 115kV Line | NM-NG | 0 | 2025-01-31
1195 | Dexter Solar, LLC | Dexter Solar | 2021-06-04 | 19.8 | 19.8 | S | Jefferson | NY | E | Dexter 23 kV Substation | NM-NG | 0 | 2021-07-31
1196 | Chelsea Road Energy Storage 1, LLC | Chelsea Energy Storage | 2021-06-07 | 30.4 | 30.4 | ES | Richmond | NY | J | Goethals Substation | ConEd | 0 | 2021-08-31
1197 | Northland Power U.S. Projects | Cold Creek Solar | 2021-06-08 | 120 | 120 | CR | Allegany | NY | B | Sta 162 to Sta 180 115 kV Line #907 | RG&E | 0 | 2023-11-30
1199 | Beacon Wind LLC | EI Steinway 1.1 | 2021-06-09 | 200 | 200 | W | Queens | NY | J | Mott Haven - Rainey 345 kV Circuits | ConEd | 0 | 2024-09-30
1200 | Beacon Wind LLC | EI Steinway 2.1 | 2021-06-09 | 300 | 300 | W | Queens | NY | J | Astoria East 138 kV | ConEd | 0 | 2024-05-31
1201 | PetaWatt Holdings, Inc. | St Lawrence Data and Agricultural Center | 2021-06-10 | 200 | 200 |  | St. Lawrence | NY | D | Dennison 115kV substation | NM-NG | 0 | 2021-08-31
1202 | Calpine Mid-Atlantic Development, LLC | Bethpage Large Battery Energy Storage Project | 2021-06-11 | 24 | 24 | ES | Nassau | NY | K | Grumman 69kV substation | LIPA | 0 | 2024-09-30
1203 | EDF Renewables Development, Inc. | Suffragette Solar Energy Center | 2021-06-14 | 50 | 50 | S | Seneca | NY | C | Hyatt Substation 34.5kV | NYSEG | 0 | 2024-05-31
1204 | Morrow Street Storage 2, LLC | Morrow Street Energy Storage | 2021-06-15 | 38 | 38 | ES | Richmond | NY | J | Goethals Substation | ConEd | 0 | 2021-08-31
1205 | Rocksdrift Energy Center, LLC | Rocksdrift Energy Center | 2021-06-16 | 300 | 300 | S | Herkimer | NY | E | Edic - Princetown 345kV Line 352 | NYPA | 0 | 2023-11-30
1206 | NY Interconnection LLC | NY Interconnection 2 | 2021-06-18 | 1200 | 1200 | W | Queens | NY | J | Rainey-Farragut 345kV line break of lines 61, 62 and 63 | ConEd | 0 | 2024-07-31
1207 | NY Interconnection LLC | NY Interconnection 1 | 2021-06-18 | 1200 | 1200 | DC | NY | NY | J | East 13th Street-Farragut 345 kV line 45 and line 46 | ConEd | 0 | 2024-05-31
1208 | Bluepoint Grid, LLC | Bluepoint Grid | 2021-06-20 | 20 | 20 | ES | Suffolk | NY | K | W. Yaphank - Holtsville 69kV | LIPA | 0 | 2021-11-30
1209 | Equinor Wind US LLC | Battoria | 2021-06-21 | 300 | 300 | ES | Queens | NY | J | Astoria East 138 kV | ConEd | 0 | 2022-03-31
1210 | Northland Power U.S. Projects | Gunns Corners Solar 2 | 2021-06-22 | 40 | 40 | CR | Jefferson | NY | E | Thousand Islands - Coffeen St. #4 115kV | NM-NG | 0 | 2024-05-31
1211 | Emeren US, LLC | Hardscrabble Solar LLC | 2021-06-25 | 19.9 | 19.9 | CR | Clinton | NY | D | Highfalls - Kents Falls 46 kV line L871 | NYSEG | 0 | 2023-05-31
1212 | EMEREN US, LLC | Roosevelt Solar LLC | 2021-06-25 | 19.9 | 19.9 | CR | St. Lawrence | NY | D | Akwesasne Station 825 Substation 34.5kV | NM-NG | 0 | 2024-12-31
1214 | Nexus Renewables U.S. Inc. | Ancram Solar Farm | 2021-06-30 | 20 | 20 | CR | Columbia | NY | G | Pulvers Corners 34.5kV | CHGE | 0 | 2021-08-31
1215 | Renesola Power Holdings LLC | Blank Hill Solar LLC | 2021-07-05 | 19.9 | 19.9 | CR | Livingston | CT | C | Moraine Road 115kV | NYSEG | 0 | 2021-09-30
1216 | ReneSola Power Holdings LLC | Cronk Solar LLC | 2021-07-08 | 19.9 | 19.9 | CR | Schuyler | NY | C | Bath - Montour Falls 115 kV | NYSEG | 0 | 2021-09-30
1217 | Emeren US, LLC | New Boston Solar LLC | 7/9/2021 | 49.9 | 49.9 | CR | Madison | NY | C | Line tap between Teal to Oneida 115 kV Substations (Line #2) | NM-NG | 0 | 2023-04-30
1218 | Farm East LLC | Locke Solar Farm | 2021-07-12 | 19.8 | 19.8 | S | Cayuga | NY | C | NYS-Locke 718 Substation | NYSEG | 0 | 2021-10-31
1219 | Nexamp Solar | 74972 Cicero | 7/26/2021 | 20 | 20 | S | Oneida | NY | C | Clay-Teall Line No.10, 115 kV line | NM-NG | 0 | 2023-03-31
1220 | Fresh Air Energy II | Lincoln ESC | 2021-07-26 | 100 | 100 | ES | Suffolk | NY | K | Holbrook - Saxville 69kV | LIPA | 0 | 2021-11-30
1221 | Anbaric Development Partners, LLC | Long Island Storage Center I | 2021-07-26 | 50 | 50 | ES | Suffolk | NY | K | Brookhaven - 8ER 138 kV | LIPA | 0 | 2023-10-31
1222 | Anbaric Development Partners, LLC | Long Island Storage Center II | 2021-07-26 | 100 | 100 | ES | Suffolk | NY | K | Brookhaven - 8ER 138 kV | LIPA | 0 | 2023-10-31
1223 | Fresh Air Energy II | Moffitt ESC | 2021-07-28 | 100 | 100 | ES | Suffolk | NY | K | Watson to Brightwaters 69kV | LIPA | 0 | 2024-05-31
1224 | Northland Power U.S. Projects | Sunwine Solar | 2021-07-28 | 50 | 50 | CR | Westfield | NY |  | Westfield Electric 115kV |  | 0 | 2021-10-31
1225 | Nexamp Solar | 26338 Westmoreland | 2021-07-29 | 20 | 20 | S | Oneida | NY |  | Oneida - Walesville 115kV | NM-NG | 0 | 2021-09-30
1226 | Nexamp Solar | 47763 Cayuta | 2021-08-04 | 20 | 20 | S | Schuyler | NY | C | Cayuta - Ridge Road 34.5kV Line #501 | NYSEG | 0 | 2024-09-30
1227 | Nexamp Solar | 18405 Scotch Ridge | 2021-08-04 | 20 | 20 | S | Schenectady | NY | F | Rotterdam-Schoharie 69kV line#18 | NM-NG | 0 | 2024-03-31
1228 | SWEB Development USA, LLC | Cuba Wind Project | 2021-08-12 | 86.5 | 86.5 | W | Alleghany | NY | A | Homer Hill - Andover 115 kV Line #157 | NM-NG | 0 | 2024-05-31
1229 | Stonewall Solar, LLC | Stonewall Solar, LLC. | 2021-08-16 | 145 | 145 | S | Delaware | NY | E | Colliers-Delhi 115KV | NYSEG | 0 | 2024-07-31
1231 | ConnectGen Montgomery County LLC | Mill Point Solar II | 2021-08-17 | 100 | 100 | CR | Montgomery | NY | E | New Scotland-Marcy 345kV | NM-NG | 0 | 2024-01-31
1232 | ConnectGen Cayuga County LLC | Harvest Hills Solar II | 2021-08-19 | 50 | 50 | S | Cayuga | NY | C | Wright Avenue - Cayuga 115kV | NYSEG | 0 | 2021-10-31
1233 | ACE Development Company | Maplewood Energy Storage | 2021-08-20 | 250 | 250 | ES | Albany | NY | F | Maplewood - Menands 115kV Line #19 & Maplewood - Reynolds 115kV Line #31 | NM-NG | 0 | 2023-10-31
1234 | ACE Development Company | Horseblock Energy Storage | 2021-08-20 | 100 | 100 | ES | Suffolk | NY | K | West Yaphank 69 kV Substation | LIPA | 0 | 2024-07-31
1235 | ACE Development Company | Peconic Energy Storage | 2021-08-20 | 100 | 100 | ES | Suffolk | NY | K | Holbrook - West Yaphank 69 kV | LIPA | 0 | 2022-12-31
1236 | Gravel Road Solar, LLC | Gravel Road Solar | 2021-08-23 | 128 | 128 | S | Seneca | NY | C | Station 127 (Hook Rd) -Elbridge and Mortimer-Elbridge 115 kV lines | NM-NG | 0 | 2024-12-31
1238 | ConnectGen Cayuga County LLC | Harvest Hills Solar 2 | 2021-08-25 | 100 | 100 | CR | Cayuga County | NY | C | Wright Avenue - Milliken 115kV line | NYSEG | 0 | 2024-07-31
1239 | NY Interconnection LLC | NY Interconnection 3 | 2021-09-02 | 130.3 | 122 | ES | NY | NY | J | Goethals - Fresh Kills 345kV | ConEd | 0 | 2024-05-31
1240 | Astoria Generating Company, L.P. | Gowanus Bay Energy Storage 1 | 2021-09-03 | 100 | 100 | ES | Kings | NY | J | Gowanus 138 kV substation (utilizing the existing feeder 42421) | ConEd | 0 | 2024-05-31
1241 | Astoria Generating Company, L.P. | Gowanus Bay Energy Storage 2 | 2021-09-03 | 49.2 | 49.2 | ES | Kings | NY | J | Feeder 42424 (Existing POI at Gowanus 138 kV) | ConEd | 0 | 2024-05-31
1242 | Light & Power Development, LLC | Ravenswood Energy Storage 3 | 2021-09-03 | 70 | 70 | ES | Queens | NY | J | Vernon 138kV | ConEd | 0 | 2021-11-30
1243 | Astoria Generating Company, L.P. | Whale Square Energy Storage 2 | 2021-09-03 | 95.7 | 95.7 | ES | Kings | NY | J | Greenwood 138kV substation, via Feeder 23162 | ConEd | 0 | 2024-05-31
1244 | Astoria Generating Company, L.P. | Whale Square Energy Storage 3 | 2021-09-03 | 49.2 | 49.2 | ES | Kings | NY | J | Greenwood 138 kV substation, via Feeder 23161 | ConEd | 0 | 2024-05-31
1246 | Hanwha Q CELLS USA | Amber Solar and Storage | 2021-09-14 | 232 | 232 | CR | St. Lawrence County | NY | D | Moses - Massena MMS 1 230kV | NYPA | 0 | 2023-02-28
1247 | Hanwha Q CELLS USA | Emerald Solar and Storage | 2021-09-14 | 174 | 174 | S | Genesee | NY | B | Lapp - East Batavia 115 kV | NM-NG | 0 | 2022-08-31
1248 | Hanwha Q CELLS USA | Garnet Solar and Storage | 2021-09-14 | 174 | 174 | S | Orleans | NY | B | Sour Springs 115 kV | NM-NG | 0 | 2022-03-31
1249 | Hanwha Q CELLS USA | Ruby Storage Project | 2021-09-14 | 115 | 115 | ES | Ontario | NY | C | Station 168 - Trelina Solar 115kV | NM-NG | 0 | 2024-05-31
1250 | Hanwha Q CELLS USA | Sapphire Solar and Storage | 2021-09-14 | 200 | 200 | CR | Wyoming | NY | C | South Perry - Meyer 230 kV | NYSEG | 0 | 2024-05-31
1251 | Hanwha Q CELLS USA | Topaz Storage Project | 2021-09-14 | 200 | 200 | ES | Rensselaer | NY | F | Knickerbocker 345 kV | Transco | 0 | 2023-05-31
1252 | Alliance Energy Storage, LLC | Hillburn Energy Storage | 2021-09-15 | 10 | 10 | ES | Rockland | NY | G | Hillburn | O&R | 0 | 2021-11-30
1253 | Alliance Energy Storage, LLC | Shoemaker Energy Storage | 2021-09-15 | 5.5 | 5.5 | ES | Orange | NY | G | Shoemaker | O&R | 0 | 2021-11-30
1256 | Canal Southampton Battery Storage | Canal Southampton Battery Storage | 2021-09-22 | 100 | 100 | ES | Suffolk | NY | K | Canal Substation 138kV | LIPA | 0 | 2025-01-31
1258 | Oriden LLC | Deerpark Energy Storage | 2021-09-22 | 50 | 50 | ES | Orange | NY | G | Deerpark 69 kV | O&R | 0 | 2022-02-28
1259 | Oriden LLC | Middletown Energy Storage | 2021-09-22 | 50 | 50 | ES | Orange | NY | G | Shoemaker 69 kV | O&R | 0 | 2021-11-30
1260 | BW Solar Holding | St. Regis River | 2021-09-23 | 85 | 85 | CR | St. Lawrence | NY | E | Dennison - Colton 115kV line #4 | NM-NG | 0 | 2024-05-31
1261 | Empire Offshore Wind LLC | EI Sunset Park 2 | 2021-09-24 | 48 | 48 | W | Kings | NY | J | Gowanus 345 kV | ConEd | 0 | 2023-02-28
1262 | East Coast Power LLC | Brunswick Energy Storage | 2021-09-24 | 150 | 165 | ES | Union | NJ | J | Goethals 345kV | ConEd | 0 | 2022-01-31
1263 | Ravenswood Energy Storage 4 | Ravenswood Energy Storage 4 | 2021-09-27 | 12 | 12 | ES | Queens | NY | J | Vernon 138kV | ConEd | 0 | 2021-11-30
1264 | ELP Claverack Solar II LLC | ELP Claverack Solar II LLC | 2021-09-27 | 20 | 20 | CR | Columbia | NY | F | Hudson - Churchtown 115kV | NYTransco/ NM-NG | 0 | 2022-01-31
1266 | Microgrid Networks, LLC | Rust Street 21.8MW ESS | 2021-09-28 | 21.8 | 22.8 | ES | Queens | NY | J | Glendale 27kV | ConEd | 0 | 2021-11-30
1267 | Microgrid Networks, LLC | Rust Street 20 MW ESS Project | 2021-09-28 | 20 | 20 | ES | Queens | NY | J | Glendale 27kV | ConEd | 0 | 2021-11-30
1268 | Microgrid Networks, LLC | 1st Avenue 20 MW ESS Project | 2021-09-28 | 20 | 20 | ES | Kings | NY | J |  | ConEd | 0 | 2021-11-30
1269 | 174 Power Global Properties, LLC | The Bruckner | 2021-09-28 | 11.6 | 11.6 | ES | Bronx | NY | J |  | ConEd | 0 | 2021-11-30
1270 | Microgrid Networks, LLC | Hinsdale 21.8MW Bulk Storage Project | 2021-09-29 | 21.8 | 21.8 | ES | Kings | NY | J | Brownsville 27kV | ConEd | 0 | 2021-11-30
1271 | LS Power Grid NY Corporation I | Atlantic Gateway | 2021-10-07 |  |  | AC | Nassau,Suffolk,Westchester | NY | H; K | Barrett 138 kV, Ruland Road 138 kV, Millwood ? Buchanan 345 kV lines(W97/W98), Millwood ? Pleasant Valley 345 kV lines (W80/W81) | ConEd, LIPA | 0 | 2023-06-30
1272 | Equinor Wind US LLC | EI Sunset BESS | 2021-10-08 | 100 | 100 | ES | Kings | NY | J | Greenwood South 138 kV | ConEd | 0 | 2023-07-31
1273 | Anbaric Development Partners,LLC | Downstate Clean Powerlink | 2021-10-08 |  |  | AC | Nassau, Suffolk, Bronx, Westchester | NY | I,J,K | Mott Haven, Sprainbrook, Dunwoodie, Ruland Road, Newbridge, East Garden City, Syosset, Shore Road | ConEd, LIPA | 0 | 2023-11-30
1274 | NY Power Authority / NY Transco LLC. | Propel NY Energy ? Base Solution 2 | 2021-10-08 |  |  | AC | Nassau, Queens, Bronx, Westchester | NY | I; J; K | Sprain Brook 345 kV; Tremont 345 kV; Barrett138 kV; Shore Road 138 kV; Syosset 138 kV; Ruland Rd 138 kV | ConEd, LIPA | 0 | 2023-07-31
1275 | NY Power Authority / NY Transco LLC. | Propel NY Energy ? Base Solution 4 | 2021-10-08 |  |  | AC | Nassau, Suffolk, Queens, Bronx | NY | J; K | Tremont 345kV; Barrett138 kV; Shore Road 138 kV; Ruland Rd 138 kV | ConEd, LIPA | 0 | 2023-07-31
1276 | NY Power Authority / NY Transco LLC. | Propel NY Energy ? Base Solution 1 | 2021-10-08 |  |  | AC | Nassau, Queens, Bronx, and Westchester | NY | I; J; K | Sprain Brook 345 kV; Tremont 345 kV; East Garden City 345 kV; Barrett 138 kV; East Garden City 138 kV; Shore Road 138 kV; Ruland Rd 138 kV | LIPA, ConEd, NYPA | 0 | 2023-07-31
1277 | NY Power Authority / NY Transco LLC. | Propel NY Energy ? Base Solution 3 | 2021-10-09 |  |  | AC | Nassau, Queens, Bronx, Westchester | NY | I; J; K | Sprain Brook 345 kV; Tremont 345 kV; East Garden City 345 kV; Barrett 138 kV; East Garden City 138 kV; Shore Road 138 kV; Ruland Rd 138 kV | LIPA, ConEd, NYPA | 0 | 2023-07-31
1278 | NextEra Energy Transmission NY, Inc | NY Renewable Connect - Core 1 | 2021-10-10 |  |  | AC | Nassau, Suffolk, Westchester | NY | I,J,K | East Garden City 345 kV, Sprain Brook 345 kV, Dunwoodie 345 kV, Jamaica 138 kV, Valley Stream 138 kV | ConEd, LIPA | 0 | 2023-10-31
1279 | NextEra Energy Transmission NY, Inc | NY Renewable Connect - Core 2 | 2021-10-10 |  |  | AC | Nassau, Suffolk, Westchester | NY | I,J,K | East Garden City, Ruland Road, Sprain Brook, Dunwoodie, Jamaica, Valley Stream, Farragut | ConEd, LIPA | 0 | 2023-10-31
1280 | NextEra Energy Transmission NY, Inc | NY Renewable Connect - Core 3 | 2021-10-10 |  |  | AC | Nassau, Suffolk, Westchester | NY | I,J,K | East Garden City, Ruland Road, Sprain Brook, Dunwoodie, Jamaica, Valley Stream, Farragut, Northport, Pilgrim | ConEd, LIPA | 0 | 2023-10-31
1281 | NextEra Energy Transmission NY, Inc | NY Renewable Connect - Core 4 | 2021-10-10 |  |  | AC | Nassau, Suffolk, Westchester | NY | I,J,K | East Garden City, Ruland Road, Sprain Brook, Dunwoodie, Jamaica, Valley Stream, Farragut, Northport, Pilgrim | ConEd, LIPA | 0 | 2023-10-31
1282 | NextEra Energy Transmission NY, Inc | NY Renewable Connect - Core 5 | 2021-10-10 |  |  | AC | Nassau, Suffolk, Westchester | NY | I,J,K | East Garden City, Ruland Road, Sprain Brook, Dunwoodie, Jamaica, Valley Stream, Northport | ConEd, LIPA | 0 | 2023-10-31
1283 | NextEra Energy Transmission NY, Inc | NY Renewable Connect - Core 6 | 2021-10-10 |  |  | AC | Nassau, Queens, Suffolk, Westchester | NY | I,J,K | East Garden City, Ruland Road, Sprain Brook, Dunwoodie, Jamaica, Valley Stream, Northport, Pilgrim | ConEd, LIPA | 0 | 2023-10-31
1284 | NextEra Energy Transmission NY, Inc | NY Renewable Connect - Core 7 | 2021-10-10 |  |  | AC | Nassau, Suffolk, Westchester | NY | H,I,J,K | East Garden City, Ruland Road, Sprain Brook, Dunwoodie, Jamaica, Valley Stream, Northport, Pilgrim, Buchanan | ConEd, LIPA | 0 | 2023-10-31
1285 | NextEra Energy Transmission NY, Inc | NY Renewable Connect - Enhanced 1 | 2021-10-10 |  |  | AC | Nassau, Suffolk, Westchester | NY | H,I,J,K | East Garden City, Ruland Road, Sprain Brook, Dunwoodie, Farragut, Holbrook, Jamaica, Valley Stream, Northport, Pilgrim, Buchanan, Barrett | ConEd, LIPA | 0 | 2023-10-31
1286 | NextEra Energy Transmission NY, Inc | NY Renewable Connect - Enhanced 2 | 2021-10-10 |  |  | AC | Nassau, Suffolk, Westchester | NY | G,H,I,J,K | East Garden City, Ruland Road, Sprain Brook, Dunwoodie, Farragut, Holbrook, Jamaica, Valley Stream, Northport, Pilgrim, Buchanan, Ramapo | O&R, ConEd, LIPA | 0 | 2023-10-31
1287 | NextEra Energy Transmission NY, Inc | NY Renewable Connect - Plus 3 | 2021-10-10 |  |  | AC | Nassau, Suffolk, Westchester | NY | I,J,K | East Garden City, Ruland Road, Sprain Brook, Dunwoodie, Jamaica, Valley Stream, Northport, Pilgrim | ConEd, LIPA | 0 | 2023-10-31
1290 | NY Power Authority / NY Transco LLC. | Propel NY Energy ? Alternate Solution 6 | 2021-10-11 |  |  | AC | Nassau, Queens, Bronx, Westchester | NY | I; J; K | Sprain Brook 345 kV; Dunwoodie 345 kV; Tremont 345 kV; East Garden City 345 kV; Barrett 138 kV; East Garden City 138 kV; Shore Road 138 kV; Syosset 138 kV; Ruland Rd 138 kV | LIPA, ConEd, NYPA | 0 | 2023-07-31
1291 | NY Power Authority / NY Transco LLC. | Propel NY Energy ? Alternate Solution 7 | 2021-10-11 |  |  | DC | Nassau, Queens, Bronx, Westchester | NY | I; J; K | Sprain Brook 345 kV; Dunwoodie 345 kV; Tremont 345 kV; Barrett 138 kV; Shore Road 138 kV; Syosset 138 kV; Ruland Rd 138 kV; Northport 138 kV | ConEd, LIPA | 0 | 2023-07-31
1292 | Liberty Renewables Inc. | Hemlock Hollow Wind | 2021-10-20 | 87.9 | 87.9 | W | Cattaraugus | NY | A | Homer Hill - Dugan Rd 115kV | NM-NG | 0 | 2024-07-31
1293 | ACE DevCo NC | White Springs Solar | 2021-10-22 | 20 | 20 | S | Ontario | NY |  | Haley Road 34.5 kV Substation | NYSEG | 0 | 2023-08-31
1294 | ACE DevCo NC | Moran Solar | 2021-10-22 | 20 | 20 | S | Fulton | NY | F | Inghams - Stoner 115 kV | NM-NG | 0 | 2024-02-29
1295 | Galehead Development, LLC | Putnam Mountain Solar | 2021-10-26 | 40 | 40 | S | Washington | NY | F | Whitehall - Cedar 115 kV | NM-NG | 0 | 2022-11-30
1296 | Nexamp Solar | 90662 Sing Sing Standalone Storage | 2021-10-28 | 20 | 20 | ES | Chemung | NY | J |  | ConEd | 0 | 2021-11-30
1297 | Algonquin Power Fund (America), Inc. | Deerpark Energy Storage | 2021-10-29 | 20 | 20 | ES | Orange | NY | G | Cuddebackville substation | O&R | 0 | 2022-01-31
1298 | Nexamp Solar | 87677 Clifton Springs Standalone Storage | 2021-10-29 | 20 | 20 | ES | Ontario | NY | J |  | ConEd | 0 | 2021-11-30
1299 | KCE NY 33, LLC | KCE NY 33 | 2021-10-29 | 20 | 20 | ES | Broome | NY | C | Langdon 34.5kV Substation | NYSEG | 0 | 2022-08-31
1300 | KCE NY 25, LLC | KCE NY 25, LLC | 2021-11-02 | 6 | 6 | ES | Ontario | NY | B | Substation 146 | RG&E | 0 | 2021-12-31
1301 | Pine Barrens Storage LLC | Pine Barrens Storage | 2021-11-09 | 75 | 75 | ES | Suffolk | NY | K | Brookhaven 138 kV Substation | LIPA | 0 | 2024-05-31
1302 | New Bremen Solar | Bremen Solar | 2021-11-10 | 102.3 | 100 | S | Lewis | NY | E | Bremen 115 kV Substation | NM-NG | 0 | 2022-03-31
1303 | Hanwha Q Cells USA | Agate Storage Project | 2021-11-12 | 200 | 200 | ES | Dutchess | NY | G | Manchester 115 kV substation | CHG&E | 0 | 2024-05-31
1304 | Hanwha Q CELLS USA | Coral Storage Project | 2021-11-12 | 100 | 100 | ES | Chemung | NY | C | Yawger 115 kV substation | NYSEG | 0 | 2024-05-31
1305 | Hanwha Q CELLS USA | Crystal Storage Project | 2021-11-12 | 175 | 175 | ES | Seneca | NY | C | Border City - Elbridge 115 kV Line#10 | NM-NG | 0 | 2024-05-31
1306 | Hanwha Q CELLS USA | Opal Storage Project | 2021-11-12 | 200 | 200 | ES | Orange | NY | G | East Walden 115 kV substation | CHG&E | 0 | 2024-05-31
1307 | Riverhead Energy | Riverhead Energy, LLC | 2021-11-16 | 100 | 100 | ES | Suffolk | NY | K | Riverhead - Jamesport 69kV | LIPA | 0 | 2024-05-31
1309 | Algonquin Power Fund (America), Inc. | Port Jefferson Energy Storage | 2021-12-07 | 48.7 | 48.7 | ES | Suffolk | NY | K | Port Jefferson 69kV Substation | LIPA | 0 | 2022-03-31
1310 | QMB1 Energy Storage | QMB1 Energy Storage | 2021-12-08 | 300 | 300 | ES | Nassua | NY | K | Ruland Rd. 138 kV | LIPA | 0 | 2024-07-31
1311 | Bronx Shores Energy Storage | Bronx Shores Energy Storage | 2021-12-08 | 300 | 300 | ES | Bronx | NY | J | Mott Haven 138 kV | ConEd | 0 | 2024-05-31
1312 | Saturn Energy Storage LLC | Orient Point BESS | 2021-12-10 | 15 | 15 | ES | Suffolk | NY | K | The existing 23kV line near PSEG?s 23 kV Orient substation | LIPA | 0 | 2022-02-28
1313 | Saturn Energy Storage LLC | Queensbury BESS | 2021-12-12 | 20 | 20 | ES | Warren | NY | F | Queensbury 34.5 kV substation | NM-NG | 0 | 2024-05-31
1314 | Regeneron Pharmaceuticals Inc | Regeneron Pharmaceutical INC | 2021-12-15 | 0.5 | 0.5 | S | Rensselaer | NY | F | On site - connecting to electrical SWGR. Technical point of interconnection for the campus is at the primary meter at the substation | NM-NG | 0 | 2022-03-31
1316 | ACE DevCo NC, LLC | Bay Breeze Solar | 2021-12-20 | 200 | 200 | S | Jefferson | NY | E | Lyme - North Watertown 115kV Line #13 | NM-NG | 0 | 2024-07-31
1317 | KCE NY 34, LLC | KCE NY 34 | 2021-12-21 | 13 | 13 | ES | Ulster | NY | G | 13.8 kV Saugerties Substation | CHGE | 0 | 2022-02-28
1318 | Algonquin Power Fund (America), Inc. | Saugerties Energy Storage | 2021-12-21 | 12.9 | 12.9 | ES | Ulster | NY | G | Saugerties substation 13.8 kV | CHGE | 0 | 2022-01-31
1319 | Grateful Storage LLC | Grateful Storage, LLC | 2021-12-23 | 100 | 100 | ES | Orange | NY | G | Chadwick Lake - East Walden 115 kV | CHG&E | 0 | 2023-12-31
1320 | Lake Ronkonkoma Storage LLC | Lake Ronkonkoma Storage, LLC | 2021-12-23 | 100 | 100 | ES | Suffolk | NY | K | Ronkonkoma 138 kV substation | LIPA | 0 | 2024-01-31
1321 | Dix Hills Storage LLC | Dix Hills, LLC | 2021-12-23 | 100 | 100 | ES | Suffolk | NY | K | Bagatelle Rd 138 kV | LIPA | 0 | 2024-05-31
1322 | Holtsville West Storage LLC | Holtsville West Storage, LLC | 2021-12-23 | 50 | 50 | ES | Suffolk | NY | K | Holtsville 69 kV substation | LIPA | 0 | 2024-07-31
1323 | Fresh Air Energy II | Lincoln ESC | 2022-01-07 | 100 | 100 | ES | SUFFOLK | NY | K | Holbrook - Bohemia 69kV | LIPA | 0 | 2024-05-31
1324 | AES | Somerset Solar Farm | 2022-01-20 | 212 | 212 | AC | USA | NY | A | Kintigh Switchyard 345kV | NYSEG | 0 | 2022-03-31
1325 | RWE Solar Development, LLC | McKean County Solar CSR Phase 1 | 2022-01-20 | 325 | 325 | CR | McKean | PA | A | Homer City - Pierce Brook 345 kV | NYSEG | 0 | 2024-05-31
1326 | RWE Solar Development, LLC | McKean County Solar CSR Phase 2 | 2022-01-20 | 325 | 325 | CR | McKean | PA | A | Homer City - Pierce Brook 345 kV | NYSEG | 0 | 2024-05-31
1327 | RWE Solar Development, LLC | McKean County BESS | 2022-01-20 | 170 | 170 | ES | McKean | PA | A | Homer City Station - Pierce Brook 345kV | NYSEG | 0 | 2022-04-30
1328 | EDF renewables development inc. | Wayland solar | 2022-01-26 | 120 | 120 | S | Steuben | NY | C | Meyer - Eelpot Road 115 kV | NYSEG | 0 | 2024-05-31
1330 | Avangrid Renewables | AGR NY-1 | 2022-02-17 | 1600 | 1600 | W | Kings | NY | J | Gowanus 345 kV Substation | ConEd | 0 | 2022-04-30
1331 | Solar Generation | Solar Generation Jennison Revitalization Facility | 2022-02-17 | 117.8 | 117.8 | S | Chenango | NY |  | Jennison 115 kV | NYSEG | 0 | 2023-08-31
1332 | Avangrid Renewables | AGR NY-2 | 2022-02-17 | 1600 | 1600 | W | Richmond | NY | J | Goethals 345 kV Substation | ConEd | 0 | 2022-04-30
1333 | QMB 1 Energy Storage | Newbridge-Ruland Storage | 2022-02-21 | 250 | 250 | ES | Nassau | NY | K | Ruland Rd - Newbridge 138 kV | LIPA | 0 | 2024-03-31
1334 | EDF renewables development inc. | Morris Sole Solar | 2022-02-23 | 110 | 110 | S | Livingston | NY | C | South Perry - Meyer 230 kV | NYSEG | 0 | 2024-05-31
1335 | Liberty Renewables Inc. | Hoffman Falls Wind 2 | 2022-02-24 | 102.5 | 102.5 | W | Madison | NY | C | Fenner-Shippey Road 115 kV Line #3 | NM-NG | 0 | 2024-05-31
1336 | Granada Solar, LLC | Abrams Solar | 2022-02-24 | 20 | 20 | S | St. Lawrence | NY |  | Alcoa - N. Ogdensburg 115 kV | NM-NG | 0 | 2023-08-31
1337 | Atlantic Shores Offshore Wind Bight, LLC | Atlantic Shores Offshore Wind Bight 1 | 2022-02-25 | 2100 | 2100 | W | Kings | NY | J | Gowanus 345 KV | ConEd | 0 | 2024-07-31
1338 | Atlantic Shores Offshore Wind Bight, LLC | Atlantic Shores Offshore Wind Bight 2 | 2022-02-25 | 2100 | 2100 | W | Richmond | NY | J | Goethals 345 kV | ConEd | 0 | 2024-07-31
1339 | Atlantic Shores Offshore Wind Bight, LLC | Atlantic Shores Offshore Wind Bight 3 | 2022-02-25 | 2100 | 2100 | W | Suffolk | NY | K | Ruland Road 138kV | LIPA | 0 | 2022-06-30
1340 | Atlantic Shores Offshore Wind Bight, LLC | Atlantic Shores Offshore Wind Bight 4 | 2022-02-25 | 2100 | 2100 | W | Kings | NY | J | Brooklyn Clean Energy Hub 345kV | ConEd | 0 | 2024-07-31
1341 | Atlantic Shores Offshore Wind Bight, LLC | Atlantic Shores Offshore Wind Bight 5 | 2022-02-25 | 2100 | 2100 | W | Richmond | NY | J | Fresh Kills 345 KV | ConEd | 0 | 2024-07-31
1342 | Astoria Renewables LLC | Astoria Annex Energy Storage | 2022-03-03 | 500 | 500 | ES | Queens | NY | J | Astoria Annex 345 kV | NYPA | 0 | 2024-05-31
1343 | Swift Current Energy | Moonlight Flats Solar Power | 2022-03-04 | 250 | 250 | S | Clearfield | PA | C | Homer City - Mainesburg 345 KV | NYSEG | 0 | 2024-05-31
1344 | Fresh Kills Battery Storage LLC | Fresh Kills Energy Storage | 2022-03-08 | 500 | 500 | ES | Richmond | NY | J | Fresh Kills 345 kV | ConEd | 0 | 2024-05-31
1345 | Staten Island Power LLC | Goethals Energy Storage Project | 2022-03-08 | 500 | 500 | ES | Richmond | NY | J | Goethals 345 kV | ConEd | 0 | 2024-05-31
1346 | Middletown Energy Storage, LLC | Middletown Energy Storage | 3/8/2022 | 100 | 100 | ES | Orange | NY | G | Tap Shoemaker-Chester 138kV line (line 27) | O&R | 0 | 2023-04-30
1347 | Hanwha Q CELLS USA | Celestine Storage | 2022-03-11 | 191.1 | 191.1 | ES | Steuben | NY | C | Bath 115 kV substation | NYSEG | 0 | 2022-06-30
1348 | Hanwha Q CELLS USA | Daphne Storage | 2022-03-11 | 45 | 45 | ES | Suffolk | NY | K | Moriches 69 kV | LIPA | 0 | 2024-05-31
1349 | Hanwha Q CELLS USA | Gemma Storage | 2022-03-11 | 190 | 190 | ES | Steuben | NY | C | Stoney Ridge 230 KV Substation | NYSEG | 0 | 2024-05-31
1350 | New Castle ESS LLC | Millwood Energy Storage | 2022-03-11 | 500 | 500 | ES | Westchester | NY | H | Millwood 345 kV Substation | ConEd | 0 | 2024-05-31
1351 | Yonkers Renewable Energy LLC | Sprain Brook Energy Storage | 2022-03-13 | 500 | 500 | ES | Westchester | NY | I | Sprain Brook 345 kV Substation | ConEd | 0 | 2024-05-31
1352 | Peekskill BESS LLC | Buchanan Energy Storage - North | 2022-03-13 | 500 | 500 | ES | Westchester | NY | H | Buchanan North 345 kV Substation | ConEd | 0 | 2024-05-31
1353 | Central Westchester Power LLC | Eastview Energy Storage Project | 2022-03-14 | 400 | 400 | ES | Westchester | NY | I | Eastview 138 kV Substation | ConEd | 0 | 2024-05-31
1354 | Hecate Energy Diamond Solar LLC | Diamond Solar | 2022-03-18 | 500 | 500 | S | Herkimer | NY | E | Edic to Gordon Rd 345 kV line | NM-NG | 0 | 2024-05-31
1355 | EDF Renewable Development, Inc | Rich Road Storage | 2022-03-23 | 20 | 20 | ES | St. Lawrence | NY | E | Moses - Adirondack 230 kV | NYPA | 0 | 2022-12-31
1356 | New Bremen Solar | Bremen Solar | 3/24/2022 | 100 | 100 | S | Lewis | NY | E | Taylorville - Boonville 115 kV | NM-NG | 0 | 2023-03-31
1357 | 174 Power Global Properties | Shoreham | 3/25/2022 | 100 | 100 | ES | Suffolk | NY | K | Shoreham 138 kV | LIPA | 0 | 2023-04-30
1358 | 174 Power Global Properties | West Babylon | 2022-03-25 | 130 | 130 | ES | Nassau | NY | K | West Babylon 69 kV | LIPA | 0 | 2022-10-31
1359 | EDF Renewable Development, Inc | Columbia Storage | 2022-03-31 | 20 | 20 | ES | Herkimer | NY | E | Edic - Fraser 345 kV | NYPA | 0 | 2022-12-31
1360 | Peekskill BESS LLC | Buchanan Energy Storage-South | 2022-04-07 | 500 | 500 | ES | Westchester | NY | H | Buchanan South 345 kV Substation | ConEd | 0 | 2024-05-31
1361 | Nexamp Solar LLC | Ditch Creek Solar | 2022-04-12 | 200 | 200 | CR | Madison | NY | C | Clay - Edic 345 kV | NYPA | 0 | 2024-10-31
1362 | EDF renewables development inc. | Fraser Storage | 2022-04-12 | 200 | 200 | ES | Delaware | NY | E | Fraser substation 115 kV | NYSEG | 0 | 2024-05-31
1363 | Delaware River Solar | State Route 52 | 2022-04-14 | 20 | 20 | S | Sullivan | NY | E | Liberty 34.5 kV substation | NYSEG | 0 | 2022-09-30
1364 | Bluewave Storage Origination LLC | NY Wappingers Falls Old Hopewell Rd Storage | 4/14/2022 | 40 | 40 | ES | Wappingers Falls | NY | G | North Chelsea - Myers Corners 69 kV | CHGE | 0 | 2023-03-31
1367 | Queensboro Development, LLC | Queensboro Renewable Express Circuit C | 2022-04-15 | N/A | N/A | AC | Queens | NY | J | New Ravenswood substation connecting to Rainey 345kV and Vernon 138kV | ConEd | 0 | 2023-02-28
1368 | Borrego Solar Systems, inc. | Hallock Ave Energy Storage | 2022-04-19 | 90 | 90 | ES | Suffolk | NY | K | Shoreham - Millers Place 138 kV | LIPA | 0 | 2022-11-30
1369 | Community Offshore Wind, LLC | Community OSW Valley Stream 1 | 2022-04-20 | 1100 | 1100 | W | Nassau | NY | K | Valley Stream 138kV | LIPA | 0 | 2022-09-30
1370 | Community Offshore Wind, LLC | Community OSW Ruland Road 1 | 2022-04-20 | 1100 | 1100 | W | Suffolk | NY | K | Ruland Road 138kV | LIPA | 0 | 2024-05-31
1371 | Community Offshore Wind, LLC | Community OSW Goethals 1 | 2022-04-20 | 1100 | 1100 | W | Staten Island | NY | J | Goethals 345 kV | ConEd | 0 | 2024-05-31
1372 | Community Offshore Wind, LLC | Community OSW Brooklyn CEH 1 | 2022-04-20 | 1100 | 1100 | W | Brooklyn | NY | J | Brooklyn Clean Energy Hub 345 kV | ConEd | 0 | 2024-05-31
1373 | Community Offshore Wind, LLC | Community OSW Barrett 1 | 2022-04-20 | 1100 | 1100 | W | Nassau | NY |  | Barrett 138 kV | LIPA | 0 | 2023-08-31
1374 | Community Offshore Wind, LLC | Community OSW East Garden City 1 | 2022-04-24 | 1100 | 1100 | W | Nassau | NY | K | East Garden City 345 kV | NYPA | 0 | 2024-05-31
1375 | Community Offshore Wind, LLC | Community OSW Valley Stream 2 | 2022-04-24 | 210 | 210 | W | Nassau | NY | K | Valley Stream 138kV | LIPA | 0 | 2022-09-30
1376 | Community Offshore Wind, LLC | Community OSW Ruland Road 2 | 2022-04-24 | 210 | 210 | W | Suffolk | NY | K | Ruland Road 138 kV | LIPA | 0 | 2023-11-30
1377 | Community Offshore Wind, LLC | Community OSW Goethals 2 | 2022-04-24 | 210 | 210 | W | Staten Island | NY | J | Goethals 345 kV | ConEd | 0 | 2024-05-31
1378 | Community Offshore Wind, LLC | Community OSW Brooklyn CEH 2 | 2022-04-24 | 210 | 210 | W | Brooklyn | NY | J | Brooklyn Clean Energy Hub 345 kV | ConEd | 0 | 2024-05-31
1379 | Community Offshore Wind, LLC | Community OSW Barrett 2 | 2022-04-24 | 210 | 210 | W | Nassau | NY |  | Barrett 138 kV | LIPA | 0 | 2023-08-31
1380 | Community Offshore Wind, LLC | Community OSW East Garden City 2 | 2022-04-24 | 210 | 210 | W | Nassau | NY | K | East Garden City 345 kV | NYPA | 0 | 2024-05-31
1381 | Bluewave Storage Origination LLC | NY Nassau 0 Waterbury Rd Storage A | 2022-04-28 | 25.2 | 25.2 | ES | Rensselaer | NY | F | Nassau-Hudson #9 Line 34.5 kV | NM-NG | 0 | 2024-02-29
1382 | OW Ocean Winds East | OW Ocean Winds East 7 | 2022-05-02 | 1600 | 1600 | W | Kings | NY | J | Gowanus 345 kV | ConEd | 0 | 2024-07-31
1383 | Bluewave Storage Origination LLC | NY Hudson Fairview Ave Storage | 2022-05-05 | 25.2 | 25.2 | ES | Columbia | NY | F | Nassau - Hudson 34.5kV | NM-NG | 0 | 2022-11-30
1384 | Daroga Power | Daroga Power Dover Plains Hydrogen Production Plant | 2022-05-19 |  |  |  | Dutchess | NY | H | Ten Mile River | NYSEG | 0 | 2022-08-31
1385 | Attentive Energy | Attentive Energy 1 | 2022-06-01 | 1310 | 1310 | W | Suffolk | NY | K | Sills Road Substation 138kV | LIPA | 0 | 2024-05-31
1386 | Attentive Energy | Attentive Energy 2 | 2022-06-01 | 1310 | 1310 | W | Brooklyn | NY | J | Farragut Substation 345 kV | ConEd | 0 | 2024-05-31
1387 | ClearCell Power | Glen Head Battery Energy Storage System | 2022-06-09 | 20.1 | 20.1 | ES | Nassau | NY | K | 1 Stanco Street Substation via a dedicated feeder from the project site | LIPA | 0 | 2022-08-31
1388 | NY Power Authority Development & LS Power Grid NY Corporation II | Kings Spoke 1310 | 2022-06-09 |  |  |  | Kings | NY | J | The proposed POI will be located at a new 345/138 kV transmission substation in East Flatbush, Brooklyn, ~4 miles from the Greenwood substation, ~3 miles from the Bensonhurst sub, ~4 miles from the Farragut, and ~3 miles from Brownsville substation. | ConEd | 0 | 2022-07-31
1389 | NY Power Authority & LS Power Grid NY Corporation II | Kings Spoke 2620 | 2022-06-09 |  |  |  | Kings | NY | J | The proposed POI will be located at a new 345/138 kV transmission substation in East Flatbush, Brooklyn, ~4 miles from the Greenwood substation, ~3 miles from the Bensonhurst substation, ~4 miles from the Farragut substation and ~3 mi from the Brownsville | ConEd | 0 | 2022-07-31
1390 | EDF Renewable Development Inc. | Ridge View Stoarge | 2022-06-10 | 20 | 20 | S | Niagara | NY | A | Kintigh-Dysinger 345kV | NYSEG | 0 | 2022-12-31
1391 | ACE DevCo NC, LLC | Beck Solar | 2022-06-21 | 20 | 20 | S | Chautauqua | NY | A | Hartfield - Moon Road 115 kV line | NM-NG | 0 | 2024-01-31
1392 | Swift Solar LLC | Swift Solar | 2022-06-23 | 300 | 300 | CR | Herkimer | NY | F | Edic - Princetown 345 kV #351 line | NYPA | 0 | 2024-05-31
1393 | Mineral Basin Solar Power, LLC | Mineral Basin II Solar Power | 2022-06-23 | 222 | 222 | S | Clearfield | PA | C | Homer City - Mainesburg 345 kV | NYSEG | 0 | 2024-05-31
1394 | Bluewave Storage Origination LLC | NY Greenport 85 Middle Rd Storage | 2022-06-23 | 104.2 | 104.2 | ES | Columbia | NY | G | North Catskill - Churchtown Line #5 115 kV and Lafarge- Churchtown Line #8 115 kV | NM-NG | 0 | 2024-02-29
1395 | Excelsior Reserve Energy | Raquette Lake Energy Storage / CAMP | 2022-06-23 | 20 | 20 | ES | Hamilton | NY | E | Raquette Lake - Eagle Bay 46 kV line | NM-NG | 0 | 2024-02-29
1396 | NY Interconnection LLC | NY Interconnection 4 | 2022-06-30 | 900 | 900 | W | NY | NY | J | Fox Hills 138 kV Substation | ConEd | 0 | 2024-05-31
1397 | NY Power Authority | Hell Gate Energy Storage | 2022-07-01 | 95 | 96 | ES | Bronx | NY | J | Hell Gate Bus Section 2 - 138kV | NYPA | 0 | 2024-05-31
1398 | NY Power Authority | Harlem River Yards Energy Storage | 2022-07-01 | 106 | 107 | ES | Bronx | NY | J | Hell Gate Annex - 138kV voltage | NYPA | 0 | 2024-05-31
1399 | NY Power Authority | Pouch Energy Storage | 2022-07-01 | 51 | 52 | ES | Staten Island | NY | J | Fox Hills 138kV Substation | ConEd | 0 | 2024-05-31
1400 | NY Power Authority | Gowanus Energy Storage | 7/1/2022 | 102 | 103 | ES | Brooklyn | NY | J | Greenwood 138kV Substation with alternate feed connected to Gowanus Substation ~ | ConEd | 0 | 2023-03-31
1401 | NY Power Authority | Brentwood Energy Storage | 2022-07-01 | 51 | 52 | ES | Suffolk | NY | K | Brentwood Substation Bus #1 - 69kV | LIPA | 0 | 2024-05-31
1402 | NY Power Authority | Flynn Energy Storage | 2022-07-01 | 160 | 160 | ES | Suffolk | NY | K | Holtsville 138 kV substation | LIPA | 0 | 2024-05-31
1403 | Poplar Energy Center, LLC | Poplar 1 Energy Center | 2022-07-11 | 60 | 60 | ES | Suffolk | NY | K | Riverhead -Tuthill 69 kV Line | LIPA | 0 | 2024-05-31
1404 | Winner Solar, LLC | Winner Solar | 2022-07-14 | 120 | 120 | S | Clinton County | PA | C | Homer City - Mainesburg 345kV | NYSEG | 0 | 2024-09-30
1405 | Athens Energy Stoarge LLC | Athens Energy Storage | 2022-07-16 | 300 | 300 | ES | Greene | NY | F | Leeds 3-Van Wagner 345 kV Line | NM-NG | 0 | 2024-05-31
1406 | North Seneca Solar Project LLC | North Seneca Storage | 2022-07-22 | 19.9 | 19.9 | ES | Seneca | NY | C | Farmington-Hamilton 115 kV Line Tap | NM-NG | 0 | 2023-10-31
1407 | Crane Brook Solar Project | Crane Brook Storage | 2022-07-22 | 19.9 | 19.9 | ES | Cayuga | NY | C | State St. - Clinton Corn 115 kV | NM-NG | 0 | 2023-07-31
1408 | Bluewave Storage Origination LLC | NY Schodack 634 Knickerbocker Rd Storage | 7/25/2022 | 57 | 57 | ES | Rensselaer | NY | F | Schodack – Valkin line 14 115 kV | NYTransco | 0 | 2023-03-31
1409 | Grateful Storage LLC | Grateful Storage, LLC | 2022-08-26 | 250 | 250 | ES | Orange | NY | G | Rock Tavern - Roseton 345kV | CHG&E | 0 | 2024-07-31
1410 | Cayuga Solar LLC | Cayuga Solar LLC | 2022-07-29 | 19.6 | 19.6 | S | Cayuga | NY | C | NYS-Locke 718 34.5 kV Substation | NYSEG | 0 | 2024-11-30
1411 | Bluewave Storage Origination LLC | NY Johnstown 378 State Hwy 334 Storage | 8/1/2022 | 62.5 | 62.5 | ES | Fulton | NY | F | Inghams - Meco #15 115 kV line | NM-NG | 0 | 2023-03-31
1412 | Poplar Energy Center, LLC | Poplar 2 Energy Center | 2022-08-10 | 20 | 20 | ES | Suffolk | NY | K | Riverhead-Tuthill 69kV | LIPA | 0 | 2023-02-28
1413 | Catlin Creek Energy Storage 1, LLC | Catlin Creek Storage | 2022-08-10 | 70 | 70 | ES | Orange County | NY | G | Westtown - Shoemaker 69 kV line #11 | O&R | 0 | 2024-08-31
1414 | Glove City Energy Center, L.L.C. | Glove City Energy Center | 2022-08-10 | 100 | 100 | S | Fulton | NY | F | Stoner to Inghams 115 kV line | NM-NG | 0 | 2022-09-30
1415 | Microgrid Networks, LLC | 57-77 Rust St | 2022-08-11 | 22.5 | 22.5 | ES | Queens | NY | J | Glendale 27kV | ConEd | 0 | 2022-12-31
1416 | Bluewave Storage Origination LLC | NY Mahopac 45 Margaret Rd Storage | 2022-08-15 | 162.5 | 162.5 | ES | Putnam | NY | H | Croton Falls - Union valley 115 kV | NYSEG | 0 | 2023-02-28
1417 | Liberty Renewables Inc. | Russet Ridge Wind | 2022-08-19 | 118 | 118 | W | Livingston | NY | C | Eelpot Road 115kV substation | NYSEG | 0 | 2024-05-31
1418 | New Hartford Solar LLC | New Hartford Solar Farm | 2022-08-22 | 20 | 20 | CR | Oneida | NY | E | Line #1 115kV YAHNUNDASIS-CHADWICKS | NM-NG | 0 | 2024-06-30
1419 | Vineyard Mid-Atlantic | Vineyard Mid-Atlantic 1 | 2022-08-24 | 1350 | 1350 | W | Kings | NY | J | Gowanus 345 kV | Coned | 0 | 2024-05-31
1420 | Glove City Energy Center, LLC | Glove City Solar | 2022-08-25 | 100 | 100 | S | Fulton | NY | F | Inghams - Stoner 115kV line #9 | NM-NG | 0 | 2024-05-31
1421 | Origis Development | Lockport Storage | 2022-08-29 | 186.2 | 186.2 | ES | Niagara | NY | A | Robinson Road 230 kV Substation | NYSEG | 0 | 2024-05-31
1422 | Pivot Energy Development LLC | Pivot Burnell | 8/31/2022 | 20 | 20 | CR | Clinton | NY | D | Lyon Mountain - Saranac 115 kV | NYSEG | 0 | 2023-04-30
1423 | Pivot Energy Development LLC | Pivot Macvean | 8/31/2022 | 19.8 | 19.8 | CR | Fulton | NY | F | Amsterdam to Ephratah 69kV | NM-NG | 0 | 2023-03-31
1424 | Pivot Energy Development LLC | Pivot Woodsmen | 8/31/2022 | 20 | 20 | CR | Oneida | NY | E | Boonville - Porter 115kV line 1 | NM-NG | 0 | 2023-04-30
1425 | Pivot Energy Development LLC | Pivot Woodsmen BESS | 2022-08-31 | 19.8 | 19.8 | ES | Oneida | NY | E | Boonville - Porter 115kV Line 1 | NM-NG | 0 | 2023-11-30
1426 | Pivot Energy Development LLC | Pivot Macvean BESS | 8/31/2022 | 19.8 | 19.8 | ES | Fulton | NY | F | Amsterdam - Ephratah 69kV (Line#7) | NM-NG | 0 | 2023-03-31
1427 | Pivot Energy Development LLC | Pivot Burnell BESS | 8/31/2022 | 20 | 20 | ES | Clinton | NY | D | Lyon Mountain - Saranac 115kV | NYSEG | 0 | 2023-03-31
1428 | Vineyard Northeast | Vineyard Northeast 1 | 2022-09-01 | 1350 | 1350 | W | Kings County | NY | J | Gowanus 345kV | ConEd | 0 | 2024-05-31
1429 | Bluewave Storage Origination LLC | NY Southold 50100 County Rd 48 Storage B | 9/1/2022 | 45.7 | 45.7 | ES | Suffolk | NY | K | 8B Peconic to 8J Southold 69kV line (69-957) | LIPA | 0 | 2023-03-31
1430 | Origis Development | Van Buren Storage | 2022-09-06 | 150 | 150 | ES | Chautauqua | NY | A | Dunkirk to Falconer 115 kV transmission | NM-NG | 0 | 2024-05-31
1431 | Juno Power Management | oyster shore III | 2022-09-06 | 300 | 300 | ES | Nassau | NY | K | Shore road 138 kV | LIPA | 0 | 2023-04-30
1432 | Cherry Valley Energy Center, L.L.C. | Cherry Valley Solar | 2022-09-07 | 125 | 125 | S | Montgomery | NY | F | Edic - Princetown 345kV Line #351 | NYPA | 0 | 2024-05-31
1433 | NY Interconnection LLC | NY Interconnection 5 | 2022-09-09 | 150 | 150 | W | NY | NY | J | Fox Hills 138kV Substation | ConEd | 0 | 2024-05-31
1434 | NY Interconnection LLC | NY Interconnection 6 | 2022-09-09 | 1050 | 1050 | W | Richmond | NY | J | Goethals-Gowanus 345kV Line Break | ConEd | 0 | 2024-05-31
1435 | New York Power Authority & LS Power Grid New York Corporation II | Kings Spoke | 2022-09-12 | N/A | N/A | AC | Kings | NY | J | Greenwood-Bensonhurst and Farragut-Brownsville 138 kV feeders | ConEd | 0 | 2023-04-30
1436 | North Foothills Energy Center, LLC | North Foothills | 2022-09-13 | 100 | 100 | S | FRANKLIN | NY | D | Malone 115 kV Substation | NM-NG | 0 | 2024-05-31
1437 | Northland Power U.S. Projects | North Norwich Solar | 2022-09-14 | 120 | 120 | CR | Chenango County | NY | E | County Line-East Norwich Tap 115 kV NYSEG | NYSEG | 0 | 2024-05-31
1438 | NY Interconnection LLC | NY Interconnection 7 | 2022-09-15 | 270 | 270 | W | Richmond | NY | J | Goethals-Gowanus 345kV line break | ConEd | 0 | 2024-05-31
1439 | East Bridge Storage, LLC | East Bridge Energy Storage | 2022-09-16 | 125 | 125 | ES | Sullivan | NY | E | Coopers Corner - Shortcut Rd 115 kV | NYSEG | 0 | 2024-03-31
1440 | Gloversville Storage, LLC | Gloversville Storage | 2022-09-21 | 50 | 50 | ES | Fulton | NY | F | MECO 115 kV Substation | NM-NG | 0 | 2024-03-31
1441 | Northbrook Lyons Falls LLC | Lyons Falls Mill Repowering Project | 9/22/2022 | 11 | 11 | H | Lewis | NY | E | 115kV Taylorville-Boonville Line 6 via the Lyonsdale Hydro tap | NM-NG | 0 | 2023-04-30
1442 | Mulberry Energy Storage 1, LLC | Mulberry Energy Storage | 2022-09-28 | 130 | 130 | ES | Saratoga | NY | F | Luther Forest - Eastover Road #308 115kV line | NM-NG | 0 | 2024-04-30
1443 | Vineyard Mid-Atlantic | Vineyard Mid-Atlantic 2 | 2022-09-28 | 1330 | 1330 | W | Nassau | NY | K | East Garden City 345 kV Substation | NYPA | 0 | 2024-07-31
1444 | Hollyhock Solar, LLC | Hollyhock Solar | 2022-11-15 | 20 | 20 | S | Albany | NY | F | Leeds-New Scotland 115 kV, Unionville-Callanan Industries 34.5 kV | NM-NG | 0 | 2023-01-31
1445 | Apalachin Solar LLC | Friendship Solar Farm | 2022-09-30 | 20 | 20 | CR | Allegany | NY | B | The POI provided in the IR was Connection to one pole of the 34 kV transmission line coming from substation 8333G (Substation address: 52 PA Ave, Friendship, NY). The line number has been identified by RGE as line # 760 34.5kV line | RG&E | 0 | 2023-05-31
1446 | Air Products and Chemicals Inc | Massena Green Hydrogen | 2022-10-05 | 110 | 110 | L | St Lawrence | NY | E | Haverstock - Adirondack 345 kV line 1 | NYPA | 0 | 2025-03-31
1447 | Capital Region Energy Storage LLC | New Scotland BESS Project | 2022-10-10 | 600 | 600 | ES | Albany | NY | F | New Scotland 345 kV Substation | NM-NG | 0 | 2024-09-30
1448 | KCE NY 30, LLC | KCE NY 30 | 2022-10-11 | 50 | 50 | ES | Suffolk | NY | K | West Babylon 69kV substation | LIPA | 0 | 2024-05-31
1449 | KCE NY 31, LLC | KCE NY 31 | 2022-10-11 | 50 | 50 | ES | Suffolk | NY | K | Shoreham 138 kV | LIPA | 0 | 2024-05-31
1450 | NYG Energy LLC | Stewart Rock Energy Storage | 2022-10-11 | 150 | 150 | ES | Orange | NY | G | Rock Tavern 345KV | CHG&E | 0 | 2023-12-31
1451 | Empire Reserve Energy, LLC | Babylon Storage | 2022-10-13 | 50 | 50 | ES | Suffolk | NY | K | Pinelawn 69 kV station | LIPA | 0 | 2024-05-31
1452 | CS Grass River Solar, LLC | Grass River Solar | 2022-10-17 | 80 | 80 | S | St. Lawrence County | NY | E | Alcoa - N. Ogdensburg 115kV line #13 | NM-NG | 0 | 2024-05-31
1453 | Delaware River Solar | Soper Road | 10/25/2022 | 20 | 20 | S | Wyoming | NY | C | Perry Center 34.5 kV substation | NYSEG | 0 | 2023-04-30
1454 | Ozone Renewables | Short Tract Energy Storage | 2022-10-25 | 20 | 20 | ES | Livingston | NY | B | RG&E Short Tract Road Substation | RG&E | 0 | 2023-02-28
1455 | Vineyard Northeast LLC | Vineyard Northeast 2 | 2022-10-31 | 1345 | 1345 | W | Kings | NY | J | Farragut 345 kV Substation | ConEd | 0 | 2024-05-31
1456 | Bluewave Storage Origination LLC | NY Amsterdam 152 Persons Rd Storage | 2022-10-31 | 114.8 | 114.8 | ES | Montgomery | NY | F | Stoner ? Rotterdam 115 kV line#12 | NM-NG | 0 | 2023-06-30
1457 | Hanwha Q CELLS USA Corp. | Jasper Storage | 2022-11-01 | 300 | 300 | ES | West Henrietta | NY | B | Henrietta (S255) 345 kV Substation | RG&E | 0 | 2024-05-31
1458 | SED NY Holdings LLC | TableTop Solar II | 2022-11-07 | 20 | 20 | S | Montgomery | NY | F | Clinton ERCC - Clinton Tap 115kV | NM-NG | 0 | 2024-05-31
1459 | ELP Chatham Storage LLC | ELP Chatham Storage | 2022-11-17 | 20 | 20 | ES | Columbia | NY | F | Chatham 34.5kV Substation | NYSEG | 0 | 2023-01-31
1460 | Bay State Wind | NY Wind - Pilgrim Uprate | 2022-11-08 | 1400 | 1400 | W | Suffolk County | NY | K | Pilgrim 138 kV | LIPA | 0 | 2024-05-31
1461 | Genesee County Economic Devel. | WNY STAMP | 2022-11-08 |  |  |  | Genesee | NY | B | Kintigh/Niagara - New Rochester 345kV | NYPA | 0 | 2022-12-31
1462 | Kearsarge Solar | Kearsarge Gloversville | 2022-11-11 | 20 | 20 | S | Fulton | NY | F | Gloversville - Hill Street #3 69kV | NM-NG | 0 | 2023-11-30
1463 | Bluewave Storage Origination LLC | NY Amsterdam 516 Millers Corners Rd Storage | 2022-11-11 | 430 | 430 | ES | Montgomery | NY | E | Edic to Princetown 345 kV transmission line ? Ckt ID 1 | LS Power | 0 | 2023-06-30
1464 | EDF Renewables inc. | Sage Creek Solar | 11/11/2022 | 250 | 250 | S | Oswego | NY | C | Edic - Fitzpatrick 345 kV | NYPA/NM-NG | 0 | 2023-03-31
1466 | Bluewave Storage Origination LLC | NY New Paltz 540 State Rte 32 S Storage | 11/15/2022 | 217 | 220.7 | ES | Ulster | NY | G | Modena-Ohioville 115 kV line | CHGE | 0 | 2023-03-31
1467 | Origis Development | Homer Hill Storage | 2022-11-16 | 54.7 | 54.7 | ES | Cattaraugus | NY | A | Homer Hill 34.5 kV Substation | NM-NG | 0 | 2024-05-31
1468 | Bay State Wind | NY Wind - Mott Haven Uprate | 2022-11-16 | 128 | 128 | W | The Bronx | NY | J | Mott Haven 345 kV | ConEd | 0 | 2024-05-31
1469 | YSG | Commodore | 2022-11-17 | 1200 | 1200 | ES | Oneida County | NY | E | connection to a new breaker position on the 345 kV Bus (Bus #147833) at Marcy | NYPA | 0 | 2023-01-31
1470 | ABUNDANT SOLAR POWER (US-NY-MARKHAM HOLLOW RD-001) LLC | Suny Fabius - Transmission Connected Solar PV Project | 2022-11-18 | 18 | 18 | S | Tully | NY | C | Tilden - Cortland 18 115kV | NM-NG | 0 | 2024-05-31
1471 | Crossbuck Energy Storage LLC | Crossbuck Energy Storage LLC | 2022-11-22 | 100 | 100 | ES | Greene County | NY | G | Coxsackie 69 kV substation | CHG&E | 0 | 2024-09-30
1472 | Origis Development | Highland Storage | 2022-11-23 | 115.1 | 115.1 | ES | Ulster | NY | G | Marlboro 115 kV Substation | CHG&E | 0 | 2024-05-31
1473 | Capital Region Energy Storage LLC | Leeds BESS Project | 2022-11-28 | 600 | 600 | ES | Greene | NY | F | Leeds 345 kV substation | NM-NG | 0 | 2024-05-31
1474 | Bluewave Storage Origination LLC | NY Catskill 0 Route 9W Storage | 11/29/2022 | 245 | 245 | ES | Greene | NY | G | 115 kV North Catskill-Churchtown 5 Line and Feura Bush -North Catskill 2 Line | NM-NG | 0 | 2023-03-31
1475 | SR1 Shift NY I | Upper Falls Solar | 2022-11-29 | 46 | 46 | CR | Wyoming | NY | B | Line 907 Substation 162, Alleghany (S1185) and Houghton Substation (S180). 115kV | RG&E | 0 | 2024-05-31
1476 | Vineyard Mid-Atlantic LLC | Vineyard Mid-Atlantic 3 | 2022-11-30 | 1330 | 1330 | W | Nassau | NY | K | East Garden City 345 kV Substation | NYPA | 0 | 2024-05-31
1477 | Terra-Gen Development Company | Nine Mile Wind Farm | 11/30/2022 | 120 | 120 | W | Allegany | NY | A | Homer Hill 115kV Substation (135282) | NM-NG | 0 | 2023-04-30
1478 | Mount Hope Stand Alone Storage 1, LLC | Mount Hope Stand Alone Storage | 2022-11-30 | 50 | 50 | ES | Orange | NY | G | 69 kV Line 13 - Cuddlebackville to Shoemaker Substation | O&R | 0 | 2024-03-31
1479 | Emeren US, LLC | Cedar Lake Solar | 2022-11-30 | 8.4 | 8.4 | CR | St. Lawrence | NY | E | Mine Road - Colony 34.5 kV Line 28 (ES 899) | NM-NG | 0 | 2024-02-29
1480 | Renesola Power Holdings LLC | Perryville Solar | 2022-12-01 | 18.6 | 18.6 | CR | Madison | NY | C | Chittenango-Rathbun 34.5kV line | NM-NG | 0 | 2022-12-31
1481 | Renesola Power Holdings LLC | Rush Creek Solar | 2022-12-01 | 19.9 | 19.9 | CR | Onondaga | NY | C | Tilden Station-Cardiff/Lords Hill 34.5kV | NM-NG | 0 | 2022-12-31
1482 | Renesola Power Holdings LLC | Quarry Solar | 2022-12-01 | 19.9 | 19.9 | CR | Madison | NY | C | Perryville-Whitman 34.5kV | NM-NG | 0 | 2022-12-31
1483 | Emeren US, LLC | Battle Hill Solar | 2022-12-01 | 35 | 35 | CR | St. Lawrence | NY | E | Battle Hill 115kV Substation | NM-NG | 0 | 2023-06-30
1485 | Sandlot Energy LLC | Sandlot | 2022-12-15 | 600 | 600 | ES | Suffolk County | NY | K | Northport - Pilgrim 138kV Line (138-679A&B) | LIPA | 0 | 2024-05-31
1486 | Bluewave Storage Origination LLC | NY Whitesboro 0 Westmoreland Rd Storage | 2022-12-16 | 40 | 40 | ES | Oneida | NY | E | Oneida - Yahnundasis #6 115kV | NM-NG | 0 | 2024-02-29
1487 | ACE DevCo NC, LLC | Three Rivers Energy Storage | 2022-12-22 | 80 | 80 | ES | Onondaga | NY | C | Curtis Street - Teall 115 kV Line #13 | NM-NG | 0 | 2024-07-31
1488 | ACE DevCo NC, LLC | Speckhardt Energy Storage | 2022-12-22 | 100 | 100 | ES | Rensselaer | NY | F | Greenbush 115 kV Substation | NM-NG | 0 | 2024-03-31
1489 | ACE DevCo NC, LLC | Block Perch Solar | 2022-12-22 | 100 | 100 | S | Chautauqua | NY | A | Moons to Falconer 115 kV Line #175 | NM-NG | 0 | 2024-09-30
1490 | ACE DevCo NC, LLC | Westtown Energy Storage | 2022-12-22 | 100 | 100 | ES | Orange County | NY | G | Westtown 69 kV Substation | O&R | 0 | 2024-11-30
1491 | ACE DevCo NC, LLC | Wallkill Energy Storage | 2022-12-22 | 100 | 100 | ES | Ulster County | NY | G | Ohioville 115 kV Substation Bus 2 | CHG&E | 0 | 2023-04-30
1492 | ACE DevCo NC, LLC | Sidecar Solar | 2022-12-22 | 100 | 100 | S | Tioga | NY | C | 115 kV South Owego Substation | NYSEG | 0 | 2024-05-31
1493 | Queensboro Development, LLC | Queensboro Renewable Express Circuit A | 2022-12-21 | 1310 | 1310 | W | Queens | NY | J | Rainey and Vernon Substations | ConEd | 0 | 2024-08-01
1494 | ACE DevCo NC, LLC | Wishbone Solar | 2022-12-22 | 200 | 200 | S | Steuben | NY | C | Canandaigua to Stony Ridge 230 kV Line | NYSEG | 0 | 2024-11-30
1495 | ACE DevCo NC, LLC | Argos Solar | 2022-12-22 | 150 | 150 | S | Tompkins | NY | C | Etna 115 kV substation | NYSEG | 0 | 2024-11-30
1496 | Yellow Feather Energy Center | Yellow Feather Energy Center | 2022-12-22 | 110 | 110 | S | Montgomery | NY | F | Inghams to Center Street 115 kV Line Tap | NM-NG | 0 | 2024-05-31
1497 | Sweet Valley Energy Center | Sweet Valley Solar | 2022-12-22 | 200 | 200 | S | Genesee | NY | B | Dysinger - Station 255 (Henrietta) #1 345kV line | NYPA | 0 | 2024-05-31
1498 | Sweet Valley Energy Center | Sweet Valley Storage | 2022-12-22 | 200 | 200 | ES | Genesee | NY | B | Dysinger - Station 255 (Henrietta) #1 345kV line | NYPA | 0 | 2024-05-31
1499 | RWE Solar Development | Farmhouse BESS | 2022-12-29 | 150 | 150 | ES | Orange | NY | G | Roseton 345 kV Substation | CHG&E | 0 | 2024-05-31
1500 | RWE Solar Development | Sullivan County Solar & BESS | 2023-01-05 | 200 | 200 | CR | Sullivan | NY | E | Coopers Corner - Middletown Tap 345 kV line | NYPA | 0 | 2024-05-31
1501 | RWE Solar Development | Zulu BESS | 2023-01-06 | 150 | 150 | ES | Orange | NY | G | Bethlehem Road 115 kV Substation | CHG&E | 0 | 2024-05-31
1502 | Oswego Clean Energy LLC | Oswego Solar | 2023-01-13 | 24.9 | 24.9 | S | Oswego | NY | C | Oswego 115 kV Substation | NM-NG | 0 | 2024-07-31
1503 | Bay State Wind | NY Wind - Pilgrim CSR | 2023-01-15 | 1400 | 1400 | CW | Suffolk County | NY | K | Pilgrim 138 kV | LIPA | 0 | 2024-05-31
1504 | Bay State Wind | NY Wind - Mott Haven CSR | 2023-01-15 | 1400 | 1400 | CW | The Bronx | NY | J | Mott Haven 345 kV | ConEd | 0 | 2024-05-31
1505 | East Setauket energy Storage, LLC | East Setauket Energy Storage II | 2023-01-19 | 300 | 300 | ES | Suffolk | NY | K | Holbrook to Miller Place 138kV | LIPA | 0 | 2024-05-31
1506 | Sourdough Energy Storage LLC | Sourdough Energy Storage LLC | 2023-01-24 | 100 | 100 | ES | Suffolk County | NY | K | Pulaski 69kV substation | LIPA | 0 | 2024-10-31
1507 | Ramapo Storage Project 1 | Ramapo Storage Project 1 | 2023-01-31 | 500 | 500 | ES | Rockland | NY | G | Ramapo Substation (345kV) | ConEd | 0 | 2024-05-31
1508 | Robin MDS BESS, LLC | Robin MDS BESS | 1/31/2023 |  |  | ES | Niagara | NY | A | Robinson Road 34.5 kV | NYSEG | 0 | 2023-04-30
1509 | ACE DevCo NC, LLC | Cayuga Solar | 2023-02-01 | 100 | 100 | S | Tompkins | NY | C | Milliken (Cayuga) 115 kV Substation | NYSEG | 0 | 2023-04-30
1510 | Ramapo Storage Project 2 | Ramapo Storage Project 2 | 2023-02-02 | 500 | 500 | ES | Rockland | NY | G | Ramapo Substation (345kV) | ConEd | 0 | 2024-05-31
1511 | Palladium Storage LLC | Palladium Storage | 2023-02-03 | 255 | 255 | ES | Bronx | NY | J | Mott Haven 138 kV substation | ConEd | 0 | 2024-05-31
1512 | Delaware River Solar | Prospect Hill Road | 2023-02-08 | 20 | 20 | S | Orange | NY | G | 69 kV Mongaup to Cuddebackville | O&R | 0 | 2023-07-31
1513 | Watson Storage LLC | Watson Storage System #1 | 2023-02-08 | 50 | 50 | ES | Queens | NY | J | Glendale 27kV Substation | ConEd | 0 | 2023-02-28
1514 | Watson Storage LLC | Watson Storage System #2 | 2023-02-08 | 50 | 50 | ES | Queens | NY | J | Glendale 27kV Substation | ConEd | 0 | 2023-02-28
1515 | Solaris Energy Storage LLC | Solaris Energy Storage | 2023-02-09 | 270 | 270 | ES | Kings | NY | J | Greenwood 138kV Substation | ConEd | 0 | 2024-05-31
1516 | Fort Edward Solar | Fort Edward Solar Farm (NY53) | 2023-02-10 | 100 | 100 | S | Washington | NY | F | Mohican-Battenkill 115kV Line #15 | NM-NG | 0 | 2023-02-28
1517 | Newport Deerfield Solar | NY115 - Newport Solar | 2023-02-13 | 130 | 130 | S | Oneida | NY | E | Porter - Deerfield 115 kV (Line#9) | NM-NG | 0 | 2023-02-28
1518 | Hodson Energy Rush LLC | Rush Solar & BESS | 2023-02-13 | 21 | 21 | CR | Monroe | NY | B | Mortimer to Golah 115kV | NM-NG | 0 | 2024-05-31
1519 | SATURN ENERGY STORAGE | Dayton Energy Storage Project | 2023-02-13 | 20 | 20 | ES | Cattaraugus | NY | A | 34.5 kV Dayton substation | NYSEG | 0 | 2024-05-31
1520 | SATURN ENERGY STORAGE | Nile Energy Storage Project | 2023-02-13 | 20 | 20 | ES | Allegany | NY | A | 34.5 kV Nile substation | RGE | 0 | 2023-06-30
1521 | Iroquois Gas Transmission System | IGTS Wright EMD Compressor | 2/14/2023 |  |  |  | Schoharie | NY |  | Rotterdam - New Scotland #13 115kV line | NM-NG | 0 | 2023-04-30
1522 | Iroquois Gas Transmission System | GTS Dover EMD Compressor | 2/15/2023 |  |  |  | Dutchess | NY | G | Pleasant Valley - Cricket Valley 345kV | ConEd | 0 | 2023-04-30
1523 | Foothills Solar | Foothills Solar | 2023-02-15 | 40 | 40 | S | Fulton | NY | F | Vails Mills-Northville 69kV | NGrid | 0 | 2023-02-28
1524 | Hodson Energy Little Falls LLC | Little Falls Solar & BESS | 2023-02-21 | 83.2 | 78 | CR | Herkimer | NY | E | Inghams 115kV - Watkins Road 115kV | NM-NG | 0 | 2024-05-31
1525 | ELP Clay Storage LLC | ELP Clay Storage | 2023-02-24 | 165 | 165 | ES | Onondaga | NY | C | 115 kV Line #7 Clay-Lighthouse Hill | NM-NG | 0 | 2024-05-31
1526 | Radial Power LLC (Radial Power BESS NY LLC) | OATT NYISO Tuxedo Project | 2/25/2023 | 5 | 5 | ES | Orange County | NY | G | 55 NY 17, Tuxedo Park, NY 10987 | O&R | 0 | 2023-03-31
1527 | Hollyhock Solar, LLC | Hollyhock Solar | 2/28/2023 |  |  | CR | Albany | NY | F | Leeds-New Scotland 115 kV | NM-NG | 0 | 2023-04-30
1528 | Coopers Corner Storage Project 1 LLC | Coopers Corner Storage Project 1 | 2023-03-02 | 250 | 250 | ES | Sullivan | NY | E | Coopers Corners 345 kV substation | NYSEG | 0 | 2024-05-31
1529 | Coopers Corner Storage Project 2 LLC | Coopers Corner Storage Project 2 | 2023-03-02 | 250 | 250 | ES | Sullivan | NY | E | Coopers Corners 345 kV Substation | NYSEG | 0 | 2024-05-31
1530 | New York Power Authority | Westchester Wind | 2023-03-02 | N/A | N/A | AC | Westchester | NY | I | Sprainbrook-Eastview 345kV #1N, #1S, and #2S. | ConEd | 0 | 2023-05-31
1531 | SATURN ENERGY STORAGE | Alden Energy Storage Project | 2023-03-07 | 17.3 | 17.3 | ES | Erie | NY | A | 34.5 kV Alden substation | NYSEG | 0 | 2023-05-31
1532 | Beaver Falls, LLC | Beaver Falls Energy Storage | 2023-03-07 | 79 | 79 | ES | Lewis | NY | E | Adirondack Substation 115kV | NYPA | 0 | 2024-05-31
1533 | Syracuse, LLC | Syracuse Energy Storage | 2023-03-07 | 79 | 79 | ES | Onondaga | NY | C | Kamine Syracuse 115 kV substation | NM-NG | 0 | 2024-05-31
1534 | ACE DevCo NC, LLC | Westtown II Energy Storage | 2023-03-08 | 20 | 20 | ES | Orange County | NY | G | Westtown 69 kV substation | O&R | 0 | 2024-11-30
1535 | Eden Renewables | New Scotland BES 1 and 2 | 2023-03-10 | 1350 | 1350 | ES | Albany | NY | F | New Scotland 345 kV Substation | NM-NG | 0 | 2024-05-31
1537 | Nexamp Solar | Pulaski Street Storage | 2023-03-28 | 20 | 20 | ES | Suffolk | NY |  | Tuthill-Riverhead 69kV Line | LIPA | 0 | 2023-08-31
1538 | SATURN ENERGY STORAGE | Kenmore Energy Storage Project | 2023-03-20 | 20 | 20 | ES | Erie | NY | A | National Grid 115kV Line 46, 2.98 miles from Praxair (Buffalo Sewer) 115kV station and 3.21 miles from Huntley 115kV station. | NM-NG | 0 | 2023-06-30
1539 | GSI Development Corp. | Mulberry Energy Storage Project | 2023-03-30 | 20 | 20 | ES | Erie | NY | F | 34.5 kV Mulberry substation | NYSEG | 0 | 2024-03-31
1540 | Nexamp | Cayuta Add-on | 2023-03-20 | 2 | 2 | ES | Schuyler | NY | C | The POI will be located 1.78mi from Cayuta 34.5kV substation and 11.78mi from Ridge Road 230kV substation. Utilizes the same gen-tie line to deliver power to the POI at existing 34.5 kV pole located at 42.272362°, -76.731007° | NYSEG | 0 | 2023-05-31
1541 | Nexamp Solar | Stonewall Add-on | 2023-03-27 | 19.7 | 19.7 | ES | Delaware | NY | E | Fraser - Colliers 115 kV | NYSEG | 0 | 2024-09-30
1542 | Blue Sky Interconnect, LLC. | Blue Sky Interconnect 1 | 2023-03-28 | 1310 | 1310 | W | Brooklyn | NY |  | Gowanus to Farragut 345 kV Line #41 and #42 | ConEd | 0 | 2023-08-31
1543 | Blue Sky Interconnect, LLC | Blue Sky Interconnect 2 | 2023-03-28 | 2620 | 2620 | W | Brooklyn | NY |  | Gowanus to Farragut 345 kV Line #41 and #42 | ConEd | 0 | 2023-08-31
1544 | EDF renewables inc. | Sage Creek Solar | 2023-03-30 | 250 | 250 | S | Oswego | NY | C | Edic to Fitzpatrick 345 kV line | NYPA/NM-NG | 0 | 2023-07-31
1545 | Elevate Arthur Kill, LLC | Elevate Arthur Kill II, LLC | 2023-04-10 | 180 | 180 | ES | Richmond | NY | J | Fresh Kills 345 kV substation | ConEd | 0 | 2024-05-31
1546 | Port Jefferson Energy Storage, LLC | Port Jefferson Energy Storage | 2023-04-21 | 400 | 400 | ES | Suffolk | NY | K | Port Jefferson 138kV station | LIPA | 0 | 2024-05-31
1547 | South Suffolk Energy Storage | South Suffolk Energy Storage | 2023-04-21 | 100 | 100 | ES | Suffolk | NY | K | Centereach 69 kV Substation | LIPA | 0 | 2024-05-31
1548 | Holbrook Energy Storage | Holbrook II Energy Storage | 2023-04-21 | 400 | 400 | ES | Suffolk | NY | K | West Bus 138 kV Substation | LIPA | 0 | 2024-05-31
1549 | Rolling Upland Wind Farm LLC | Rolling Upland Wind Farm LLC | 2023-04-25 | 79.8 | 79.8 | W | Madison | NY | E | County-Brothertown Line 115kV | NYSEG | 0 | 2024-05-31
1550 | KCE NY 35, LLC | KCE NY 35 | 2023-04-27 | 200 | 200 | ES | Greene | NY | F | Leeds 345kV substation | NM-NG | 0 | 2024-05-31
1551 | Terra-Gen Development Company, LLC | Nine Mile Wind Energy | 2023-05-04 | 200 | 200 | W | Allegany | NY | A | Homer Hill 115kV Substation | NM-NG | 0 | 2023-06-30
1552 | Emeren US, LLC | Kettlebail Solar | 2023-05-09 | 250 | 250 | CR | Cortland | NY | C | Clarks Corner - Lafayette Station 345 kV | NM-NG | 0 | 2024-05-31
1553 | KCE NY 36, LLC | KCE NY 36 LLC | 2023-05-09 | 150 | 150 | ES | Oneida | NY | E | Yahnundasis substation 115kV | NM-NG | 0 | 2024-04-30
1554 | RWE Solar Development | Sullivan County Solar & BESS Uprate | 2023-05-10 | 60 | 60 | CR | Sullivan | NY | E | Coopers Corner - Middletown Tap 345 kV line | NYPA | 0 | 2024-05-31
1556 | North Bergen Liberty Generating | Liberty BESS | 2023-05-12 | 600 | 600 | ES | Hudson County | NJ | J | W49th St 345kV substation | ConEd | 0 | 2024-05-31
1557 | Blue Spruce Storage LLC | Blue Spruce Storage | 2023-05-18 | 245 | 245 | ES | Bronx | NY | J | Hell Gate Annex 138KV Substation | NYPA | 0 | 2024-05-31
1558 | Roma Storage LLC | Roma Storage | 2023-05-18 | 255 | 255 | ES | Queens | NY | J | Astoria East 138KV Substation | ConEd | 0 | 2024-05-31
1559 | SED NY Holdings LLC | Flat Creek Storage | 2023-05-22 | 300 | 300 | ES | Montgomery | NY | F | Edic to Princetown 345kV Line 352 | NYPA | 0 | 2024-05-31
1560 | YSG Land Holdings, LLC | Ramadi Utility | 2023-05-26 | 136 | 140 | ES | Suffolk | NY | K | 138 KV LIPA Transmission System at LIPA Existing Sills Road Substation | LIPA | 0 | 2023-07-31
1561 | Wild Ox Solar Project, LLC | Wild Ox Solar | 2023-05-31 | 131.7 | 131.7 | CR | Yates | NY | C | Eelpot Rd to Flat St 115 kV | NYSEG | 0 | 2024-05-31
1562 | Iris Bloom Solar Project | Iris Bloom Solar Project, LLC | 2023-06-02 | 151.8 | 151.8 | CR | Chautauqua | NY | A | Moon Road Sub, 115 kV | NM-NG | 0 | 2024-05-31
1563 | Middletown Energy Storage LLC | Middletown Energy Storage | 2023-06-07 | 100 | 100 | ES | Orange | NY | G | Shoemaker-Chester 138kV line #27 | O&R | 0 | 2024-05-31
1564 | Terra-Gen Development Company, LLC | Arch Energy Storage | 2023-06-07 | 250 | 250 | ES | Orange | NY | G | Rock Tavern 345kV Substation | CHGE | 0 | 2024-07-31
1565 | North River Development, LLC | North River | 2023-06-09 | 1310 | 1310 | DC | Sullivan and Queens | NY | E, J | Coopers Corner 345 kV substation (sending) and Rainey 345 kV substation (receiving) | NYSEG, ConEd | 0 | 2024-05-31
1566 | Golden Knight Solar, LLC | Golden Knight Solar | 2023-06-13 | 140 | 140 | S | St. Lawrence | NY | D | Colton to Malone Line #3 115kV | NM-NG | 0 | 2024-05-31
1567 | Anbaric Development Partners | Hera Power Link 1200 | 2023-06-14 | 0 | 0 | DC | Kings County | NY |  | Brooklyn Clean Energy Hub 345kV | ConEd | 0 | 2023-08-31
1568 | Anbaric Development Partners | Hera Power Link 1500 | 2023-06-14 | 0 | 0 | DC | Kings County | NY |  | Brooklyn Clean Energy Hub 345kV | ConEd | 0 | 2023-08-31
1569 | Appian Way Energy Partners East LLC | Meyer XF Upgrade Proposal | 2023-06-16 |  |  | AC | Livingston | NY |  | MEYER 115kV_1 BK4S, MEYER 230kV_1 BK4P | NYSEG | 0 | 2023-08-31
1570 | QMB 2 Energy Storage, LLC | QMB2 Storage II | 2023-06-20 | 200 | 200 | ES | Queens | NY | J | Corona 138kV station | ConEd | 0 | 2024-05-31
1571 | Marathon Power LLC | Marathon | 2023-06-22 | 59 | 59 | ES | Suffolk County | NY | K | Greenlawn 138kV Substation | LIPA | 0 | 2024-05-31
1572 | Empire Reserve Energy, LLC | Orchard BESS | 2023-06-23 | 80 | 80 | ES | Ulster County | NY | G | 115 kV Modena Substation | CHGE | 0 | 2024-05-31
1573 | Empire Reserve Energy, LLC | Sugarloaf BESS | 2023-06-23 | 180 | 180 | ES | Orange County | NY | G | 138kV Sugarloaf Substation | O&R | 0 | 2024-05-31
1574 | Mission Clean Energy | Cassiopeia Energy Center | 2023-06-27 | 200 | 200 | ES | Onondaga | NY | C | Geres Lock 115 kV Substation | NM-NG | 0 | 2024-05-31
1575 | NJR Clean Energy Ventures III Corporation | Barrington Solar | 2023-06-29 | 18.4 | 18.4 | S | Yates | NJ | C | Porter's corner to Dundee 34.5kV Line, Line #594 | NYSEG | 0 | 2024-11-30
1576 | ACE DevCo NC, LLC | Riptide Storage | 2023-07-06 | 200 | 200 | ES | Suffolk | NY | K | Edwards Avenue 138 kV Substation | LIPA | 0 | 2024-09-30
1577 | ACE DevCo NC, LLC | Gillie Brook Solar | 2023-07-06 | 200 | 200 | S | Onondaga | NY | C | Elbridge 115 kV Substation | NM-NG | 0 | 2024-04-30
1578 | Saturn Energy Storage | Alden Energy Storage Project | 2023-07-11 | 17.1 | 17.1 | ES | Erie | NY | A | Alden 34.5kV | NYSEG | 0 | 2023-10-31
1579 | ELP Holland Solar LLC | ELP Holland Solar | 2023-07-13 | 20 | 20 | CR | Erie | NY | A | A new 34.5kV three breaker ring bus switching station, tapped on the NYSEG?s existing 34.5 kV line #520 from NYSEG?s Cobble Hill_34.5 kV to NYSEG?s Stolle Rd_34.5 kV. 10.5 miles from Cobble Hill_34.5 kV, 17 miles to Stolle Rd_34.5 kV. | NYSEG | 0 | 2023-09-30
1580 | Terra-Gen Development Company | Alcazar Energy Storage | 2023-07-17 | 250 | 250 | ES | Ulster | NY | G | Hurley 345kV Substation | CHGE | 0 | 2024-05-31
1581 | Nexamp Solar | Mud Mill Storage | 2023-07-17 |  |  | ES | Onondaga | NY | C | Bartell 13.2kV Substation | NM-NG | 0 | 2023-07-31
1582 | Nexamp Solar | Moreau Storage | 2023-07-17 |  |  | ES | Saratoga | NY | F | Hudson Falls-McCrea St 17 Sub-Transmission 34.5kV line | NM-NG | 0 | 2023-09-30
1583 | Liberty Renewables | Agricola Wind 2 | 2023-07-21 | 79.3 | 79.3 | W | Cayuga | NY | C | 115kV line # 973 from Milliken to Wright Ave | NYSEG | 0 | 2024-05-31
1584 | PA-Hockenberry | PA-Hockenberry | 2023-07-28 | 400 | 400 | S | Jefferson | PA | A | Homer City - Pierce Brook 345 kV | NYSEG | 0 | 2024-05-31
1585 | Bear Peak Power LLC | BPP NY Lansing BESS I | 2023-07-31 | 200 | 200 | ES | Tompkins | NY | C | Milliken 115 kV Substation | NYSEG | 0 | 2024-05-31
1586 | RWE Solar Development | Basecamp BESS | 2023-07-31 | 170 | 170 | ES | Chautauqua | NY | A | Arkwright 115 kV Substation | NM-NG | 0 | 2024-05-31
1587 | RWE Solar Development | Erie Canal BESS | 2023-07-31 | 230 | 230 | ES | Niagara | NY | A | Robinson Road 115 kV | NYSEG; | 0 | 2024-05-31
1588 | NYSERDA | BR Project 2 | 2023-08-01 | 14.5 | 14.5 | CR | Tompkins | NY | C | Peruville 34.5kV Substation | NYSEG | 0 | 2024-05-31
1589 | Grid Connected Infrastructure, LLC | Lighthouse Energy Storage | 2023-08-07 | 250 | 250 | ES | Monroe | NY | A | Dunkirk to Gardenville 230 kV line #74 | NM-NG | 0 | 2024-05-31
1590 | Grid Connected Infrastructure, LLC | Icebox Energy Storage | 2023-08-07 | 202.3 | 202.3 | ES | Onondaga | NY | C | Solvay Station 57 115kV | NM-NG | 0 | 2024-05-31
1592 | Jupiter Power LLC | EGC BESS II | 2023-08-16 | 200 | 200 | ES | Nassau | NY | K | East Garden City 345kV bus | NYPA | 0 | 2024-05-31
1593 | Bluewave Origination LLC | NY New Scotland 99 New Scotland South Rd Storage | 2023-08-17 | 181.4 | 181.4 | ES | Albany | NY | F | 115 kV New Scotland substation | NM-NG | 0 | 2024-05-31
1594 | Budbreak Solar, LLC | Budbreak Solar I | 2023-08-23 | 100 | 100 | S | Yates | NY | C | Greenidge to Montour Falls 115kV Line | NYSEG | 0 | 2024-05-31
1595 | Budbreak Solar, LLC | Budbreak Solar II | 2023-08-23 | 100 | 100 | S | Yates | NY | C | Greenidge Substation | NYSEG | 0 | 2023-12-31
1596 | Budbreak Storage, LLC | Budbreak Storage I | 2023-08-23 | 100 | 100 | ES | Yates | NY | C | Greenidge to Montour 115kV Line | NYSEG | 0 | 2024-05-31
1597 | Budbreak Storage, LLC | Budbreak Storage II | 2023-08-23 | 100 | 100 | ES | Yates | NY | C | Greenidge to Texas Eastern 115kV Line | NYSEG | 0 | 2024-05-31
1598 | Nexamp Solar | Green Street Storage | 2023-08-25 |  |  | ES | Cayuga | NY | C | Green Street 34.5kV | NYSEG | 0 | 2023-12-31
1599 | Braen Energy LLC | Braen Energy Storage Project | 2023-08-31 | 500 | 500 | ES | Rockland | NY | G | Con Edison Ramapo Substation | ConEd | 0 | 2023-10-31
1600 | Andrew van Doorn | NY - 74 Michigan Hill Rd - 1 | 2023-08-31 |  |  | S | Tioga | NY | C | Feeder: 4304201 34.5kv Substation: NYS-HARFORD 524 | NYSEG | 0 | 2023-09-30
1601 | Andrew van Doorn | NY - 74 Michigan Hill Rd - 2 | 2023-08-31 |  |  | S | Tioga | NY | C | Feeder: 4304201 Substation: NYS-HARFORD 524 | NYSEG | 0 | 2023-09-30
1602 | Roma Storage LLC | Roma Storage 2 | 2023-09-05 | 255 | 255 | ES | Queens | NY | J | ConEd Vernon 138KV Substation | ConEd | 0 | 2023-10-31
1603 | Blue Frost Energy Center, LLC | Blue Frost | 2023-09-05 | 400 | 400 | ES | Montgomery | NY | F | Princetown - Edic 345 kV | LS Power | 0 | 2024-05-31
1604 | Blue Frost Energy Center, LLC | Blue Frost | 2023-09-05 | 400 | 400 | ES | Montgomery | NY | E | Marcy - New Scotland 345 kV | NM-NG | 0 | 2024-05-31
1605 | Grid Connected Infrastructure, LLC | Eastwater Energy Storage | 2023-09-07 | 101.1 | 101.1 | ES | Onondaga | NY | B | Mortimer 115 kV Bus | NM-NG | 0 | 2023-11-30
1606 | Jericho Solar Park | Jericho Solar | 2023-09-11 | 100 | 100 | S | Franklin | NY | D | NYPA's Willis Sub @115kV | NYPA | 0 | 2024-05-31
1607 | North Creek Solar LLC | 117656 North Creek Solar+Storage | 2023-09-14 | 206.7 | 206.7 | CR | Herkimer | NY | E, F | Edic- Gordon Road 345 kV Line #14 | NM-NG | 0 | 2024-05-31
1608 | Consolidated Edison | Fresh Kills Battery Storage | 2023-09-20 | 11.6 | 11.6 | ES | USA | NY | J | Fresh Kills Substation | ConEd | 0 | 2023-09-30
1609 | Bear Peak Power | BPP NY Somerset BESS I | 2023-09-22 | 200 | 200 | ES | Niagara | NY | A | NYSEG KINTIGH 345 kV Station. | NYSEG | 0 | 2024-05-31
1610 | Bluepoint Wind LLC | Bluepoint Wind 1 | 2023-09-26 | 1310 | 1310 | W | Brooklyn County | NY | J | Brooklyn Clean Energy Hub 345 kV | ConEd | 0 | 2024-05-31
1611 | Bluepoint Wind LLC | Bluepoint Wind 2 | 2023-09-26 | 1310 | 1310 | W | Kings County | NY | J | Gowanus 345 kV | ConEd | 0 | 2024-05-31
1612 | Bluepoint Wind LLC | Bluepoint Wind 3B | 2023-09-26 | 1310 | 1310 | W | Richmond | NY | J | Goethals- Gowanus 345 kV underground transmission lines #25 and #26 | ConEd | 0 | 2024-02-29
1613 | Bluepoint Wind LLC | Bluepoint Wind 4 | 2023-09-26 | 1381.8 | 1381.1 | W | Nassau | NY | K | East Garden City 345 kV | NYPA | 0 | 2024-05-31
1614 | Bluepoint Wind LLC | Blue Point Wind 3A | 2023-09-26 | 1310 | 1310 | W | Richmond | NY | J | Goethals - Gowanus 345 kV underground transmission lines #25 and #26 | ConEd | 0 | 2024-05-31
1615 | KCE NY 38 LLC | KCE NY 38 | 2023-09-26 | 250 | 250 | ES | Columbia | NY | F | Transco 115kV Churchtown substation bus | Transco | 0 | 2024-07-31
1616 | YSG Community Solar | Ramadi Utility | 2023-09-27 | 140 | 140 | ES | Suffolk | NY | K | Sills Road 138kV Substation | LIPA | 0 | 2024-05-31
1617 | P&M Brick LLC | POWI Project | 2023-09-27 |  |  |  | Albany | NY |  | 345 Interconnection to Line between New Scotland and Knickerbocker 69 kV Interconnection to CHG&E 69kV Loop, | NM-NG, CHGE and NY Transco | 0 | 2024-01-31
1618 | Nexamp Solar | Cayuta Add-on | 2023-10-10 | 2 | 2 | ES | Schuyler | NY | C | Cayuta - Ridge Road 34.5 kV line, Line#501 | NYSEG | 0 | 2024-04-30
1619 | Braen Energy LLC | Braen Energy Storage Phase 1 | 2023-10-11 | 500 | 500 | ES | Rockland | NY | G | Ramapo 345 kV | ConEd | 0 | 2024-07-31
1620 | Nexamp Solar | Jerry Smith Storage | 2023-10-12 | 20 | 20 | ES | Tompkins | NY | C | Miliken- Ludlowville 34.5kV line | NYSEG | 0 | 2024-05-31
1621 | BPUS Generation Development LLC | Porter Energy Storage | 2023-10-12 | 50 | 50 | ES | Essex | NY | F | 115kV Hague Road Substation | NM-NG | 0 | 2024-05-31
1622 | BPUS Generation Development LLC | Hudson Energy Storage | 2023-10-17 | 200 | 200 | ES | Greene | NY | F | 345kV Leeds Substation | NM-NG | 0 | 2024-05-31
1623 | Emeren US, LLC | Altona Energy Storage | 2023-10-25 | 19.9 | 19.9 | ES | Clinton | DE | D | 46 kV bus at the NYSEG Flat Rock Substation | NYSEG | 0 | 2024-03-31
1624 | Emeren US, LLC | Lake City Storage | 2023-10-25 | 120 | 120 | ES | Clinton | NY | D | Lyon Mountain - Kent Falls 115 kV line | NYSEG | 0 | 2024-05-31
1625 | Emeren US, LLC | Marble River Storage | 2023-10-25 | 160 | 160 | ES | Clinton | NY | D | NYPA 230 kV Ryan Substation | NYPA | 0 | 2024-05-31
1626 | HW Power, LLC | Cross County Energy Storage | 2023-10-25 | 200 | 200 | ES | Westchester | NY | H, I | Eastview to Buchanan 345kV line | ConEd | 0 | 2024-09-30
1628 | Anbaric Development Partners | Hera Power Link 1200 | 2023-11-02 | 1200 | 1200 | DC | Kings | NY | J | Brooklyn Clean Energy Hub 345 kV | ConEd | 0 | 2024-04-30
1629 | Anbaric Development Partners | Hera Power Link 1500 | 2023-11-02 | 1500 | 1500 | DC | Kings | NY | J | Brooklyn Clean Energy Hub 345 kV | ConEd | 0 | 2024-04-30
1630 | Orange & Rockland | Suffern Quarry Data Center | 2023-11-03 |  |  |  | Rockland | NY | G | We anticipate a new substation being built on our site off of a transmission line tower that abuts our property. Additionally, we may need to tie in for redundancy to the Hillburn Area Substation | O&R | 0 | 2023-12-31
1631 | Eden Renewables | New Scotland BESS | 2023-11-03 | 1350 | 1350 | ES | Albany | NY | F | Princetown - New Scotland 345kv Line | NM-NG | 0 | 2024-01-31
1632 | Shallow Seam Energy Storage | Shallow Seam BESS | 2023-11-08 | 400 | 400 | ES | Clearfield | PA | C | Homer City to Mainesburg 345 kV Line | NYSEG | 0 | 2024-05-31
1633 | Robert Delcalzo | Suffern Quarry Data Center | 2023-11-13 |  |  |  | Rockland | NY | G | There is a 135kv line abutting our property. We will be building a substation. We currently connect to the Hillburn Area Station. | O&R | 0 | 2024-01-31
1634 | North Farm Solar LLC | North Farm Solar LLC | 2023-11-14 | 19.9 | 19.9 | S | Clinton | NY | D | Plattsburgh Substation - 115kV | NYPA | 0 | 2024-05-31
1635 | BPUS Generation Development LLC | Malone Energy Storage | 2023-11-15 | 80 | 80 | ES | Franklin | NY | D | 115kV Malone Substation | NM-NG | 0 | 2024-05-31
1636 | BPUS Generation Development LLC | Vail Energy Storage | 2023-11-15 | 35 | 35 | ES | Fulton | NY | F | 69 kV Vail Substation | NM-NG | 0 | 2024-05-31
1637 | Elevate Bethlehem LLC | Elevate Bethlehem LLC | 2023-11-16 | 120 | 120 | ES | Albany | NY | F | Albany Steam 115 kV Substation | NM-NG | 0 | 2024-05-31
1638 | ACE DevCo NC, LLC | Beck Storage | 2023-11-16 | 85 | 85 | ES | Chautauqua | NY | A | 159 Moon Rd to Hartfield | NM-NG | 0 | 2024-05-31
1639 | Genesee River Solar, LLC | Prospect Hill Road | 2023-11-20 | 20 | 20 | Solar | Orange | NY | G | 69 kV Mongaup to Cuddebackville | O & R | 0 | 2024-04-30
1640 | Genesee River Solar, LLC | Douglas Road Solar | 2023-11-21 | 20 | 20 | S | Tompkins | NY | C | Line 982 between Montour Falls and Coddington Substation 115kV | NYSEG | 0 | 2024-05-31
1641 | 174 Power Global Properties | Harlem River II | 2023-11-21 | 79.9 | 79.9 | ES | Queens | NY | J | NYPA's Hell Gate Annex 138 kV | NYPA ConEd | 0 | 2023-12-31
1642 | Light & Power Development | Queensboro B | 2023-11-28 | 1310 | 1310 | W | Queens | NY | J | Ravenswood Substation 345kV | ConEd | 0 | 2024-05-31
1643 | Community Offshore Wind, LLC | Community OSW Brooklyn CEH 3 | 2023-11-28 | 1364.5 | 1310 | W | Brooklyn | NY | J | 345 kV Brooklyn Clean Energy Hub | ConEd | 0 | 2024-05-31
1644 | ACE DevCo NC, LLC | White Springs | 2023-11-28 | 150 | 150 | S | Ontario | NY | C | Haley Road to AES Greenidge Substation 115 kV | NYSEG | 0 | 2024-11-30
1645 | Emeren US, LLC | Battle Hill Storage | 2023-11-29 | 80 | 80 | ES | St. Lawrence | NY | E | 115 kV Battle Hill Substation | NM-NG | 0 | 2024-05-31
1647 | Black Cherry Wind Power | Black Cherry Wind 1 | 2023-12-05 | 300 | 300 | W | Mckean County | PA | A | Five Mile 345 kV to Homer City 345 kV line | NM-NG | 0 | 2024-05-31
1648 | Black Cherry Wind Power | Black Cherry Wind 2 | 2023-12-05 | 300 | 300 | W | Mckean County | PA | A | Five Mile - Homer City 345 kV line | NM-NG | 0 | 2024-05-31
1649 | Black Cherry Wind Power | Black Cherry Battery | 2023-12-05 | 400 | 400 | ES | Mckean County | PA | A | Five Mile 345 kV to Homer City 345 kV line | NM-NG | 0 | 2024-05-31
1650 | Emeren US, LLC | Moose Creek 1 | 2023-12-12 | 130 | 130 | ES | Lewis | NY | E | Boonville Substation 115 kV | NM-NG | 0 | 2024-03-31
1651 | Independence BESS LLC | Independence BESS | 2023-12-14 | 200 | 200 | ES | Oswego | NY | C | Independence 345kV substation | NM-NG | 0 | 2024-02-29
1652 | ACE DevCo NC, LLC | Coopers Corner BESS | 2023-12-20 | 300 | 300 | ES | Sullivan | NY | E | Coopers Corner 345 kV Substation | NYSEG | 0 | 2024-08-31
1653 | Community Offshore Wind, LLC | Community OSW Barrett 3 | 2023-12-21 | 1310 | 1310 | W | Nassau | NY | K | Liotta 138kV | LIPA | 0 | 2024-05-31
1654 | Hydrostor USA Holdings, Inc , a subsidiary of Hydrostor Inc | Antelope Energy Storage Center | 2023-12-21 | 500 | 500 | ES | Lewis | NY | E | Adirondack 345kV substation | NYPA | 0 | 2024-05-31
1655 | ACE DevCo NC,LLC | West Laurens | 2023-12-21 | 350 | 350 | S | Ostego | NY | E | Marcy 345 kV to Coopers Corner 345 kV | NYPA | 0 | 2024-09-30
1656 | Hydrostor USA Holdings, Inc , a subsidiary of Hydrostor Inc | Chinook Energy Storage Center | 2023-12-21 | 500 | 500 | ES | Lewis | NY | E | Chases Lake 345kV substation | NM-NG | 0 | 2024-05-31
1657 | BayWa r.e. Development LLC | Lincoln Park | 2023-12-27 | 150 | 150 | ES | Ulster | NY | G | LINCOLN PARK-EAST KINGSTON 115 kV | CHGE | 0 | 2024-05-31
1658 | BayWa r.e. Development LLC | North Catskill Energy Storage | 2023-12-27 | 100 | 100 | ES | Greene | NY | G | North Catskill 69 kV | CHGE | 0 | 2024-05-31
1659 | ACE DevCo NC,LLC | Krenzer Solar | 2023-12-27 | 150 | 150 | S | Monroe | NY | B | Station 128 to Station 82 115 kV | RGE | 0 | 2024-09-30
1660 | Emeren US, LLC | Valcour Storage | 2023-12-28 | 150 | 150 | ES | Clinton | NY | D | Patnode Substation 230 kV | NYPA | 0 | 2024-05-31
1661 | Crown Point Solar LLC | Crown Point Solar | 2023-12-28 | 20 | 20 | CR | Essex | NY | F | 115kV Line #2 between Ticonderoga substation and Republic substation | NM-NG | 0 | 2024-04-30
1662 | Deerpark Energy Storage | Deerpark Energy Storage | 2024-01-09 | 50 | 50 | ES | Orange | NY | G | Cuddebackville 69 kV Substation | O&R | 0 | 2024-05-31
1663 | Saugerties Energy Storage | Saugerties Energy Storage | 2024-01-09 | 50 | 50 | ES | Ulster | NY | G | Line tap to Cements - Saugerties 69 kV circuit | CHGE | 0 | 2024-05-31
1664 | MN8 Energy Operating Company | Janes Rd Storage | 2024-01-10 | 100 | 100 | ES | Monroe | NY | B | Station 69 to Station 7 115 kV line tap | RG&E | 0 | 2024-05-31
1665 | MN8 Energy Operating Company | Buffalo Avenue Storage | 2024-01-10 | 150 | 150 | ES | Niagra | NY | A | Station 184(Olin) 115 kV | NM-NG | 0 | 2024-05-31
1666 | MN8 Energy Operating Company | River Road Storage | 2024-01-10 | 250 | 250 | ES | Erie | NY | A | Huntley 115 kV Substation | NM-NG | 0 | 2024-05-31
1668 | Genesee River Solar, LLC | State Route 26 Solar | 2024-01-17 |  |  | S | Courtland | NY | C | Line Tap of 34.5kv subtransmission line, adjacent to 115kv Line ID: 108289, connecting between NYSEG substation at Parcel ID 151.00-01-35.100 approximately 0.67 Miles to the west, and NYSEG substation Smithville Flats 144864 approximately 6.07 miles east | NYSEG | 0 | 2024-03-31
1669 | SR1 Shift Holdco I | Keshequa Creek Solar | 2024-01-17 | 20 | 20 | CR | Livingston | NY | C | Line 934 Between South Perry and Meyer 115kV | NYSEG | 0 | 2024-05-31
1673 | Abei Energy Green XIII | VINO | 2024-02-09 |  |  | S | Greene | NY | G | LAWRENCE (125110) --N.CAT 6 (125116) | CHGE | 0 | 2024-03-31
1674 | Eden Devco LP | Oakdale BESS | 2024-02-14 | 1091 | 1091 | ES | Broome | NY | C | Oakdale 345kv Substation | NYSEG | 0 | 2024-05-31
1675 | Blue Stone Renewable XXIII | HELIOS | 2024-02-16 |  |  | S | RENSSELAER | NY | F | (137563) EASTOVER - (137895) SCHAGHTICOKW | NM-NG | 0 | 2024-03-31
1676 | Eden DevCo | New Scotland BESS | 2024-02-16 | 1350 | 1350 | ES | Albany | NY | F | Princetown - New Scotland 345kv Line 361 | LS Power | 0 | 2024-05-31
1677 | Abundant Solar Power INC. | NY-5632 D Turnpike Road | 2024-02-28 | 18.05 | 18.05 | S | Stueben | NY | C | Line Tap between Bath to Benett 115 kV Substation | NYSEG | 0 | 2024-05-31
1678 | NSF Aurelius BESS | NSF Aurelius BESS, LLC | 2024-03-01 | 100 | 100 | ES | Cayuga | NY | C | NYSEG Wright Ave 115 kV Substation | NYSEG | 0 | 2024-05-31
1679 | SR1 Shift NY I | Smokey Hollow Solar | 2024-03-11 | 70 | 70 | CR | Wyoming | NY | C | South Perry to Indeck Silver Springs Energy Center 115k, Line 101 | NYSEG | 0 | 2024-05-31
1680 | USLE West Leyden Road I LLC | USLE West Leyden Road I LLC | 2024-03-29 |  |  | CR | Oneida | NY | E | Municipal Commission of Boonville 115kV bus at West Street substation, connected to the National Grid 115kV Boonville-Porter line | NM-NG, MCBoonville | 0 | 2024-05-31
1682 | Equity Suffern Developers, LLC | Hudson Valley Data Center | 2024-04-24 | 50 | 50 |  | Rockland | NY | G | Line 60 138kV - Ramapo to Tallman | O&R | 0 | 2024-07-31
1684 | Abundant Solar Power | NY-Markham Hollow Road | 2024-05-23 |  |  |  | Onondaga | NY | C | Tilden Substation, Cortland 18 substation via 115kv line. | NM-NG | 0 | 2024-05-31
1719 | ZeroC Data Centers, LLC | New York State Artificial Intelligence Data Center | 2024-09-18 |  |  |  | St. Lawrence | NY | D | Dennison 115kV substation | NM-NG | 0 | 2025-02-28
1723 | Olean Digital LLC | Olean Digital Data Center | 2024-11-07 |  |  | L | Cattaraugus | NY | A | Homer Hill 115kV Substation | NM-NG | 0 | 2025-02-28
1724 | Alcoa | Alcoa East Energy Allocation Project | 2024-12-09 |  |  |  | St. Lawrence | NY | D | Haverstock - Willis 345kV lines HW1 & HW2 | NYPA | 0 | 2025-01-31
1727 | Empire Generating Co., LLC | Wet Compression | 2025-02-18 |  |  |  | Rensselaer | NY | F | Reynolds Road Line 5 through existing on-site infrastructure and metering. | NM-NG | 0

## Cluster Projects-Withdrawn
Queue Pos. | Owner/Developer | Project Name | Date of IR | SP (MW) | WP (MW) | Type/ Fuel | County | State | Z | Interconnection Point | Utility | S | Last Update
C24-001 | Vineyard Mid-Atlantic LLC | Vineyard Mid-Atlantic East | 2024-08-01 | 1187 | 1187 | W | Nassau | NY | K | Ruland Rd 345kV | NYPA | 0 | 2025-01-31
C24-002 | Atlantic Shores Offshore Wind Bight LLC | ATLANTIC SHORES OFFSHORE WIND PROJECT 4 | 2024-08-01 | 1400 | 1400 | W | Kings | NY | J | BROOKLYN CLEAN ENERGY HUB NORTH 345kV | ConEd | 0 | 2025-02-28
C24-006 | ATLANTIC SHORES OFFSHORE WIND BIGHT LLC | ATLANTIC SHORES OFFSHORE WIND PROJECT 5 | 2024-08-01 | 1400 | 1400 | W | Suffolk | NY | K | RULAND ROAD 345 kV | NYPA | 0 | 2025-03-31
C24-007 | KCE NY 38, LLC | KCE NY 32 | 2024-08-01 | 250 | 250 | ES | Columbia | NY | F | Churchtown 115kV Substation | Transco | 0 | 2024-09-30
C24-009 | Vineyard Northeast LLC | Vineyard Northeast | 2024-08-01 | 884 | 884 | W | Nassau County | NY | K | Ruland Rd 345kV substation. | NYPA | 0 | 2024-12-31
C24-011 | ATLANTIC SHORES OFFSHORE WIND LLC | ATLANTIC SHORES OFFSHORE WIND PROJECT 3 | 2024-08-01 | 1400 | 1400 | W | kings county | NY | J | BROOKLYN CLEAN ENERGY HUB 345kV | ConEd | 0 | 2025-02-28
C24-012 | Empire Wind 2 LLC | EI Melville | 2024-08-01 | 1240 | 1240 | W | Offshore | NY | K | Ruland Road 345 kV | NYPA | 0 | 2025-03-31
C24-017 | Community Offshore Wind, LLC | COSW Barrett | 2024-08-01 | 1310 | 1310 | W | Suffolk | NY | K | Barrett 345kV | Transco | 0 | 2024-11-30
C24-018 | Granite Twinleaf Solar Energy LLC | Twinleaf Solar | 2024-08-01 | 75 | 75 | S | Croghan | NY | E | Taylorville to North Carthage 115 kV ckt 1 | NM-NG | 0 | 2025-03-31
C24-019 | American Wintergreen Solar Energy LLC | American Wintergreen | 2024-08-01 | 75 | 75 | S | Canajoharie | NY | F | Marshville - Clinton 115 kV, Line #12 | NM-NG | 0 | 2024-12-31
C24-020 | Verona Solar II LLC | Verona Solar II | 2024-08-01 | 115 | 115 | S | Verona | NY | E | Oneida - Rome 115kV, Line 1 | NM-NG | 0 | 2025-01-31
C24-022 | Community Offshore Wind, LLC | COSW BCEH | 2024-08-01 | 1310 | 1310 | W | Kings | NY | J | Brooklyn Clean Energy Hub 345 kV | ConEd | 0 | 2025-01-31
C24-025 | KCE NY 32, LLC | KCE NY 32 | 2024-08-01 | 79 | 79 | ES | Orange | NY | G | Cuddebackville 69 kV | O&R | 0 | 2025-01-31
C24-027 | EDF Renewables Development, Inc. | Moraine Solar Energy Center | 2024-08-01 | 93.55 | 93.55 | S | Allegany | NY | C | 115kV Moraine Road Substation | NYSEG | 0 | 2025-01-31
C24-028 | EDF Renewables Development, Inc. | Tracy Solar Energy Center | 2024-08-01 | 119 | 119 | S | Jefferson | NY | E | Thousand Island - Lyme 115kV | NM-NG | 0 | 2025-01-31
C24-029 | Bull Run Solar LLC | Bull Run Solar | 2024-08-01 | 100 | 100 | S | Clinton | NY | D | 230 kV Ellenburg Substation | NYPA | 0 | 2025-01-31
C24-030 | Bluepoint Wind LLC | Bluepoint Wind 2 | 2024-08-01 | 1310 | 1310 | W | Nassau | NY | K | East Garden City 345 kV | NYPA | 0 | 2025-03-31
C24-035 | Dix Hills Storage, LLC | Dix Hills Storage, LLC | 2024-08-01 | 100 | 100 | ES | Suffolk | NY | K | Ruland-Pilgrim 138kV | LIPA | 0 | 2024-12-31
C24-036 | Queensboro Development, LLC | Queensboro Renewable Express Circuit A | 2024-08-01 | 1310 | 1310 | W | Queens | NY | J | Rainey East 345kV | ConEd | 0 | 2024-11-30
C24-040 | EDF Renewables Development, Inc. | Rich Road Solar Energy Center | 2024-08-01 | 240 | 240 | CR | St. lawrence | NY | E | Haverstock - Adirondack 345KV line HA2 | NYPA | 0 | 2025-01-31
C24-041 | BayWa r.e. Solar Projects LLC | Vestal Battery Storage | 2024-08-01 | 110 | 110 | ES | Broome | NY | C | Castle Garden - Jones 115 kV | NYSEG | 0 | 2025-01-31
C24-045 | New Scotland BESS | New Scotland BESS | 2024-08-01 | 1350 | 1350 | ES | Albany | NY | F | New Scotland 345kV | NM-NG | 0 | 2025-03-31
C24-046 | Oakdale BESS | Robinson Hill BESS | 2024-08-01 | 1117 | 1091 | ES | Broome | NY | C | Oakdale 345kv Substation | NYSEG | 0 | 2025-03-31
C24-051 | Liberty Renewables Inc. | Russet Ridge Wind | 2024-08-01 | 119.1 | 119.1 | W | Steuben | NY | C | Meyer-Eelpot 115 kV | NYSEG | 0 | 2025-02-28
C24-053 | Liberty Renewables Inc. | Agricola Wind | 2024-08-01 | 97 | 97 | W | Cayuga | NY | C | Milliken - Wright Ave 115kV Line 973 | NYSEG | 0 | 2024-10-31
C24-054 | Liberty Renewables Inc. | Hoffman Falls Wind | 2024-08-01 | 72 | 72 | W | Madison | NY | C | Fenner - Shippy Rd 115 kV | NM-NG | 0 | 2025-01-31
C24-055 | Sketch Book Storage 1, LLC | Sketch Book Storage | 2024-08-01 | 100 | 100 | ES | Columbia | NY | F | 115 kV Falls Park Substation | NYSEG | 0 | 2025-02-28
C24-068 | Holbrook Energy Storage, LLC | Holbrook Energy Storage II | 2024-08-01 | 260 | 260 | ES | Suffolk | NY | K | West Bus 138kV | LIPA | 0 | 2024-12-31
C24-069 | South Suffolk Energy Storage, LLC | South Suffolk Storage | 2024-08-01 | 77 | 77 | ES | Suffolk | NY | K | Centereach 69kV | LIPA | 0 | 2024-12-31
C24-070 | Port Jefferson Energy Storage, LLC | Port Jefferson Energy Storage | 2024-08-01 | 168 | 168 | ES | Suffolk | NY | K | Port Jefferson 138kV | LIPA | 0 | 2024-12-31
C24-073 | GCI Icebox Energy Storage, LLC | Icebox Energy Storage | 2024-08-02 | 50 | 50 | ES | Onondaga | NY | C | Solvay Station 34.5 kV | NM-NG | 0 | 2025-05-31
C24-075 | Shore Rd ESS LLC | Oyster shore Energy storage | 2024-08-02 | 275 | 275 | ES | Nassau | NY | K | Shore Road 138 kV | LIPA | 0 | 2025-01-31
C24-082 | Terra-Gen Development, LLC | Arch 1 | 2024-08-09 | 100 | 100 | ES | Orange | NY |  | Rock Tavern 345kV Substation (South position)- ROCK TAV - Bus#: 125001 |  | 0
C24-083 | Terra-Gen Development, LLC | Arch 2 | 2024-08-09 | 150 | 150 | ES | Orange | NY |  | Rock Tavern 345kV Substation (South position)- ROCK TAV - Bus#: 125001 |  | 0
C24-084 | Terra-Gen Development, LLC | Arch 3 | 2024-08-09 | 100 | 100 | ES | Orange | NY |  | Rock Tavern 345kV Substation (North position)- ROCK TAV - Bus#: 125001 |  | 0
C24-096 | ACE DevCo NC,LLC | Coopers Corner BESS | 2024-08-23 | 300 | 300 | ES | Sullivan | NY | E | Coopers Corner 345 kV Substation | NYSEG | 0 | 2025-01-31
C24-100 | RWE Solar Development, LLC | Erie Canal BESS | 2024-08-26 | 230 | 230 | ES | Niagara | NY | A | Robinson Road 115 kV | NYSEG | 0 | 2024-09-30
C24-106 | Granby Storage LLC | Granby Storage | 2024-08-28 | 150 | 150 | ES | Oswego | NY | C | South Oswego to Curtis Street 115kV Line 10 | NM-NG | 0 | 2025-05-31
C24-107 | Boralex US Development LLC | NY125B - Two Rivers Solar | 2024-08-29 | 200 | 200 | S | St. Lawrence | NY | D | Haverstock to Willis 345kV HW2 Line | NYPA | 0 | 2025-01-31
C24-110 | Fort Covington Solar LLC | NY125A - Fort Covington Solar | 2024-08-29 | 250 | 250 | S | Franklin | NY | D | 345 kV line HW1 from Haverstock to Willis | NYPA | 0 | 2025-01-31
C24-112 | Boralex US Development LLC | NY48 - Diamond Solar | 2024-08-29 | 60 | 60 | S | Herkimer | NY | E | Porter - Valley 115 kV, Line #4 | NM-NG | 0 | 2025-02-28
C24-113 | Newport Deerfield Solar LLC | NY115 - Newport Solar | 2024-08-29 | 130 | 130 | S | Oneida | NY | E | Porter - Deerfield 115 kV, Line #9 | NM-NG | 0 | 2025-02-28
C24-114 | Foothills Solar LLC | NY128 - Foothills Solar | 2024-08-29 | 40 | 40 | S | Fulton | NY | F | Mayfield to Northville 69kV line #8 | NM-NG | 0 | 2024-12-31
C24-116 | Wild Ox Solar Project, LLC | Wild Ox Solar | 2024-08-30 | 130 | 130 | CR | Yates | NY | C | Eelpot Road to Flat St Substations 115 kV line | NYSEG | 0 | 2024-10-31
C24-117 | RWE Solar Development, LLC | Town Line Solar CSR Phase I | 2024-08-30 | 240 | 240 | HSR | Sullivan | NY | E | Coopers Corner to Middletown Tap 345 kV Line | NYPA | 0 | 2024-09-30
C24-119 | North Bergen Liberty Generating LLC | Liberty BESS | 2024-09-02 | 1200 | 1200 | ES | Hudson | NJ | J | West 49th Street 345 kV Substation | ConEd | 0
C24-123 | ACE DevCo NC,LLC | Wallkill Energy Storage | 2024-09-05 | 100 | 100 | ES | Ulster | NY | G | Ohioville 115kV Substation | CHGE | 0 | 2025-01-31
C24-133 | MN8 Energy Development Company LLC | Janes Road Energy Storage | 2024-09-06 | 100 | 100 | ES | Monroe | NY | B | Station 7 - Station 69 115 kV Line #917 | RG&E | 0 | 2024-11-30
C24-140 | Emeren US, LLC | Altona Energy Storage | 2024-09-09 | 40 | 40 | ES | Clinton | NY | D | Flatrock 46kV | NYSEG | 0 | 2025-01-31
C24-141 | Upper Falls Solar | Upper Falls Solar | 2024-09-09 | 46 | 46 | CR | Wyoming | NY | B | Station 162 - Station 180 115kV, Line 907 | RGE | 0 | 2024-09-30
C24-142 | Nexus Renewables U.S. Inc. | Beaver Kill Storage | 2024-09-09 | 12 | 12 | ES | Ulster | NY | G | CHGE SAUGERTIES Substation, Feeder 3003, 13.8kV |  | 0 | 2024-10-31
C24-143 | Smokey Hollow Solar | Smokey Hollow Solar | 2024-09-09 | 70 | 70 | CR | Wyoming | NY | B | Line 907 Substation 162 and Houghton Substation (S180). 115kV | RGE | 0 | 2024-10-31
C24-144 | Granada Solar, LLC | Blue Line Solar | 2024-09-09 | 70 | 70 | S | St Lawrence County | NY | E | Battle Hill - Corning 115 kV (National Grid Line #4) | NM-NG | 0 | 2024-12-31
C24-145 | ACE DevCo NC,LLC | Riptide Storage | 2024-09-10 | 200 | 200 | ES | Suffolk | NY | K | Edwards Ave 138kV Substation | LIPA | 0 | 2025-03-31
C24-146 | BGTF US Development Holdings LLC | Amsterdam Energy Storage | 2024-09-10 | 100 | 100 | ES | Montgomery | NY | F | Stoner to Amsterdam 115 kV Line | NM-NG | 0 | 2024-09-30
C24-147 | Emeren US, LLC | Battle Hill Storage | 2024-09-10 | 79.9 | 79.9 | ES | St. Lawrence | NY | E | Battle Hill 115kV | NM-NG | 0 | 2025-05-31
C24-151 | ACE DevCo NC, LLC | Richardson BESS | 2024-09-11 | 100 | 100 | ES | Lawrence | NY | E | McIntyre 115 kV Substation | NM-NG | 0 | 2025-01-31
C24-153 | Hydrostor USA Holdings, Inc , a subsidiary of Hydrostor Inc | Chinook Energy Storage Center | 2024-09-11 | 500 | 500 | ES | Lewis | NY | E | Adirondack - Austin Road Line #13, 345kV line. | NM-NG | 0 | 2025-03-31
C24-157 | Granada Solar, LLC | Fuller Storage | 2024-09-12 | 20 | 20 | ES | Orange | NY | G | East Walden 1115 kV Substation | CHGE | 0 | 2025-04-30
C24-161 | Emeren US, LLC | Cedar Lake Storage | 2024-09-13 | 300 | 300 | ES | St. Lawrence | NY | E | Moses (Haverstock) - Adirondack 345 kV line | NYPA | 0 | 2024-10-31
C24-166 | KCE NY 41, LLC | KCE NY 41 | 2024-09-16 | 100 | 100 | ES | Suffolk | NY | K | West Yaphank 69kV Substation | LIPA | 0 | 2024-10-31
C24-170 | Zenith Power LLC | Zenith BESS | 2024-09-17 | 165 | 165 | ES | Onondaga | NY | C | Geres Lock-Tilden Line 16 115kV | NM-NG | 0 | 2025-01-31
C24-171 | Fieldstone Power Station LLC | North Chelsea (Fieldstone Power Station) | 2024-09-17 | 150 | 150 | ES | Dutchess | NY | G | North Chelsea 115 kV Substation | CHGE | 0 | 2025-02-28
C24-172 | Blue Stone Renewable XVI | BRESH HYBRID | 2024-09-17 | 59.2 | 59.2 | CR | Ulster | NY | G | BOULEVARD 69 kV SUBSTATION | CHGE | 0 | 2025-03-31
C24-174 | Bay State Wind | Long Island Wind | 2024-09-17 | 1310 | 1310 | W | Suffolk | NY | K | Ruland Road 345kV | NYPA | 0 | 2025-03-31
C24-180 | East Setauket Energy Storage, LLC | East Setauket Storage | 2024-09-17 | 125 | 125 | ES | Suffolk | NY | K | Holbrook - North Shore Beach 138kV line | LIPA | 0 | 2024-11-30
C24-181 | Setauket energy Storage, LLC | Setauket Storage | 2024-09-17 | 65.3 | 65.3 | ES | Setauket | NY | K | Terryville - Port Jefferson 69kV | LIPA | 0 | 2025-03-31
C24-185 | Flat Creek Solar NY LLC | Flat Creek Solar | 2024-09-18 | 200 | 200 | S | Montgomery | NY | F | Edic to Princetown 345kV Line 352 | NYPA | 0 | 2024-10-31
C24-187 | Flat Creek Solar NY LLC | Flat Creek Solar II | 2024-09-18 | 100 | 100 | S | Montgomery | NY | F | Edic to Princetown 345kV Line #352 | NYPA | 0 | 2024-10-31
C24-192 | Blue Frost Energy Center, LLC | Blue Frost Solar | 2024-09-19 | 200 | 200 | S | Montgomery | NY | E | Marcy - New Scotland 345kV line 18 | NM-NG | 0 | 2024-12-31
C24-193 | North Seneca Solar Project, LLC | North Seneca | 2024-09-19 | 90 | 90 | S | Seneca | NY | C | Hooks Road - Elbridge 115kV line #7 | NM-NG | 0 | 2024-12-31
C24-194 | Sapphire Sun Energy Center, LLC | Sapphire Sun | 2024-09-19 | 120 | 120 | S | Allegany | NY | A | Homer Hill-Andover Line 157 115kV line | NM-NG | 0 | 2024-12-31
C24-195 | Sweet Valley Energy Center, LLC | Sweet Valley Solar | 2024-09-19 | 100 | 100 | S | Genesee | NY | B | Dysinger - Station 255 345kV, line #1 | NYPA | 0 | 2024-12-31
C24-196 | Yellow Feather Energy Center, LLC | Yellow Feather | 2024-09-19 | 90 | 90 | S | Fulton and Montgomery | NY | F | Inghams-Stoner Line 9 115kV | NM-NG | 0 | 2024-12-31
C24-197 | Sweet Valley Energy Center, LLC | Sweet Valley Storage | 2024-09-19 | 200 | 200 | ES | Genesee | NY | B | Dysinger - Station 255 (Henrietta) #1 345kV line | NYPA | 0 | 2024-12-31
C24-198 | Blue Frost Energy Center, LLC | Blue Frost Storage I | 2024-09-19 | 200 | 200 | ES | Montgomery | NY | E | Marcy - New Scotland 345kV line | NM-NG | 0 | 2024-11-30
C24-199 | Blue Frost Energy Center, LLC | Blue Frost Storage II | 2024-09-19 | 200 | 200 | ES | Montgomery | NY | E | Edic - Gordon Road 345kV Line 14 | NM-NG | 0 | 2024-11-30
C24-200 | BGTF US Development Holdings LLC | Hickory Hill Energy Storage | 2024-09-19 | 100 | 100 | ES | Montgomery | NY | F | Inghams-Meco-Marshville Line 15/12 115kV | NM-NG | 0 | 2024-12-31
C24-201 | Yellow Barn Solar, LLC | Yellow Barn Solar | 2024-09-19 | 160 | 160 | S | Tompkins | NY | C | Milliken - Etna 115 kV #975 | NYSEG | 0 | 2024-12-31
C24-203 | Renew Development HoldCo LLC | Mill Run BESS | 2024-09-19 | 260 | 260 | ES | Onondaga | NY | C | Elbridge - Geres Lock 115kV 18 & 19 lines | NM-NG | 0 | 2025-02-28
C24-206 | York Run Solar, LLC | York Run Solar, LLC | 2024-09-19 | 90 | 90 | S | Chautauqua | NY | A | Falconer - Warren 115 kV line #171 | NM-NG | 0 | 2024-10-31
C24-210 | The Commodore Storage, LLC | Marcy BESS 1 | 2024-09-20 | 120 | 120 | ES | Oneida | NY | E | Volney - Marcy | NYPA | 0 | 2024-10-31
C24-212 | The Commodore Storage, LLC | Marcy BESS 3 | 2024-09-20 | 435 | 435 | ES | Oneida | NY | E | Marcy-Volney 345 kV Line | NYPA | 0 | 2024-10-31
C24-219 | ACE DevCo NC, LLC | Krenzer | 2024-09-20 | 150 | 150 | S | Monroe | NY | B | Station 128 to Station 82 115 kV | RG&E | 0 | 2025-01-31
C24-220 | ACE DevCo NC, LLC | Blue Mountain BESS | 2024-09-20 | 100 | 100 | ES | Ulster | NY | G | Saugerties to Hurley 69 kV Line | CHGE | 0 | 2024-11-30
C24-221-003 | Snowy Knoll Wind Project, LLC | Snowy Knoll Wind Project | 2024-09-20 | 350 | 350 | CW | Oneida | NY | E | Edic - Fraser 345kV | NYPA | 0 | 2025-02-28
C24-226 | Lucy?s Energy Reserve LLC | South Dow (Lucy's Energy Reserve) | 2024-09-20 | 175 | 175 | ES | Chautauqua | NY | A | Falconer 115kV Substation | NM-NG | 0 | 2025-03-31
C24-228 | Winterberry Wind LLC | Winterberry Wind | 2024-09-21 | 100 | 100 | W | Bradford | PA | C | Hillside to East Towanda 230 kV | NYSEG | 0 | 2024-10-31
C24-231 | Azalea Wind LLC | Azalea Wind 1 | 2024-09-21 | 50 | 50 | W | Schuyler | NY | C | Montour Falls Substation to Coddington Road Substation 115kV | NYSEG | 0 | 2024-10-31
C24-232 | Azalea Wind LLC | Azalea Wind 2 | 2024-09-21 | 50 | 50 | W | Schuyler | NY | C | Montour Falls Substation (#130830) to Coddington Road Substation 115kV (#130787) | NYSEG | 0 | 2024-10-31
C24-239 | Zenobe Americas Inc. | Zenobe Wellsville LLC | 2024-09-23 | 100 | 100 | ES | Allegany | NY | A | Homer Hill - Andover 115 kV Line 157 | NM-NG | 0 | 2025-05-31
C24-240 | ACE DevCo NC LLC | Moran 2 | 2024-09-23 | 100 | 100 | S | Fulton | NY | F | Inghams-Stoner Line 9 115 kV | NM-NG | 0 | 2024-11-30
C24-241 | Genesee River Solar | Soper Road Solar | 2024-09-23 | 20 | 20 | S | Wyoming | NY | C | Perry Center Substation | NYSEG | 0 | 2024-10-31
C24-242 | Genesee River Solar | State Route 26 Solar | 2024-09-23 | 20 | 20 | S | Cortland | NY | C | Willet - Tarbell 34.5kV | NYSEG | 0 | 2024-11-30
C24-243 | Genesee River Solar | Gravel Road Solar | 2024-09-23 | 128 | 128 | S | Seneca | NY | C | Lovers Lane-Elbridge Line 6 & Station 168-Elbridge Line 2 | NM-NG | 0 | 2024-10-31
C24-246 | ACE DevCo NC LLC | Block Perch solar | 2024-09-23 | 85 | 85 | S | Chautauqua | NY | A | Moon Road-Falconer Line 175 115V | NM-NG | 0 | 2025-02-28
C24-254 | Genovia Storage LLC | Genovia Storage | 2024-09-23 | 300 | 300 | ES | Basom | NY | B | 345 kV Line 1 QP580_POI2 (# 148773) Substation to Q721_POI (#149914) Substation | NYPA | 0 | 2024-12-31
C24-258 | Genovia Storage LLC | Genovia Storage | 2024-09-23 | 300 | 300 | ES | Basom | NY | B | QP580_POI2 - Q721_POI 345 kV Line | NYPA | 0 | 2024-12-31
C24-260 | ACE DevCo NC, LLC | West Laurens | 2024-09-23 | 350 | 350 | S | Otsego | NY | E | Marcy to Coopers Corner - 345 kV | NYPA | 0 | 2024-11-30
C24-261 | Beacon Wind LLC | EI Steinway 1 | 2024-09-23 | 1300 | 1300 | W | Queens | NY | J | Mott Haven to Rainey 345kV line tap | ConEd | 0 | 2025-02-28
C24-262 | Beacon Wind | EI Steinway 1.1 | 2024-09-23 | 1600 | 1600 | W | Queens | NY | J | Mott Haven - Rainey 345kV circuits | ConEd | 0 | 2024-10-31
C24-267 | ACE DevCo NC LLC | Beck Storage | 2024-09-23 | 85 | 85 | ES | Chautauqua | NY | A | Moon Road-Hartfield Line 159 115 kV | NM-NG | 0 | 2024-12-31
C24-271 | Sturgeon Pool BESS, LLC | Margarita Storage | 2024-09-24 | 110 | 110 | ES | Ulster | NY | G | Sturgeon Pool 115 kV | CHGE | 0 | 2024-11-30
C24-272 | Kerhonkson, LLC | File Cabinet Storage | 2024-09-24 | 100 | 100 | ES | Ulster | NY | G | GALEVILLE to KERHONKS 115 kV | CHGE | 0 | 2024-10-31
C24-275 | Springville BESS, LLC | Warrior Storage | 2024-09-24 | 100 | 100 | ES | Erie | NY | A | Gardenville to Arcade 115 kV Line 151 | NM-NG | 0 | 2024-10-31
C24-276 | Cobble Hill BESS, LLC | Dime Energy Storage | 2024-09-24 | 150 | 150 | ES | Erie | NY | A | Cobble Hill 115 kV Substation | NYSEG | 0 | 2024-10-31
C24-277 | Tierken Storage 1, LLC | Tierken Storage | 2024-09-24 | 50 | 50 | ES | Rensselaer | NY | F | Reynolds Road - Greenbush 115 kV Line #9 | NM-NG | 0 | 2024-11-30
C24-285 | ACE DevCo NC,LLC | North Watertown BESS | 2024-09-26 | 200 | 200 | ES | Jefferson | NY | E | 115kV North Watertown Substation | NM-NG | 0 | 2025-02-28
C24-286 | Mastodon Storage 1, LLC | Mastodon Storage | 2024-09-26 | 80 | 80 | ES | Orange | NY | G | Rock Tavern - Sugarloaf 115 kV Line SL | Transco | 0 | 2024-10-31
C24-287 | ACE DevCo NC,LLC | Harrigan Solar | 2024-09-26 | 100 | 100 | S | Franklin | NY | D | Willis to Lyon Mountain Line Tap 115 kV | NYSEG | 0 | 2025-01-31
C24-290 | ACE DevCo NC,LLC | Cazenovia Solar | 2024-09-27 | 80 | 80 | S | Madison | NY | C | Fenner-Shippey Line 3 115 kV | NM-NG | 0 | 2025-01-31
C24-291 | BayWa r.e. Solar Projects, LLC | Pine Hill Energy Storage | 2024-09-27 | 120 | 120 | ES | Ulster | NY | E | Belleayre 115 kV | NYSEG | 0 | 2024-12-31
C24-295 | ACE DevCo NC,LLC | Winn Hill Solar | 2024-09-27 | 60 | 60 | S | Broome | NY | C | Kattelville to Jennison Line Tap 115 kV | NYSEG | 0 | 2025-01-31
C24-296 | ACE DevCo NC LLC | Medina Solar | 2024-09-27 | 100 | 100 | S | Orleans | NY | B | Connection on Brunner to Sour Springs 115 kV Line 118 | NM-NG | 0 | 2025-01-31
C24-305 | BW Solar Holding Inc. | St. Regis River LLC | 2024-10-01 | 58.5 | 58.5 | CR | St. Lawrence | NY |  | Lawrence - A [136781] to Sugar Island [136806] 115kV line. |  | 0 | 2024-10-31
C24-307 | Oriden | Marshville BESS | 2024-10-01 | 50 | 50 | ES | Montgomery | NY | F | Marshville 115kV Substation | NM-NG | 0 | 2025-03-31
C24-308 | Oriden | Chazy Lake BESS | 2024-10-01 | 50 | 50 | ES | Clinton | NY | D | Patnode 230kV | NYPA | 0 | 2025-03-31
C24-310 | Fresh Air Energy II, LLC | Lincoln ESC | 2024-10-02 | 100 | 100 | ES | Suffolk | NY | K | Holbrook - Bohemia Ckt#1, 69kV | LIPA | 0 | 2025-03-31
C24-311 | Fresh Air Energy II, LLC | Moffitt ESC | 2024-10-02 | 100 | 100 | ES | Suffolk | NY | K | Watson (Bus #129777) - Brightwaters (Bus #129723) Ckt #2, 69 kV | LIPA | 0 | 2024-10-31
C24-314 | GB II New York | Bethlehem Energy Center Uprate | 2024-10-03 | 875 | 926.1 | CC | Albany | NY | F | Albany Steam Station, Jawside of 6177, 6277, 6377, 6477 Disconnects | NM-NG | 0 | 2024-12-31
C24-315 | Arthur Kill Power | Arthur Kill Upgrade | 2024-10-03 | 369.9 | 369.9 | ST | Richmond | NY |  | Fresh Kills Substation between breakers BT1-4 and BT1-3 |  | 0 | 2024-12-31
C24-316 | DOVER PLAINS ENERGY PROPERTIES LLC | DOVER NY BESS | 2024-10-03 | 1000 | 1000 | ES | DUTCHESS | NY | G | Pleasant Valley-Cricket Valley 345kV | ConEd | 0 | 2025-03-31
C24-328 | SWEB Development USA LLC | WEB Worth Wind | 2024-10-08 | 63.6 | 68.61 | W | Jefferson | NY | E | 115 kV Middle Road - Lighthouse Hill Line 6 | NM-NG | 0 | 2024-10-31
C24-329 | SWEB Development USA LLC | WEB Addison Solar | 2024-10-08 | 100 | 100 | S | Steuben | NY | C | Stony Ridge - Sullivan Park 115 kV | NYSEG | 0 | 2025-03-31
C24-330 | Granada Solar, LLC | Pine Hill Storage | 2024-10-08 | 120 | 120 | ES | Chautauqua | NY | A | Homer Hill - Falconer 115kV, Line #154 | NM-NG | 0 | 2024-12-31
C24-339 | Capital Region Energy Storage LLC | Chateauguay BESS | 2024-10-10 | 200 | 200 | ES | Greene | NY | F | Leeds 345kV | NM-NG | 0 | 2025-01-31
C24-340 | Solitude Solar, LLC d/b/a U.S. Light Energy | USLE West Leyden Road I LLC | 2024-10-10 | 19.6 | 19.6 | CR | Oneida | NY | E | Weststreet Boonville 115kV | MC Boonville | 0 | 2024-12-31
C24-343 | Avangrid Renewables, LLC | AGR NY1 | 2024-10-11 | 1152 | 1229 | W | Nassau | NY | K | East Garden City 345 kV | NYPA | 0 | 2025-03-31
C24-345 | Athens Energy Storage LLC | Athens Energy Storage | 2024-10-12 | 300 | 300 | ES | Greene | NY | G | Tap of Leeds-Van Wagner 345kV line 92 | NM-NG | 0 | 2024-11-30
C24-346 | Middletown Energy Storage LLC | Middletown Energy Storage | 2024-10-12 | 100 | 100 | ES | Orange | NY | G | Shoemaker-Chester 138kV, Line 27 | O&R | 0 | 2025-01-31
C24-351 | CEDAR HOLDCO LLC | Green Isles Energy Storage | 2024-10-15 | 400 | 400 | ES | Suffolk | NY | K | Brookhaven - Sills Rd 138 kV Circuit #1 | LIPA | 0 | 2025-03-31
C24-353 | Caithness LI Energy Storage LLC | CLIES 70 MW | 2024-10-15 | 70 | 70 | ES | Suffolk | NY | K | Sills Road 138kV substation | LIPA | 0 | 2024-10-31
C24-354 | AMBAR POWER HOLDCO LLC | Bayonne Energy Storage I | 2024-10-15 | 600 | 600 | ES | Hudson | NJ | J | Gowanus 345 kV | ConEd | 0 | 2025-02-28
C24-355 | AMBAR POWER HOLDCO LLC | Bayonne Energy Storage II | 2024-10-15 | 400 | 400 | ES | Hudson | NJ | J | Gowanus Substation 345 kV | ConED | 0 | 2025-01-31
C24-356 | Five Mile Energy, LLC | 5Mile Storage Project | 2024-10-15 | 360 | 360 | ES | Cattaraugus | NY | A | Five Mile 345 kV | NM-NG | 0 | 2025-01-31
C24-360 | North Foothills Energy Center, LLC | North Foothills Solar | 2024-10-15 | 100 | 100 | S | Franklin | NY | D | line tap between 115kV NMNG Lake Colby (136777) and Malone (136783) substations | NM-NG | 0 | 2024-10-31
C24-365 | Genesee River Solar, LLC | Ford Hill Road Solar | 2024-10-15 | 19.6 | 19.6 | S | Cortland | NY | C | Whitney Point Southwest 34.5kV substation | NYSEG | 0 | 2024-10-31
C24-368 | CEDAR HOLDCO LLC | Huntley Energy Storage | 2024-10-15 | 300 | 300 | ES | Erie | NY | A | Huntley 230 kV Substation | NM-NG | 0 | 2025-03-31
C24-369 | Winterberry Wind LLC | Winterberry Wind | 2024-10-15 | 50 | 50 | W | Bradford | PA | C | Hillside - East Towanda 230 kV | NYSEG | 0 | 2024-10-31
C24-371 | EZ ENERGY SOLUTIONS LLC | EZ ENERGY SOLUTIONS LLC 5802 BESS | 2024-10-15 | 328.9 | 328.9 | ES | KINGS | NY | J | Gowanus 138 kV | ConEd | 0 | 2024-10-31
CR24-1001 | Suffolk County Energy Storage II, LLC | Suffolk County Storage II | 2024-09-18 |  |  | ES | Suffolk | NY | K | Southold 69kV station. | LIPA | 0 | 2024-12-31
CR24-1005 | KCE NY 29, LLC | KCE NY 29 | 2024-10-15 |  |  | ES | Suffolk | NY | K | Kings 138 kV | LIPA | 0 | 2024-10-31

## Affected System- Withdrawn
Queue Pos. | Owner/Developer | Project Name | Date of IR | SP (MW) | WP (MW) | Type/ Fuel | County | State | Z | Interconnection Point | Utility | S | Last Update
1720 | Elk Run Storage LLC | Elk Run Storage | 2024-10-16 |  |  | AC | Tioga | PA | C | Mainesburg 115 kV Substation | PJM | 0 | 2025-01-31
1722 | Treebeard BESS Project Co LLC | Treebeard BESS | 2024-10-29 |  |  | AC | New Milford | CT | G | 115 kV line 1555 between Rocky River and Bulls Bridge substations | ISO-NE | 0 | 2025-05-31

## In Service
Queue |  |  | Date | SP | WP | Type/ | Location |  | Z | Interconnection |  |  | Last Update | Availability | Proposed | Proposed
Pos. | Owner/Developer | Project Name | of IR | (MW) | (MW) | Fuel | County | State |  | Point | Utility | S |  | of Studies | In-Service | COD
0001 | Con Edison | Middletown Station | 1989-09-15 | N/A | N/A | AC | Orange County | NY | G | Coop Corn-Rock Tav Lines | NYPA | 14 | 2002-03-31 | None | I/S | N/A
0002 | Athens Gen Co./ PG&E | Athens Gen | 1998-04-27 | 1080 |  | NG | Athens | NY | F | Leeds-Pl.Val. 91 Line | NM-NG | 14 | 2004-05-31 | SRIS | I/S | N/A
0003 | PSEG Power NY | Bethlehem Energy Center | 1998-04-27 | 350 |  | NG | Albany | NY | F | Albany 115kV | NM-NG | 14 | 2005-07-31 | SRIS | I/S | N/A
0004 | TransEnergie US, Ltd | CT-LI DC Tie-line | 1998-07-20 | 330 |  | DC | Shoreham | NY | K | Shoreham, Long Island | LIPA | 14 | 2003-12-31 | SRIS,CY01 | I/S | I/S
0011 | East Coast Power-Linden Venture LP | East Coast Power-Linden | 1999-03-25 | 20 |  | NG | Linden | NY | J | Goethals | CONED | 14 | 2002-03-31 |  | I/S | I/S
0017 | KeySpan Energy, Inc. | KeySpan Ravenswood | 1999-04-21 | 270 |  | NG | NY | NY | J | Vernon | CONED | 14 |  | SRIS,CY01,CY02 | I/S | I/S
0018 | NYPA | Poletti Expansion | 1999-04-30 | 500 |  | NG | Queens | NY | J | Astoria 138kV | CONED | 14 | 2008-02-26 | SRIS, CY01 | I/S | I/S
0025 | Consolidated Edison of NY | East River Repowering | 1999-08-10 | 288 |  | NG | NY | NY | J | E. 13th St. 138kV | CONED | 14 |  | SRIS, CY01 | I/S | I/S
0031 | SCS Energy, LLC | Astoria Energy - Phase 1 | 1999-11-16 | 500 |  | NG | Queens | NY | J | Astoria 138kV | CONED | 14 | 2008-02-26 | SRIS, CY01 | Part I/S | Part I/S
0055 | Canastota Wind Power, LLC | Fenner Wind Energy Fac. | 2000-03-14 | 30 |  | W | Madison | NY | C | Fenner-Whitman | NM-NG | 14 |  | SRIS,CY02 | I/S | I/S
0066 | TransEnergie HQ | Langlois Converter | 2000-06-02 | 100 | N/A | AC |  | Quebec |  | Langlois, Quebec | NM-NG | 14 |  | SRIS | I/S | N/A
0069 | Empire Generating Co., LLC | Empire Generating | 2000-07-14 | 635 |  | NG | Rensselaer | NY | F | Reynolds Road 345kV | NM-NG | 14 | 2010-09-30 | SRIS, CY05 | I/S | N/A
0079 | NYPA | Harlem River Yards | 2000-12-05 | 79.9 |  | CT | NY | NY | J | Hell Gate Substation | CONED | 14 |  | SRIS,CY01 | I/S | N/A
0080 | NYPA | Hell Gate | 2000-12-05 | 79.9 |  | CT | NY | NY | J | Hell Gate Substation | CONED | 14 |  | SRIS,CY01 | I/S | I/S
0081 | NYPA | Vernon Blvd | 2000-12-05 | 79.9 |  | CT | NY | NY | J | Vernon Substation | CONED | 14 |  | SRIS,CY01 | I/S | I/S
0082 | NYPA | N First St and Grand Ave | 2000-12-05 | 44 |  | CT | NY | NY | J | Vernon-Greenwood line | CONED | 14 |  | SRIS,CY01 | I/S | I/S
0083 | NYPA | 23rd St and 3rd Ave | 2000-12-05 | 79.9 |  | CT | NY | NY | J | Gowanus Substation | CONED | 14 |  | SRIS,CY01 | I/S | I/S
0084 | NYPA | Fox Hills | 2000-12-05 | 44 |  | CT | NY | NY | J | Fox Hills Substation | CONED | 14 |  | SRIS,CY01 | I/S | I/S
0085 | NYPA | Brentwood | 2000-12-05 | 44 |  | CT | Nassau | NY | K | Brentwood 69 kV | LIPA | 14 |  | SRIS,CY01 | I/S | I/S
0094 | Atlantic Energy, LLC | Project Neptune DC PJM-LI | 2001-05-22 | 660 |  | DC | Nassau | NY-NJ | K | Newbridge Road 138kV | LIPA | 14 | 2008-10-14 | SRIS, CY05 | I/S | I/S
0095 | KeySpan Energy Development Corp. | Glenwood Gas Plant | 2001-05-22 | 79.9 |  | CT | Nassau | NY | K | Glenwood 69 kV | LIPA | 14 |  |  | I/S | I/S
0099 | Central Hudson Gas & Electric | Rock Tavern Transformer | 2001-06-28 | N/A | N/A | AC | Orange | NY | G | Rock Tavern | CHG&E | 14 |  | SRIS | I/S | N/A
0107 | Caithness Long Island, LLC | Caithness Long Island | 2001-10-09 | 310 |  | NG | Suffolk | NY | K | Brookhaven-Holbrook or H'ville 138kV | LIPA | 14 | 2009-11-30 | SRIS, CY06 | I/S | N/A
0115 | Central Hudson Gas & Electric | East Fishkill Transformer | 2002-04-24 | N/A | N/A | AC | Dutchess | NY | G | East Fishkill 345kV/115kV | CONED/CHG&E | 14 | 2013-03-31 | None | I/S | N/A
0121 | KeySpan Energy for LIPA | Holtsville Emergency Gen | 2002-05-31 | 66 |  | CT | Suffolk | NY | K | Holtsville | LIPA | 14 |  | SRIS | I/S | N/A
0122 | KeySpan Energy for LIPA | Shoreham Emergency Gen | 2002-05-31 | 66 |  | CT | Suffolk | NY | K | Holtsville | LIPA | 14 |  | SRIS | I/S | N/A
0123 | KeySpan Energy for LIPA | Wading River Emergency Gen | 2002-05-31 | 79.9 |  | CT | Suffolk | NY | K | Holtsville | LIPA | 14 |  | SRIS | I/S | I/S
0125 | East Coast Power, LLC | Linden VFT Inter-Tie | 2002-07-18 | 300 | N/A | AC | Richmond | NY-NJ | J | Goethals 345kV | CONED | 14 | 2009-11-30 | SRIS, CY06 | I/S | I/S
0127A | Airtricity Munnsville Wind Farm, LLC | Munnsville - Phase 1 | 2002-10-09 | 34.5 |  | W | Madison | NY | E | 46kV line | NYSEG | 14 | 2013-03-31 | SRIS, CY06 | Part I/S | Part I/S
0133 | KeySpan Energy for LIPA | Holtsville Emergency Gen | 2003-05-15 | 66 |  | CT | Suffolk | NY | K | Holtsville | LIPA | 14 |  | SRIS | I/S | I/S
0135 | UPC Wind Management, LLC | Canandaigua Wind Farm | 2003-05-30 | 82.5 | 82.5 | W | Steuben | NY | C | Avoca 230kV line | NYSEG | 14 | 2009-03-02 | SRIS, CY06 | I/S | I/S
0136 | Rochester Gas & Electric | Rochester Transmission | 2003-06-12 | N/A | N/A | AC | Monroe | NY | B | RG&E System | RG&E | 14 | 2009-04-08 | SRIS | I/S | N/A
0138 | Entergy Nuclear Operations, Inc. | Indian Point 2 Uprate | 2003-07-23 | 36 |  | NU | Westchester | NY | H | Buchanan 345kV | CONED | 14 | 2009-04-08 | SRIS, CY05 | I/S | I/S
0139 | Entergy Nuclear Operations, Inc. | Indian Point 3 Uprate | 2003-07-23 | 38 |  | NU | Westchester | NY | H | Indian Point 345kV | CONED | 14 | 2009-04-08 | SRIS, CY05 | I/S | I/S
0141 | Flat Rock Wind Power, LLC | Flat Rock Wind Power | 2003-08-27 | 321 |  | W | Lewis | NY | E | Adirondack-Porter 230kV | NM-NG | 14 | 2008-02-26 | SRIS, CY05 | I/S | I/S
0143 | Constellation | Ginna Uprate Project | 2004-01-30 | 95 |  | NU | Wayne | NY | B | Ginna-115kV | RG&E | 14 | 2008-02-26 | SRIS, CY05 | I/S | I/S
0144 | Sheldon Energy, LLC | High Sheldon Windfarm | 2004-02-18 | 112.5 | 112.5 | W | Wyoming | NY | C | Stolle Rd-Meyer 230kV | NYSEG | 14 | 2009-06-24 | SRIS, CY06,CY07 | I/S | I/S
0145 | KeySpan Energy for LIPA | LIPA Summer Mobile Gens | 2004-03-02 | 96 |  | NG | Suffolk | NY | K | Holtsville and Shoreham 138kV | LIPA | 14 | 2008-02-26 | SRIS | I/S | I/S
0146 | Con Edison | Mott Haven Substation | 2004-03-16 | N/A | N/A | AC | Westchester | NY | J | Dunwoodie-Rainey lines | CONED | 14 | 2009-04-08 | SRIS | I/S | N/A
0149 | KeySpan Energy for LIPA | LIPA Wading River Em Gen | 2004-06-03 | 79.9 |  | CT | Suffolk | NY | K | Wading River | LIPA | 14 |  | SRIS | I/S | I/S
0153 | Con Edison | Sprain Brook-Sherman Creek | 2004-08-13 | 500 | N/A | AC | Westchester | NY | I, J | Sprain Brook & Sherman Creek | CONED | 14 | 2011-03-31 | SIS | I/S | N/A
0156 | Hardscrabble Wind Power, LLC | Fairfield Wind Project | 2004-09-28 | 74 | 74 | W | Herkimer | NY | E | Valley-Inghams 115kV | NM-NG | 14 | 2011-02-28 | SRIS, CY06 | I/S | I/S
0160A | Innovative Energy Systems Inc. | DANC | 2004-11-19 | 6.4 | 6.4 | M | Jefferson | NY | E | 115kV | NM-NG | 14 | 2008-10-14 |  | I/S | I/S
0161 | Marble River, LLC | Marble River Wind Farm | 2004-12-07 | 83 | 83 | W | Clinton | NY | D | Willis-Plattsburgh WP-1 230kV | NYPA | 14 | 2013-03-31 | SRIS, FS | I/S | I/S
0171 | Marble River, LLC | Marble River II Wind Farm | 2005-02-08 | 132.2 | 132.2 | W | Clinton | NY | D | Willis-Plattsburgh WP-2 230kV | NYPA | 14 | 2013-03-31 | SRIS, FS | I/S | I/S
0172 | Noble Environmental Power, LLC | Clinton Windfield | 2005-02-14 | 79.5 | 79.5 | W | Clinton | NY | D | Willis-Plattsburgh WP-2 230kV | NYPA | 14 | 2008-10-14 | SRIS, CY06 | I/S | I/S
0173 | Noble Environmental Power, LLC | Bliss Windfield | 2005-02-14 | 72 | 72 | W | Wyoming | NY | A | Arcade Substation 115kV | Village of Arcade | 14 | 2008-10-14 | SRIS, CY06 | I/S | I/S
0174 | Noble Environmental Power, LLC | Altona Windfield | 2005-02-14 | 99 | 99 | W | Clinton | NY | D | Willis-Plattsburgh WP-1 230kV | NYPA | 14 | 2009-03-02 | SRIS, CY06 | I/S | I/S
0175 | Noble Environmental Power, LLC | Ellenburg Windfield | 2005-02-14 | 81 | 81 | W | Clinton | NY | D | Willis-Plattsburgh WP-2 230kV | NYPA | 14 | 2008-10-14 | SRIS, CY06 | I/S | I/S
0177 | Noble Wethersfield Windpark, LLC | Wethersfield 230kV | 2005-02-14 | 126 | 126 | W | Wyoming | NY | C | Stolle-Meyer 230kV | NYSEG | 14 | 2009-03-02 | FES,SRIS,CY07 | I/S | I/S
0182 | Howard Wind, LLC | Howard Wind | 2005-03-21 | 57.4 | 57.4 | W | Steuben | NY | C | Bennett-Bath 115kV | NYSEG | 14 | 2011-12-31 | FES, SRIS, CY07 | I/S | I/S
0185 | NY Power Authority | Blenheim Gilboa Storage | 2005-03-29 | 120 | 120 | PS | Schoharie | NY | F | Valenti Rd., Gilboa 345kV | NYPA | 14 | 2010-06-30 | SRIS, CY06 | I/S | I/S
0199 | UPC Wind Management, LLC | Canandaigua II | 2005-07-26 | 42.5 | 42.5 | W | Steuben | NY | C | Meyer - Avoca 230kV | NYSEG | 14 | 2009-04-08 | SRIS, CY07 | I/S | I/S
0201A | Innovative Energy Systems | Seneca Energy Expansion | 2005-09-02 | 17.6 | 17.6 | M | Seneca | NY | C | 34.5kV | NYSEG | 14 | 2008-04-22 |  | I/S | I/S
0201B | Minnesota Methane, LLC | MM Albany Landfill | 2005-09-15 | 2 | 4 | M | Albany | NY | F | 34.5kV | NM-NG | 14 | 2008-10-14 |  | I/S | I/S
0205 | National Grid | Luther Forest | 2005-11-02 | 40 | 40 | L | Saratoga | NY | F | Round Lake 115kV | NM-NG | 14 | 2013-03-31 | SIS | I/S | I/S
0206 | Hudson Transmission Partners | Hudson Transmission | 2005-12-14 | 660 | 660 | DC | NY - Bergen | NY-NJ | J | West 49th Street 345kV | CONED | 14 | 2013-06-30 | FES, SRIS, FS | I/S | I/S
0209A | Casella Waste Systems | Hyland Landfill | 2006-02-28 | 6.4 | 6.4 | M | Livingston | NY | C | 34.5kV | NYSEG | 14 | 2008-10-14 |  | I/S | I/S
0211 | Noble Environmental Power, LLC | Clinton II Windfield | 2006-04-03 | 21 | 21 | W | Clinton | NY | D | Willis-Plattsburgh WP-2 230kV | NYPA | 14 | 2008-10-14 | SRIS, CY07 | I/S | I/S
0212 | Noble Environmental Power, LLC | Bliss II Windfield | 2006-04-03 | 28.5 | 28.5 | W | Wyoming | NY | A | Freedom Substation 115kV | Village of Arcade | 14 | 2008-10-14 | SRIS, CY07 | I/S | I/S
0214 | Noble Chateaugay Windpark, LLC | Chateaugay Windpark | 2006-04-03 | 106.5 | 106.5 | W | Franklin-Clinton | NY | D | Willis-Plattsburgh 230kV | NYPA | 14 | 2009-03-02 | FES, SRIS, CY07 | I/S | I/S
0216 | Nine Mile Point Nuclear, LLC | Nine Mile Point Uprate | 2006-05-05 | 168 | 168 | NU | Oswego | NY | C | Scriba Station 345kV | NM-NG | 14 | 2013-03-31 | SRIS, FS | I/S | I/S
0217A | New Athens Generating Co., LLC | Athens SPS Project | 2006-06-30 | N/A | N/A | AC | Greene-W.Chester | NY | F, H | Athens - Millwood | NM-NG/CONED | 14 | 2009-04-08 | SIS | I/S | N/A
0224A | Bio-Energy Partners | High Acres Landfill | 2006-08-25 | 6.4 | 6.4 | M | Monroe | NY | C | 34.5 | NYSEG | 14 | 2008-12-22 |  | I/S | I/S
0225 | NY State Electric & Gas | Ithaca Transmission | 2006-09-07 | N/A | N/A | AC | Thompkins | NY | C | Oakdale - Lafayette 345kV | NYSEG | 14 | 2011-01-31 | SIS | I/S | N/A
0232 | Bayonne Energy Center, LLC | Bayonne Energy Center | 2006-11-27 | 500 | 500 | D | Bayonne | NJ | J | Gowanus Substation 345kV | ConEd | 14 | 2013-03-31 | FES, SRIS, CY09 | I/S | I/S
0233 | Erie Boulevard Hydro Power, LP | Sherman Island Uprate | 2006-11-27 | 8.5 | 8.5 | H | Warren | NY | F | Spier - Queensbury 115kV | NM-NG | 14 | 2010-02-16 | SRIS,CY08 | I/S | I/S
0234 | Steel Winds, LLC | Steel Winds II | 2006-12-08 | 15 | 15 | W | Erie | NY | A | Substation 11A 115kV | NM-NG | 14 | 2012-01-31 | SRIS, CY08 | I/S | I/S
0237A | Chautauqua County | Chautauqua Landfill | 2007-01-11 | 6.4 | 6.4 | M | Chautauqua | NY | A | Hartfield  South Dow 34.5kV | NM-NG | 14 | 2009-10-28 | FES,SIS,FS | I/S | I/S
0245 | Innovative Energy System, Inc. | Fulton County Landfill | 2007-04-17 | 3.2 | 3.2 | M | Montgomary | NY | F | Ephratah  Amsterdam 69kV | NM-NG | 14 | 2011-11-30 | FES,SIS,CY09 | I/S | I/S
0250 | Seneca Energy II, LLC | Ontario | 2007-07-02 | 5.6 | 5.6 | M | Ontario | NY | C | Haley Rd. - Hall 34.5kV | NYSEG | 14 | 2013-03-31 | FES,FS | I/S | I/S
0251 | CPV Valley, LLC | CPV Valley Energy Center | 2007-07-05 | 677.6 | 690.6 | D | Orange | NY | G | Coopers  Rock Tavern 345kV | NYPA | 14 | 2018-03-31 | FES, SRIS, FS | I/S | I/S
0260 | Stephentown Regulation Services, LLC | Stephentown | 2007-09-25 | 20 | 20 | F | Rensselaer | NY | F | Stephentown 115kV | NYSEG | 14 | 2011-11-30 | SIS,CY10 | I/S | I/S
0263 | Stony Creek Wind Farm, LLC | Stony Creek Wind Farm | 2007-10-12 | 92.8 | 92.8 | W | Wyoming | NY | C | Stolle Rd - Meyer 230kV | NYSEG | 14 | 2014-03-31 | FES, SRIS, CY10 | I/S | I/S
0270A | National Grid | Luther Forest Transmission | 2007-12-18 | N/A | N/A | AC | Saratoga | NY | F | Ngrid 115kV | NM-NG | 14 | 2008-10-14 | SIS | I/S | N/A
0284 | Broome Energy Resources, LLC | Nanticoke Landfill | 2008-03-06 | 1.6 | 1.6 | M | Broome | NY | C | Nanticoke Landfill Plant 34.5kV | NYSEG | 14 | 2013-09-30 | FES | I/S | I/S
0289 | NY State Electric & Gas | Corning Valley Trans. | 2008-04-01 | N/A | N/A | AC | Steuben | NY | C | Avoca and Hillside 230kV | NYSEG | 14 | 2011-09-30 | SIS | I/S | N/A
0290A | Green Island Power Authority | Green Island Power | 2008-04-07 | 20 | 20 | L | Albany | NY | F | Maplewood - Johnson Rd 115kV | NM-NG | 14 | 2011-11-30 | SIS | I/S | I/S
0294 | Orange & Rockland | Ramapo-Sugarloaf | 2008-04-29 | N/A | N/A | AC | Orange/Rockland | NY | G | Ramapo - Sugarloaf 138kV | O&R | 14 | 2015-04-30 | SIS | I/S | N/A
0308 | Astoria Energy II, LLC | Astoria Energy II | 2008-08-20 | 576 | 617.2 | NG | Queens | NY | J | Astoria 345kV | NYPA | 14 | 2011-11-30 | SRIS | I/S | I/S
0318 | AES Energy Storage, LLC | Westover Energy Storage | 2008-12-03 | 20 | 20 | ES | Broome | NY | C | Westover 115kV | NYSEG | 14 | 2010-12-31 | None | I/S | I/S
0326 | NYSEG/RG&E | Rochester SVC/PST Trans. | 2009-03-09 | N/A | N/A | AC | Monroe | NY | B | Station 124 115kV | NYSEG | 14 | 2014-04-30 | SIS | I/S | N/A
0330 | Long Island Solar Farm LLC | Upton Solar Farms | 2009-04-07 | 31.5 | 32 | S | Suffolk | NY | K | 8ER Substation 69kV | LIPA | 14 | 2011-11-30 | SRIS | I/S | I/S
0331 | National Grid | Northeast NY Reinforcement | 2009-04-22 | N/A | N/A | AC | Saratoga | NY | F | NGrid 230kV | NM-NG | 14 | 2019-03-31 | SIS | I/S | N/A
0333 | National Grid | Western NY Reinforcement | 2009-05-05 | N/A | N/A | AC | Cattaraugus | NY | A | NGrid 115kV | NM-NG | 14 | 2019-03-31 | SIS | I/S | N/A
0337 | Long Island Power Authority | Northport Norwalk Harbor | 2009-07-14 | N/A | N/A | AC | Suffolk | NY | K | Northport 138kV | LIPA | 14 | 2011-01-31 | SIS | I/S | N/A
0339 | RG&E | Transmission Reinforcement | 2009-08-17 | N/A | N/A | AC | Monroe | NY | B | Niagara - Kintigh 345kV | RG&E | 14 | 2019-04-30 | SIS | I/S | N/A
0340 | RG&E | Brown's Race III | 2009-09-02 | 2 | 2 | H | Monroe | NY | B | Station 6 34.5 kV | RG&E | 14 | 2012-01-31 | None | I/S | I/S
0342 | Albany Energy, LLC | Albany Landfill | 2009-09-03 | 6.4 | 6.4 | M | Albany | NY | F | 34.5kV | NM-NG | 14 | 2013-03-31 | None | I/S | I/S
0353 | Chautauqua County | Chautauqua County Landfill | 2010-04-26 | 3.2 | 3.2 | M | Chautauqua | NY | A | Hartfield  South Dow 34.5kV | NM-NG | 14 |  | None | I/S | I/S
0355 | Brookfield Renewable Power | Stewarts Bridge Hydro | 2010-08-03 | 3 | 3 | H | Saratoga | NY | F | Spier Falls - EJ West 115kV | NM-NG | 14 | 2015-04-30 | SRIS, FS | I/S | I/S
0368 | Consolidated Edison Co. of NY | Feeder 76 Ramapo to Rock Tavern | 2011-10-13 | N/A | N/A | AC | Orange, Rockland | NY | G | Ramapo to Rock Tavern 345 kV | ConEd/CenHud | 14 | 2016-05-31 | SIS | I/S | N/A
0373 | NY Power Authority | Coopers Corners Shunt Reactor | 2011-12-21 | N/A | N/A | AC | Sullivan | NY | E | Coopers Corners 345 kV | NYSEG | 14 | 2015-08-31 | SIS | I/S | N/A
0375 | Eagle Creek Hydro, LLC | Eagle Creek Hydro | 2012-03-06 | 0.8 | 0.8 | H | Sullivan | NY | E | Rio 69kV Switchyard | O&R | 14 | 2014-01-31 | None | I/S | I/S
0378 | Invenergy NY LLC | Marsh Hill Wind | 2012-03-29 | 16.2 | 16.2 | W | Steuben | NY | C | Jasper - Marshall Warriner 34.5kV | NYSEG | 14 | 2014-12-31 | None | I/S | I/S
0380 | NY Power Authority | Marcy South Reinforcement | 2012-05-14 | N/A | N/A | AC | Oneida-Sullivan | NY | E | Marcy/Edic-Coopers Corners 345kV | NYSEG | 14 | 2016-07-31 | SIS | I/S | N/A
0387 | Cassadaga Wind, LLC | Cassadaga Wind | 2012-07-19 | 126.5 | 126.5 | W | Chautauqua | NY | A | Dunkirk - Moon 115 kV | NM-NG | 14 | 2020-05-31 | FES, SRIS, FS | I/S | I/S
0390 | Trail Co. | Farmers Valley Substation | 2012-09-14 | N/A | N/A | AC | Cattaraugus | NY-PA | A | Homer City - Stolle Rd. 345kV | NM-NG/NYSEG | 14 | 2016-06-30 | SIS | I/S | N/A
0394 | Trail Co. | Mainesburg Substation | 2012-10-16 | N/A | N/A | AC | Chemung | NY-PA | C | Homer City - Watercure 345kV | NYSEG | 14 | 2015-12-31 | SIS | I/S | N/A
0395 | Copenhagen Wind Farm, LLC | Copenhagen Wind | 2012-11-12 | 79.9 | 79.9 | W | Lewis | NY | E | Black River-Lighthouse Hill 115kV | NM-NG | 14 | 2019-03-31 | FES, SRIS, FS | I/S | I/S
0396 | Baron Winds, LLC | Baron Winds | 2012-11-30 | 238.8 | 238.8 | W | Steuben | NY | C | Hillside - Meyer 230kV | NYSEG | 15 | 2022-12-31 | FES, SRIS, FS | IS | I/S
0397 | Jericho Rise Wind Farm, LLC | Jericho Rise Wind | 2012-12-21 | 77.7 | 77.7 | W | Franklin | NY | D | Willis Substation 115kV | NYPA | 14 | 2017-02-28 | SRIS, FS | I/S | I/S
0403 | PSEG Power NY | Bethlehem Energy Center Uprate | 2013-05-28 | 72 | 51.2 | D | Albany | NY | F | Bethlehem Energy Center | NM-NG | 14 | 2019-03-31 | FES, SRIS, FS | I/S | I/S
0421 | Arkwright Summit Wind Farm LLC | Arkwright Summit | 2013-11-01 | 78.4 | 78.4 | W | Chautauqua | NY | A | Dunkirk - Falconer 115 kV | NM-NG | 14 | 2021-08-31 | SRIS, FS | IS | I/S
0422 | NextEra Energy Resources, LLC | Eight Point Wind Energy Center | 2013-11-07 | 101.8 | 101.8 | W | Steuben-Allegany | NY | C | Bennett 115kV | NYSEG | 14 | 2021-03-31 | FES, SRIS, FS | IS | I/S
0431 | Greenidge Generation | Greenidge Unit #4 | 2014-04-11 | 106.3 | 106.3 | NG | Yates | NY | C | Greenidge Substation 115kV | NYSEG | 14 | 2018-02-28 | SIS, FS | 10/2021 | N/A
0432 | NY State Electric & Gas | South Perry Transformer | 2014-04-15 | N/A | N/A | AC | Wyoming | NY | B | South Perry Substation 115kV | NYSEG | 14 | 2018-07-31 | SRIS, FS | I/S | I/S
0444 | Cricket Valley Energy Center, LLC | Cricket Valley Energy Center II | 2014-06-18 | 1020 | 1132 | CC | Dutchess | NY | G | Pleasant Valley - Long Mt. 345kV | ConEd | 14 | 2019-07-31 | SIS | I/S | N/A
0461 | Consolidated Edison Co. of NY | East River 1 Uprate | 2014-12-01 | 2 | 2 | CT | NY | NY | J | East River Complex | ConEd | 14 | 2019-12-31 | SRIS, FS | IS | I/S
0462 | Consolidated Edison Co. of NY | East River 2 Uprate | 2014-12-01 | 2 | 2 | CT | NY | NY | J | East River Complex | ConEd | 14 | 2019-12-31 | SRIS, FS | IS | I/S
0467 | Shoreham Solar Commons LLC | Shoreham Solar | 2014-12-22 | 25 | 25 | S | Suffolk | NY | K | Ridge - Wildwood 69kV | LIPA | 14 | 2019-07-31 | SRIS, FS | IS | I/S
0477 | Riverhead Solar Farm LLC | Riverhead Solar | 2015-02-18 | 20 | 20 | S | Suffolk | NY | K | Edwards Substation 138kV | LIPA | 14 | 2019-05-31 | SRIS, FS | IS | I/S
0490 | NY Power Authority | Marcy South Series Comp | 2015-03-16 | N/A | N/A | AC | Oneida-Sullivan | NY | E | Marcy/Edic-Coopers Corners 345kV | NYSEG/NM-NG | 14 | 2016-07-31 | FES, SIS, FS | IS | I/S
0505 | Ball Hill Wind Energy, LLC | Ball Hill Wind | 2015-06-02 | 103 | 103 | W | Chautauqua | NY | A | Dunkirk - Gardenville 230kV | NM-NG | 14 | 2023-10-31 | FES, SRIS, FS | IS | I/S
0510 | Bayonne Energy Center | Bayonne Energy Center II | 2015-08-03 | 120.4 | 129.4 | D | Hudson | NJ | J | Gowanus Substation 345kV | ConEd | 14 | 2019-12-31 | SIS | I/S | N/A
0513 | Orangeville Energy Storage LLC | Orangeville | 2015-09-21 | 20 | 20 | ES | Wyoming | NY | C | Stony Creek 230kV | NYSEG | 14 | 2021-12-31 | SRIS, FS | IS | I/S
0517 | National Grid | Western NY Reactors & Capacitors | 2015-10-14 | N/A | N/A | AC | Niagara | NY | A | Packard - Huntley 230kV | NM-NG | 14 | 2016-06-30 | SIS, FS | I/S | 04/2022
0531 | Number Three Wind LLC | Number 3 Wind Energy | 2016-01-11 | 103.9 | 103.9 | W | Lewis | NY | E | Taylorville - Boonville 115kV | NM-NG | 14 | 2023-07-31 | FES, SRIS, FS | IS | I/S
0543 | National Grid | Segment B Knickerbocker-PV | 2016-05-04 | N/A | N/A | AC | Albany-Dutchess | NY | F, G | Greenbush - PV 345kV | NM-NG/NYSEG/ CHGE/ConEd | 15 | 2022-04-30 | SIS | IS | 12/2023-06/2025
0545A | NextEra Energy Transmission NY, Inc. | Empire State Line Alt | 2016-05-17 | N/A | N/A | AC | Niagara-Erie | NY | A | Dysinger - Stolle 345kV | NYPA/NYSEG | 14 | 2022-04-30 | SIS | I/S | N/A
0546 | PPM Roaring Brook, LLC | Roaring Brook Wind | 2016-05-19 | 79.7 | 79.7 | W | Lewis | NY | E | Chases Lake Substation 230kV | NM-NG | 14 | 2022-01-31 | SIS, FS | IS | I/S
0556 | LS Power Grid NY, LLC | Segment A Double Circuit | 2016-07-06 | N/A | N/A | AC | Oneida-Albany | NY | E, F | Edic - New Scotland 345kV | NM-NG | 15 | 2022-04-30 | SIS, FS | IS | I/S
0570 | Hecate Energy Albany 1 LLC | Albany County 1 | 2016-08-17 | 20 | 20 | S | Albany | NY | F | Long Lane - Lafarge 115kV | NM-NG | 14 | 2023-12-31 | SIS, FS | IS | I/S
0579 | Bluestone Wind, LLC | Bluestone Wind | 2016-09-21 | 111.8 | 111.8 | W | Broome | NY | E | Afton - Stilesville 115kV | NYSEG | 14 | 2023-12-31 | FES, SRIS, FS | IS | I/S
0583 | Erie Boulevard Hydropower, LP | Fulton | 2016-10-31 | 1.3 | 1.3 | H | Oswego | NY | C | Fay St. 34.5kV | NM-NG | 14 | 2018-03-31 | FES, SRIS, FS | I/S | I/S
0598 | Hecate Energy Albany 2 LLC | Albany County 2 | 2017-01-10 | 20 | 20 | S | Albany | NY | F | Long Lane - Lafarge 115kV | NM-NG | 14 | 2023-12-31 | SIS, FS | IS | I/S
0612 | South Fork Wind, LLC | South Fork Wind Farm | 2017-02-14 | 96 | 96 | W | Suffolk | NY | K | East Hampton 69kV | LIPA | 14 | 2024-07-31 | SRIS, FS | IS | I/S
0618 | High River Energy Center, LLC | High River Solar | 2017-03-27 | 90 | 90 | S | Montgomery | NY | F | Inghams - Rotterdam 115kV | NM-NG | 14 | 2024-07-31 | SRIS, FS | IS | I/S
0619 | East Point Energy Center, LLC | East Point Solar | 2017-03-27 | 50 | 50 | S | Schoharie | NY | F | Cobleskill - Marshville 69kV | NM-NG | 14 | 2024-04-30 | SRIS, FS | IS | I/S
0638 | Pattersonville Solar Facility, LLC | Pattersonville | 2017-07-11 | 20 | 20 | S | Montgomery | NY | F | Rotterdam - Meco 115kV | NM-NG | 14 | 2023-07-31 | FES, SIS, FS | IS | I/S
0678 | LI Solar Generation, LLC | Calverton Solar Energy Center | 2017-10-26 | 22.9 | 22.9 | S | Suffolk | NY | K | Edwards Substation 138kV | LIPA | 14 | 2022-09-30 | SIS, FS | IS | I/S
0682 | Grissom Solar, LLC | Grissom Solar | 2018-01-17 | 20 | 20 | S | Montgomery | NY | F | Ephratah - Florida 115kV | NM-NG | 14 | 2022-11-30 | FS | I/S | I/S
0695 | South Fork Wind, LLC | South Fork Wind Farm II | 2018-02-16 | 40 | 40 | W | Suffolk | NY | K | East Hampton 69kV | LIPA | 14 | 2024-07-31 | SRIS, FS | IS | I/S
0696 | Eagle Creek Hydro Power, LLC | Swinging Bridge Unit 3 | 2018-03-21 | 1.2 | 1.2 | H | Orange | NY | G | Swing Bridge 69 kV | O&R | 14 | 2019-05-31 | SRIS, FS | IS | I/S
0701 | KCE NY 1, LLC | KCE NY 1 | 2018-03-15 | 20 | 20 | ES | Saratoga | NY | F | Luther Forest 34.5kV | NYSEG | 14 | 2019-12-31 | FES, SIS, FS | IS | I/S
0717 | Morris Ridge Solar Energy Center, LLC | Morris Ridge Solar Energy Center | 2018-06-04 | 177 | 177 | S | Steuben | NY | C | South Perry - Meyer 230kV | NYSEG | 14 | 2024-09-30 | FES, SRIS, FS | 09-2024 | 11-2024
0730 | Darby Solar, LLC | Darby Solar | 2018-06-11 | 20 | 20 | S | Washington | NY | F | Mohican - Schaghticoke 115kV | NM-NG | 14 | 2022-11-30 | FES, SIS | IS | I/S
0731 | Branscomb Solar, LLC | Branscomb Solar | 2018-06-11 | 20 | 20 | S | Washington | NY | F | Battenkill - Eastover 115kV | NM-NG | 14 | 2021-12-31 |  | IS | I/S
0735 | ELP Stillwater Solar LLC | ELP Stillwater Solar | 2018-06-12 | 20 | 20 | S | Saratoga | NY | F | Luther Forest - Mohican 115kV | NM-NG | 14 | 2023-11-30 | FES, SIS, FS | IS | I/S
0748 | Regan Solar, LLC | Regan Solar | 2018-08-09 | 20 | 20 | S | Montgomery | NY | F | Market Hill - Johnstown 69kV | NM-NG | 14 | 2022-12-31 |  | IS | I/S
0758 | Sithe/Independence Power Partners, LP | Sithe Independence | 2018-09-06 | 9 | 27 | CC | Oswego | NY | C | Sithe 345kV Substation | NM-NG | 14 | 2023-12-31 | SRIS, FS | IS | I/S
0759 | KCE NY 6, LLC | KCE NY 6 | 2018-09-06 | 20 | 20 | ES | Erie | NY | A | Gardenville - Bethlehem Steel Wind 115kV Line #150 | NM-NG | 14 | 2022-01-31 | SIS | IS | I/S
0768 | Janis Solar, LLC | Janis Solar | 2018-10-01 | 20 | 20 | S | Cortland | NY | C | Willet 34.5kV | NYSEG | 14 | 2022-11-30 | FES, SIS, FS | I/S | I/S
0769 | NY Power Authority | North County Energy Storage | 2018-10-05 | 20 | 20 | ES | Franklin | NY | D | Willis 115kV | NYPA | 14 | 2023-09-30 | SIS | IS | I/S
0775 | Puckett Solar, LLC | Puckett Solar | 2018-10-22 | 20 | 20 | S | Chenango | NY | C | Chenango Forks 34.5kV | NYSEG | 14 | 2022-09-30 | SIS, FS | IS | I/S
0781 | NY Power Authority | Marcy South SSR Detection | 2018-12-03 | N/A | N/A | AC | Delaware | NY | E | Fraser - Annex 345 kV Substation | NYPA | 14 | 2019-09-30 | SIS, FS | IS | I/S
0849 | Somerset Operating Company, LLC | Somerset Load | 2019-05-21 | 250 | 250 | L | Niagara | NY | A | Kintigh 345kV | NYSEG | 14 | 2022-07-31 | SIS, FS | IS | I/S