# NYISO

Project Budgeting and

Financing Process

## Draft

05/14/03

- Introduction

An effective project budgeting and financing process is essential to ensure sound investment decisions that result in reliable, efficient and cost effective operations over the long term.  Such a process is also essential towards assuring that the NYISO remains competitive with neighboring ISOs.  This report sets forth a proposed budgeting process, or framework, which would be used to: identify, screen, evaluate, select, prioritize, fund, and monitor operating and capital project investments within the pre-established long-term budget targets of the NYISO.   This proposal is designed to allow market participants, NYISO staff and the ISO Board to effectively manage the budgeting process through the existing committee structure.  This process is not intended nor designed to either manage staffing or the ongoing operations of the NYISO.

It is envisioned that all proposed projects in excess of $500,000 would be subject to this process.

The process proposed herein is comprised of the five elements as described below.

1.1	Budgeting

An initial step in the process is the establishment of a multi-year (5 year) budget target that is reflective of the NYISO long-term strategic plan.  Market Participants and the NYISO Board would be responsible for establishing the long-term (5 year) budget target.  The budget target would clearly identify those funds that would be treated as an expense and those funds that would be available for longer term financing.  It is recognized that the budgeting process needs to be flexible to accommodate new and changing missions in future year budgets.

1.2	Identification

Project requests can originate from a number of different sources for a variety of reasons including: NYISO identified enhancements or correction of market flaws, FERC orders, Committee, Subcommittee and Working Group Actions, PSC initiatives,  Seams Issues Resolution, and Market Participant requests.  All project requests will be documented and included in a single list.  Among other things, this list will identify the proposed project’s proponent/s along with the current status of the project in the process.

All proposed projects having an estimated cost in excess of $500,000 and which would be funded from the Project Expense Budget or the Project Financing Budget will be subject to the Project budgeting and financing process.

1.3	Selection

Under the proposed budget process, the proponent/s of any project must first present their request to either the Business Issues Committee (BIC) or the Operating Committee (OC) for consideration and approval.  In certain cases, project requests may be directly presented to the Management Committee (MC).

For those project requests receiving approval (“qualified projects”), the NYISO staff will perform, in consultation with the project’s proponent/s, analyses in conformance with the Management Committee (MC) Cost and Justification Guidelines (“Guidelines”).    The NYISO staff will also evaluate the potential budget impacts.

Upon completion of the qualified project’s cost and justification analysis, this information will be submitted to the Management Committee (MC) and the BS&P.  If deemed necessary, the MC may refer the project to the BS&P for further study and consideration.

Those projects receiving MC approval will be forwarded to the Project Priority Team (PPT) for prioritization and scheduling.  The PPT shall take into account the budget impacts when determining prioritization and scheduling.

Upon completion of an FRS, the MC will be notified of any project that is projected to exceed its initial cost estimate by 25% or $500,000, whichever is lees.  The MC will also be notified of any project whose initial cost was less than $500,000 but is now expected to exceed that threshold.  If the foregoing cost threshold is exceeded, the MC, by a 58% vote, may stop or modify the project.  All other approved projects would be forwarded to the NYISO staff for implementation.

1.4	Monitoring

A procedure for monitoring all ongoing and approved projects needs to be in place to ensure that each investment continues to be required and, as such, meets scope, is on schedule and within budget.  The NYISO staff will have the responsibility for preparing periodic status reports and advising the PPT and BS&P Subcommittee.  In the event of potential significant budget impacts, the MC will also be notified.

Schedules will be developed for each project along with the identification of major milestones, cash flow tracking and critical path analysis.   Status reports will be prepared monthly and forwarded to the PPT for review.  Additionally, the status of key and strategic projects will also be reported to the Committees on a periodic basis.

Significant changes in a project’s scope, schedule or cost may require re-evaluation and reprioritization.  The NYISO will report to the MC any project whose cost is expected to exceed its estimated cost or subsequently approved FRS cost estimate by the lesser of $500,000 or 25%.  The MC, by a 58% vote, may stop or modify a project whose cost exceeds the foregoing threshold.    The MC will also be notified of any project whose initial cost was less than $500,000 but is now expected to exceed that threshold.  It will take an action of the MC and NYISO Board to reschedule and reprioritize projects in a manner that will exceed the future year project budgets.

1.5	Evaluation

The review process will be tied into the project closeout process.  It will be used to determine whether a project has realized its expected mission and business performance goals.  The overall effectiveness of the budgeting process associated with each project will be reviewed and lessons learned will be used to modify the budgeting process and selection decisions for future projects.

1.6	Exceptions

In the event of an emergency where it is determined that the reliability of the system may be in jeopardy this process may be bypassed.

# 2.0	Project Budgeting And Reporting

The yearly budgeting process will include the development of a  budget target, by year, for the immediately succeeding five years (“budget target”).  The budget target will be for both NYISO operations and capital projects.  The initial five- year budget projection (2004-2008) will be developed using the 2003 original approved budget as a base point.  Commencing with the establishment of the 2004 Budget, the five-year budget target will be developed and approved as part of the yearly  budgeting process.  The first year of the budget target will be quite detailed and provide, as a minimum, the same level of information as is currently the case.  The budget target values for the remaining four years, by its nature, will be less precise and detailed.  At a minimum, the  target values for those four years will provide an estimate of expenditures for ongoing operations as well as approved and anticipated projects, both expensed and capitalized.

2.1	Project Budget Summary Report

Depending upon the nature, scope and resources required, the costs of some projects may be borne as an operating expense in the year incurred whereas, the cost of other projects may be funded through external capital financing with the related debt service obligations (principal and interest) being recovered over a period of years.  The  budget target will include supporting documentation  that separately identifies by project, that portion of a project’s cost which will be expensed and recovered through the Operating Budget and that portion of the project’s costs of which is to be capitalized.

For those projects, the costs of which are to be expensed, the report documentation will provide the following information by project, by year for the five-year period:

- The total amount of money estimated to be available for project expense funding.

- Estimated expenditures (costs) for those MC approved projects that are already underway.

- Estimated expenditures (costs) for those MC approved projects that have been prioritized and scheduled by the PPT but are not yet underway.

- Funding available for project expenses that have not yet been prioritized and scheduled.

For those projects, the costs of which are to be funded through external capital financing, the report documentation will provide the following information by project, by year for the five-year period:

- The estimated capital budget (financing requirements).

- The total amount of money estimated to be available for the debt service payments of financed projects.

- The debt service payments for completed projects.

- The debt service payments  for MC approved projects already underway.

- The estimated debt service payments associated with MC approved projects that have been prioritized and scheduled by the PPT but are not yet underway.

- The estimated funds (revenue) available for the payment of debt service for projects that have not yet been prioritized and scheduled.

For those projects where certain of its costs may be expensed and remaining portion of its costs capitalized, the same information as described above shall be reported.

### 2.2	Project Budgets Report

The Project Budget Report will be updated by NYISO staff as new projects are prioritized and scheduled by the PPT.  The report would contain the following

- Project Budget Summary Report described above.

- A listing of completed financed projects grouped by year with the past and remaining future recovery.

- A listing of active projects, by project, showing the budgeted amounts, historic expenditures and projected expenditures along with a breakdown by expensed and financed portions of the project.  For financed projects, the expected debt service obligation cost recovery of the project by year.

- A listing of scheduled projects, by project, showing the budgeted amounts with a breakdown of expensed and financed portions of the project.  For financed projects, the expected cost recovery of the project by year.

- A listing of approved but unscheduled projects with budgeted costs by quarter.

# 3.0	INITIAL SCREENING OF PROJECT INVESTMENTS

As a general practice, all proposed projects will pass the initial screening phase conducted by BIC, or the OC, before being deemed eligible for further consideration.  Eligible projects will be submitted to the NYISO Staff for detailed analysis and ultimately, consideration by the MC.  In certain cases there may be exceptions to this process.  Examples of exceptions include: those proposed projects submitted directly to the MC for consideration and instances where the NYISO Staff has already commenced its detailed analysis.

Table 1 sets forth the specific roles and responsibilities of the key participants in the initial screening phase of the project budgeting process.

Table 1.   Screening Phase

| Party | Roles & Responsibilities |
| --- | --- |
| Project Proponent/s and/or Working Group/Task Force | Develop project proposal. Submit proposal to BIC or OC. Provide additional screening information if requested. |
| BIC or OC | Review proposal. Accept or reject. If accepted (deemed eligible) forward project proposal to NYISO Staff for detailed analysis to be conducted in accordance with the MC Cost and Justification Guidelines. |
| NYISO Staff | Where appropriate commence detailed analysis. Present results of analysis to BIC or OC as appropriate. |

### 3.1	Develop Project Proposal

The first phase of the project budgeting process centers on the project proponent/s developing a preliminary proposal and the subsequent screening of that proposal by BIC or OC.    The preliminary project proposal should include, as a minimum, the following information:

- Project Name

- Project Description, including perceived need

- Project Type (economics, replacement, regulatory, etc.)

- Potential alternatives

- Initial description of expected benefits

- Desired/required completion/on-line date

### 3.2	BIC or OC Initial Screening

The principal objective of the screening phase is to determine whether the proposed project is viable and merits further detailed analysis by the NYISO Staff.

The project proponent will submit its proposal to either BIC or the OC.  The Committee conducting the review may use the following as screening criteria to assist in its determination of whether the proposed project qualifies for detailed analysis to be conducted by the NYISO Staff.

- Does the project support core business functions?

- Is it critical to the performance of these functions?

- Does the project provide economic benefits?

- Does the project support operational, or work, processes that have been simplified or otherwise redesigned?

- Does the project improve service reliability?

- What are the expected benefits of the proposal?

- Is the project required by regulation?

- Are there major risks involved that will reduce the likelihood of the project performing as expected?

- How do the alternatives compare with the proposal?

Projects deemed qualified by either BIC or the OC will be submitted to the NYISO Staff for detailed analysis under the MC Cost Analyses and Justification Guidelines.

### 3.3	NYISO Detailed Analysis s

If a proposed project is deemed qualified, the NYISO Staff, in conjunction with the project’s proponent/s, will conduct a detailed analysis of the proposal.  In conducting its analysis the NYISO Staff will consistently apply the Guidelines.  The NYISO Staff’s analysis will include:

- Project Name

- Project Description, including need.

- Project Type (economics, replacement, regulatory, etc.)

- Alternatives, including potential costs and benefits.

- Estimated stream of expected benefits (both quantitative and qualitative).

- Estimated stream of project costs (identify components separately – labor, hardware, software, consultants, etc.).

- Estimated timeline for project completion.

- Whether project can be accommodated within the budget target without impacting other already scheduled projects.

- Whether project qualifies for long term financing.

- Whether the project woul require deferral of other already scheduled projects.

- Whether the project would require funding beyond that which is contained in the budget target.

- Associated risks of not implementing the proposed project.

- A recommendation as to whether the project should be approved by the MC.

The NYISO Staff will forward the results of its analysis to the MC for its consideration.

The MC will be responsible for determining whether to proceed with the proposed project.  Those projects which are approved by the MC will be forwarded to the PPT for scheduling and prioritization.

- Monitoring

The NYISO staff will have the responsibility for monitoring the status of all approved projects and preparing periodic reports.  Among other things, these periodic reports will identify project progress relative to schedule, actual costs incurred versus approved budget, whether the project can be completed within scope, budgeted cost and schedule.

The NYISO Staff will advise the MC of any project whose cost is expected to exceed its approved budgeted cost by 25% or $500,000, whichever is less.  The MC, by a 58% vote may stop, or modify, the project whose cost exceeds that threshold.

### 4.1	Establish and Maintain Project Cost, Schedule, and Technical Baselines

The NYISO Staff will be responsible for establishing project management and execution plans, procedures, and practices to support project-monitoring activities.  The NYISO Staff should provide periodic updates to PPT and BS&P on the status of the project’s cost, schedule, and technical baselines.  Baselines provide both the framework and sufficient detail to assess the status of the project’s major milestones, decisions, activities, and work products and deliverables.

Additionally, the NYISO Staff will collect information on resources allocated and expended throughout the pre-operational stage of the project.  The NYISO staff also will maintain a record of changes to the technical components of on-going projects.  Changes may later be reviewed for continued funding.

### 4.2	Assess Project Progress

During the pre-operational stage of a project, the NYISO staff will determine whether additional project evaluation is warranted.  If so, the NYISO staff will perform a more detailed review of the project to assess progress against its planned cost, schedule, and technical baselines.  The primary purpose of assessments is to ensure that projects remain on schedule and budget by identifying issues or deficiencies that require corrective action.

### 4.3	Prepare Project Monitoring Status Reports

With a project's monitoring review schedule established during the selection phase, the NYISO staff should prepare a Monitoring Status report for review by PPT and BS&P.  The status report will, among other things, be used to determine whether to recommend to the Management Committee that the project continue, be modified, or canceled.

# 5.0	Evaluate Initiatives

The evaluation phase of the project budgeting process begins after an investment becomes operational, suggested within six months of deployment.  The Evaluation Phase “closes the loop” of the budgeting process by comparing actual cost and benefits against budget and expectations.  This will not only allow performance to be assessed, but also helps identify areas where decision-making can be improved.  The evaluation phase focuses on two primary steps.

- Determining if the specific investment met performance, cost, and schedule objectives.

- Determining the extent to which the budgeting process improved the outcome of the investment.

The two steps of the evaluation phase include conducting a Post Implementation Review (PIR) and applying lessons learned, both at project and process levels.  Results of the PIR are reported to the PPT and BS&P to offer a better understanding of project performance and to assist the NYISO Staff in directing any adjustments to the project or to the budgeting process.

The timing of the PIR would be initially determined during the selection phase.  The PIR for a new project generally should take place about six months after the project is in service.  If a project is cancelled, the PIR should take place immediately.  Review of a cancelled project defines lessons learned for future investment decisions and activities.

The central objective of the PIR is the investment evaluation, in which the NYISO Staff assesses the impact the project has had on reliability, economics, customer satisfaction and system capability.

The evaluation focuses on three primary areas described below.

1.	Impact on Stakeholders

The project’s impact on stakeholders would be measured by the NYISO Staff through use of surveys (formal or informal), interviews, and feedback studies.

2.	Ability to deliver performance measures (Quantitative and Qualitative)

The project’s impact should be carefully evaluated to determine whether it met its original and possible modified performance goals.

3.	Ability to Meet Performance Goals

- Cost:

- Return:

- Schedule:

A report should also be submitted to the PPT and BS&P for all projects to document lessons learned, including costs, project management and technical insights.   A high-level assessment of management techniques, including organizational approaches, budgeting, acquisition and contracting strategies, tools and techniques, and testing methodologies is essential to establish realistic baselines and ensure the future success of other projects.  To capture lessons learned the project manager should develop a summary report after completion of the PIR.

Having identified the strengths and the weaknesses of the current process, the NYISO Staff, PPT and BS&P will work together to develop, recommend, and modify the project budgeting process as appropriate.

# Footnotes

The Budget, Standards and Performance Subcommittee would have the responsibility for the development of proposed cost and justification guidelines for MC consideration and adoption, if deemed appropriate.  These guidelines would be uniformly applied to all qualified projects.