# NYISO

Project Budgeting and

Financing Process

## Draft

05/14/03

- Introduction

An effective project budgeting and financing process is essential to ensure sound investment decisions that result in reliable, efficient and cost effective operations over the long term.  Such a process is also essential towards assuring that the NYISO remains competitive with neighboring ISOs.  This report sets forth a proposed budgeting process, or framework, which would be used to: identify, screen, evaluate, select, prioritize, fund, and monitor operating and capital project investments within the pre-established long-term budget targets of the NYISO.   This proposal is designed to allow market participants, NYISO staff and the ISO Board to effectively manage the budgeting process through the existing committee structure.  This process is not intended nor designed to either manage staffing or the ongoing operations of the NYISO.

It is envisioned that all proposed projects in excess of $500,000 would be subject to this process.

The process proposed herein is comprised of the five elements as described below.

1.1	Budgeting

An initial step in the process is the establishment of a multi-year (5 year) budget target that is reflective of the NYISO long-term strategic plan.  Market Participants and the NYISO Board would be responsible for establishing the long-term (5 year) budget target.  The budget target would clearly identify those funds that would be treated as an expense and those funds that would be available for longer term financing.  It is recognized that the budgeting process needs to be flexible to accommodate new and changing missions in future year budgets.

1.2	Identification

Project requests can originate from a number of different sources for a variety of reasons including: NYISO identified enhancements or correction of market flaws, FERC orders, Committee, Subcommittee and Working Group Actions, PSC initiatives,  Seams Issues Resolution, and Market Participant requests.  All project requests will be documented and included in a single list.  Among other things, this list will identify the proposed project’s proponent/s along with the current status of the project in the process.

All proposed projects having an estimated cost in excess of $500,000 and which would be funded from the Project Expense Budget or the Project Financing Budget will be subject to the Project budgeting and financing process.

1.3	Selection

Under the proposed budget process, the proponent/s of any project must first present their request to either the Business Issues Committee (BIC) or the Operating Committee (OC) for consideration and approval.  In certain cases, project requests may be directly presented to the Management Committee (MC).

For those project requests receiving approval (“qualified projects”), the NYISO staff will perform, in consultation with the project’s proponent/s, analyses in conformance with the Management Committee (MC) Cost and Justification Guidelines (“Guidelines”).    The NYISO staff will also evaluate the potential budget impacts.

Upon completion of the qualified project’s cost and justification analysis, this information will be submitted to the Management Committee (MC) and the BS&P.  If deemed necessary, the MC may refer the project to the BS&P for further study and consideration.

Those projects receiving MC approval will be forwarded to the Project Priority Team (PPT) for prioritization and scheduling.  The PPT shall take into account the budget impacts when determining prioritization and scheduling.

Upon completion of an FRS, the MC will be notified of any project that is projected to exceed its initial cost estimate by 25% or $500,000, whichever is lees.  The MC will also be notified of any project whose initial cost was less than $500,000 but is now expected to exceed that threshold.  If the foregoing cost threshold is exceeded, the MC, by a 58% vote, may stop or modify the project.  All other approved projects would be forwarded to the NYISO staff for implementation.

1.4	Monitoring

A procedure for monitoring all ongoing and approved projects needs to be in place to ensure that each investment continues to be required and, as such, meets scope, is on schedule and within budget.  The NYISO staff will have the responsibility for preparing periodic status reports and advising the PPT and BS&P Subcommittee.  In the event of potential significant budget impacts, the MC will also be notified.

Schedules will be developed for each project along with the identification of major milestones, cash flow tracking and critical path analysis.   Status reports will be prepared monthly and forwarded to the PPT for review.  Additionally, the status of

key and strategic projects will also be reported to the Committees on a periodic basis.

Significant changes in a project’s scope, schedule or cost may require re-evaluation and reprioritization.  The NYISO will report to the MC any project whose cost is expected to exceed its estimated cost or subsequently approved FRS cost estimate by the lesser of $500,000 or 25%.  The MC, by a 58% vote, may stop or modify a project whose cost exceeds the foregoing threshold.    The MC will also be notified of any project whose initial cost was less than $500,000 but is now expected to exceed that threshold.  It will take an action of the MC and NYISO Board to reschedule and reprioritize projects in a manner that will exceed the future year project budgets.

1.5	Evaluation

The review process will be tied into the project closeout process.  It will be used to determine whether a project has realized its expected mission and business performance goals.  The overall effectiveness of the budgeting process associated with each project will be reviewed and lessons learned will be used to modify the budgeting process and selection decisions for future projects.

1.6	Exceptions

In the event of an emergency where it is determined that the reliability of the system may be in jeopardy this process may be bypassed.

The Budget, Standards and Performance Subcommittee would have the responsibility for the development of proposed cost and justification guidelines for MC consideration and adoption, if deemed appropriate.  These guidelines would be uniformly applied to all qualified projects.