## BPWG Excel Sheet
Enterprise | Market | [5 empty] | Estimated Cost (in millions)
Enterprise Item | Markets Item | Project | Product Area | Project Type | 2022 Proposed Deliverable | 2021 Deliverable | Labor | Capital | Prof. Serv. | Total
| 1 | Capacity Value Study | Capacity Market | Mandatory | Study Defined |  | 0.18118 | 0 | 0.45 | 0.63118
| 2 | CRIS Tracking | Capacity Market | Mandatory | Development Complete | Software Design | 0.16872 | 0 | 0 | 0.16872
| 3 | DER Participation Model | New Resource | Mandatory | Deployment | Deployment | 4.6734 | 0.1 | 6.5 | 11.2734
| 4 | Support TSO and DSO Coordination Efforts | New Resource | Mandatory | Issue Discovery | Issue Discovery | 0.1181 | 0 | 0.2 | 0.3181
| 5 | Comprehensive Mitigation Review | Capacity Market | Continuing | Deployment | Market Design Complete | 0.165 | 0 | 0.6 | 0.765
| 6 | Grid in Transition | New Resource | Continuing | Study Complete | Issue Discovery | 0.17206 | 0 | 0.5 | 0.67206
| 7 | 15-Minute Transactions Enhancement - Requested by HQUS | Energy Market | Prioritize | Market Design Complete |  | 0.086488 | 0 | 0.25 | 0.33649
| 8 | 5 Minute Transaction Scheduling - Requested by HQUS | Energy Market | Prioritize | Market Design Concept Proposed |  | 0.10245 | 0 | 0.25 | 0.35245
| 9 | Adjustment of Energy Offer/Bid Floor (SOM) | Energy Market | Prioritize | Market Design Complete |  | 0.061408 | 0 | 0 | 0.061408
| 10 | Advancing NYISO Transparency - Requested by DC Energy | Energy Market | Prioritize | Deployment |  | 0.13323 | 0 | 0.25 | 0.38323
| 11 | Capacity Demand Curve Adjustments | Capacity Market | Prioritize | Study Complete |  | 0.13399 | 0 | 0.35 | 0.48399
| 12 | Constraint Specific Transmission Shortage Pricing (SOM) | Energy Market | Prioritize | Functional Requirements | Market Design Complete | 0.10321 | 0 | 0 | 0.10321
| 13 | Coordination of Interconnection and Transmission Expansion Study | Planning | Prioritize | Market Design Complete |  | 0.06422 | 0 | 0 | 0.06422
| 14 | CRIS Expiration Evaluation | Capacity Market | Prioritize | Market Design Complete | Market Design Concept Proposed | 0.1295 | 0 | 0 | 0.1295
| 15 | Demand Curve Translation Enhancement (SOM) | Capacity Market | Prioritize | Market Design Complete |  | 0.058064 | 0 | 0 | 0.058064
| 16 | Dynamic Reserves (SOM) | Energy Market | Prioritize | Market Design Concept Proposed | Study Complete | 0.11727 | 0 | 0.4 | 0.51727
| 17 | Eliminate Fees for CTS Transactions with PJM (SOM) | Energy Market | Prioritize | Market Design Concept Proposed |  | 0.050236 | 0 | 0 | 0.050236
| 18 | Eliminate Offline GT Pricing (SOM) | Energy Market | Prioritize | Market Design Complete |  | 0.11233 | 0 | 0 | 0.11233
| 19 | Engaging the Demand Side | New Resource | Prioritize | Study Complete | Issue Discovery | 0.17624 | 0 | 0.25 | 0.42624
| 20 | Enhanced BSM Forecasts Assumptions (SOM) | Capacity Market | Prioritize | Market Design Concept Proposed |  | 0.1181 | 0 | 0 | 0.1181
| 21 | Expanding Application of Peak Hour Forecasts | Capacity Market | Prioritize | Market Design Complete | Market Design Concept Proposed | 0.07904 | 0 | 0 | 0.07904
| 22 | Grid Services from Renewable Generators - Requested by NYSERDA | Energy Market | Prioritize | Market Design Concept Proposed | Study Complete | 0.099028 | 0 | 0.15 | 0.24903
| 23 | Hybrid Aggregation Model | New Resource | Prioritize | Functional Requirements | Market Design Complete | 0.23036 | 0 | 0.3 | 0.53036
| 24 | Improve Duct-Firing Modeling (SOM) | Energy Market | Prioritize | Market Design Complete |  | 0.099408 | 0 | 0.3 | 0.39941
| 25 | Improving Capacity Accreditation (SOM) | Capacity Market | Prioritize | Market Design Concept Proposed |  | 0.31791 | 0 | 0.4 | 0.71791
| 26 | Internal Controllable Lines | New Resource | Prioritize | Market Design Complete |  | 0.36153 | 0 | 0.4 | 0.76153
| 27 | Lines in Series Constraint Pricing | Energy Market | Prioritize | Study Complete |  | 0.063232 | 0 | 0 | 0.063232
| 28 | Locational Marginal Pricing of Capacity (SOM) | Capacity Market | Prioritize | Market Design Concept Proposed |  | 0.26562 | 0 | 0.65 | 0.91562
| 29 | Long Island Reserve Constraint Pricing (SOM) | Energy Market | Prioritize | Market Design Complete |  | 0.088768 | 0 | 0 | 0.088768
| 30 | Monthly Demand Curves (SOM) | Capacity Market | Prioritize | Issue Discovery |  | 0.11278 | 0 | 0 | 0.11278
| 31 | More Granular Operating Reserves (SOM) | Energy Market | Prioritize | Market Design Concept Proposed |  | 0.10587 | 0 | 0 | 0.10587
| 32 | Multi-Level References | Energy Market | Prioritize | Functional Requirements |  | 0.1029 | 0 | 0.05 | 0.1529
| 33 | Reserving Capacity for TCC Balance-of-Period (BOP) Auctions | TCC | Prioritize | Software Design | Functional Requirements | 0.25194 | 0 | 0 | 0.25194
| 34 | Storage as Transmission - Requested by NYSERDA | New Resource | Prioritize | Market Design Concept Proposed |  | 0.28888 | 0 | 0.55 | 0.83888
| 35 | Time Differentiated TCCs – Requested by Calpine and Vitol | TCC | Prioritize | Market Design Complete | Market Design Concept Proposed | 0.1748 | 0 | 0.2 | 0.3748
| 36 | Transmission Security in the ICAP Market | Capacity Market | Prioritize | Market Design Concept Proposed |  | 0.25468 | 0 | 0.125 | 0.37968
| 37 | Capacity Transfer Rights for Internal Transmission Upgrades (SOM) | Capacity Market | Future
| 38 | Carbon Pricing | Energy Market | Future |  | Software Design
| 39 | Enhanced PAR Modeling (SOM) | Energy Market | Future
| 40 | Long Island PAR Optimization and Financial Rights (SOM) | Energy Market | Future
| 41 | Review of Real-Time Market Structure (SOM) | Energy Market | Future
1 |  | ACC Control Room Renovations | Enterprise | Continuing | Deployment |  | 0.48708 | 5.6609 | 0 | 6.1479
2 |  | Application Platform Upgrade | Enterprise | Continuing | Deployment | Deployment | 0.4927 | 0 | 0 | 0.4927
3 |  | Database Upgrade | Enterprise | Continuing | Deployment | Deployment | 0.26439 | 0 | 0 | 0.26439
4 |  | EMS/BMS Operational Enhancements | Operations & Reliability | Continuing | Deployment | Deployment | 0.085111 | 0 | 1.2084 | 1.2935
5 |  | IT Infrastructure Automation | Enterprise | Continuing | Deployment | Deployment | 0.19789 | 0.102 | 0.215 | 0.51489
6 |  | ITSM Security Enhancements | Enterprise | Continuing | Deployment | Deployment | 0.42604 | 0.33654 | 0.31 | 1.0726
7 |  | Network Infrastructure Upgrade | Enterprise | Continuing | Deployment | Deployment | 0.19417 | 1.56 | 0 | 1.7542
8 |  | Outage Management System (OMS) | Operations & Reliability | Continuing | Deployment | Development Complete | 0.61939 | 0 | 0.85823 | 1.4776
9 |  | UPS Replacement | Enterprise | Continuing | Study Complete |  | 0.085041 | 0.65 | 0 | 0.73504
10 |  | Windows System Upgrade | Enterprise | Continuing | Deployment | Deployment | 0.23224 | 1.655 | 0.15 | 2.0372
11 |  | ASIS Rule for Re-write - Validating Exports | Energy Market | Prioritize | Deployment |  | 0.077746 | 0 | 0 | 0.077746
12 |  | BMS Performance Certification | Enterprise | Prioritize | Study Complete |  | 0.075389 | 0 | 1 | 1.0754
13 |  | BTM Solar Demand Forecasting Product Enhancements | Planning | Prioritize | Functional Requirements |  | 0.099408 | 0 | 0 | 0.099408
14 |  | Business Entity and Credit Questionnaire Enhancements | Business & Finance | Prioritize | Deployment |  | 0.18103 | 0 | 0 | 0.18103
15 |  | CMS and ConInvoice Data Integration | Business & Finance | Prioritize | Functional Requirements |  | 0.079721 | 0 | 0 | 0.079721
16 |  | Content Management and Collaboration Solution | Enterprise | Prioritize | Deployment |  | 0.12988 | 0.025 | 0 | 0.15488
17 |  | Contingency Analysis Results for Transmission Owner Situational Awareness | Operations & Reliability | Prioritize | Functional Requirements |  | 0.086941 | 0 | 0 | 0.086941
18 |  | Control Room Logging Replacement | Operations & Reliability | Prioritize | Study Complete |  | 0.13687 | 0.209 | 0 | 0.34587
19 |  | Credit Price Spread Updates Virtual and External Transactions | Business & Finance | Prioritize | Functional Requirements |  | 0.072656 | 0.085 | 0 | 0.15766
20 |  | Demand Forecasting Operational Reporting Enhancements | Planning | Prioritize | Functional Requirements |  | 0.093556 | 0 | 0 | 0.093556
21 |  | Finance Systems Technology Upgrades | Enterprise | Prioritize | Deployment |  | 0.13649 | 0 | 0 | 0.13649
22 |  | ICAP Supplier Status Enhancements | Capacity Market | Prioritize | Functional Requirements |  | 0.038608 | 0 | 0 | 0.038608
23 |  | IT Development and Control of Compliance Reports | Operations & Reliability | Prioritize | Deployment |  | 0.078584 | 0 | 0 | 0.078584
24 |  | Krey Control Room A/V Replacement | Enterprise | Prioritize | Study Complete |  | 0.029707 | 0 | 0.05 | 0.079707
25 |  | LFDR Upgrade and Enhancements | Planning | Prioritize | Functional Requirements |  | 0.095532 | 0 | 0 | 0.095532
26 |  | Market Validation, Reporting and Penalty Enhancements | Capacity Market | Prioritize | Functional Requirements |  | 0.083144 | 0 | 0 | 0.083144
27 |  | Meter Services System | Business & Finance | Prioritize | Functional Requirements |  | 0.079192 | 0 | 0 | 0.079192
28 |  | Microsoft 365 | Enterprise | Prioritize | Deployment |  | 0.46884 | 0.284 | 0.55 | 1.3028
29 |  | Minimum Oil Burn Enhancements | Business & Finance | Prioritize | Deployment |  | 0.18438 | 0 | 0 | 0.18438
30 |  | Natural Gas Notices Enhancement Project | Operations & Reliability | Prioritize | Functional Requirements |  | 0.062089 | 0 | 0.136 | 0.19809
31 |  | NetBackup Appliance Refresh | Enterprise | Prioritize | Deployment |  | 0.096967 | 1.385 | 0.25 | 1.732
32 |  | Next Generation Test Environment Study | Enterprise | Prioritize | Study Complete |  | 0.034805 | 0 | 0 | 0.034805
33 |  | NYISO Hosted Siemens Cloud | Planning | Prioritize | Deployment |  | 0.040657 | 0.18152 | 0 | 0.22217
34 |  | On-Boarding of New Resources | New Resource | Prioritize | Study Complete |  | 0.16051 | 0 | 0 | 0.16051
35 |  | Outage States Portal/Dashboard | Capacity Market | Prioritize | Functional Requirements |  | 0.076304 | 0 | 0 | 0.076304
36 |  | PI Tools Upgrade | Operations & Reliability | Prioritize | Deployment |  | 0.16248 | 0 | 0.112 | 0.27448
37 |  | Price Validation Technology Upgrades | Enterprise | Prioritize | Software Design |  | 0.15456 | 0 | 0.15 | 0.30456
38 |  | Privilege Access Management Upgrade and Enhancements | Enterprise | Prioritize | Deployment |  | 0.13686 | 0 | 0.05 | 0.18686
39 |  | Salesforce CRM Optimization | Business & Finance | Prioritize | Deployment |  | 0.19364 | 0.075 | 0.225 | 0.49364
40 |  | SDDB Steady State Dynamics Database MP Portal | Planning | Prioritize | Deployment |  | 0.24327 | 0 | 0.04 | 0.28327
41 |  | System Demand End Use and Electrification Forecasting Enhancements | Planning | Prioritize | Study Complete |  | 0.03952 | 0 | 0.095 | 0.13452
42 |  | Transactions Modifications and Confirmation Tool | Business & Finance | Prioritize | Deployment |  | 0.11727 | 0 | 0 | 0.11727
43 |  | Unified Communications Platform | Enterprise | Prioritize | Deployment |  | 0.066722 | 0.345 | 0 | 0.41172
44 |  | Web Content Management System Upgrade | Enterprise | Prioritize | Deployment |  | 0.10008 | 0 | 0.125 | 0.22508
|  | Subtotal |  |  |  |  | 16.8194 | 12.6539 | 18.6496 | 48.123