## Summary
Section 40.9.3.1.1 - Posting matrix These metrics are provided by the ISO in accordance with OATT Section 40.9.3.1.1.1. | Results
Number of individual Phase 1 Study reports completed during the Phase 1 Study | 272 Reports for 203 Projects
Number of individual Phase 1 Study reports during the Phase 1 Study that were finalized beyond the timeframe set forth in Section 40.10.5 (i.e.,reports finalized after September 3, 2025 ). Each such report is highlighted in red on the Phase 1 "Reports Metrics" tab. | 102 Reports for 93 Projects
The total time (in Calendar Days) from the Phase 1 Study Start Date to the date the ISO provided the applicable Transmission Owner with an updated Cluster Study Project List persuant to Section 40.10.4.1 (and if that total time calculated is greater than the time period for the ISO to provide the required materials to the applicable Transmission Owner as set forth in Section 40.10.4.1) | 2 Calendar Days
The total time (in Calendar Days) from the Phase 1 Study Start Date to the date the ISO provided the applicable Transmission Owner with the finalized CPA short-circuit base case pursuant to Section 40.10.4.1 (and if that total time calculated is greater than the time period for the ISO to provide the required materials to the applicable Transmission Owner as set forth in Section 40.10.4.1) | 5 Calendar Days
Total time (in Calendar Days) from the Phase 1 Study Start Date to the date when the ISO presents the Phase 1 Cost Estimates Summary Report to the ISO Operating Committee | 250 Calendar Days
Number of Interconnection Requests or CRIS-Only Requests withdrawn from the ISO’s Queue during the period between the commencement of the Customer Engagement Window and the completion of the Phase 2 Entry Decision Period | 255
Section 40.9.3.1.3 - Total Phase 1 Study Hours This information is provided by the ISO in accordance with OATT Section 40.9.3.1.3 | Results
Total number of NYISO, Transmission Owner and third party consultant hours expended towards the Phase 1 Study process. | 99,398 Hours

## Phase 1 Reports Metrics
OATT Section 40.9.3.1.1.1 Metrics
No | Queue Number | Project Name | CTO | CTO Ph1 Report Finalization Date | Total Time Calculated | Reason(s) for Delay | ATO1 | ATO1 Ph1 Report Finalization Date | Total Time Calculated | Reason(s) for Delay | ATO2 | ATO2 Ph1 Report Finalization Date | Total Time Calculated | Reason(s) for Delay | ATO3 | ATO3 Ph1 Report Finalization Date | Total Time Calculated | Reason(s) for Delay
1 | C24-003 | Vineyard Mid-Atlantic West | NYPA | 08/21/2025 | 170 | NA | NA | NA | NA | NA | Transco | 08/22/2025 | 171 | NA | NA | NA | NA | NA
2 | C24-004 | Palladium Storage | NYPA | 08/22/2025 | 171 | NA | ConEd | 08/22/2025 | 171 | NA | NA | NA | NA | NA | NA | NA | NA | NA
3 | C24-005 | Blue Spruce Storage | ConEd | 08/21/2025 | 170 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
4 | C24-008 | KCE NY 30 | LIPA | 10/10/2025 | 220 | 3d | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
5 | C24-010 | KCE NY 21 | LIPA | 08/15/2025 | 164 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
6 | C24-013 | Battery Park Storage | ConEd | 08/22/2025 | 171 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
7 | C24-014 | Roma Storage | ConEd | 08/22/2025 | 171 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
8 | C24-015 | Seventy Seven Project | NYSEG | 08/21/2025 | 170 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
9 | C24-016 | Salt Rush Wind Energy | NYSEG | 10/24/2025 | 234 | 3d | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
10 | C24-021 | Bluepoint Wind 1 | CONED | 08/22/2025 | 171 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
11 | C24-023 | KCE NY 26 | LIPA | 10/14/2025 | 224 | 3d | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
12 | C24-024 | Verona Solar I | NYPA | 09/22/2025 | 202 | 2b | NM-NG | 10/23/2025 | 233 | 2c | NA | NA | NA | NA | NA | NA | NA | NA
13 | C24-026 | Taproot Solar | LSPower | 08/22/2025 | 171 | NA | NYPA | 08/20/2025 | 169 | NA | NM-NG | 08/22/2025 | 171 | NA | NA | NA | NA | NA
14 | C24-031 | Crossbuck Energy Storage, LLC | CHGE | 08/21/2025 | 170 | NA | NA | N/A | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
15 | C24-032 | Oakdale Battery Storage LLC | NYSEG | 08/20/2025 | 169 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
16 | C24-033 | KCE NY 31 | LIPA | 10/10/2025 | 220 | 3d | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
17 | C24-034 | Kalmia Storage, LLC | LIPA | 10/10/2025 | 220 | 3d | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
18 | C24-037 | Gunns Corners Solar | NM-NG | 10/22/2025 | 232 | 2b, 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
19 | C24-038 | Long Island City Energy Storage | ConEd | 08/21/2025 | 170 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
20 | C24-039 | Golden Knight Solar | NM-NG | 10/22/2025 | 232 | 2b, 2c, 3f | NA | N/A | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
21 | C24-042 | Hoffman Falls Wind 2 | NM-NG | 08/25/2025 | 174 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
22 | C24-043 | Rosalen Solar Energy Center | NYPA | 08/20/2025 | 169 | NA | RG&E | 08/15/2025 | 164 | NA | NM-NG | 08/22/2025 | 171 | NA | NA | NA | NA | NA
23 | C24-044 | Honey Bee Battery Storage, LLC | NM-NG | 10/15/2025 | 225 | 2b | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
24 | C24-047 | Lincoln Park DG, LLC | CHGE | 08/21/2025 | 170 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
25 | C24-048 | BPP NY Lansing BESS I | NYSEG | 08/28/2025 | 177 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
26 | C24-049 | North Catskill DG LLC | CHGE | 08/21/2025 | 170 | NA | Transco | 08/22/2025 | 171 | NA | NM-NG | 10/17/2025 | 227 | 3c | NA | NA | NA | NA
27 | C24-052 | Hemlock Hollow Wind | NM-NG | 10/22/2025 | 232 | 2a, 2b, 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
28 | C24-056 | Naples Energy Storage | NYSEG | 08/20/2025 | 169 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
29 | C24-057 | Highland BESS | O&R | 08/22/2025 | 171 | NA | Transco | 08/22/2025 | 171 | NA | CHGE | 08/21/2025 | 170 | NA | NA | NA | NA | NA
30 | C24-058 | Slide Energy Center | CHGE | 08/21/2025 | 170 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
31 | C24-059 | Orchard BESS | CHGE | 08/21/2025 | 170 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
32 | C24-060 | Gemma Energy Storage | NYSEG | 08/18/2025 | 167 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
33 | C24-061 | Daphne Energy Storage | LIPA | 10/10/2025 | 220 | 3d | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
34 | C24-062 | Highbush Energy Storage | CHGE | 08/21/2025 | 170 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
35 | C24-063 | Heritage BESS | O&R | 08/22/2025 | 171 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
36 | C24-064 | Fraser Energy Storage | NYSEG | 08/18/2025 | 167 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
37 | C24-065 | Maplehurst Energy Park | NM-NG | 10/16/2025 | 226 | 2a, 2b, 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
38 | C24-066 | Coral Energy Storage | NYSEG | 08/19/2025 | 168 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
39 | C24-067 | Gala Grove BESS | LIPA | 10/10/2025 | 220 | 3d | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
40 | C24-072 | Eastwater Energy Storage | NM-NG | 08/25/2025 | 174 | NA | RG&E | 09/16/2025 | 196 | 2d, 3b | NA | NA | NA | NA | NA | NA | NA | NA
41 | C24-074 | Lighthouse Energy Storage | NM-NG | 10/16/2025 | 226 | 2a, 2b, 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
42 | C24-076 | Springbrooke | NM-NG | 10/17/2025 | 227 | 2b, 2c, 3g | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
43 | C24-077 | NY-5632 Turnpike Rd | NYSEG | 08/18/2025 | 167 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
44 | C24-078 | NY-MARKHAM HOLLOW RD | NM-NG | 10/17/2025 | 227 | 2b, 2c, 3f | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
45 | C24-079 | Maple Harvest Wind | NM-NG | 10/21/2025 | 231 | 2b, 2c, 3f | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
46 | C24-081 | Port Morris Energy Storage | NYPA | 08/21/2025 | 170 | NA | ConEd | 08/22/2025 | 171 | NA | NA | NA | NA | NA | NA | NA | NA | NA
47 | C24-085 | Arch 4 | CHGE | 10/07/2025 | 217 | 2c | Coned | 08/22/2025 | 171 | NA | O&R | 08/22/2025 | 171 | NA | NYPA | 08/20/2025 | 169 | NA
48 | C24-086 | Arch 1 | CHGE | 10/07/2025 | 217 | 2c | Coned | 08/22/2025 | 171 | NA | O&R | 08/22/2025 | 171 | NA | NYPA | 08/20/2025 | 169 | NA
49 | C24-087 | Arch 2 | CHGE | 10/07/2025 | 217 | 2c | Coned | 08/22/2025 | 171 | NA | O&R | 08/22/2025 | 171 | NA | NYPA | 08/20/2025 | 169 | NA
50 | C24-088 | Arch 3 | CHGE | 10/07/2025 | 217 | 2c | Coned | 08/22/2025 | 171 | NA | O&R | 08/22/2025 | 171 | NA | NYPA | 08/20/2025 | 169 | NA
51 | C24-089 | Braen Energy Storage Phase 1 | ConEd | 08/22/2025 | 171 | NA | O&R | 09/08/2025 | 188 | 3e | CHGE | 08/21/2025 | 170 | NA | NA | NA | NA | NA
52 | C24-090 | Cuba Solar Facility | NM-NG | 10/20/2025 | 230 | 2a, 2b, 2c | NA | N/A | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
53 | C24-092 | Scio Solar Facility | NM-NG | 10/20/2025 | 230 | 2a, 2b, 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
54 | C24-093 | Alcazar 1 | CHGE | 08/21/2025 | 170 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
55 | C24-094 | Alcazar 2 | CHGE | 08/21/2025 | 170 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
56 | C24-095 | Westerlo Solar | CHGE | 08/21/2025 | 170 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
57 | C24-097 | Basecamp BESS | NM-NG | 10/20/2025 | 230 | 2a, 2b, 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
58 | C24-098 | Farmhouse BESS | CHGE | 08/20/2025 | 169 | NA | NYPA | 08/22/2025 | 171 | NA | NA | NA | NA | NA | NA | NA | NA | NA
59 | C24-099 | Crown Point Solar | NM-NG | 08/21/2025 | 170 | NA | NYSEG | 10/07/2025 | 217 | 2b, 2d | NA | NA | NA | NA | NA | NA | NA | NA
60 | C24-101 | Halo Energy Storage | NYSEG | 10/08/2025 | 218 | 3d | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
61 | C24-102 | ELP Rotterdam Solar | NM-NG | 10/21/2025 | 231 | 2b, 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
62 | C24-103 | Bath Solar | NYSEG | 08/22/2025 | 171 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
63 | C24-104 | Horseblock Energy Storage | LIPA | 08/16/2025 | 165 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
64 | C24-105 | ELP Clay Storage | NM-NG | 08/22/2025 | 171 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
65 | C24-108 | NY125C - Little Salmon Solar | NYPA | 09/22/2025 | 202 | 3d | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
66 | C24-109 | Falls Park Energy Storage | NYSEG | 08/18/2025 | 167 | NA | Transco | 08/22/2025 | 171 | NA | NA | NA | NA | NA | NA | NA | NA | NA
67 | C24-111 | Fort Edward Solar Farm (NY53) | NM-NG | 10/20/2025 | 230 | 2b, 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
68 | C24-115 | Iris Bloom Solar | NM-NG | 10/20/2025 | 230 | 2a, 2b, 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
69 | C24-120 | Field Day Solar | NM-NG | 10/21/2025 | 231 | 2b, 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
70 | C24-121 | Beacon Harbor Solar | NM-NG | 10/17/2025 | 227 | 2b, 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
71 | C24-122 | Capital Energy Storage | NM-NG | 10/15/2025 | 225 | 2b, 2c | NYPA | 08/21/2025 | 170 | NA | NA | NA | NA | NA | NA | NA | NA | NA
72 | C24-124 | Dunkirk Energy Storage | NM-NG | 10/17/2025 | 227 | 2a, 2b, 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
73 | C24-125 | Town Line Solar Phase II | NYPA | 08/21/2025 | 170 | NA | NYSEG | 08/22/2025 | 171 | NA | O&R | 8/22/2025 | 171 | NA | NA | NA | NA | NA
74 | C24-126 | Pine Grove Energy Storage | NM-NG | 10/15/2025 | 225 | 2b, 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
75 | C24-128 | Winner Solar | NYSEG | 10/24/2025 | 234 | 2b | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
76 | C24-129 | Buffalo Road Energy Storage | NM-NG | 09/18/2025 | 198 | 2b | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
77 | C24-130 | Elevate Bethlehem | NM-NG | 10/15/2025 | 225 | 2b | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
78 | C24-131 | Elevate Arthur Kill II | ConEd | 08/21/2025 | 170 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
79 | C24-134 | River Road Energy Storage | NM-NG | 07/29/2025 | 147 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
80 | C24-135 | Cayuga Solar | NYSEG | 08/28/2025 | 177 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
81 | C24-138 | Marathon BESS | LIPA | 10/10/2025 | 220 | 3d | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
82 | C24-139 | Valcour Storage | NYPA | 08/20/2025 | 169 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
83 | C24-148 | Willard Storage | NM-NG | 10/09/2025 | 219 | 2b, 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
84 | C24-149 | Manchester Solar | NM-NG | 10/16/2025 | 226 | 2b | RG&E | 08/26/2025 | 175 | NA | NA | NA | NA | NA | NA | NA | NA | NA
85 | C24-150 | Kingbird Solar | NM-NG | 10/17/2025 | 227 | 2a, 2b, 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
86 | C24-152 | Antelope Energy Storage Center | NYPA | 08/20/2025 | 169 | NA | NM-NG | 08/22/2025 | 171 | NA | NA | NA | NA | NA | NA | NA | NA | NA
87 | C24-154 | Sandlot IFB | LIPA | 10/10/2025 | 220 | 3d | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
88 | C24-155 | Zenobe Stockton LLC | NM-NG | 10/21/2025 | 231 | 2a, 2b, 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
89 | C24-156 | Grass River Solar | NM-NG | 10/22/2025 | 232 | 2b | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
90 | C24-158 | KCE NY 27 | LIPA | 10/10/2025 | 220 | 3d | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
91 | C24-162 | Ramadi Utility Storage | LIPA | 10/10/2025 | 220 | 3d | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
92 | C24-163 | Porter Energy Storage | NM-NG | 08/21/2025 | 170 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
93 | C24-164 | KCE NY 28 | LIPA | 10/10/2025 | 220 | 3d | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
94 | C24-165 | KCE NY 38 | Transco | 08/22/2025 | 171 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
95 | C24-167 | KCE NY 37 | LIPA | 08/15/2025 | 164 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
96 | C24-168 | Ball Hill BESS | NM-NG | 09/18/2025 | 198 | 2a, 2b, 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
97 | C24-169 | Endurance | LIPA | 10/16/2025 | 226 | 3d | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
98 | C24-173 | KCE NY 34 | CHGE | 08/21/2025 | 170 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
99 | C24-175 | Stargazer I | NYSEG | 8/18/2025 | 167 | 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
100 | C24-176 | Stargazer II | NYSEG | 8/18/2025 | 167 | 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
101 | C24-177 | Commack(Jericho Power Station) | LIPA | 10/10/2025 | 220 | 3d | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
102 | C24-178 | Gowanus Energy Storage | ConEd | 08/21/2025 | 170 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
103 | C24-179 | Silverline Energy Center | NYSEG | 08/22/2025 | 171 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
104 | C24-182 | Southern Tier Energy Center | NYSEG | 08/20/2025 | 169 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
105 | C24-183 | East Setauket Storage II | LIPA | 08/15/2025 | 164 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
106 | C24-184 | Tabletop Solar | NM-NG | 10/21/2025 | 231 | 2b, 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
107 | C24-186 | THOR SOLAR | Transco | 08/22/2025 | 171 | NA | NM-NG | 10/17/2025 | 227 | 2a, 2b | NYSEG | 10/24/2025 | 234 | 2b | NA | NA | NA | NA
108 | C24-188 | Wheelhouse Solar Energy Center | NYPA | 08/25/2025 | 174 | NA | NM-NG | 10/22/2025 | 232 | 2a, 2b | LS Power | 07/25/2025 | 143 | NA | NA | NA | NA | NA
109 | C24-189 | North Country Wind | NYPA | 08/22/2025 | 171 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
110 | C24-190 | North Country Wind II | NYPA | 08/25/2025 | 174 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
111 | C24-191 | Zenobe Rotterdam LLC | NM-NG | 10/15/2025 | 225 | 2b | LSPower | 08/22/2025 | 171 | NA | NA | NA | NA | NA | NA | NA | NA | NA
112 | C24-202 | Brusselville Solar Energy Center | NYPA | 08/20/2025 | 169 | NA | NYSEG | 08/20/2025 | 169 | NA | RG&E | 08/20/2025 | 169 | NA | NA | NA | NA | NA
113 | C24-204 | Declaration Energy Center | NYPA | 09/18/2025 | 198 | 2b | NM-NG | 10/22/2025 | 232 | 2a, 2b | RG&E | 08/26/2025 | 175 | NA | NA | NA | NA | NA
114 | C24-205 | Wheelhouse Energy Storage | NYPA | 08/20/2025 | 169 | NA | NM-NG | 10/22/2025 | 232 | 2a, 2b | LS power | 07/25/2025 | 143 | NA | NA | NA | NA | NA
115 | C24-207 | Trelina Energy Storage | NYSEG | 08/19/2025 | 168 | NA | NM-NG | 08/22/2025 | 171 | NA | RG&E | 08/19/2025 | 168 | NA | NA | NA | NA | NA
116 | C24-208 | Independence BESS | NM-NG | 10/15/2025 | 225 | 2b | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
117 | C24-209 | Sidecar | NYSEG | 08/20/2025 | 169 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
118 | C24-213 | Zenobe Lancaster LLC | NYSEG | 08/18/2025 | 167 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
119 | C24-214 | Mulberry Energy Storage | NM-NG | 10/22/2025 | 232 | 2b, 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
120 | C24-217 | Bay Breeze solar | NM-NG | 10/23/2025 | 233 | 1, 2b, 2c, 4d | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
121 | C24-218 | Poplar Energy Center, LLC | LIPA | 10/10/2025 | 220 | 3d | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
122 | C24-222 | Knickerbocker Energy Storage | Transco | 08/22/2025 | 171 | NA | NM-NG | 08/22/2025 | 171 | NA | NA | NA | NA | NA | NA | NA | NA | NA
123 | C24-224 | Cohocton | NYSEG | 08/25/2025 | 174 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
124 | C24-225 | Goldenrod Wind | NM-NG | 10/21/2025 | 231 | 2a, 2b, 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
125 | C24-229 | Buttercup Wind | NM-NG | 10/22/2025 | 232 | 2a, 2b, 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
126 | C24-230 | Dewdrop Wind | NM-NG | 10/22/2025 | 232 | 2a, 2b, 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
127 | C24-233 | Shallow Seam BESS | NYSEG | 08/20/2025 | 169 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
128 | C24-234 | Zulu BESS | CHGE | 08/21/2025 | 170 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
129 | C24-235 | Champlain Solar Uprate | NM-NG | 10/22/2025 | 232 | 2b, 2c | NA | N/A | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
130 | C24-236 | Champlain Solar | NM-NG | 10/22/2025 | 232 | 2b, 2c | NA | N/A | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
131 | C24-237 | SBMT Energy Center, LLC | ConEd | 08/22/2025 | 171 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
132 | C24-238 | Zenobe Burns LLC | NYSEG | 08/21/2025 | 170 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
133 | C24-245 | PA-Hockenberry LLC | NYSEG | 8/18/2025 | 167 | 3d | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
134 | C24-247 | Jerry Smith Energy Storage | NYSEG | 08/25/2025 | 174 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
135 | C24-249 | Empire | NM-NG | 10/22/2025 | 232 | 2a, 2b, 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
136 | C24-250 | Honey Ridge Solar | NM-NG | 10/23/2025 | 233 | 2b, 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
137 | C24-252 | Maple City Energy Storage | NYSEG | 08/21/2025 | 170 | NA | NM-NG | 08/22/2025 | 171 | NA | NA | NA | NA | NA | NA | NA | NA | NA
138 | C24-253 | Troy Heights Energy Storage | NYSEG | 08/20/2025 | 169 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
139 | C24-255 | Saltgrass Storage | LIPA | 10/23/2025 | 233 | 2b, 3d | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
140 | C24-256 | Springer Storage | NM-NG | 10/22/2025 | 232 | 2b, 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
141 | C24-257 | Grapevine Storage | NM-NG | 10/16/2025 | 226 | 2a, 2b, 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
142 | C24-259 | Christmas Tree | NYSEG | 08/22/2025 | 171 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
143 | C24-263 | Jefferson Energy Storage | NM-NG | 10/03/2025 | 213 | 2b, 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
144 | C24-264 | Berry Farm Storage | NM-NG | 10/22/2025 | 232 | 2a, 2b, 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
145 | C24-265 | Bethpage Battery Storage Project | LIPA | 10/10/2025 | 220 | 3d | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
146 | C24-268 | Arnold Energy Storage | NM-NG | 10/22/2025 | 232 | 2b, 2c, 3f | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
147 | C24-269 | Stonewall Solar | NYSEG | 08/19/2025 | 168 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
148 | C24-270 | Bassett Energy Storage | NYSEG | 08/20/2025 | 169 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
149 | C24-278 | Sullivan-Woodbourne Solar Project | NYSEG | 08/15/2025 | 164 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
150 | C24-279 | Eastern Solar PV Project | CHGE | 08/21/2025 | 170 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
151 | C24-281 | Brentwood Energy Storage | LIPA | 08/15/2025 | 164 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
152 | C24-282 | Millwood Energy Storage | ConEd | 08/22/2025 | 171 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
153 | C24-283 | Resilient New York Energy Storage | ConEd | 08/22/2025 | 171 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
154 | C24-284 | South Bronx Energy Storage | NYPA | 08/20/2025 | 169 | NA | ConEd | 08/22/2025 | 171 | NA | NA | NA | NA | NA | NA | NA | NA | NA
155 | C24-289 | Genovia Storage | NYPA | 08/22/2025 | 171 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
156 | C24-292 | Loganberry Energy Storage, LLC | NM-NG | 10/20/2025 | 230 | 2a, 2b, 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
157 | C24-293 | Oswego Clean Energy | NM-NG | 10/14/2025 | 224 | 2b, 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
158 | C24-294 | Birch-Whistler | NYPA | 09/03/2025 | 183 | NA | NM-NG | 08/22/2025 | 171 | NA | NYSEG | 08/27/2025 | 176 | NA | NA | NA | NA | NA
159 | C24-297 | Deer River Wind | NM-NG | 09/18/2025 | 198 | 2b, 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
160 | C24-298 | Black Cherry Wind 1 | NYSEG | 08/18/2025 | 167 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
161 | C24-299 | Black Cherry Wind 2 | NYSEG | 08/18/2025 | 167 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
162 | C24-300 | Kimberlite Solar | NYSEG | 08/20/2025 | 169 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
163 | C24-301 | Moonlight Flats Solar | NYSEG | 08/22/2025 | 171 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
164 | C24-302 | NY Oswego 200 Erie St Storage | NM-NG | 10/14/2025 | 224 | 2b, 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
165 | C24-304 | NY Chateaugay 0 Willis Rd Storage | NYPA | 08/21/2025 | 170 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
166 | C24-306 | Lock 26 BESS | RG&E | 08/19/2025 | 168 | NA | NM-NG | 08/22/2025 | 171 | NA | NYSEG | 08/19/2025 | 168 | NA | NA | NA | NA | NA
167 | C24-309 | Black Cherry BESS | NYSEG | 08/18/2025 | 167 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
168 | C24-312 | St. Regis | NM-NG | 10/22/2025 | 232 | 2b, 2c, 3f | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
169 | C24-313 | Southport Solar PV Project | NYSEG | 08/28/2025 | 177 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
170 | C24-317 | Leo Energy Storage | NYSEG | 08/19/2025 | 168 | NA | NYPA | 08/20/2025 | 169 | NA | NA | NA | NA | NA | NA | NA | NA | NA
171 | C24-318 | Sherburne Storage | NYSEG | 08/19/2025 | 168 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
172 | C24-319 | Ditch Creek | NYPA | 08/25/2025 | 174 | NA | NM-NG | 2025-10-23 | 233 | 2a, 2b | NA | NA | NA | NA | NA | NA | NA | NA
173 | C24-320 | Boonville Standalone Storage | NM-NG | 10/23/2025 | 233 | 2b , 2c, 3f | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
174 | C24-321 | Jericho Solar | NYPA | 09/19/2025 | 199 | 3d | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
175 | C24-322 | Rolling Upland Wind Farm | NYSEG | 08/20/2025 | 169 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
176 | C24-323 | Echo Lake | NM-NG | 10/21/2025 | 231 | 2b, 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
177 | C24-324 | Overlook Storage | CHGE | 08/21/2025 | 170 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
178 | C24-325 | Van Buren Storage | NM-NG | 10/20/2025 | 230 | 2a, 2b, 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
179 | C24-326 | Lockport Storage | NYSEG | 08/19/2025 | 168 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
180 | C24-327 | North Creek | NM-NG | 08/26/2025 | 175 | NA | LSPower | 8/22/2025 | 171 | NA | NA | NA | NA | NA | NA | NA | NA | NA
181 | C24-331 | Hell Gate Energy Storage | NYPA | 08/21/2025 | 170 | NA | ConEd | 08/22/2025 | 171 | NA | NA | NA | NA | NA | NA | NA | NA | NA
182 | C24-332 | Stoner Trail Storage | NM-NG | 10/21/2025 | 231 | 2b, 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
183 | C24-333 | Pouch Energy Storage System | ConEd | 08/21/2025 | 170 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
184 | C24-335 | PA-Fritz Kiln LLC | NYSEG | 08/18/2025 | 167 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
185 | C24-336 | Mill Point Solar II | NM-NG | 08/25/2025 | 174 | NA | NYPA | 08/21/2025 | 170 | NA | NA | NA | NA | NA | NA | NA | NA | NA
186 | C24-337 | Aria Storage 1 | ConEd | 08/22/2025 | 171 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
187 | C24-338 | Aria Storage 2 | ConEd | 08/22/2025 | 171 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
188 | C24-341 | Marlboro Storage | CHGE | 08/21/2025 | 170 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
189 | C24-344 | Deerpark Energy Storage | O&R | 08/22/2025 | 171 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
190 | C24-347 | Little Falls Solar | NM-NG | 10/17/2025 | 227 | 2b | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
191 | C24-348 | Harvest Hills Solar | NYSEG | 10/24/2025 | 234 | 2b | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
192 | C24-349 | Richland III Solar | NM-NG | 09/18/2025 | 198 | 2b, 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
193 | C24-350 | Hickling Storage, LLC | NYSEG | 10/13/2025 | 223 | 2d | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
194 | C24-352 | Swiss Valley Energy Storage | NYSEG | 08/21/2025 | 170 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
195 | C24-358 | Sugar Loaf Energy Storage I | O&R | 10/07/2025 | 217 | 3e | Transco | 08/22/2025 | 171 | NA | NA | NA | NA | NA | NA | NA | NA | NA
196 | C24-359 | Sugar Loaf Energy Storage II | O&R | 10/07/2025 | 217 | 3e | Transco | 08/22/2025 | 171 | NA | NA | NA | NA | NA | NA | NA | NA | NA
197 | C24-361 | Cherry Valley Solar | NYPA | 08/21/2025 | 170 | NA | NM-NG | 10/22/2025 | 232 | 2a, 2b | LS power | 07/25/2025 | 143 | NA | NA | NA | NA | NA
198 | C24-362 | Amsterdam Solar | NM-NG | 08/26/2025 | 175 | NA | NYPA | 08/20/2025 | 169 | NA | LS power | 08/22/2025 | 171 | NA | NA | NA | NA | NA
199 | C24-363 | Town Line Solar CSR Phase I | NYPA | 08/21/2025 | 170 | NA | NYSEG | 08/22/2025 | 171 | NA | O&R | 08/22/2025 | 171 | NA | NA | NA | NA | NA
200 | C24-364 | Erie Canal BESS | NYSEG | 08/19/2025 | 168 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
201 | C24-366 | Azalea Wind 1 | NYSEG | 10/15/2025 | 225 | 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
202 | C24-367 | Lewis Wind | NM-NG | 09/18/2025 | 198 | 2b | NYPA | 09/15/2025 | 195 | 2b | NA | NA | NA | NA | NA | NA | NA | NA
203 | C24-370 | Azalea Wind 2 | NYSEG | 10/15/2025 | 225 | 2c | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
204 | CR24-1002 | West Babylon Internal Combustion (IC), Unit 4 | LIPA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
205 | CR24-1003 | Bethlehem Energy Center Uprate | NM-NG | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
206 | CR24-1004 | Arthur Kill Unit 2 Uprate | ConEd | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA

## Legend
Legends : - PHASE 1 STUDIES EXPLANATIONS/REASONS
1. Clarifications required to the data and/or diagram provided by the Interconnection Customer
2. Technical challenges due to:
a) Cluster size
b) Complexity of designing local System Upgrade Facilities associated with the POI proposed by the Interconnection Customer
c) More than one project proposing to interconnect in the same electrical vicinity
d) Clarification of detailed design of facilities in the Existing System Representation
3. Administrative challenges due to:
a) Technical issues with electronic platform to exchange information among the NYISO, Interconnection Customer, consultants and/or CTO
b) Finalization of project-specific agreement among consultants and CTOs for scope of technical work required to study
c) Identification of ATOs later in the Phase 1 Studies
d) Comments on the Phase 1 Reports had not been incorporated or required additional clarification and/or coordination, necessitating follow-up and/or revisions to the Phase 1 Study Report
e) Inadvertent identification of upgrades beyond the scope of Phase 1 Study necessitating revisions to the Phase 1 Study Report
f) Inadvertent mischaracterization of upgrades necessitating revisions to the Phase 1 Study Report
g) Project withdrawals or reinstatement due to Dispute Resolution process
4. Revisions to study base cases due to:
a) Modeling errors in base cases
b) Project withdrawals or reinstatement due to Dispute Resolution processes
c) Interconnection Customer deficiencies and associated withdrawal or cure periods
d) Interconnection Customer corrections/revisions to project data and/or diagrams